## Site Monitoring Hub
SITE DEVELOPMENT & ACTIVITY MONITORING DASHBOARD
|  | TOTAL SITES |  | COMPLETED |  |  | IN PROGRESS |  |  | DELAYED / PENDING
|  | 6 |  | 0 |  |  | 6 |  |  | 0
ACTIVE ACTIVITY MONITORING PLAN
No. | PROJECT/ PROGRAM | SITE NAME | SITE ID | ACTIVITY | RAAWA | VALIDITY | TOWERCO | VALIDITY | RESPONSIBLE | TARGET DATE | STATUS | REMARKS | GT PROPONENT | ISSUES
1 | B2B_B2C | CDO-713 | MIN2668 | SURVEY | YES |  | GT |  | JOHN RABANES - B* JERICO - R** RYLIE - B | 2026-06-22 | CLOSE | 22JUNE2026: RELOCATE OLT INSTALLATION TO MIN355 LCGCDO. RAAWA IS AVAILABLE BUT NEEDS PHILTOWER ACCESS PERMIT APPROVAL.
2 | FTTH HORIZONTAL | POBMAMBAJAO | MIN666 | PAT | YES |  | FTAP |  | JERICHO BATIQUIN/JOHN CARLO RABANES/ RYLIE (B) | 2026-06-11 | ONGOING | 19JUNE2026: DONE PAT. WAITING FOR TEAM INVOLVED TO EMAIL PATDOCS TO FO FOR APPROVAL.
3 | DISMANTLING | PATPAT | MIN97 | DISMANTLING | NO |  | FTAP |  | ENOVELL | TBA | ONGOING | 19JUNE2026: STILL NOT YET APPROVED. FOLLOW UP WITH SIR ROWEL.
4 | DISMANTLING | DONROSTUBAYAGN | MIN24 | DISMANTLING | NO |  | GT |  | ENOVELL | TBA | ONGOING | 19JUNE2026: STILL NOT YET APPROVED. FOLLOW UP WITH SIR ROWEL.
5 | DISMANTLING | BALASNGINGOMISOR | MIN1846 | DISMANTLING | NO |  | PHILTOWER |  | JERICHO BATIQUIN/ RYLIE | 2026-06-13 | ONGOING | 19JUNE2026: STILL NOT YET APPROVED. FOLLOW UP WITH SIR ROWEL.
6 | EUL MIGRATION - ADVANCE SURVEY | DIPOLO | MIN821 | TSSR | NO |  | GT |  | JOHN CARLO RABANES | TBA | ONGOING | 22June2026: SCHEDULED FOR REVISIT AT JULY 3, 2026. EMAILED RAAWA FOR APPROVAL
7 | B2C_EUL MIGRATION | PRKPHILVSURGAOSDN | MIN779 | TSSR | NO |  | PHILTOWER |  | TBA | TBA | ONGOING | 22June2026: SCHEDULED FOR SITE REVISIT ON JUNE 30, 2026. EMAILED RAAWA FOR APPROVAL
8 | EUL MIGRATION - ADVANCE SURVEY | GSN-602 | MIN1035 | SURVEY | NO
| B2C_EUL MIGRATION | DIG-704 | MIN1163 | SURVEY | NO
| EUL MIGRATION - ADVANCE SURVEY | DIG-705 | MIN1164 | SURVEY | NO
| EUL MIGRATION - ADVANCE SURVEY | DVO-741 | MIN1182 | SURVEY | NO
| EUL MIGRATION - ADVANCE SURVEY | PNB-703-HS | MIN1195 | SURVEY | NO
| EUL MIGRATION - ADVANCE SURVEY | ILG-706-HS | MIN1279 | SURVEY | NO
| EUL MIGRATION - ADVANCE SURVEY | ZMB-711 | MIN1315 | SURVEY | NO
| EUL MIGRATION - ADVANCE SURVEY | PGD-706 | MIN1323 | SURVEY | NO
| EUL MIGRATION - ADVANCE SURVEY | PGD-701 | MIN1324 | SURVEY | NO
| EUL MIGRATION - ADVANCE SURVEY | CDO-707 | MIN1338 | SURVEY | NO
| EUL MIGRATION - ADVANCE SURVEY | DVO-742-HS | MIN1346 | SURVEY | NO
| FTTH HORIZONTAL | KALASUNGAY | MIN1533 | SURVEY | NO |  |  |  | JOHN CARLO RABANES | 2026-06-26 | ONGOING | 22JUNE2026: SCHEDULED FOR SITE SURVEY ON JUNE 25, 2026. EMAILED RAAWA FOR APPROVAL
| B2C_EUL MIGRATION | TSORAPOBBUTUANAGN | MIN624 | TSSR | NO |  |  |  | JOHN CARLO RABANES | 2026-07-01 | ONGOING | 22JUNE2026: SCHEDULED FOR REVISIT ON JULY 1, 2026. EMAILED RAAWA FOR APPROVAL
| B2B_B2C | LCGCDO | MIN355 | SURVEY | YES |  |  |  | JOHN CARLO RABANES | 2026-06-25 | ONGOING | 22JUNE2026: RAAWA IS AVAILABLE BUT NEEDS PHILTOWER ACCESS PERMIT APPROVAL.
| FTTH HORIZONTAL | POBMALITADVOC | MIN1846 | SURVEY
| FTTH HORIZONTAL | BANSAL | MIN678 | SURVEY
| FTTH HORIZONTAL | MAKILA | MIN8 | SURVEY
| FTTH HORIZONTAL | BABAK | MIN132 | SURVEY

## EUL material list
QTY | 22 | 3 | 3 | 6 | 10 | 30 | 6 | 22 | 44 | 52 | 424 | 424 | 44 | 34 | 52 | 26 | 26 | 52 | 52 | 52 | 26 | 148 | 144 | 56 | 144 | 44 | 616 | 220 | 26 | 160 | 3 | 30 |  | 15 | 3 | 1 | 29
PART NUMBER | 3FE76762AA | 3FE61087DA | 3FE64991AB | 3FE71256AB | 3FE76986AA | L00RC01-3.5 | 3FE52344DAAA | 3FE76518AA | 3FE76559BA | 3FE62600AA | 3FE53441AA | 3FE47581AB | 3FE76476AA | 3FE76353AA | 3FE52344FLAA | Blaine-Spiral-1/2mmx10ft | L00HLT_VELCRO_10M | Blaine-16mm-Shrinkable | Blaine-8mmShrinkable | Blaine-12mmShrinkable | Blaine-Cartridge9mm | L00TL14AWG | L00Lugs10mm2 | L00Lugs16mm2 | L00Lugs8mm2 | 3FE77365BAAA | 3FE60713CAAA | L00YG16MM2 | Blaine-ButterflyTie | 3FE60713BLAA | Blaine-8"Tie | 1AZ661980001
Site ID | Lightspan MF-2 shelf incl. fan unit (LMXR-A) | Fiber Routing Kit ISAM FX-4(brand: Nokia) | Shelf 7360 ISAM FX-4 48V only(brand: Nokia) | 7360 ISAM FX 1280Gbps NT with clock sync(brand: Nokia) | ISAM FX 16port GPON line card(brand: Nokia) | 3.5MM x 2C PD ROYAL CORD (75m/roll) | Simplex patch cord, LC/UPC - LC/UPC 3m | MF2-FAN Module | Lightspan MF-2 DC power module (LPWR-B DC) | Optical Transceiver SFP+,1310nm SM,10km(brand: Nokia) (10GBase-LR) | PON Transceiver20km 1310nm(Tx)1490nm(Rx) - GPON SFP B+ | Transcvr XGS-PON/GPON MPM B+(28dBm)Ctemp | LightspanMF-2 240Gbps NT with clock sync(brand: Nokia) (LMNT-A) | Lightspan MF 16port Multi-PON Line board (LWLT-C) | Simplex patch cord, LC/UPC - LC/UPC 8m(brand: Nokia) | Spiral Wrap 10mmx10ft | VELCRO (HOOK & LOOP TIE) BLACK 10m/roll | Shrinkable tube 16mm x 200mm | Shrinkable tube 8mm x 200mm | Shrinkable tube 12mm x 200mm | Labeller tape | cable shoe (#14 AWG) | 10mm2 Terminal Lugs | 16-10mm2 Terminal Lugs | terminal lugs 8mm | POSITIVE POWER CABLE BLACK/10M | Simplex Patch Cord, SC/UPC - SC/APC 2m(brand: Nokia) | WIRE GROUNDING CABLE YELLOW/GREEN 16MM N/A | butterfly cable tie | Simplex patch cord, SC/UPC -SC/APC 1.5m(brand: Nokia) | Plastic Cable Tie white | HT RVVZ Single Ground Cable 16mm2 (Yellow/Green) | Circuit Breaker Type | Ratings 16A | Ratings 20A | Ratings 32A | QTY Needed
MIN1035 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 2
MIN1163 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 1
MIN1164 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 2
MIN1182 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Huawei
MIN1195 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 2
MIN1279 |  | 1 | 1 | 2 | 4 | 10 | 2 |  |  | 2 | 32 | 32 |  |  | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 20 | 4 | 4 | 4 |  |  |  | 1 | 64 | 1 | 10 | Huawei |  | 20A |  | 1
MIN1315 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 1
MIN1323 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 1
MIN1324 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 2
MIN1338 |  | 1 | 1 | 2 | 3 | 10 | 2 |  |  | 2 | 24 | 24 |  |  | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 20 | 4 | 4 | 4 |  |  |  | 1 | 48 | 1 | 10 | Huawei |  | 20A |  | 1
MIN1346 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 1
MIN1356 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Huawei
MIN1360 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Huawei
MIN1363 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 2
MIN1365 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 1
MIN1368 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 1
MIN1371 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 1
MIN1374 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Huawei
MIN624 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Nader or Schneider | 16A |  |  | 2
MIN779 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | ZTE |  |  |  | 2
MIN985 |  | 1 | 1 | 2 | 3 | 10 | 2 |  |  | 2 | 24 | 24 |  |  | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 20 | 4 | 4 | 4 |  |  |  | 1 | 48 | 1 | 10 | Huawei |  | 20A |  | 1
MIN995 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Huawei | 16A |  |  | 1
MIN1804 |  | 1 | 1 | 2 | 9 | 10 | 2 |  |  | 2 | 72 | 72 |  |  | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 20 | 4 | 4 | 4 |  | 72 |  | 1 |  | 1 | 10 | Nader or Schneider |  |  | 32A | 2
MIN623 | 1 | [6 empty] | 1 | 2 | 2 | 8 | 8 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 16 | 10 | 1 |  |  |  | Nader or Schneider
MIN1807 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Nader or Schneider
MIN821 | 1 | [6 empty] | 1 | 2 | 2 | 16 | 16 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 4 | 6 | 2 | 6 | 2 | 32 | 10 | 1 |  |  |  | Nader or Schneider | 16A |  |  | 2

## EUL Sites
[5 empty] | BAPE | BAPE | BAPE | BAPE | BAPE | BAPE | BAPE | BAPE |  | BAPE | BAPE | BAPE | BAPE | BAPE | BAPE | VENDOR | VENDOR | VENDOR | VENDOR | VENDOR | VENDOR | VENDOR | VENDOR
B2C/B2B | PLA ID | Site Name | Region | Territory | Active Lines | sum RFS LINE CAPACITY | sum GPON PORT USED | product(sum DSL64()) | Number of PON Need to build | Old OLT Type | Wireline Solution | Equipment Type (New Build) | VENDOR | No. of Chassis (New Build) | Space Requirement | Power Requirement (W) | Required AN 10G Ports | Uplink Capacity Requirement (Mbps) | No. of Cards (New Build) | SURVEY PO | PSOW ENDORSED DATE | RAAWA | SURVEY | TSSR SUBMITTED | APPROVED TSSR | SOLUTION | ISSUES
B2C | MIN1035 | GSN-602 | MIN | T7 | 491 | 928 | 15 | 0 | 15 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 8500 | 1 | 4540536545 | 2026-01-23 | Done | 2026-02-12 | 2026-02-23 | 2026-03-05 | MF2 - NEW BUILD
B2C | MIN1163 | DIG-704 | MIN | T7 | 336 |  | 16 | 320 | 16 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 6500 | 1 | 4540536545 | 2026-01-23 | Done | 2026-02-10 | 2026-02-23 | 2026-03-05 | MF2 - NEW BUILD
B2C | MIN1164 | DIG-705 | MIN | T7 | 282 | 560 | 16 | 256 | 16 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 6500 | 1 | 4540536545 | 2026-01-23 | Done | 2026-02-10 | 2026-02-25 | 2026-03-03 | MF2 - NEW BUILD
B2C | MIN1182 | DVO-741 | MIN | T7 | 599 | 624 | 13 | 256 | 13 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 6000 | 1 | 4540536545 | 2026-01-23 | Done | 2026-02-21 | 2026-02-23 | 2026-03-05 | MF2 - NEW BUILD | CABINET SITE IS BLOCK BY VENDORS 10 feb 2026 : the cabinet is still block by vendors, and refused to vacate the front of cabinet
B2C | MIN1195 | PNB-703-HS | MIN | T7 | 374 | 632 | 14 | 192 | 14 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 6000 | 1 | 4540536545 | 2026-01-23 | Done | 2025-02-13 | 2026-02-23 | 2026-03-05 | MF2 - NEW BUILD
B2C | MIN1279 | ILG-706-HS | MIN | T8 | 2171 | 2464 | 54 | 0 | 54 | MA5603T | New Build | Mid OLT | NOKIA | 1 | 6RU | 1200W;25-30A(DC) | 2x10G | 22000 | 4 | 4540536545 | 2026-01-23 | Done | 2026-02-17 | 2026-02-23 | 2026-03-09 | FX4 - NEW BUILD
B2C | MIN1315 | ZMB-711 | MIN | T8 | 747 | 1304 | 29 | 192 | 29 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 12000 | 2 | 4540536545 | 2026-01-23 | Done | 2026-02-11 | 2026-02-23 | 2026-02-26 | MF2 - NEW BUILD
B2C | MIN1323 | PGD-706 | MIN | T8 | 816 | 1216 | 23 | 192 | 23 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 9500 | 2 | 4540536545 | 2026-01-23 | Done | 2026-02-16 | 2026-02-23 | 2026-03-02 | MF2 - NEW BUILD
B2C | MIN1324 | PGD-701 | MIN | T8 | 528 | 1016 | 19 | 128 | 19 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 8000 | 2 | 4540536545 | 2026-01-23 | Done | 2026-02-16 | 2026-02-23 | 2026-02-26 | MF2 - NEW BUILD
B2C | MIN1338 | CDO-707 | MIN | T8 | 544 | 1768 | 39 | 128 | 39 | MA5603T | New Build | Mid OLT | NOKIA | 1 | 6RU | 1200W;25-30A(DC) | 2x10G | 16000 | 3 | 4540536545 | 2026-01-23 | Done | 2026-02-19 | 2026-02-23 | 2026-03-02 | FX4 - NEW BUILD
B2C | MIN1346 | DVO-742-HS | MIN | T7 | 628 | 888 | 20 | 256 | 20 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 8500 | 2 | 4540536545 | 2026-01-23 | Done | 2026-02-04 | 2026-02-25 | 2026-03-03 | MF2 - NEW BUILD
B2C | MIN1356 | OZA-701 | MIN | T8 | 536 | 992 | 20 | 128 | 20 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 8500 | 2 | 4540536545 | 2026-01-23 | Done | 2026-03-09 | 2026-03-10 | 2026-03-13 | MF2 - NEW BUILD
B2C | MIN1360 | OZA-702 | MIN | T8 | 358 | 656 | 12 | 192 | 12 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 6000 | 1 | 4540536545 | 2026-01-23 | Done | 2026-03-09 | 2026-03-10 | 2026-03-13 | MF2 - NEW BUILD
B2C | MIN1363 | ZMB-702 | MIN | T8 | 259 | 288 | 5 | 192 | 5 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 3500 | 1 | 4540536545 | 2026-01-23 | Done | 2026-02-11 | 2026-02-24 | 2026-03-05 | MF2 - NEW BUILD
B2C | MIN1365 | PGD-707 | MIN | T8 | 529 | 1280 | 32 | 192 | 32 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 2x10G | 13000 | 2 | 4540536545 | 2026-01-23 | Done | 2026-02-16 | 2026-02-23 | 2026-02-26 | MF2 - NEW BUILD
B2C | MIN1368 | ZMB-708 | MIN | T8 | 655 | 920 | 18 | 128 | 18 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 7500 | 2 | 4540536545 | 2026-01-23 | Done | 2026-02-11 | 2026-02-23 | 2026-03-02 | MF2 - NEW BUILD
B2C | MIN1371 | GNG-701 | MIN | T8 | 359 | 672 | 12 | 0 | 12 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 6500 | 1 | 4540536545 | 2026-01-23 | Done | 2026-02-16 | 2026-02-23 | 2026-03-02 | MF2 - NEW BUILD
B2C | MIN1374 | PLM-702 | MIN | T7 | 367 | 648 | 15 | 0 | 15 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 6500 | 1 | 4540536545 | 2026-01-23 | Done | 2026-02-11 | 2026-02-23 | 2026-03-05 | MF2 - NEW BUILD
B2C | MIN624 | TSORAPOBBUTUANAGN | MIN | T8 | 428 | 904 | 18 | 0 | 18 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 7500 | 2 | 4540536545 | 2026-01-23 | Done | 2026-02-28 | 2026-03-16 |  | MF2 - NEW BUILD
B2C | MIN779 | PRKPHILVSURGAOSDN | MIN | T8 | 684 | 1216 | 27 | 256 | 27 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 11000 | 2 | 4540536545 | 2026-01-23 | Done | 2026-03-03 | 2026-03-09 |  | MF2 - NEW BUILD
B2C | MIN985 | BTN-609 | MIN | T8 | 761 | 1592 | 43 | 0 | 43 | MA5603T | New Build | Mid OLT | NOKIA | 1 | 6RU | 1200W;25-30A(DC) | 2x10G | 17500 | 3 | 4540536545 | 2026-01-23 | Done | 2026-02-28 | 2026-03-09 | 2026-03-13 | FX4 - NEW BUILD
B2C | MIN995 | CDO-604 | MIN | T8 | 818 | 1232 | 27 | 128 | 27 | MA5603T | New Build | Mini OLT | NOKIA | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 11000 | 2 | 4540536545 | 2026-01-23 | Done | 2026-02-19 | 2026-02-23 | 2026-03-02 | MF2 - NEW BUILD
B2B | MIN1803 | LNANG2-LSA01-001-MIN1803 | MIN | T7 | B2B | 11 | 48 | 5 | 0 | MA5600T | New Build | MiniOLT | Nokia | N/A | N/A | N/A | N/A | N/A | N/A | 4540536545 | 2026-02-11 | Done | N/A | N/A |  | N/A | CANCELLED for Decommissioning
B2B | MIN1804 | DONMAR-LSA01-001-MIN1804 | MIN | T7 | B2B | 5960 | 3397 | 131 | 0 | MA5600T | New Build | Large OLT | Nokia | 1 | 17RU | 3400W;63-100A(DC) | 2x100G |  | 9 | 4540536545 | 2026-02-11 | Done | 2026-03-14 | 2026-03-20 | 2026-04-10 | FX16 - NEW BUILD
B2B | MIN623 | BUTUAN-LSA01-001-MIN623 | MIN | T8 | B2B | 21 | 48 | 0 | 0 | MA5600T | New Build | MiniOLT | Nokia | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 11000 | 1 | 4540536545 | 2026-02-11 | Done | 2026-03-02 | 2026-03-16 | 2026-04-15 | MF2 - NEW BUILD
B2B | MIN1807 | CDOLGC-LSA01-001-MIN1807-A1 | MIN | T8 | B2B | 34 | 83 | 11 | 3 | MA5600T | New Build | MiniOLT | Nokia | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 11000 | 1 | 4540536545 | 2026-02-11 | Done | 2026-02-26 | 2026-03-14 | 2026-04-15 | MF2 - NEW BUILD
B2B | MIN821 | DPOLOG-LSA01-001-MIN821 | MIN | T8 | B2B | 14 | 81 | 6 | 8 | MA5600T | New Build | MiniOLT | Nokia | 1 | 2RU | 400W;10-15A(DC) | 1x10G | 11000 | 1 | 4540536545 | 2026-02-11 | Done | 2026-03-10 | 2026-03-13 |  | MF2 - NEW BUILD
B2B | MIN1419 | PVALEN-LSA04-001-MIN1419 | MIN | T8 | B2B | 6 | 64 | 0 | 0 | MA5603T | New Build | MiniOLT | Nokia | N/A | N/A | N/A | N/A | N/A | N/A | 4540536545 | 2026-02-11 | Done | N/A | N/A |  | N/A | CANCELLED for Decommissioning

## MIN OLT Project
| 76 | 76 | 76 |  |  | 76 | 76 | 76 | 76 | 76 | 16 | [11 empty] | 10 | 7 | 10 | 0 | 10 | 0 | 27 | 9 | 0 | 0 | 0
SN | PROJECT or PROGRAM | Site Name | PLAID | Destination Site Name | Destination PLAID | Region | TERRITORY | Scope Status | OLT Scope | Electronics Equipment | Number of Cards | Facilities Scope | BASEFRAME | SUBCON TSSR | SUBCON Implementation | Subcon Basepad | PO SERVICES | PO SUPPLY | PO SURVEY | Survey Date | TSSR Approved Date | TSSR Remarks | Installed date | Powertapped Date | Integrated Date | Pre PAT Date | PAT'ed | Submitted to GT for signature | PAC'ed | FAC'ed | COC/FAC | Docs Handover to OPS | Implementation Progress %
1 | SPBD | Casa Mira Tower A - LPU Davao | MIN1053 |  |  | MIN | T7 | POSSIBLE DROP | New Build | MF2 | 1 |  |  | Nokia Internal | Enovell |  | 4540530505
2 | SPBD | One Lakeshore Drive T3 | MIN4840 |  |  | MIN | T7 | Active | New Build | MF2 | 1 |  |  | Nokia Internal | Not yet allocated |  | 4540530505
3 | SPBD | Matina Enclaves | MIN4721 |  |  | MIN | T7 | Active | New Build | MF2 | 1 | New Rectifier |  | Nokia Internal | Enovell |  |  |  |  | 2025-04-01 | 2025-05-13 | TSSR not applicable. New site | 2025-04-12 | 2025-04-12 | 2025-05-30 |  | 2025-06-10 |  | 2025-10-20 | 2025-10-30
4 | SPBD | Peak Lanes ( West) - DONMAR | MIN1804 |  |  | MIN | T7 | Active | New Build | MF2 | 1 |  |  | Enovell | Enovell |  |  |  |  | 2025-02-28 | 2025-04-10 | New RS to be installed by Nokia. | 2025-03-11 | 2025-03-11 | 2025-06-18 |  | 2025-06-25 |  | 2025-10-20 | 2025-10-30
5 | SPBD | Peak Lanes ( East ) - DONMAR | MIN1804 |  |  | MIN | T7 | Active | New Build | MF2 | 2 |  |  | Enovell | Enovell |  |  |  |  | 2025-02-28 | 2025-03-05 |  | 2025-03-11 | 2025-03-11 | 2025-06-18 |  | 2025-06-25 |  | 2025-10-20 | 2025-10-30
6 | SPBD | Legacy Leisure Residence Tower 2 ( TCEDCDJRMAADAVAODDS) | MIN3308 |  |  | MIN | T7 | DROPPED | New Build | MF2 | 1 | ODC+RS | YES | Nokia Internal | Enovell |  | 4540531883
7 | SPBD | BANALEPGDIA | MIN1519 |  |  | MIN | T8 | Active | New Build | MF2 | 2 |  |  | TBA | TBA |  | NO PO
8 | B2B_B2C | 8 SPATIAL | MIN2857 |  |  | MIN | T7 | Active | New Build | MF2 | 2 |  |  |  | ENOVELL | ENOVELL | 4540536156
9 | B2B_B2C | CDOO_713_HYB_01 | MIN2668 |  |  | MIN | T7 | Active | New Build | MF2 | 1
10 | FTTH HORIZONTAL | MARAGU | MIN126 |  |  | MIN | T7 | Active | New Build | MF2 | 2 |  |  | Enovell | Enovell |  |  |  |  | 2025-05-23 | 2025-05-27 |  | 2025-05-30 | 2025-05-30 | 2025-07-02 |  | 2025-07-29 |  | 2025-10-20 | 2025-11-25
11 | FTTH HORIZONTAL | POBMANJAO | MIN666 |  |  | MIN | T8 | Active | New Build | MF2 | 1 |  |  | Enovell | Enovell |  | 4540530822 |  |  | 2025-09-11 | 2025-10-01 |  | 2025-09-11 | 2025-09-11 | 2025-11-07
12 | FTTH HORIZONTAL | SMCPOBSULOP | MIN2482 |  |  | MIN | T7 | Active | New Build | MF2 | 1 |  |  | Enovell | Enovell |  | - PO SURVEY 4540535741 -PO Electronic 4540535741 |  |  | 2026-02-05 |  |  | 2026-04-15 | 2026-04-15 | 2026-04-17 |  | 2026-05-06
13 | FTTH HORIZONTAL | LAMITA | MIN631 |  |  | MIN | T8 | Active | New Build | MF2 | 1 |  |  | Nokia | Nokia |  | 4540544694 |  |  | 2026-05-10
14 | FTTH HORIZONTAL | MALUSO BASILAN | MIN4299 |  |  | MIN | T8 | Active | New Build | MF2 | 1 |  |  | TBA | TBA |  | 4540538271
15 | FTTH HORIZONTAL | ISB_001 ISABEL | MIN828 |  |  | MIN | T8 | Active | New Build | MF2 | 1 |  |  | Nokia | Nokia |  |  | DISMANTLED FROM MIN24 - DONROS |  | 2026-05-25
16 | DISMANTLING | PATPAT | MIN97 |  |  | MIN | T8 | Active | Dismantling MF2 * 1 CARD | N/A | 0 |  |  | N/A | ENOVELL
17 | DISMANTLING | DONROS | MIN24 |  |  | MIN | T8 | Active | Dismantling MF2 * 1 CARD | N/A | 0 |  |  | N/A | ENOVELL
18 | DISMANTLING | BRGY BAL | MIN1846 |  |  | MIN | T8 | Active | Dismantling MF2 * 1 CARD | N/A | 0 |  |  | N/A | ENOVELL
19 | EUL MIGRATION - ADVANCE SURVEY | GSN-602 | MIN1035 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-12 | 2026-03-05 | [7 empty] | 2026-04-20
20 | EUL MIGRATION - ADVANCE SURVEY | DIG-704 | MIN1163 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 1 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-10 | 2026-03-05
21 | EUL MIGRATION - ADVANCE SURVEY | DIG-705 | MIN1164 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 1 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-10 | 2026-03-03 | [7 empty] | 2026-03-31
22 | EUL MIGRATION - ADVANCE SURVEY | DVO-741 | MIN1182 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 1 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-21 | 2026-03-05 | [7 empty] | 2026-04-20
23 | EUL MIGRATION - ADVANCE SURVEY | PNB-703-HS | MIN1195 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 1 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2025-02-13 | 2026-03-05 | [7 empty] | 2026-04-20
24 | EUL MIGRATION - ADVANCE SURVEY | ILG-706-HS | MIN1279 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | FX4 | 4 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-17 | 2026-03-09 | 03/09/2026: Ready for Build Space ok for Coloc | [6 empty] | 2026-05-04
25 | EUL MIGRATION - ADVANCE SURVEY | ZMB-711 | MIN1315 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-11 | 2026-02-26 | 02/26/2026: NO AC UPGRADE RS SUFFICIENT , BCO TO 150AH FOR 8HRS BBUT Okay for space and tapping point | [6 empty] | 2026-03-31
26 | EUL MIGRATION - ADVANCE SURVEY | PGD-706 | MIN1323 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-16 | 2026-03-02 | 03/02/2026:Build Upgrade NO AC UPGRADE RS SUFFICIENT , BCO TO 150AH Okay for space and tapping point | [6 empty] | 2026-03-31
27 | EUL MIGRATION - ADVANCE SURVEY | PGD-701 | MIN1324 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-16 | 2026-02-26 | 02/26/2026: NO AC UPGRADE RS SUFFICIENT Okay for space and tapping point | [6 empty] | 2026-03-31
28 | EUL MIGRATION - ADVANCE SURVEY | CDO-707 | MIN1338 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | FX4 | 3 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-19 | 2026-03-02 | 03/02/2026: NO AC UPGRADE RS SUFFICIENT Okay for space and tapping point | [6 empty] | 2026-03-31
29 | EUL MIGRATION - ADVANCE SURVEY | DVO-742-HS | MIN1346 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-04 | 2026-03-03 | RS IS SUFFICIENT TO CATER LOADS OK FOR SPACE AND TAPPING POINT | [6 empty] | 2026-04-20
30 | EUL MIGRATION - ADVANCE SURVEY | OZA-701 | MIN1356 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-03-09 | 2026-03-13 | 03/13/2026: Ready for Build Space and Power OK | [6 empty] | 2026-05-04
31 | EUL MIGRATION - ADVANCE SURVEY | OZA-702 | MIN1360 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 1 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-03-09 | 2026-03-13 | 03/13/2026: Ready for Build Space and Power OK | [6 empty] | 2026-05-04
32 | EUL MIGRATION - ADVANCE SURVEY | ZMB-702 | MIN1363 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 1 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-11 | 2026-03-05 | 03/05/2026: Ready for Build | [6 empty] | 2026-05-04
33 | EUL MIGRATION - ADVANCE SURVEY | PGD-707 | MIN1365 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-16 | 2026-02-26 | 2/26/2026: NO AC UPGRADE RS SUFFICIENT Okay for space and tapping point | [6 empty] | 2026-03-31
34 | EUL MIGRATION - ADVANCE SURVEY | ZMB-708 | MIN1368 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-11 | 2026-03-02 | 03/02/2026:Build Upgrade NO AC UPGRADE RS SUFFICIENT , BCO TO 150AH Okay for space and tapping point | [6 empty] | 2026-03-31
35 | EUL MIGRATION - ADVANCE SURVEY | GNG-701 | MIN1371 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 1 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-16 | 2026-03-02 | 03/02/2026: NO AC UPGRADE RS SUFFICIENT Okay for space and tapping point | [6 empty] | 2026-03-31
36 | EUL MIGRATION - ADVANCE SURVEY | PLM-702 | MIN1374 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 1 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-11 | 2026-03-05 | [7 empty] | 2026-04-20
37 | EUL MIGRATION - ADVANCE SURVEY | TSORAPOBBUTUANAGN | MIN624 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-28
38 | EUL MIGRATION - ADVANCE SURVEY | PRKPHILVSURGAOSDN | MIN779 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-03-03 |  | no space, no power. For rehoming or new homing
39 | EUL MIGRATION - ADVANCE SURVEY | BTN-609 | MIN985 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | FX4 | 3 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-28 | 2026-03-13 | 03/13/2026: Ready for Build Space and Power OK
40 | EUL MIGRATION - ADVANCE SURVEY | CDO-604 | MIN995 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | N/A | 0 | MF2 | 2 | ENOVELL |  |  | 4540542443 | 4540542574 | 4540536545 | 2026-02-19 | 2026-03-02 | 03/02/2026: NO AC UPGRADE RS SUFFICIENT Okay for space and tapping point | [6 empty] | 2026-03-31
41 | EUL MIGRATION - ADVANCE SURVEY | DONMAR-LSA01-001-MIN1804 | MIN1804 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | FX8/FX16 | 9 |  |  | ENOVELL |  |  |  |  | 4540536545 | 2026-03-14 | 2026-04-15
42 | EUL MIGRATION - ADVANCE SURVEY | BUTUAN-LSA01-001-MIN623 | MIN623 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 1 |  |  | ENOVELL |  |  |  |  | 4540536545 | 2026-03-02
43 | EUL MIGRATION - ADVANCE SURVEY | CDOLGC-LSA01-001-MIN1807-A1 | MIN1807 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 |  |  | ENOVELL |  |  |  |  | 4540536545 | 2026-02-26 | 2026-04-16
44 | EUL MIGRATION - ADVANCE SURVEY | DPOLOG-LSA01-001-MIN821 | MIN821 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 |  |  | ENOVELL |  |  |  |  | 4540536545 | 2026-03-10 | 2026-03-16
45 | EUL MIGRATION - ADVANCE SURVEY | PVALEN-LSA04-001-MIN1419 | MIN1419 |  |  | MIN | T8 | DROPPED | TSSR + NEW BUILD | MF2 | 1 |  |  | ENOVELL |  |  |  |  | 4540536545 |  |  | FOR DECOMMISSIONING
46 | EUL MIGRATION - ADVANCE SURVEY | LNANG2-LSA01-001-MIN1803 | MIN1803 |  |  | MIN | T7 | DROPPED | TSSR + NEW BUILD | MF2 | 1 |  |  | ENOVELL |  |  |  |  | 4540536545 |  |  | FOR DECOMMISSIONING
47 | SRW | TALIGALEGBUTUANAGN | MIN1594 |  |  | MIN | T8 | Active | SRW | N/A | 0 |  |  | ENOVELL | [12 empty] | 2025-09-12 |  | 2025-10-01 | 2025-10-07
48 | SRW | MIN576 | MIN576 |  |  | MIN | T8 | Active | SRW | N/A | 0 |  |  | ENOVELL
49 | SRW | BUTUA3_NEW | MIN632 |  |  | MIN | T8 | Active | SRW | N/A | 0 |  |  | ENOVELL
50 | SRW | POB5CABAD | MIN645 |  |  | MIN | T8 | Active | SRW | N/A | 0 |  |  | ENOVELL | [12 empty] | 2025-12-15 |  | 2025-12-15 | 2025-12-19
51 | SFP LINK UPGRADE | MYB_004_GPONA_01 | MIN69 |  |  | MIN | T7 | Active | SFP UPGRADE 10GE | N/A | 0 |  |  |  | Enovell |  | 4540454765 | [5 empty] | 2025-04-29 |  | 2025-04-29 |  | 2025-05-19 |  | 2025-10-01 | 2025-10-07
52 | SFP LINK UPGRADE | VLN_004_GPONA_01 | MIN1703 |  |  | MIN | T8 | Active | SFP UPGRADE 10GE | N/A | 0 |  |  |  | Enovell |  | 4540454765 | [5 empty] | 2025-04-30 |  | 2025-04-30 |  | 2025-05-19 |  | 2025-10-01 | 2025-10-07
53 | SFP LINK UPGRADE | SNG_001_GPONA_01 | MIN789 |  |  | MIN | T8 | Active | SFP UPGRADE 10GE | N/A | 0 |  |  |  | Enovell |  | 4540454765 | [5 empty] | 2025-07-15 |  | 2025-07-15 |  | 2025-05-19 |  | 2025-09-29 | 2025-10-07
54 | SFP LINK UPGRADE | SFA_001_GPONA_01 | MIN286 |  |  | MIN | T8 | Active | SFP UPGRADE 10GE | N/A | 0 |  |  |  | Enovell |  | 4540543473 | [5 empty] | 2026-05-19 | 2026-05-19 | 2026-05-19
55 | B2C_EUL MIGRATION | GSN-602 | MIN1035 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
56 | B2C_EUL MIGRATION | DIG-704 | MIN1163 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | MF2 | 1 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
57 | B2C_EUL MIGRATION | DIG-705 | MIN1164 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | MF2 | 1 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
58 | B2C_EUL MIGRATION | DVO-741 | MIN1182 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | MF2 | 1 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
59 | B2C_EUL MIGRATION | PNB-703-HS | MIN1195 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | MF2 | 1 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
60 | B2C_EUL MIGRATION | ILG-706-HS | MIN1279 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | FX4 | 4 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
61 | B2C_EUL MIGRATION | ZMB-711 | MIN1315 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
62 | B2C_EUL MIGRATION | PGD-706 | MIN1323 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
63 | B2C_EUL MIGRATION | PGD-701 | MIN1324 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
64 | B2C_EUL MIGRATION | CDO-707 | MIN1338 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | FX4 | 3 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
65 | B2C_EUL MIGRATION | DVO-742-HS | MIN1346 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
66 | B2C_EUL MIGRATION | OZA-701 | MIN1356 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
67 | B2C_EUL MIGRATION | OZA-702 | MIN1360 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 1 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
68 | B2C_EUL MIGRATION | ZMB-702 | MIN1363 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 1 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
69 | B2C_EUL MIGRATION | PGD-707 | MIN1365 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
70 | B2C_EUL MIGRATION | ZMB-708 | MIN1368 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
71 | B2C_EUL MIGRATION | GNG-701 | MIN1371 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 1 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
72 | B2C_EUL MIGRATION | PLM-702 | MIN1374 |  |  | MIN | T7 | Active | TSSR + NEW BUILD | MF2 | 1 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
73 | B2C_EUL MIGRATION | TSORAPOBBUTUANAGN | MIN624 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
74 | B2C_EUL MIGRATION | PRKPHILVSURGAOSDN | MIN779 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
75 | B2C_EUL MIGRATION | BTN-609 | MIN985 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | FX4 | 3 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574
76 | B2C_EUL MIGRATION | CDO-604 | MIN995 |  |  | MIN | T8 | Active | TSSR + NEW BUILD | MF2 | 2 | N/A | N/A | Enovell |  |  | 4540542443 | 4540542574

## GLOBE SITE MASTERLIST
PLAID | SITE | WIRELINE_NAME (NMS NAMES) | BCF_NAME | REGION | PROVINCE | MUNICIPALITY | BARANGAY | TERRITORY | LATITUDE | LONGITUDE | SITE_ADD | ASSIGN_HUB | TOWERCO | NEW ASSIGN_AREA | NEW ASSIGN_AREA NAME | NEW ASSIGN_HUB | NEW ENGINEER_AH | NEW ENGINEER_ANM1 | NEW ENGINEER_ANM1 ID NUMBER | CONTACT NUMBER | NEW ANM HEAD | NEW ROH
MIN3283 | TCFGAD6PUNTANASIPAGN | NA | TCFGAD6PUNTANASIPAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9886 | 125.3531 | District 6, Brgy Punta, Nasipit, Agusan del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4567 | TCAICP5MABINICABADAGN | NA | TCAICP5MABINICABADAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | CITY OF CABADBARAN |  | Territory 8 | 9.1108 | 125.5582 | Brgy. Mabini, Cabadbaran City, Agusan del Norte | AMPAYON FOC | UNITY | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1247 | TCFGAASINANPILARSDN | NA | TCFGAASINANPILARSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | PILAR |  | Territory 8 | 9.8649 | 126.0982 | BRGY. ASINAN (POB.),PILAR,SURIGAO DEL NORTE | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4681 | TCEDCLDOONGANBUTUANAGN | NA | TCEDCLDOONGANBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9589 | 125.5225 | Brgy Doongan_Butuan City_Agusan del Norte | AMPAYON FOC | EDOTCO | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN780 | CAPHILLSURGAOSDN | SRG_705_GPONA_01 / SRG_703_HYB_01 | CAPHILLSURGAOSDNFHKLVY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7689 | 125.4853 | Capitol Hill Luna, Surigao City, Surigao Del Norte | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4632 | PRK2SJUANSURGAOSDNAS | NA | PRK2SJUANSURGAOSDNAS | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | s | 125.4853 | A. ENSOMO STREET, CORNER L. REYNA STREET, PUROK 2, SAN JUAN, SURIGAO CITY, SDN | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4635 | TCEDCSANTONPOBLIBJODNGT | NA | TCEDCSANTONPOBLIBJODNGT | REGION XIII (Caraga) | DINAGAT ISLANDS | LIBJO |  | Territory 8 | 10.2155 | 125.5756 | Brgy. San Antonio (Pob.) Libjo(Albor) Surigao Del Norte , Libjo (Albor), Dinagat Islands | CAPHILLSURGAOSDN | EDOTCO | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN39 | SLCALOBUTUANAGN | BTN_914_GPONA_01 | SLCALOBUTUANAGNFKLVYFLVW SLCALOFLVWYFKLV TCFGASLCALOBUTUANAGNFKLVWYFHK | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9621 | 125.5349 | S.L. Calo St. Obrero Pob. (Bgy. 18), Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2501 | BRGYMAGDAGJABONAGN | NA | BRGYMAGDAGJABONAGNFLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | JABONGA |  | Territory 8 | 9.3436 | 125.4993 | Santo Nino, Jabonga, Agusan Del Norte, Philippines | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4178 | TCAICRSARIOTANDAGSDS | NA | NA | REGION XIII (Caraga) | SURIGAO DEL SUR | TAGO | Victoria | Territory 8 | 9.0374 | 126.2156 | Barangay Victoria, Tago, Surigao Del Sur | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4634 | PRK5SJUANSURGAOSDNAS | NA | PRK5SJUANSURGAOSDNAS | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.789 | 125.4845 | A. ENSOMO STREET, CORNER L. REYNA STREET, PUROK 2, SAN JUAN, SURIGAO CITY, SDN | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3366 | P10TAFTSURIGAOSDN | NA | P10TAFTSURIGAOSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7815 | 125.4989 | Purok 10, Brgy Taft, Surigao City, Surigao del Norte | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4141 | TCFGAMAHAYSNJOSEDNGT | NA | TCFGAMAHAYSNJOSEDNGT | REGION XIII (Caraga) | DINAGAT ISLANDS | SAN JOSE |  | Territory 8 | 10.0051 | 125.5837 | BRGY. MAHAYAHAY, SAN JOSE, DINAGAT ISLANDS | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN52 | SNROQU | SFN_003_GPONA_01 | SNROQUFHLWY TCFGABAYUGAN2SFRANCAGSFHLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.4529 | 125.9609 | Purok 8 Bayugan 2, San Francisco, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1217 | SUMILIBUTUANAGN | BTN_008_GPONA_01 | SUMILIBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9929 | 125.6117 | Sumilihon, Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3811 | STIBRGY2SFRANCAGS | NA | NA | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.5083 | 125.9765 | Quezon Street, STI Building, Brgy 2, San Francisco, Agusan del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4633 | PRK1BSJUANSURGAOSDNAS | NA | PRK1BSJUANSURGAOSDNAS | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.79 | 125.4879 | SANTOS CEDRO ST., COR. I. CORTES ST., PUROK 1-B, BRGY. SAN JUAN, SURIGAO CITY | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN489 | NAVARROSOCOROSDN | NA | NAVARROSOCOROSDNFHLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SOCORRO |  | Territory 8 | 9.6202 | 125.9587 | Navarro (Pob.), Socorro, Surigao Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1249 | ADLAY | NA | ADLAYFLWYZ | REGION XIII (Caraga) | SURIGAO DEL SUR | CARRASCAL | Adlay | Territory 8 | 9.4163 | 125.8897 | Adlay, Carrascal, Surigao Del Sur | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN44 | AFGA | NA | AFGAFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SIBAGAT |  | Territory 8 | 8.8823 | 125.6845 | Sibagat, Agusan Del Norte, Philippines | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN17 | PRKABIPEQBUTUANAGN | NA | PRKABIPEQBUTUANAGNFHKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9777 | 125.5233 | Purok Abiabihon Agusan Pequeño, Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN518 | POBAGUSTNSDS | NA | POBAGUSTNSDS_DJFHKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | SAN AGUSTIN |  | Territory 8 | 8.7452 | 126.2216 | SanAgustinPoblacion, San Agustin, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN466 | PRK5ALIPALEGRISDN | NA | PRK5ALIPALEGRISDNFH TCFGAALIPALEGRISDNFLVWYFHK | REGION XIII (Caraga) | SURIGAO DEL NORTE | ALEGRIA |  | Territory 8 | 9.4963 | 125.5809 | Purok 5 Alipao, Alegria, Surigao Del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN18 | AMBAGOBUTUANAGN | NA | AMBAGOBUTUANAGNFHKLWYFLW AMBAGOFLWYFHKLW TCFGAAMBAGOBUTUANAGNFHKLWYFHK | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9601 | 125.506 | Ambago, Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN621 | BLK5VPARBUTUANAGN | NA | BLK5VPARBUTUANAGNFHLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Ampayon | Territory 8 | 8.959 | 125.6011 | Block 5 Villa Paraiso, Purok 3A Ampayon, Butuan City, Agusan Del Norte | BUTUAN (TECHNICAL OFFICE) | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1347 | Butuan | BTN_009_GPONA_01 | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.958 | 125.6005 | Purok 3A Villa Paraiso, Ampayon Butuan City Agusan del Norte 8600 | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN495 | ARASCAGWITSDS | CWT_001_GPONA_01 | ARASCAGWITSDSFHKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | CAGWAIT |  | Territory 8 | 8.8886 | 126.3087 | ArasAsan, Cagwait, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN19 | BAANKM3BUTUANAGN | NA | BAAN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9577 | 125.5836 | Baan KM 3, Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN467 | POBBACUAGSDN | NA | POBBACUAGSDNFHKLVWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | BACUAG |  | Territory 8 | 9.6045 | 125.6422 | Bacuag_Poblacion, Bacuag, Surigao Del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN496 | BALIBA | NA | BALIBAFHWY | REGION XIII (Caraga) | SURIGAO DEL SUR | CORTES |  | Territory 8 | 9.1426 | 126.17 | Balibadon, Cortes, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1503 | BANCASBUTUANAGN | BTN_012_GPONA_01 | BANCASBUTUANAGNFKLVWY BANCASBUTUANFLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.945 | 125.487 | Butuan Airport Bancasi Butuan City | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN498 | PRK1POBBAROBOSDS | BRB_001_GPONA_01 | PRK1POBBAROBOSDSFHLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | BAROBO |  | Territory 8 | 8.5296 | 126.1194 | Purok 1 Barobo_Poblacion, Barobo, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN469 | POBRIZALBASILIDNGT | NA | BASILIFLWYFLWY POBRIZALBASILIDNGTFLWYFLVWY | REGION XIII (Caraga) | DINAGAT ISLANDS | BASILISA |  | Territory 8 | 10.0662 | 125.5917 | Basilisa(Rizal)_Poblacion, Basilisa (Rizal), Dinagat Islands | CAPHILLSURGAOSDN | FTAP | [6 empty] | #N/A
MIN499 | BAYABA | NA | BAYABAFF | REGION XIII (Caraga) | SURIGAO DEL SUR | BAYABAS |  | Territory 8 | 8.9672 | 126.2851 | Balete (Pob.), Bayabas, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN20 | KM2JCAQUINBUTUANAGN | BTN_014_GPONA_01 | KM2JCAQUINBUTUANAGNFKLVWYTCFGAKM2JCAQUINBUTUANAGNFKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.945 | 125.5247 | Km. 2, J.C. Aquino Ave.Bayanihan Pob. (Bgy. 27), Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1218 | BAYUG3 | BYG_003_GPONA_01 | BAYUG3FHKLWYF TCFGABAYUGAN3ROSARAGSFHKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | ROSARIO |  | Territory 8 | 8.3117 | 126.0093 | Banhawan Purok 1 A Bayugan 3, Rosario, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN626 | BAYUGA | BYG_001_GPONA_01 | BAYUGAFHKLVWXYF | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7151 | 125.742 | New Salem, Bayugan, Agusan Del Sur | BAYUGAN SDH | PHILTOWER | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1891 | BAYUGAN SDH | NA | NONE | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7167 | 125.7412 | Narra Avenue, Purok 4, Bayugan_Poblacion, Bayugan, Agusan Del Sur | PROSPERIDAD FOC | GT | [6 empty] | #N/A
MIN781 | BAREMANGBISLIGSDS | BSL_002_GPONA_01 / BSL_002_GPONA_02 | LAURTEPOBBISLIGSDSFHKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | BISLIG CITY |  | Territory 8 | 8.1856 | 126.3575 | Bareda St.Mangagoy, Bislig, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1893 | BN001 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9092 | 125.5553 | Near Pajarillo Residence, San Vicente Street, San Vicente, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1895 | BN002 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9367 | 125.5353 | Beside House No. 026 cor San Santan Villakananga Road, Villa Kananga, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1896 | BN003 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9421 | 125.5249 | Near ComagonResidences Felipe St, Luz Village, Bayanihan Pob. (Bgy. 27), Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1897 | BN004 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9427 | 125.5153 | Front Baldo Residences, JC Aquino Ave. cor Casa Rivera Rd, Bayanihan Pob. (Bgy. 27), Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1902 | BN005 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9543 | 125.5036 | Front Abundo Residence Along Ambago Road, Ambago, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1910 | BN007 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9649 | 125.5017 | Beside Blk 6 Lot 16 Phase 3 Emenvill Subdivision, Ambago, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1900 | BN008 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.947 | 125.5356 | Front Lutheran Church Along Jc Aquino Avenue, Lapulapu Pob. (Bgy. 8), Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1904 | BN009 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9558 | 125.5284 | Beside Manalo Reidence Balbarino Street Balbarino Subdivision, Doongan, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1911 | BN010 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9732 | 125.5285 | Beside Egay Residence Purok Silangan Road, Agusan Pequeño, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1908 | BN011 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9627 | 125.5385 | Inside Obrero Elem School Along S Calo St Cor North Montilla Blvd, Obrero Pob. (Bgy. 18), Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1899 | BN014 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9463 | 125.5387 | Near Leyson Residences Along Ipil Cor Acacia Road, Lapulapu Pob. (Bgy. 8), Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1901 | BN015 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9513 | 125.5493 | Via Duct Brgy. Baan, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1894 | BN016 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9227 | 125.5408 | Near Wendels Inn along Mandacpan Road, Agao Pob. (Bgy. 3), Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1906 | BN017 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9571 | 125.5821 | P-15 ALVIOLA beside RD Pawnshop, Baan KM 3, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1909 | BN018 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.964 | 125.6047 | Front Ampayon Elem School Ampayon National HiWay, Ampayon, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1905 | BN019 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9568 | 125.6114 | Near Martinez Residence Along Maharlika Highway, Ampayon, Butuan City, Agusan Del Norte | BLK5VPARBUTUANAGN | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN627 | BNAWAN | BNW_001_GPONA_01 | BNAWANFHLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | BUNAWAN |  | Territory 8 | 8.1761 | 125.996 | Purok 2 Bunawan_Poblacion, Bunawan, Agusan Del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN470 | KM7BONIFSURGAOSDN | SRG_005_GPONA_01 | BONSURFLWY KM7BONIFSURGAOSDNFLWY TCFGABONIFSURGAOSDNFLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.739 | 125.4931 | Km. 7, Bonifacio, Surigao City, Surigao Del Norte | CAPHILLSURGAOSDN | FTAP | [6 empty] | #N/A
MIN2272 | BRGY1SANFRANSADS | NA | BRGY1SANFRANSADSFHKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.5124 | 125.9775 | Barangay 4, San Francisco, Agusan del Sur, Philippines | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1250 | POBBISLIGSDS | NA | POBBISLIGSDSFHKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | BISLIG CITY |  | Territory 8 | 8.1905 | 126.3285 | BEHIND LTO AND DPWH BISLIG, Mancarogo, Bislig, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN986 | BTN-600 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9392 | 125.5372 | ALONG BLUMENTRIT ST. COR. 8TH ST., BRGY. J. P. RIZAL, BUTUAN CITY | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN977 | BTN-601 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9435 | 125.5411 | INTERSECTION OF R. CALO & F. DURANO ST., BRGY GOLDEN RIBBON, BUTUAN CITY | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN978 | BTN-602 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9444 | 125.536 | BESIDE BRGY. HALL OF DAGOHOY, ALONG R. PALMA ST. ,BRGY. DAGOHOY, BUTUAN CITY | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN980 | BTN-603 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9517 | 125.5387 | ALONG ROSALES ST., BRGY. SAN IGNACIO, BUTUAN CITY | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN981 | BTN-606 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.948 | 125.5308 | ALONG J. ROSALES AVE. COR. T. CALO ST., BRGY. LIMAHA, BUTUAN CITY | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN983 | BTN-607 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9429 | 125.5189 | BESIDE 2GO WAREHOUSE, ALONG J.C AQUINO AVE., BRGY. LIBERTAD, BUTUAN CITY | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN984 | BTN-608 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9434 | 125.5074 | ALONG J.C. AQUINO BESIDE LIBERTAD SPORT COMPLEX, BUTUAN CITY | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN985 | BTN-609 | BTN_609_GPONA_01 | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9534 | 125.5007 | BESIDE BLISS ELEMENTARY SCHOOL,BRGY. LIBERTAD, BUTUAN CITY | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1329 | BTN-701 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9545 | 125.5678 | HUAWEI CABINETBESIDE SOLAR CONCRETE PRODUCTS ALONG NATIONAL ROAD KM 3 BRGY. BAAN BUTUAN CITY | AMPAYON FOC | GT | [6 empty] | #N/A
MIN622 | POB3BUENVAGN | NA | POB3BUENVAGNFHKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUENAVISTA |  | Territory 8 | 8.9697 | 125.4057 | Buenavista_Poblacion 3, Buenavista, Agusan Del Norte | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1912 | BUENAVISTA PDH | None | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUENAVISTA |  | Territory 8 | 8.9753 | 125.4071 | Burgos Street Purok 4, Buenavista_Poblacion 4, Buenavista, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN42 | STACRUZBUTUANAGN | NA | BUGABUFLWY STACRUZBUTUANAGNFLWY TCFGASTACRUZBUTUANAGNFLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.8225 | 125.5143 | Sition Sta. Cruz Manila de Bugabus, Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN472 | ILIHANPOB2BURGOSSDN | NA | ILIHANPOB2BURGOSSDNFHLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | BURGOS |  | Territory 8 | 10.0165 | 126.0679 | Ilihan Burgos_Poblacion 2, Burgos, Surigao Del Norte | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN624 | TSORAPOBBUTUANAGN | BTN_918_GPONA_01 | BUTUA2FLVWY TSORAPOBBUTUANAGNFKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.947 | 125.5334 | Tandang Sora Pob. (Bgy. 12), Butuan City, Agusan Del Norte | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN632 | BAYANCALOBUTUANAGN | BTN_001_GPONA_02 | BAYANCALOBUTUANAGNFKVDWY BUTUA3FVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9448 | 125.5441 | Bayantel Marcos Calo St Silongan Pob. (Bgy. 5), Butuan City, Agusan Del Norte | BAYANCALOBUTUANAGN | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN623 | GUIGSUBD7STBUTUANAGN | BTN_002_GPONA_01 | BUTUANFLVWY GUIGSUBD7STBUTUANAGNFKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9389 | 125.535 | 7th St., Guigona Subd., Jose Rizal Pob. (Bgy. 25), Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1330 | BYG-701 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7139 | 125.7512 | ALONG NATIONAL HIGHWAY FRONT OF PUBLIC PLAZA NEAR KALMUNGGAY ST. BRGY. POBLACION BAY | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1331 | BYG-702 | BYG_702_GPONA_01 / BYG_702_GPONA_02 | NA | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7128 | 125.7601 | Taglatawan, Bayugan City, Agusan del Sur, Philippines | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN21 | POB9CABADAGN | CBD_001_GPONA_01 / CBD_001_GPONA_02 | POB9CABADAGNFHKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.1218 | 125.5451 | Government Center Cabadbaran_Poblacion 9, Cabadbaran, Agusan Del Norte | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1920 | CABADBARAN PDH | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.1245 | 125.5415 | Near Bayantel Tower Circumferential St., Cabadbaran_Poblacion 9, Cabadbaran, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN473 | SRAMPOBCAGDIADNGT | NA | CAGDIAFWY SRAMPOBCAGDIADNGTFLWY | REGION XIII (Caraga) | DINAGAT ISLANDS | CAGDIANAO |  | Territory 8 | 9.9264 | 125.6638 | San Ramon Cagdianao_Poblacion, Cagdianao, Dinagat Islands | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN474 | CAGMINCAGDIADNGT | NA | CAGMINCAGDIADNGTFX | REGION XIII (Caraga) | DINAGAT ISLANDS | CAGDIANAO |  | Territory 8 | 10.1631 | 125.6615 | Cagdianao Mining Corp Valencia, Cagdianao, Dinagat Islands | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN11 | PRK2POBCAGWITSDS | NA | PRK2POBCAGWITSDSFLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | CAGWAIT |  | Territory 8 | 8.9209 | 126.3003 | Purok 2 Cagwait_Poblacion, Cagwait, Surigao Del Sur | TELAJETANDAGSDS | UNITY | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1065 | CAGWAIT RELAY | NA | NA | REGION XIII (Caraga) | SURIGAO DEL SUR | BAYABAS |  | Territory 8 | 8.9421 | 126.2753 | Amag, Bayabas, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN500 | CANTIL | NA | CANTILFHKLVWY | REGION XIII (Caraga) | SURIGAO DEL SUR | CANTILAN |  | Territory 8 | 9.3368 | 125.9722 | Purok 3 Magosilom (Pob.), Cantilan, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2737 | CARIDADPILARSDN | NA | CARIDADPILARSDNFKLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | PILAR |  | Territory 8 | 9.8841 | 126.1163 | Caridad, Pilar, Surigao del Norte, Philippines | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1915 | CARMEN PDH | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | CARMEN |  | Territory 8 | 8.9889 | 125.2946 | Purok Tapon Carmen National Highway, Poblacion (Carmen), Carmen, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN503 | CARRAS | NA | CARRASFHLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | CARRASCAL |  | Territory 8 | 9.3679 | 125.951 | Baybay (Pob.), Carrascal, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2738 | CATANGNANGLUNASDN | NA | CATANGNANGLUNASDNFHLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | GENERAL LUNA |  | Territory 8 | 9.8083 | 126.157 | Catangnan, General Luna, Surigao del Norte, Philippines | CAPHILLSURGAOSDN | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1918 | CD002 | CBD_902_GPONA_01 | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.1156 | 125.5454 | Mabini, Cabadbaran City, Agusan Del Norte, Philippines | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1919 | CD003 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.1212 | 125.5328 | Opp Hse # 5722 Along Calibunan Road, Mabini, Cabadbaran, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1921 | CD004 | CBD_904_GPONA_01 CBD_904_GPONA_02 | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.1249 | 125.5353 | Beside Hse# 5529 Along Curato Cor Mortola St., Cabadbaran_Poblacion 6, Cabadbaran, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN476 | LADGARONCLAVERSDN | CLE_001_GPONA_01 | LADGARONCLAVERSDNF_DFHKLVWDY | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER |  | Territory 8 | 9.57 | 125.7385 | Ladgaron (Pob.), Claver, Surigao Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1089 | CONSUELOADN | NA | CONSUELOADNFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | BUNAWAN |  | Territory 8 | 8.2495 | 125.9781 | Purok 6 Consuelo, Bunawan, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN881 | CORTES RELAY | NA | NA | REGION XIII (Caraga) | SURIGAO DEL SUR | CORTES |  | Territory 8 | 9.2982 | 126.1679 | Tuboran, Cortes, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN501 | CRMENS | CRE_001_GPONA_01 | CRMENSFHLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | CARMEN |  | Territory 8 | 9.2272 | 126.017 | Arado St Carmen (Pob.), Carmen, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN23 | CULITNASIPAGN | NA | CULITNASIPAGNFWY TCFGACULITNASIPAGNFLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9503 | 125.3549 | Culit, Nasipit, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1954 | DAGOCDOCSDS | NA | DAGOCDOCSDSFHLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | TANDAG CITY |  | Territory 8 | 9.0788 | 126.198 | June Eden Fedy Cuanans Lot Fedymart Bldg. Osmena St, Awasian, Tandag, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN777 | HILLMANBRGY3DAPASDN | NA | HILLMANBRGY3DAPASDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | DAPA |  | Territory 8 | 9.7607 | 126.0531 | Hilltop Mansion Dapa_Barangay 3 (Pob.), Dapa, Surigao Del Norte | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1287 | CONSUELOGLUNASDN | NA | CONSUELOGLUNASDNFLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | GENERAL LUNA |  | Territory 8 | 9.7915 | 126.1041 | Brgy. Consuelo General Luna Surigao Del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN477 | SVICENTEDCARMESDN | NA | SVICENTEDCARMESDNFHLDWYF | REGION XIII (Caraga) | SURIGAO DEL NORTE | DEL CARMEN |  | Territory 8 | 9.8714 | 125.9695 | San Vicente San Jose (Pob.), Del Carmen, Surigao Del Norte | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN478 | WBEACHDNAGATDNGT | NA | DINAGAFLWYFHLWY | REGION XIII (Caraga) | DINAGAT ISLANDS | DINAGAT |  | Territory 8 | 9.9552 | 125.5939 | White Beach (Pob.), Dinagat, Dinagat Islands | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN24 | DONROSTUBAYAGN | NA | DONROSTUBAYAGNFHKLWYF | REGION XIII (Caraga) | AGUSAN DEL NORTE | TUBAY |  | Territory 8 | 9.1612 | 125.5634 | Doña Rosario, Tubay, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN43 | BANANAVILLBUTUANAGN | BTN_007_GPONA_01 | BANANAVILLBUTUANAGNFHKLWY DOONGAFHKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9673 | 125.5156 | Banana Village Doongan, Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN34 | KM9DUMALBUTUANAGN | NA | KM9DUMALBUTUANAGNFHLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9527 | 125.4626 | Km. 9 Dumalagan, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN25 | GMALLJCAVEBUTUANAGN | NA | GAIBUTFK GMALLJCAVEBUTUANAGNFKWYFL | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9445 | 125.5321 | Gaisano Mall Imadejas Pob. (Bgy. 24), Butuan City, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN479 | P4HINAMGIGAQTSDN | NA | P4HINAMGIGAQTSDNFHKLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | GIGAQUIT |  | Territory 8 | 9.5873 | 125.6955 | P4 Hinambuyan Ipil (Pob.), Gigaquit, Surigao Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1497 | HAYANGCLAVERSDN | NA | HAYANGCLAVERSDNFLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER |  | Territory 8 | 9.5395 | 125.844 | Brgy.hayanggabon, Claver Surigao del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1702 | SORIANOCABADAGN | NA | SORIANOCABADAGNFHKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.0998 | 125.5646 | Soriano Cabadbaran, Agusan del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN506 | ZONE3POBHINATUSDS | NA | ZONE3POBHINATUSDSHV | REGION XIII (Caraga) | SURIGAO DEL SUR | HINATUAN |  | Territory 8 | 8.3691 | 126.3369 | Hinatuan Mining Zone III Maharlika (Pob.), Hinatuan, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN659 | IPILSURGAOSDN | SRG_004_GPONA_01 | IPILSURGAOSDNFHKLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.795 | 125.4459 | Ipil, Surigao City, Surigao Del Norte | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN26 | PRK4POBJABONAGN | NA | PRK4POBJABONAGNFHLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | JABONGA |  | Territory 8 | 9.3433 | 125.5155 | Purok 4 Poblacion (Jabonga), Jabonga, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN517 | KAHAYBISLIGSDS | BSL_004_GPONA_01 | KAHAYBISLIGSDSFHKLVWY TCFGAKAHAYBISLIGSDSFKLVWY | REGION XIII (Caraga) | SURIGAO DEL SUR | BISLIG CITY |  | Territory 8 | 8.238 | 126.289 | Kahayag, Bislig, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN58 | KAPATU | TRN_001_GPONA_01 | KAPATUFHLWY TCFGAKAPATUTRENTOAGSFHLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | TRENTO |  | Territory 8 | 8.0801 | 126.0361 | Kapatungan, Trento, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN28 | KINABJANASIPAGN | NA | KINABJANASIPAGNFHLWYH | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9749 | 125.3618 | Kinabjangan, Nasipit, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN29 | POBKITCHAAGN | NA | POBKITCHAAGNFHKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | KITCHARAO |  | Territory 8 | 9.4536 | 125.5755 | Kitcharao_Poblacion, Kitcharao, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN56 | LANKIL | NA | LANKILFHLWY TCFGALANGKILATRENTOAGSFHLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | TRENTO |  | Territory 8 | 7.9552 | 126.0825 | Langkilaan, Trento, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1407 | LBRTAD | NA | LBRTADFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | BUNAWAN |  | Territory 8 | 8.1071 | 126.0263 | Purok 1, Brgy. Libertad, Bunawan, Agusan del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN509 | PRK1POBLIANGASDS | NA | PRK1POBLIANGASDSFHLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | LIANGA | Banahao | Territory 8 | 8.6307 | 126.0938 | Purok 1 Lianga_Poblacion, Lianga, Surigao Del Sur | BUTUAN (TECHNICAL OFFICE) | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2026 | LIB01 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.944 | 125.502 | Near Libertad Elementary School, J.C. Aquino Ave. Libertad, Butuan City | AMPAYON FOC | GT | [6 empty] | #N/A
MIN2024 | LIB02 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9441 | 125.5053 | Corner PNPCamp Evangelista & front of Sto. Nino Church, Libertad, Butuan City | AMPAYON FOC | GT | [6 empty] | #N/A
MIN481 | GENAGUINLIBJODNGT | NA | GENAGUINLIBJODNGTXFW | REGION XIII (Caraga) | DINAGAT ISLANDS | LIBJO |  | Territory 8 | 10.2155 | 125.5755 | General Aguinaldo (Bolodbolod), Libjo (Albor), Dinagat Islands | CAPHILLSURGAOSDN | EDOTCO | [6 empty] | #N/A
MIN480 | LIBERTADSMONICSDN | NA | LIBERTADSMONICSDNFX | REGION XIII (Caraga) | SURIGAO DEL NORTE | SANTA MONICA |  | Territory 8 | 9.9843 | 126.0419 | Libertad, Santa Monica (Sapao), Surigao Del Norte | CAPHILLSURGAOSDN | GT | [6 empty] | #N/A
MIN31 | PRK6LIBERBUTUANAGN | NA | LIBTADFLVWY PRK6LIBERBUTUANAGNFKLVDWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9543 | 125.5 | Purok 6, Libertad, Butuan City, Agusan Del Norte | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN511 | PRK2POBLINGIGSDS | LGI_001_GPONA_01 | PRK2POBLINGIGSDSFHKLWDY | REGION XIII (Caraga) | SURIGAO DEL SUR | LINGIG |  | Territory 8 | 8.041 | 126.4142 | Purok 2B Lingig_Poblacion, Lingig, Surigao Del Sur | TELAJETANDAGSDS | PHILTOWER | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN482 | CARMENPOBLORETODNGT | NA | CARMENPOBLORETODNGTFXF | REGION XIII (Caraga) | DINAGAT ISLANDS | LORETO |  | Territory 8 | 10.3477 | 125.5757 | Carmen (Pob.), Loreto, Dinagat Islands | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN45 | LPINIG | NA | LPINIGFHKLWY TCFGALAPINIGANSFRANCAGSFHKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.4278 | 125.9839 | Purok 5 Lapinigan, San Francisco, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN30 | POBLNIEVAGN | NA | LSNIEVFWYFKLWY LSNIEVWYFKLWYF LSNIEVYFKLWYFH POBLNIEVAGNFKLWYFHK | REGION XIII (Caraga) | AGUSAN DEL NORTE | LAS NIEVES |  | Territory 8 | 8.7351 | 125.6021 | LasNieves_Poblacion, Las Nieves, Agusan Del Norte | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN512 | MADRDS | MDR_001_GPONA_01 | MADRDSFHKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | MADRID |  | Territory 8 | 9.2595 | 125.9652 | Linibonan, Madrid, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN32 | BUHANGMGALANAGN | NA | BUHANGMGALANAGNFHLWY MAGALLFHLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | MAGALLANES |  | Territory 8 | 9.0371 | 125.5258 | Buhang, Magallanes, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1812 | MAGALLANES PDH | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | MAGALLANES |  | Territory 8 | 9.0267 | 125.5208 | Bayantel Building, Infront of Cemetery, Buhang, Magallanes, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1930 | MAGKIANGKANG RELAY | NA | NA | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7204 | 125.8471 | Brgy. Villa Undayon, Bayugan City | PROSPERIDAD FOC | GT | [6 empty] | #N/A
MIN778 | QUEZONMAINITSDN | NA | QUEZONMAINITSDNFH | REGION XIII (Caraga) | SURIGAO DEL NORTE | MAINIT |  | Territory 8 | 9.5374 | 125.5244 | Quezon (Pob.), Mainit, Surigao Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1852 | MAINIT RELAY | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | MAINIT |  | Territory 8 | 9.604 | 125.5306 | Barangay Silop, Placer, Surigao del Norte, Philippines | AMPAYON FOC | GT | [6 empty] | #N/A
MIN33 | MALAPONGBUENVAGN | NA | MALAPONGBUENVAGNFLWYFLWY TCFGAMALAPONGBUENVAGNFLWYRFKL | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUENAVISTA |  | Territory 8 | 8.9351 | 125.4055 | Malapong, Buenavista, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN483 | SANISIDROMALIMOSDN | NA | SANISIDROMALIMOSDNFHLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | MALIMONO |  | Territory 8 | 9.6178 | 125.4031 | San Isidro (Pob.), Malimono, Surigao Del Norte | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN514 | LAURTEPOBBISLIGSDS | BSL_001_GPONA_01 / BSL_001_GPONA_02 | BAREMANGBISLIGSDSFHKLVWY | REGION XIII (Caraga) | SURIGAO DEL SUR | BISLIG CITY |  | Territory 8 | 8.2159 | 126.3137 | Laurente St. Bislig_Poblacion, Bislig, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1704 | PRK4MANGBISLIGSDS | NA | PRK4MANGBISLIGSDSFHKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | BISLIG CITY |  | Territory 8 | 8.178 | 126.3562 | John Bosco District, Mangagoy, Bislig, Surgao Del Sur, Mangagoy, Bislig, Surigao Del Sur | TELAJETANDAGSDS | PHILTOWER | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN516 | POBMRIHATSDS | NA | POBMRIHATSDSFHKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | MARIHATAG |  | Territory 8 | 8.7972 | 126.298 | Marihatag_Poblacion, Marihatag, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN947 | MASAOBUTUANAGN | NA | MASAOBUTUANAGNFLWY MASAOFW | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9969 | 125.4871 | Masao, Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN49 | MAUG | NA | MAUGFHLWY TCFGAMAUGPROSPAGSFHLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.6403 | 125.9283 | New Maug, Prosperidad, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN468 | BADASPLACERSDN | NA | BADASPLACERSDNFLWXY | REGION XIII (Caraga) | SURIGAO DEL NORTE | PLACER |  | Territory 8 | 9.6047 | 125.5308 | Badas, Placer, Surigao Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN22 | POBCARCARMENAGN | NA | POBCARCARMENAGNFHWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | CARMEN |  | Territory 8 | 8.9886 | 125.2896 | Poblacion (Carmen), Carmen, Agusan Del Norte | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1093 | MJSHOSPBUTUANAGNIO | NA | MJSHOSFL MJSHOSPBUTUANAGNIDFWYKLV | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9473 | 125.5402 | MJ Santos Hospital JC Aquino Ave., corner Montilla Blvd Agao Pob. (Bgy. 3), Butuan City, Agusan Del Norte | BLK5VPARBUTUANAGN | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN46 | MLORET | NA | MLORETFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | LORETO |  | Territory 8 | 8.1847 | 125.8558 | Loreto_Poblacion, Loreto, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN50 | MROSAR | RSA_001_GPONA_01 | MROSARFLVWY TCFGAP2POBROSARAGSFLVWY | REGION XIII (Caraga) | AGUSAN DEL SUR | ROSARIO |  | Territory 8 | 8.3842 | 126.002 | Quirino St. Purok 2 Rosario_Poblacion, Rosario, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN519 | TINAMIGUELSDS | NA | TINAMIGUELSDSFHKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | SAN MIGUEL |  | Territory 8 | 8.9471 | 126.0392 | Tina, San Miguel, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN488 | POBSANPEDSISONSDN | NA | POBSANPEDSISONSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | SISON |  | Territory 8 | 9.6589 | 125.5222 | Poblacion (San Pedro), Sison, Surigao Del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN494 | MAHAYAHAYSNJOSEDNGT | NA | MAHAYAHAYSNJOSEDNGTFHKLWYFHK MSNJOSFHKLWYFLW TCFGAMAHAYSNJOSEDNGTFLWYFHKLW | REGION XIII (Caraga) | DINAGAT ISLANDS | SAN JOSE (Capital) | San Jose (Pob.) | Territory 8 | 10.0051 | 125.5839 | Mahayahay, San Jose, Dinagat Islands | BUTUAN (TECHNICAL OFFICE) | FTAP | [6 empty] | #N/A
MIN625 | BRGY7POBNASIPAGN | NA | BRGY7POBNASIPAGNFHKLVWY NASIPIFHKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9847 | 125.3457 | Nasipit_Barangay 7 (Pob.), Nasipit, Agusan Del Norte | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN484 | NONOCSURGAOSDN | NA | NONOCSURGAOSDNFHLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.8276 | 125.6053 | Nonoc, Surigao City, Surigao Del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1913 | NP001 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9819 | 125.3458 | Near Bayantel Tower Along Jp Rizal Avenue, Nasipit_Barangay 7 (Pob.), Nasipit, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1914 | NP002 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9844 | 125.345 | Beside Escana Residence District 1, Punta, Nasipit, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1916 | NP003 | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9903 | 125.3486 | Opp Hse# 429 Along Iglesias Street, Nasipit_Barangay 1 (Pob.), Nasipit, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN1447 | PGMCCLAVERSDN | NA | PGMCCLAVERSDNFHL | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER |  | Territory 8 | 9.4962 | 125.878 | PGMC Bagakay (Pob. West), Claver, Surigao Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN485 | MAGSAYPOBPLACERSDN | NA | MAGSAYPOBPLACERSDNFHLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | PLACER |  | Territory 8 | 9.6574 | 125.6017 | Magsaysay (Pob.), Placer, Surigao Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1645 | GARPOB5CABADAGN | CBD_904_GPONA_01 & CBD_902GPONA_01 | GARPOB5CABADAGNFHKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.1192 | 125.5334 | Garame Street Brgy. 5, Cabadbaran City | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN508 | POBLANUZASDS | LNU_001_GPONA_01 | POBLANUZASDSFH | REGION XIII (Caraga) | SURIGAO DEL SUR | LANUZA |  | Territory 8 | 9.2311 | 126.0559 | Zone I (Pob.), Lanuza, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN47 | POBLAPAZADS | NA | POBLAPAZADSFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | LA PAZ |  | Territory 8 | 8.2808 | 125.8094 | LaPaz_Poblacion, La Paz, Agusan Del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1143 | PROSP2 | PSP_001_GPONA_01 | PROSP2FHKLVWY TCFGAPROSP2PROSPAGSFKLVWY | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.6 | 125.9193 | Purok 1, Prosperidad_Poblacion (Bahbah), Prosperidad, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN628 | PROSPE | NA | PROSPEFHKLWY TCFGAPROSPEPROSPAGSFHKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.6223 | 125.9096 | Prosperidad_Poblacion (Bahbah), Prosperidad, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1512 | PROSPERIDAD FOC | SFN_001_GPONA_01 | NA | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.509 | 125.9728 | San Francisco Barangay 3 (Pob.), San Francisco, Agusan Del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1890 | PROSPERIDAD SDH | NA | NONE | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.5996 | 125.9175 | Near Iglesia ni Cristo, Prosperidad National Highway, Prosperidad_Poblacion (Bahbah), Prosperidad, Agusan Del Sur | PROSPERIDAD FOC | GT | [6 empty] | #N/A
MIN48 | PTINAY | PLC_001_GPONA_01& PSP_002_GPONA_01 | PTINAYFHLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.5494 | 125.9441 | Patinay, Prosperidad, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN129 | PULALU | NA | PULALUFHLWY TCFGAPULALUTRENTOAGSFHLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | TRENTO |  | Territory 8 | 8.0109 | 126.076 | Pulanglupa, Trento, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN497 | BAHIBAROBOSDS | NA | BAHIBAROBOSDSFHL | REGION XIII (Caraga) | SURIGAO DEL SUR | BAROBO |  | Territory 8 | 8.4951 | 126.04 | Bahi, Barobo, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN471 | SATUYAYHONSOCOROSDN | NA | SATUYAYHONSOCOROSDNZ | REGION XIII (Caraga) | SURIGAO DEL NORTE | SOCORRO |  | Territory 8 | 9.6586 | 125.9613 | Sitio Atuyay Honrado, Socorro, Surigao Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN502 | RCARAS | NA | RCARASFLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | CARRASCAL |  | Territory 8 | 9.3415 | 125.9402 | Carrascal Relay, Sitio TabonTabon Bacolod, Carrascal, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN507 | SANJUHINATUSDS | NA | SANJUHINATUSDSF | REGION XIII (Caraga) | SURIGAO DEL SUR | HINATUAN |  | Territory 8 | 8.4122 | 126.22 | San Juan, Hinatuan, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN510 | PALOLINGIGSDS | NA | PALOLINGIGSDSFKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | LINGIG |  | Territory 8 | 7.9875 | 126.4278 | Palo Alto, Lingig, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN513 | VALENLINGIGSDS | NA | VALENLINGIGSDSFHLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | BISLIG CITY |  | Territory 8 | 8.2294 | 126.4454 | Valencia, Lingig, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1680 | ROBNSNBUTUANAGNID | BTN_003_GPONA_01 / BTN_003_GPONA_02 | ROBNSNBUTUANAGNEXPIDFWYDWYZ | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.941 | 125.519 | Robinsons Place Butuan J.C. Aquino Ave., Bayanihan Pob. (Bgy. 27), Butuan City, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN35 | ROSAURDPOBBUTUANAGN | BTN_005_GPONA_01 | ROSALEFLWY ROSAURDPOBBUTUANAGNFKLVDWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9518 | 125.5386 | Rosales St. Urduja Pob. (Bgy. 9), Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1063 | RTALACADS | NA | RTALACADSFWY | REGION XIII (Caraga) | AGUSAN DEL SUR | TALACOGON |  | Territory 8 | 8.5128 | 125.81 | Brgy Rizal Talacogon, Agusan Del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1917 | RTR PDH | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | REMEDIOS T. ROMUALDEZ |  | Territory 8 | 9.0524 | 125.5867 | Near Former Capt Apat Resi Prk 2 LantaO Street, RemediosTRomualdez_Poblacion I (Agay), Remedios T. Romualdez, Agusan Del Norte | AMPAYON FOC | GT | [6 empty] | #N/A
MIN36 | POB1AGAYREMRAGN | NA | POB1AGAYREMRAGNFHKLWYFHL | REGION XIII (Caraga) | AGUSAN DEL NORTE | REMEDIOS T. ROMUALDEZ |  | Territory 8 | 9.053 | 125.5852 | RemediosTRomualdez_Poblacion I (Agay), Remedios T. Romualdez, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2591 | SAMPAVERUELADS | NA | SAMPAVERUELADSFKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | VERUELA |  | Territory 8 | 8.0251 | 125.9481 | Sampaguita, Agusan del Sur, Philippines | PROSPERIDAD FOC | PHILTOWER | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1888 | SAN FRANCISCO SDH | SFN_901_GPONA_01 | NA | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.5057 | 125.9861 | Front Davao Central Warehouse, SanFrancisco_Barangay 5 (Pob.), San Francisco, Agusan Del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN629 | SANFRA | SFN_002_GPONA_01 | SANFRAFHKLVWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.5042 | 125.9757 | Purok 3, SanFrancisco_Barangay 1 (Pob.), San Francisco, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN487 | PRK3POBSFRANCSDN | NA | PRK3POBSFRANCSDNFHLWY TCFGAPOBSFRANCSDNFLVWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SAN FRANCISCO |  | Territory 8 | 9.7734 | 125.4217 | Purok 3 SanFrancisco(Anaoaon)_Poblacion, San Francisco (AnaoAon), Surigao Del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN486 | DELCARMENISIDROSDN | NA | DELCARMENISIDROSDNFLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SAN ISIDRO |  | Territory 8 | 9.9348 | 126.0897 | Del Carmen (Pob.), San Isidro, Surigao Del Norte | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN51 | SANLUI | NA | SANLUIFHKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN LUIS |  | Territory 8 | 8.5005 | 125.7396 | SanLuis_Poblacion, San Luis, Agusan Del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1508 | SAYAKAIRDCARMESDN | NA | SAYAKAIRDCARMESDNFLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | DEL CARMEN |  | Territory 8 | 9.856 | 126.018 | Sayak Airport Sayak, Del Carmen, Surigao Del Norte | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN504 | SCORTS | NA | SCORTSFW | REGION XIII (Caraga) | SURIGAO DEL SUR | CORTES |  | Territory 8 | 9.2763 | 126.1875 | Cortes_Poblacion, Cortes, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1887 | SFC-02 | SFN_902_GPONA_01 | NA | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.5079 | 125.9814 | Near Amatorio Residences, SanFrancisco_Barangay 1 (Pob.), San Francisco, Agusan Del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN782 | PUROK4GLUNASDN | GNA_001_GPONA_01 | PUROK4GLUNASDNFHKLVWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | GENERAL LUNA |  | Territory 8 | 9.7882 | 126.153 | GeneralLuna_Poblacion IV (Purok IV), General Luna, Surigao Del Norte | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN53 | SIBAGA | SBG_001_GPONA_01 | SIBAGAFHLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SIBAGAT |  | Territory 8 | 8.8249 | 125.6929 | Purok 10 Sibagat_Poblacion, Sibagat, Agusan Del Sur | PROSPERIDAD FOC | PHILTOWER | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN505 | SPRNZA | NA | SPRNZAFKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | ESPERANZA |  | Territory 8 | 8.6794 | 125.6482 | Esperanza_Poblacion, Esperanza, Agusan Del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1190 | SRG-701 | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7906 | 125.4945 | ALONG MAGALLANES ST. CORNER BORROMEO ST. , FRONT CALTEX GAS STATION, BARANGAY TAFT., SURIGAO CITY | CAPHILLSURGAOSDN | GT | [6 empty] | #N/A
MIN1191 | SRG-702 | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7852 | 125.4903 | ALONG RIZAL ST. FRONTING MERCURY DRUG, SURIGAO CITY MINDANAO | CAPHILLSURGAOSDN | GT | [6 empty] | #N/A
MIN1187 | SRG-703 | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7771 | 125.4822 | ALONG NATIONAL HIGHWAY FRONTING OF CT MOTOR POOL BESIDE ALLIED MOTOR SHOP, BARANGAY LUNA, SURIGAO CI | CAPHILLSURGAOSDN | GT | [6 empty] | #N/A
MIN1189 | SRG-704 | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7741 | 125.4783 | CORNER NATIONAL HWAY AND TOGBONGON ROAD BRGY. RIZAL, SURIGAO CITY | CAPHILLSURGAOSDN | GT | [6 empty] | #N/A
MIN1732 | SRG-705 | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7579 | 125.4829 | INFRONT OF CITI HARDWARE ALONG NATIONAL HIGHWAY, ALANGALANG, SURIGAO CITY | CAPHILLSURGAOSDN | GT | [6 empty] | #N/A
MIN1188 | SRG-706 | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7383 | 125.4922 | BESIDE WAITING SHED, BEFORE BONIFACIO ELEM. SCHOOL, ALONG NATIONAL HIGHWAY, BRGY.BONAFICIO, , SURIGA | CAPHILLSURGAOSDN | GT | [6 empty] | #N/A
MIN54 | STAIRE | NA | STAIREFHKLWY TCFGASTAMARIAPROSPAGSFHKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.6606 | 125.8904 | Santa Maria, Prosperidad, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN55 | STAJOS | NA | STAJOSFHKLVWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SANTA JOSEFA |  | Territory 8 | 7.9837 | 126.029 | Purok 9 SantaJosefa_Poblacion, Santa Josefa, Agusan Del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN37 | POB1SNTGOAGN | NA | POB1SNTGOAGNFHKLWY TCFGAPOB1SNTGOAGNFHKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | SANTIAGO |  | Territory 8 | 9.2639 | 125.5613 | Santiago_Poblacion I, Santiago, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1267 | STIREN | NA | STIRENFLWYFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7351 | 125.7538 | Purok 1, Santa Irene, Bayugan, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN779 | PRKPHILVSURGAOSDN | SRG_702_GPONA_01 | PRKPHILVSURGAOSDNFHKLVWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7834 | 125.489 | Purok Philvocs Washington (Pob.), Surigao City, Surigao Del Norte | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1820 | SURIGAO NDC | SRG_003_GPONA_01 | BAYWASHINSURGAOSDNFK | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7913 | 125.4919 | Cabrera Street, Brgry 2, Baybay, Surigao City, Surigao Del Norte | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN490 | SENARESTAGANASDN | NA | SENARESTAGANASDNFHLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | TAGANAAN |  | Territory 8 | 9.6935 | 125.5829 | Senares St. Aurora (Pob.), TaganaAn, Surigao Del Norte | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN491 | TAGANITOCLAVERSDN | NA | TAGANITOCLAVERSDNFX | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER |  | Territory 8 | 9.5417 | 125.8204 | Taganito, Claver, Surigao Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN520 | POBTAGBINASDS | TGI_001_GPONA_01 | POBTAGBINASDSFHKLWY TCFGAPOBTAGBINASDSFHKLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | TAGBINA |  | Territory 8 | 8.4595 | 126.1637 | Tagbina_Poblacion, Tagbina, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1117 | SBILITAGCATCARMENAGN | NA | SBILITAGCATCARMENAGNFKLWY TAGCATONGADNFWYFKLWY TCFGASBILITAGCATCARMENAGNFKLWYFWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | CARMEN |  | Territory 8 | 9.0089 | 125.2573 | Sitio Bilihon Tagcatong, Carmen, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1553 | TAGLATAWAN | BYG_002_GPONA_01 | TAGLATAWANFHKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.9383 | 125.6304 | Narra Ave. Taglatawan Bayugan Agusan del Sur | PROSPERIDAD FOC | PHILTOWER | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN40 | TAGMAMTUBAYAGN | NA | TAGMAMTUBAYAGNFHLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | TUBAY |  | Territory 8 | 9.2054 | 125.5644 | Tagmamarkay, Tubay, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1142 | TALAC2 | NA | TALAC2FLW | REGION XIII (Caraga) | AGUSAN DEL SUR | TALACOGON |  | Territory 8 | 8.4947 | 125.8446 | Del Monte, Talacogon, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN57 | TALACO | NA | TALACOFHKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | TALACOGON |  | Territory 8 | 8.448 | 125.7854 | San Agustin (Pob.), Talacogon, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1594 | TALIGALEGBUTUANAGN | NA | TALIGABUTUANFHKLWY TALIGALEGBUTUANAGNFHKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9383 | 125.6304 | Taligaman, Alipao Butuan City | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN785 | TANDAG | NA | NA | REGION XIII (Caraga) | SURIGAO DEL SUR | TANDAG CITY |  | Territory 8 | 9.0716 | 126.1937 | Pimentel St., Telaje, Tandag, Surigao Del Sur | TELAJETANDAGSDS | GT | [6 empty] | #N/A
MIN1509 | TANDAGAIRPT | NA | TANDAGAIRPTFHKLVWY | REGION XIII (Caraga) | SURIGAO DEL SUR | TANDAG CITY |  | Territory 8 | 9.0774 | 126.1706 | Tandag Airport Awasian, Tandag, Surigao Del Sur | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1709 | THPALCLAVERSDN | NA | THPALCLAVERSDNFHWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER |  | Territory 8 | 9.5434 | 125.8117 | THPAL(Taganito HPAL Mining)_Claver_Surigao del NorteBagakay (Pob. West), Claver, Surigao Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN946 | TIMAMANATUBODSDN | NA | TCFGATIMAMANATUBODSDNFLWDY TIMAMANATUBODSDNFLWDY | REGION XIII (Caraga) | SURIGAO DEL NORTE | TUBOD |  | Territory 8 | 9.5969 | 125.5656 | Timamana, Tubod, Surigao del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN630 | TRENTO | TRN_002_GPONA_01 | TRENTOFHKLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | TRENTO |  | Territory 8 | 8.0454 | 126.064 | Trento_Poblacion, Trento, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN492 | STACRUZTUBJONDNGT | NA | STACRUZTUBJONDNGTFF | REGION XIII (Caraga) | DINAGAT ISLANDS | TUBAJON |  | Territory 8 | 10.3143 | 125.5715 | Santa Cruz (Pob.), Tubajon, Dinagat Islands | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN41 | POB1TUBAYAGN | NA | POB1TUBAYAGNFLWY TCFGAPOB1TUBAYAGNFHKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | TUBAY |  | Territory 8 | 9.1659 | 125.5227 | Tubay_Poblacion 1, Tubay, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN493 | POBTUBODSDN | NA | POBTUBODSDNFHKLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | TUBOD |  | Territory 8 | 9.5493 | 125.5668 | Poblacion (Tubod), Tubod, Surigao Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1266 | TUBRAN | NA | TUBRANFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.5388 | 125.8585 | San Vicente, Prosperidad, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2739 | UNIONDAPASDN | NA | UNIONDAPASDNFHLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | DAPA |  | Territory 8 | 9.7528 | 126.1081 | Dapa, Surigao del Norte, Philippines | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN38 | PRK16SVCNTBUTUANAGN | NA | TCFGAPRK16SVCNTBUTUANAGNFKLVWY VCENTEFKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9065 | 125.5499 | Purok 16A San Vicente, Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1302 | VILLATAGBINASDS | NA | TCFGAVILLATAGBINASDSYSZ | REGION XIII (Caraga) | SURIGAO DEL SUR | TAGBINA |  | Territory 8 | 8.4889 | 126.2711 | Sitio Ambacon Villaverde, Tagbina, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN27 | DINOPVKNANGBUTUANAGN | BTN_006_GPONA_1 & BTN_006_GPONA_02 | DINOPVKNANGBUTUANAGNFHKLWY TCFGADINOPVKNANGBUTUANAGNFHKLWYFH VKNANGFHKLWYUF | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9313 | 125.536 | Dinopol St. Villa Kananga, Butuan City, Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN59 | VRUELA | NA | VRUELA | REGION XIII (Caraga) | AGUSAN DEL SUR | VERUELA |  | Territory 8 | 8.063 | 125.9542 | Sitio Maasin Veruela_Poblacion, Veruela, Agusan Del Sur | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1248 | WASHINSURGAOSDN | NA | WASHINSURGAOSDNFHKLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7902 | 125.483 | Washington (Pob.), Surigao City, Surigao Del Norte | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN515 | YLIMSURGAOSDN | SRG_002_GPONA_01 / SRG_002_GPONA_02 | YLIMSURGAOSDNFKLVWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7864 | 125.4985 | YUIPCOLIM Building Borromeo St. Taft (Pob.), Surigao City, Surigao Del Norte | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2273 | ROSARIOTANDAGSDS | NA | ROSARIOTANDAGSDSFLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | TANDAG CITY |  | Territory 8 | 9.0488 | 126.2086 | Barangay Road, Rosario, Tandag, Surigao del Sur, Philippines | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2503 | PDGAISATANDAGSDSPC | NA | NA | REGION XIII (Caraga) | SURIGAO DEL SUR | TANDAG CITY |  | Territory 8 | 9.0761 | 126.1984 | G/F GAISANO CAPITAL BUILDING CABRERA & NAVALES STREET, POBLACION TANDAG CITY, SURIGAO DEL SUR. | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2599 | BNV_901 | BNV_901_GPONA_01 | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUENAVISTA |  | Territory 8 | 8.9765 | 125.4066 | 271 SORIANO ST., Poblacion 6, BUENAVISTA, AGUSAN DEL NORTE, REGION XIII (Caraga), MIN | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2809 | SMCBUTUAN | NA | SMCBUTUAN1IDFKWYFKWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9454 | 125.5336 | JC AQUINO, BUTUAN CITY, AGUSAN DEL NORTE | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2933 | CLOUD9GLUNASDNEM | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | GENERAL LUNA |  | Territory 8 | 9.8124 | 126.1628 | CLOUDNINE,GENERAL LUNA,SURIGAO DEL NORTE | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3140 | TRVLINGGLUNASDNCOW | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | GENERAL LUNA |  | Territory 8 | 9.7952 | 126.1609 | TOURISM ROAD, GENERAL LUNA, SURIGAO DEL NORTE | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3141 | SRELCOPOBDAPASDNSPEM | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | DAPA |  | Territory 8 | 9.7606 | 126.048 | ADDRESS: BRGY. POBLACION, DAPA, SIARGAO ISLAND, SURIGAO DEL NORTE | CAPHILLSURGAOSDN | UNITY | [6 empty] | #N/A
MIN2592 | LAFORTUNAVRUELAAGS | NA | LAFORTUNAVRUELAAGSFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | VERUELA |  | Territory 8 | 8.0264 | 125.9126 | La Fortuna, Veruela, Agusan del Sur, Philippines | BNAWAN | PHILTOWER | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2729 | P2AMBAGOBUTUANAGN | NA | P2AMBAGOBUTUANAGNFHKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9777 | 125.5019 | Masao Rd, Butuan City, Agusan Del Norte, Philippines | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2794 | LEMOND10BUTUANAGN | NA | LEMOND10BUTUANAGNFLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9417 | 125.5869 | Lemon, Butuan City, Agusan Del Norte, Philippines | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2589 | DONMATEOVRUELAAGS | NA | DONMATEOVRUELAAGSFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | VERUELA |  | Territory 8 | 8.0895 | 125.8884 | Don Mateo National Road, Veruela, 8509 Agusan del Sur, Philippines | BNAWAN | PHILTOWER | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2271 | ALEGRIASFRANCAGS | NA | ALEGRIASFRANCAGSFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.5065 | 125.9968 | BrgyAlegria_SanFrancisco_AgusanDelSur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2590 | MASAYANVRUELAAGS | NA | MASAYANVRUELAAGSFLWY | REGION XIII (Caraga) | AGUSAN DEL SUR | VERUELA |  | Territory 8 | 8.0547 | 125.9054 | BrgyCaigangan_Veruela_AgusandelSur | BNAWAN | PHILTOWER | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2698 | STCHRISTNLIANGASDS | NA | STCHRISTNLIANGASDSFHLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | LIANGA |  | Territory 8 | 8.671 | 126.1304 | BrgySaintChristine_Lianga | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1750 | TAGOSDS | NA | NA | REGION XIII (Caraga) | SURIGAO DEL SUR | TAGO |  | Territory 8 | 9.0212 | 126.2345 | Tago, Surigao del Sur, Philippines | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2696 | SALVACIONTANDAGSDS | NA | SALVACIONTANDAGSDSFLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | TANDAG CITY |  | Territory 8 | 9.1091 | 126.1561 | Salvacion, Tandag,, Bayan ng Tandag, Surigao del Sur, Philippines | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2792 | BITOSBUTUANAGN | NA | BITOSBUTUANAGNFLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.8859 | 125.5397 | Bit-os, Butuan City, Agusan del Norte | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3476 | TELAJETANDAGSDS | TND_001_GPONA_01 / TND_001_GPONA_02 | TELAJETANDAGSDSFKLVWY | REGION XIII (Caraga) | SURIGAO DEL SUR | TANDAG CITY |  | Territory 8 | 9.0726 | 126.1935 | Pimentel Street, Telaje, Tandag, Surigao del Sur, Philippines | TELAJETANDAGSDS | GT | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2963 | GTWASHINSURGAOSDNPC | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7868 | 125.492 | Ground Floor Salinas Bldg corner Rizal Street Gimena Street,Washington, Surigao City, 8400 Surigao del Norte, Philippines | CAPHILLSURGAOSDN | GT | [6 empty] | #N/A
MIN2687 | MAHAYBUTUANAGN | NA | MAHAYBUTUANAGNFL | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9258 | 125.5627 | Brgy. Mahay, Butuan City, Agusan Del Norte, Philippines | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2731 | P4BAANBUTUANAGN | NA | P2KM3BAANBUTUANAGNFKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9473 | 125.5661 | Purok 2 Km 3 Barangay Baan, Butuan City, Agusan Del Norte, Philippines | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2701 | PIGDAULANBUTUANAGN | NA | P3PGDAULNBUTUANAGNFKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Pigdaulan | Territory 8 | 8.9 | 125.5 | Brgy. Pigdaulan, Butuan City, Agusan Del Norte, Philippines | BUTUAN (TECHNICAL OFFICE) | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2881 | SANVICENBUTUANAGN | NA | SANVCNTEBUTUANAGNFKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9 | 125.5 | Brgy. San Vicente, Butuan City, Agusan Del Norte, Philippines | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2593 | SANGABVRUELAGS | NA | SANGABVRUELAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | VERUELA |  | Territory 8 | 8.0982 | 125.9428 | Brgy. San Gabriel, Veruela, Agusan del Sur | BNAWAN | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3091 | MABUHAYPILARSDN | NA | MABUHAYPILARSDNFL | REGION XIII (Caraga) | SURIGAO DEL NORTE | PILAR |  | Territory 8 | 9.8225 | 126.108 | Surigao City, Surigao del Norte, Philippines | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2871 | PANGABUGNBUTNADN | NA | PANGABUGNBUTNADNFLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9247 | 125.5475 | Brgy. Pangabugan, Butuan City, Agusan Del Norte, Philippines | AMPAYON FOC | UNITY | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3302 | P2PISAANSFRANCAGS | NA | P2PISAANSFRANCAGSFKLVWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.5317 | 125.952 | San Francisco, Agusan del Sur, Philippines | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3282 | P2PASTASFRANCAGS | NA | P2PASTASFRANCAGSFKLVWY | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.4332 | 125.9945 | San Francisco, Agusan del Sur, Philippines | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3278 | POB8BUENVAGN | NA | POB8BUENVAGNFKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUENAVISTA |  | Territory 8 | 8.9791 | 125.4108 | Buenavista, Agusan Del Norte, Philippines | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2798 | BANZABUTUANAGN | NA | BANZABUTUANAGNFKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9815 | 125.5452 | Brgy Banza_Butuan City_Agusan del Norte | AMPAYON FOC | PHILTOWER | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2903 | BILAYBUTUANAGN | NA | BILAYBUTUANAGNFKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.8546 | 125.5791 | Brgy Bilay_Butuan City_Agusan del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3697 | PRK6BRGY4SFRANCAGS | NA | PRK6BRGY4SFRANCAGSFLVWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | SAN FRANCISCO |  | Territory 8 | 8.5073 | 125.9841 | CapSite_Brgy2_SanFranciso_SDN | PROSPERIDAD FOC | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2795 | BRGY19POBBUTUANADN | NA | BRGY19POBBUTUANADNFKLVWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9504 | 125.5526 | Brgy 19 Buhangin, Butuan City, Agusan del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2797 | BADINGPOBBUTUANAGN | NA | BADINGPOBBUTUANAGNFKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9704 | 125.5336 | Brgy Bading (Pob), Butuan City Agusan Del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2868 | LUMBOCBUTUANAGN | NA | LUMBOCBUTUANAGNFKLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.0086 | 125.5049 | Brgy. Lumbocan, Butuan City, Agusan del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3566 | TALISAYNASIPAGN | NA | TALISAYNASIPAGNFHLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.98 | 125.3394 | Purok Narra, Brgy Talisay, Nasipit, Agusan del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3695 | P2MALINAOGLUNASDN | NA | P2MALINAOGLUNASDNFLVWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | GENERAL LUNA |  | Territory 8 | 9.7706 | 126.1259 | P-2, Brgy. Malinao, General Luna, Surigao Del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3740 | TCFGAIPILSURGAOSDN | NA | TCFGAIPILSURGAOSDNFLW | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7826 | 125.4318 | Sitio Kabugwason, Barangay Ipil, Surigao City | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3770 | TCFGAP4MATISURIGSDN | NA | TCFGAP4MATISURIGSDNFLW | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7173 | 125.4768 | Purok 4, Barangay Mat-i, Surigao City, SURIGAO DEL NORTE | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3779 | TCFGASKLNGSURGAOSDN | NA | TCFGASKLNGSURGAOSDNFLW | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.6733 | 125.5039 | Purok 1, Barangay Sukailang, Surigao City | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3912 | TCFGACMBYNBACUAGSDN | NA | TCFGACMBYNBACUAGSDNLY | REGION XIII (Caraga) | SURIGAO DEL NORTE | BACUAG |  | Territory 8 | 9.5564 | 125.6411 | Brgy. Cambuayon, Bacuag, Surigao del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3928 | TCFGADYWANCLAVERSDN | NA | TCFGADYWANCLAVERSDNLY | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER |  | Territory 8 | 9.5618 | 125.7138 | Purok 3, Barangay Daywan, Claver, Surigao del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3929 | TCFGAHAYANCLAVERSDN | NA | TCFGAHAYANCLAVERSDNFLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER |  | Territory 8 | 9.5401 | 125.8411 | Purok 1, Hayanggabon, Claver, Surigao del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3090 | TUBORANDELCARSDN | NA | TUBORANDELCARSDNLY | REGION XIII (Caraga) | SURIGAO DEL NORTE | DEL CARMEN |  | Territory 8 | 9.8212 | 126.0495 | Maasin, Pilar, Surigao del Norte | CAPHILLSURGAOSDN | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3933 | TCFGAPNTODAGUSTNSDS | NA | TCFGAPNTODAGUSTNSDSFLWY | REGION XIII (Caraga) | SURIGAO DEL SUR | MARIHATAG |  | Territory 8 | 8.7748 | 126.249 | Purok 6, Barangay Pongtod, San Agustin, Surigao del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3713 | VALBUECOPOBBAYUGAGS | NA | VALBUECOPOBBAYUGAGSFW | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7173 | 125.7501 | Valbueco Street, Poblacion, Bayugan City, Agusan del Sur | PROSPERIDAD FOC | GT | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3767 | TCFGALUNASURGAOSDN | NA | TCFGALUNASURGAOSDNFLW | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7497 | 125.4912 | Sitio Bacud, Barangay Luna, Surigao City | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3777 | TCFGABILARSURGAOSDN | NA | TCFGABILARSURGAOSDNFLW | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.8192 | 125.4426 | Purok 4 Looc, Barangay Punta Bilar, Surigao City | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3887 | TCFGALIPATASURGAOSDN | NA | TCFGALIPATASURGAOSDNFLW | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.8053 | 125.4523 | Brgy. Lipata, Surigao City, Surigao del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3300 | TCFGAP4MABNSURGAOSDN | NA | TCFGAP4MABNSURGAOSDNFLW | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.6964 | 125.4725 | Purok 4, Togonan, Brgy. Mabini, Surigao City, Surigao del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3337 | TCFGARIZALSURGAOSDN | NA | TCFGARIZALSURGAOSDNFLW | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.7821 | 125.4725 | Brgy Rizal, Surigao City | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3927 | TCFGAURBIZCLAVERSDN | NA | TCFGAURBIZCLAVERSDNFLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER |  | Territory 8 | 9.5534 | 125.7735 | Purok 4, Urbiztondo, Claver, Surigao del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3762 | TCFGAPOB1GLUNASDN | NA | TCFGAPOB1GLUNASDNFLWY | REGION XIII (Caraga) | SURIGAO DEL NORTE | GENERAL LUNA |  | Territory 8 | 9.7816 | 126.1545 | Bgy. 1, Poblacion , Gen.Luna , Siargao Island, SDN | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4081 | TCISCUBINASIPAGN | NA | TCISCUBINASIPAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9739 | 125.3843 | Brgy.Cubi-cubi,NASIPIT,AGUSAN DEL NORTE | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4092 | TCISTINIWISBUTUANAGN | NA | TCISTINIWISBUTUANAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9793 | 125.5793 | Brgy.Tiniwisan,BUTUAN CITY (Capital),AGUSAN DEL NORTE | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4093 | TCISTRIANGULNASIPAGN | NA | TCISTRIANGULNASIPAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9744 | 125.3491 | Brgy.Triangulo,NASIPIT,AGUSAN DEL NORTE | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4125 | TCAGLBRTAD1BUTUANAGN | NA | TCAGLBRTAD1BUTUANAGNFW | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9468 | 125.5133 | P-A89, Employees Village, Libertad, Butuan City | AMPAYON FOC | ALT GLOBAL | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3954 | TLISAYBENITSDNLEGO | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY |  | Territory 8 | 9.9576 | 126.0046 | Talisay (Pob.), SAN BENITO, SURIGAO DEL NORTE, REGION XIII (Caraga), MIN | CAPHILLSURGAOSDN | GT | [6 empty] | #N/A
MIN3914 | CPTOLSNJOSEDNGTLEGO | NA | NA | REGION XIII (Caraga) | DINAGAT ISLANDS | SAN JOSE |  | Territory 8 | 10.0231 | 125.5971 | 2JC4+C8G, San Jose, Dinagat Islands, Philippines | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW53 | MALINAOSPCOW | NA | NA | REGION XIII (Caraga) | SURIGAO DEL NORTE | GENERAL LUNA |  | Territory 8 | 9.7754 | 126.1365 | Malinao, Gen. Luna, Siargao Island, Surigao del Norte | CAPHILLSURGAOSDN | GT | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2692 | TUNGAOBUTUANAGN | NA | TUNGAOBUTUANAGNFLWY | REGION XIII (Caraga) | AGUSAN DEL NORTE | Butuan City (Capital) |  | Territory 8 | 8.783 | 125.5677 | Brgy tungao, Butuan City, Agusan Del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2164 | Britania Resort | NA | NA | REGION XIII (Caraga) | SURIGAO DEL SUR | SAN MIGUEL |  | Territory 8 | 126.2056 | 8.6965 | Brgy Britania, Surigao | TELAJETANDAGSDS | GT | [6 empty] | #N/A
MIN4194 | TCAGBAANKM3BUTUANAGN | NA | TCAGBAANKM3BUTUANAGNFW | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) |  | Territory 8 | 8.9559 | 125.5712 | Brgy. Baan KM 3, Butuan City, Agusan Del Norte | AMPAYON FOC | ALT GLOBAL | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4113 | TCAGPOYOHONBUTUANAGN | NA | TCAGPOYOHONBUTUANAGNFW | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) |  | Territory 8 | 8.9584 | 125.541 | Brgy.Port Poyohon Pob. (Bgy. 17 - New Asia),BUTUAN CITY (CAPITAL),AGUSAN DEL NORTE | AMPAYON FOC | ALT GLOBAL | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4192 | TCAGVKANANGABUTUANAGN | NA | TCAGVKANANGABUTUANAGNFW | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) |  | Territory 8 | 8.936 | 125.5272 | Villa Kananga, Butuan City, Agusan Del Norte | AMPAYON FOC | ALT GLOBAL | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4143 | TCISALEGRIASFRANCAGS | NA | TCISALEGRIASFRANCAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO |  | Territory 8 | 8.5076 | 126.0138 | Brgy.Alegria,SAN FRANCISCO,AGUSAN DEL SUR | PROSPERIDAD FOC | ISON | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4040 | TCISAURORAPROSPAGS | NA | TCISAURORAPROSPAGSLY | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD (Capital) |  | Territory 8 | 8.5932 | 125.8399 | Brgy.Aurora, Prosperidad Agusan del Sur | PROSPERIDAD FOC | ISON | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4045 | TCISMYGATASNBAYUGAGS | NA | TCISMYGATASNBAYUGAGSLY | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.727 | 125.7309 | Brgy,Maygatasan, Bayugan City, Agusan del Sur | PROSPERIDAD FOC | ISON | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4046 | TCISSALVCIONBAYUGAGS | NA | TCISSALVCIONBAYUGAGSLY | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.6868 | 125.7125 | Brgy,Salvacion, Bayugan City, Agusan del Sur | PROSPERIDAD FOC | ISON | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4203 | TCFGABRGYPOBBAROBOSDS | NA | TCFGABRGYPOBBAROBOSDSFW | REGION XIII (Caraga) | SURIGAO DEL SUR | BAROBO |  | Territory 8 | 8.5393 | 126.1199 | Brgy. Poblacion, Barobo, Surigao Del Sur | TELAJETANDAGSDS | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3741 | TCFGALIBERTBUTUANAGN | NA | TCFGALIBERTBUTUANAGNFW | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) |  | Territory 8 | 8.9443 | 125.5078 | Brgy Libertad, Butuan City, Agusan del Norte | AMPAYON FOC | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3565 | P14VICENTEBUTUANAGN | NA | P14VICENTEBUTUANAGNFW | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) |  | Territory 8 | 8.8985 | 125.549 | Purok 14 San Vicente, Butuan City, Agusan del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3874 | TCAICTRINIDADSURGAOSDN | NA | TCAICTRINIDADSURGAOSDNFW | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) |  | Territory 8 | 9.688 | 125.5093 | Brgy. Trinidad, Surigao City, Surigao del Norte | CAPHILLSURGAOSDN | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4139 | TCFGABONIFSURGAOSDN | NA | TCFGABONIFSURGAOSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) |  | Territory 8 | 9.739 | 125.4932 | KM. 7,BRGY. BONIFACIO,SURIGAO CITY,SURIGAO DEL NORTE | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4041 | TCISBUCACBAYUGAGS | NA | TCISBUCACBAYUGAGSLY | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7 | 125.7637 | Brgy,.Bucac , Bayugan City, Agusan del Sur | PROSPERIDAD FOC | ISON | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4042 | TCISCANAYUGNBAYUGAGS | NA | TCISCANAYUGNBAYUGAGSLY | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7506 | 125.7216 | Brgy.Canayugan, Bayugan, Agusan del Sur | PROSPERIDAD FOC | ISON | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2940 | TCISMATABAOBUENVAGN | NA | TCISMATABAOBUENVAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUENAVISTA |  | Territory 8 | 8.9676 | 125.4197 | Brgy. Matabao, Buenavista, Agusan Del Norte | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4089 | TCISPINAMACBUTUANAGN | NA | TCISPINAMACBUTUANAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) |  | Territory 8 | 8.9676 | 125.4772 | Brgy.Pinamanculan,BUTUAN CITY (Capital),AGUSAN DEL NORTE | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2869 | BAANRVRSIDBUTUANAGN | None | BAANRVRSIDBUTUANAGNFW | REGION XIII (Caraga) | AGUSAN DEL NORTE | Butuan City (Capital) |  | Territory 8 | 8.9595 | 125.5501 | Brgy. Mahogany, Butuan City, Agusan del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2697 | TAGABACABUTUANAGN | none | TAGABACABUTUANAGNFW | REGION XIII (Caraga) | AGUSAN DEL NORTE | Butuan City (Capital) |  | Territory 8 | 8.9034 | 125.5619 | Brgy. Tagabaca, Butuan City, Agusan del Norte | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4079 | TCISBANCASIBUTUANAGN | None | TCISBANCASIBUTUANAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) |  | Territory 8 | 8.9347 | 125.4704 | Brgy.Bancasi,BUTUAN CITY (Capital),AGUSAN DEL NORTE | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4160 | TCISCAMAGONGNASIPAGN | N/A | TCISCAMAGONGNASIPAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9693 | 125.3355 | Brgy. Camagong, Nasipit, Agusan Del Sur | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4043 | TCISFILIBAYUGAGS | TCISFILIBAYUGAGSLY | TCISFILIBAYUGAGSLY | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7118 | 125.7771 | Brgy.Fili, Bayugan City Agusan del Sur | PROSPERIDAD FOC | ISON | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4230 | TCFGATALISAYSBENITSDN | NA | TCFGATALISAYSBENITSDNLY | REGION XIII (Caraga) | SURIGAO DEL NORTE | San Benito |  | Territory 8 | 9.9547 | 126.005 | Poblacion Talisay, San Benito, Surigao Del Norte | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4190 | TCAGPAGPATANBUTUANAGN | None | TCAGPAGPATANBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) |  | Territory 8 | 8.9856 | 125.5221 | Brgy. Pagatpatan, Butuan City, Agusan Del Norte | AMPAYON FOC | ALT GLOBAL | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4140 | TCFGABASILIDNGT | NA | NA | REGION XIII (Caraga) | DINAGAT ISLANDS | BASILISA (RIZAL) |  | Territory 8 | 10.0662 | 125.5917 | BRGY. FERDINAND,BASILISA (RIZAL),DINAGAT ISLANDS | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3095 | TCLDCPACIFCISIDROSDN | NA | TCLDCPACIFCISIDROSDNLY | REGION XIII (Caraga) | SURIGAO DEL NORTE | San Isidro |  | Territory 8 | 9.9462 | 126.101 | Purok 2, Brgy Pacifico, San Isidro, Surigao del Norte | CAPHILLSURGAOSDN | LDIC | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4078 | TCISACLANASIPAGN | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.991 | 125.3137 | Brgy.Aclan,NASIPIT,AGUSAN DEL NORTE | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4170 | TCISAMPAYONBUTUANAGN | None | TCISAMPAYONBUTUANAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) |  | Territory 8 | 8.969 | 125.604 | Brgy. Ampayon, Butuan City, Agusan Del Norte | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4149 | TCISCAASINANCABADAGN | NA | NA | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.136 | 125.5241 | Brgy.Caasinan,CABADBARAN CITY,AGUSAN DEL NORTE | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4117 | TCISDELPILARCABADAGN | NA | TCISDELPILARCABADAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.1504 | 125.5879 | Brgy.Del Pilar,CABADBARAN CITY,AGUSAN DEL NORTE | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4044 | TCISLASUERTEPROSPAGS | None | TCISLASUERTEPROSPAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.5813 | 125.8968 | Brgy.Alegria,San Francisco, Agusan del Sur | PROSPERIDAD FOC | ISON | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4695 | TCCREP5WASIANROSARAGS | NA | TCCREP5WASIANROSARAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | ROSARIO |  | Territory 8 | 8.3268 | 126.0078 | Brgy. Wasi-an, Rosario, Agusan Del Sur | PROSPERIDAD FOC | CREI | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4724 | TCEDCP7DIAGATLIANGASDS | NA | TCEDCP7DIAGATLIANGASDS | REGION XIII (Caraga) | SURIGAO DEL SUR | LIANGA |  | Territory 8 | 8.6723 | 126.1387 | Brgy. Diatagon, Lianga, Surigao Del Sur | TELAJETANDAG | EDOTCO | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4708 | TCEDCP1CONSUELBUNAWAGS | NA | TCEDCP1CONSUELBUNAWAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | BUNAWAN |  | Territory 8 | 8.2363 | 125.9824 | Brgy. Consuelo, Bunawan, Agusan del Sur | PROSPERIDAD FOC | EDOTCO | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4252 | BAYANCALOBUTUANAGN_D | NA | BAYANCALOBUTUANAGN_D | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Doongan | Territory 8 | 8.9558 | 125.5284 | Near Tioaquen Residence, Balbarino Subd. Doongan, Butuan City | BUTUAN (TECHNICAL OFFICE) | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4215 | ROSAURDPOBBUTUANAGN_D | NA | ROSAURDPOBBUTUANAGN_D | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.948 | 125.5308 | ALONG J. ROSALES AVE. COR. T. CALO ST., BRGY. LIMAHA, BUTUAN CITY | AMPAYON FOC | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4119 | TCISLAUNIONCABADAGN | NA | TCISLAUNIONCABADAGNLY | REGION XIII (Caraga) | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.0876 | 125.5414 | Brgy.La Union,CABADBARAN CITY,AGUSAN DEL NORTE | AMPAYON FOC | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1086 | TCFGABRGYLUNA1SURGAOSDN | NA | TCFGABRGYLUNA1SURGAOSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) |  | Territory 8 | 9.7788 | 125.4839 | Brgy. Luna, Prk. Payawan, Surigao City | CAPHILLSURGAOSDN | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1979 | 12STNAZARETH | NA | 12STNAZARETHCDOMORFLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4728 | 124.6518 | 12th St Nazareth, Cagayan de Oro, Misamis Oriental, Philippines | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN69 | AGLAYA | MYB_004_GPONA_01 | AGLAYAFHKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF MALAYBALAY (Capital) | Aglayan | Territory 8 | 8.0535 | 125.1348 | Aglayan, City Of Malaybalay, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN110 | AGOHO | NA | AGOHOFWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2444 | 124.676 | Lower Banlas Agoho, Mambajao, Camiguin | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN724 | AGUSAN | NA | AGUSANFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4899 | 124.7369 | Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1667 | AGUSANCDO | CDO_030_GPONA_01 | AGUSANCDOFKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4949 | 124.748 | Bugo_CAGAYAN DE ORO CITY_MISAMIS ORIENTAL_P24_1 Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN70 | ALAE | MFR_001_GPONA_01 | ALAEFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.4234 | 124.8146 | Alae, Manolo Fortich, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN331 | ALUBIJIDPOB | ALU_001_GPONA_02 | ALUBIJIDPOBFHLWXY TCFGAPOBLACIONALUBIJMORFLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | ALUBIJID |  | Territory 8 | 8.5699 | 124.4728 | Alubijid_Poblacion, Alubijid, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052
MIN332 | ANAKAN | NA | ANAKANFLVWXY TCFGAANAKANGINGOOMORFLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8451 | 125.1594 | Anakan, Gingoog City, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1075 | ARDENT REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2286 | 124.6886 | Agoho, Mambajao, Camiguin | GINGOO | GT | [6 empty] | #N/A
MIN2258 | B19GINGOOMISOR | GNG_007_GPONA_01 | B19GINGOOMISORFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8304 | 125.1206 | Unnamed Road, Gingoog, Misamis Oriental, Philippines | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN72 | BAGONT | NA | BAGONTFKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.945 | 125.1026 | Bagontaas, City of Valencia, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2002 | BAGONTASVALN | VLN_001_GPONA_01 | BAGONTASVALNFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.924 | 125.0931 | Bagontaas, City of Valencia, Bukidnon | GVALEN | PHILTOWER | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN333 | BAIKON | NA | Z6BAIKINGONCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4583 | 124.5671 | Zone 6 Baikingon, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1846 | BALASNGINGOMISOR | NA | BALASNGINGOMISORFLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.698 | 125.1302 | Bal-ason, Gingoog City, Misamis Oriental, Philippines | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN111 | BALBAG | NA | BALBAGFHWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2421 | 124.7365 | Port Area Balbagon, Mambajao, Camiguin | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN806 | BALING | NA | BALINGFLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | KINOGUITAN |  | Territory 8 | 8.9617 | 124.8114 | Salubsob, Kinoguitan, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1851 | BALIWAGMISOR | NA | BALIWAGMISORFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGASAG |  | Territory 8 | 8.7277 | 124.7827 | Brgy Baliwag Balingasag Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN93 | BALUBL | NA | BALUBLFHKLWXY TCFGAP1MAMBATMFORTBUKFHKLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.4716 | 124.7876 | Purok 1 Mambatangan, Manolo Fortich, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN334 | BALUL2 | NA | TCFGAGALOPECOMPCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4429 | 124.6339 | 16 Galope Compund Balulang, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN996 | BALUL3 | NA | L1UPPERBALULACDOMORFKLMNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4539 | 124.6284 | Zone 1 , Upper Balulang , Cagayan de Oro City | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN807 | BALULA | CDO_010_GPONA_01 | CANITOANCDOMORFHKLMVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4465 | 124.6201 | Upper Canitoan, Cagayan de Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1536 | BANGCUDMALAY | NA | BANGCUDMALAYFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 7.9922 | 125.1364 | Purok 3 Bangcud, City Of Malaybalay, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2383 | BARNGCOTDANGCABUK | NA | BARNGCOTDANGCABUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DANGCAGAN |  | Territory 8 | 7.5831 | 124.9973 | Barongcot, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN329 | BARRA | OPL_016_GPONA_01 | BARRAFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | OPOL |  | Territory 8 | 8.5075 | 124.6022 | B21 L11 SapphireCoral St Johndorf Subd Barra, Opol, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1090 | BAYABS | NA | TCFGAZ1BAYABASCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5123 | 124.6303 | Sitio Zone 1 Bayabas, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN84 | BAYONG | NA | BAYONGFHKLWXY TCFGABAYONGIMPASBUKFHKLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUGONG |  | Territory 8 | 8.266 | 125.0262 | ImpasugOng_Poblacion, Impasugong, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN726 | BINUAN | NA | BINUANFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BINUANGAN |  | Territory 8 | 8.9245 | 124.7853 | Mercado Ave., 9016 Gingoog City,Provincial Road, Binuangan_Poblacion, Binuangan, Misamis Oriental | GINGOO | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1237 | BLING1 | BIO_001_GPONA_01 | BLING1FHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGOAN |  | Territory 8 | 9.004 | 124.8534 | Baukbauk Pob. (G.E. Antonino), Balingoan, Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN725 | BLNGSG | BLI_001_GPONA_01 | BLNGSGFHWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGASAG |  | Territory 8 | 8.7436 | 124.7779 | Balingasag_Barangay 1 (Pob.), Balingasag, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2323 | BOBUNTGNJASNMISOR | NA | BOBUNTGNJASNMISORFLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | JASAAN |  | Territory 8 | 8.6589 | 124.7445 | Bobontugan, Jasaan, Misamis Oriental, Philippines | CDO NDC | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN112 | BOLBONBONCATARMCMGN | NA | BOLBONBONCATARMCMGNFWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | CATARMAN |  | Territory 8 | 9.2071 | 124.6369 | Bolangon Bonbon, Catarman, Camiguin | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2343 | BRANDIASPANGANBUK | NA | BRANDIASPANGANBUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | PANGANTUCAN |  | Territory 8 | 7.8227 | 124.7945 | Barandias, Pangantucan, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN809 | BUGO | CDO_031_GPONA_01 | BUGOFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5034 | 124.7559 | Bantiles St. Bugo, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1751 | BUGOCDOBYN | NA | BUGOCDOBYNFLWXY Z4BUGOCDOMORFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.511 | 124.7555 | Zone 4, Bugo, Cagayan De Oro City, Misamis Oriental | CDO NDC | ALT GLOBAL | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1472 | BULUA | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5018 | 124.6129 | Bulua, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | [6 empty] | #N/A
MIN810 | BULUA2 | NA | BULUA2FKLNVWXY TCFGABULUA2CDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5053 | 124.6211 | Zone11 Coacoa Compound Bulua, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1629 | BULUACDO | CDO_037_GPONA_01 | Z9BULUACDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5052 | 124.611 | Zone 7, Bulua, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN727 | BURNAY | NA | BURNAYFHLWXY TCFGABURNAYGTAGUMMORFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GITAGUM |  | Territory 8 | 8.593 | 124.3875 | Burnay, Gitagum, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN74 | BUSCO | NA | BUSCOFHLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.8113 | 125.0735 | Busco Butong, Quezon, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2387 | CABADIANGKADINGBUK | NA | CABADIANGKADINGBUKFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | KADINGILAN |  | Territory 8 | 7.5305 | 124.8424 | Brgy. Cabadiangan, Kadingilan, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN76 | CABANG | NA | CABANGFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | CABANGLASAN |  | Territory 8 | 8.0767 | 125.2973 | Purok 7 Cabanglasan_Poblacion, Cabanglasan, Bukidnon | MALAY2 | PHILTOWER | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN75 | CABARD | NA | CABARDFHKLWXY TCFGAPROPIASTMALAYBBUKFHKLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.0084 | 125.1335 | Melendes compound, Propia st. Cabangahan, City Of Malaybalay, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN812 | CAGAYA | CDO_007_GPONA_01 | CAGAYAX CRUZTAALCDOMORFHKLMVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4832 | 124.6439 | Globe Telecom Tower Kalambaguhan St. CagayandeOroCity_Barangay 11 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1575 | CALACAPANCDO | NA | CALACAPANCDOFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4482 | 124.6481 | BrgyUpperAluba_Macasandig_CDO_MisOr, Macasandig, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2380 | CALAODCARLSBUK | NA | CALAODCARLSBUKFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS |  | Territory 8 | 7.6802 | 124.916 | New Nongnongan, Masimag, Don Carlos, Bukidnon | MARAMA | UNITY | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1198 | CAMAMA | CDO_035_GPONA_01 | TCFGACAMAMANANCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4656 | 124.6612 | Sitio Buntong Camamanan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1962 | CAMP1MARAMBUK | MRM_004_GPONA_01 | CAMP1MARAMBUKFHKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7366 | 125.0105 | Camp 1, Maramag, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1663 | CAMPEVACDO | CDO_017_GPONA_01 | CAMPEVANGCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4889 | 124.6211 | Camp Evangelista, Patag Cagayn de Oro City | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN919 | CAMPPH | NA | CAMPPHFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3182 | 124.8162 | Del Monte Camp Philips Agusan Canyon, Manolo Fortich, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1978 | CANITOANCDO | NA | CANITOANCDOFRFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4782 | 124.6098 | BrgyCanitoan(SilverCreek)_CagayanDeOroCity_MisamisOriental, Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN352 | CASING | NA | CASINGFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TAGOLOAN |  | Territory 8 | 8.5244 | 124.7608 | Villa Rosario Casinglot, Tagoloan, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1222 | CASISA | MYB_002_GPONA_01 | CASISAFKLVWXY TCFGACASISANGMALAYBBUKFKLVWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1288 | 125.1266 | Casisang, City Of Malaybalay, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2793 | CASISANGMALAYBUK | NA | CASISANGMALAYBUKFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1403 | 125.1175 | Casisang, Malaybalay, Bukidnon, Philippines | MALAY2 | PHILTOWER | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN814 | CATAR2 | NA | CATARCHFHWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | CATARMAN |  | Territory 8 | 9.1627 | 124.641 | Lawigan, Catarman, Camiguin | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN665 | CATARC | NA | LAWIGANCATARMCMGNFWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | CATARMAN |  | Territory 8 | 9.1252 | 124.6773 | Catarman_Poblacion, Catarman, Camiguin | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1778 | CATUMBALVALN | NA | CATUMBALVALNFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8484 | 125.1019 | Catumbalon, City of Valencia, Bukidnon | GVALEN | PHILTOWER | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1623 | CAWAY | NA | CAWAYFWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3721 | 124.8377 | Brgy. San Miguel Manolo Fortich Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1807 | CDO NDC | CDO_016_GPONA_01 | NONE | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4828 | 124.651 | 3F, Legacy Building, A. Luna Street, CagayandeOroCity_Barangay 27 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1002 | CDO-101 | NA | CD0-101 | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4537 | 124.6191 | REGATA SQUARE PUEBLO DE ORO, UPPER CARMEN. CAGAYAN DE ORO CITY. | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1003 | CDO-102 | CDO_102_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4442 | 124.6214 | XAVIER ESTATE, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1004 | CDO-103 | CDO_103_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4282 | 124.6125 | GRAND EUROPA, LUMBIA, CAGAYAN DE ORO CITY. | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN995 | CDO-604 | CDO_604_HYB_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4692 | 124.6476 | 13TH ST. FRONT TENNIS COURT BRGY. NAZARETH CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1006 | CDO-605 | CDO_605_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4729 | 124.6595 | INFRONT OF CAMAMANAN ELEM. SCHOOL, CAMAMANAN RD. BRGY CAMAMANAN, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN997 | CDO-606 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4628 | 124.6435 | ALONG TIBASAK RD. COR. ALUBA ROAD BRGY MACASANDIG CAGAYAN DE ORO CITY | CDO NDC | GT | [6 empty] | #N/A
MIN998 | CDO-607 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4809 | 124.6303 | INFRONT RVM DORMITORY BRGY. CARMEN CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN999 | CDO-608 | CDO_608_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4739 | 124.6331 | NEAR BELIEVERS CONSTRUCTION, ALONG ZAYAS ST. BRGY. CARMEN, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1740 | CDO-609 | CDO_609_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.449 | 124.631 | INFRONT XAVIER HEIGHTS WATER PUMP STATION, BALULANG ROAD, BRGY. BALULANG, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1000 | CDO-610 | NA | CDO-610 | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4955 | 124.6318 | BESIDE MONTESSORI DE ORO, FACING RONS CHICKEN, NATIONAL HIGHWAY BRGY. KAUSWAGAN, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1007 | CDO-611 | CDO_611_HYB_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5033 | 124.621 | BESIDE THE CHURCH OF JESUS CHRIST OF THE LATTER DAY SAINTS, BULUA ROAD, BRGY. BULUA CAGAYAN DE ORO C | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN975 | CDO-614 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4784 | 124.675 | INFRONT OF AYALA LIFE INSURANCE, NATIONAL HIGHWAY BRGY. GUSA, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1154 | CDO-701 | NA | CDO-701 | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4788 | 124.6532 | ALONG LIMKETKAI DRIVE BESIDE BRGY HALL BRGY 34, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1155 | CDO-702 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4798 | 124.6459 | BESIDE CITY CENTRAL COLLEGE, ALONG YACAPINCORRALER ST., BRGY 12, CGAYAN DE ORO | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1157 | CDO-704 | NA | CDO-704 | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5077 | 124.6429 | ALONG MINISITO CHAVEZ SUBD. BRGY. BAYABAS ,CAGAYAN DE ORO | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1197 | CDO-705 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.48 | 124.6358 | NEAR CARMEN MARKET, DABATIAN ST., BRGY. CARMEN, CDO | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1338 | CDO-707 | CDO_707_HYB_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4678 | 124.6086 | HUAWEI CABINET ALONG HIGHWAY, BRGY.CANITOAN, FRONT FOREST VIEW HOMES, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN335 | CDOBON | NA | BONBONCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5064 | 124.6471 | Bonbon, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1513 | CENTRIOCDO | NA | CENTRIO2CDOFDDZ | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4842 | 124.6516 | Centrio Mall, Brgy. 24, Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN338 | CGNMKT | CDO_009_GPONA_01 | COGONMKTCDOMORFHKLMVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.477 | 124.6502 | Cogon Market CagayandeOroCity_Barangay 38 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN815 | CLAVER | NA | CLAVERFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CLAVERIA |  | Territory 8 | 8.6471 | 124.906 | Centro VII, Provincial Road, Tamboboan, Claveria, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN475 | CLAVR2 | NA | CLAVR2FHKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CLAVERIA |  | Territory 8 | 8.6136 | 124.8946 | Provincial Rd Claveria_Poblacion, Claveria, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW3 | CMUSPCOW | NA | CMUSPCOW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8602 | 125.0519 | CMU Musuan Maramag, Bukidnon | GVALEN | GT | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1742 | COC-01 | CDO_902_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4817 | 124.6364 | Max Suniel St., Carmen, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1850 | COGONELSLVDR | NA | COGONELSLVDRFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | EL SALVADOR CITY |  | Territory 8 | 8.5386 | 124.4938 | Brgy Bolisong, El Salvador City Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1605 | COGONIPCDO | CDO_033_GPONA_01 | COGONIPCDOVRFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4967 | 124.6007 | Iponan, Cagayan de Oro, Misamis Oriental, Philippines | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1722 | COMCCDO | NA | COMCCDOFWXYT | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4858 | 124.6469 | CagayanDeOro_MedicalCenter, Macalaban St., CagayandeOroCity_Barangay 19 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2355 | COMPOLCATARCAMGN | NA | P3COMPOLCATARMCMGNFLWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | CATARMAN |  | Territory 8 | 9.1407 | 124.6608 | Mainit, Catarman, Camiguin, Pilipinas | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN733 | CONSUE | NA | CONSUEFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MAGSAYSAY |  | Territory 8 | 8.912 | 125.1866 | Consuelo, Magsaysay (Linugos), Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1967 | CORRALESCDO | NA | CORRALESCDOMORFHKLMWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4807 | 124.6476 | Brgy40 Cagayan de Oro City Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN345 | CRMEN2 | NA | CRMEN2FKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4831 | 124.6369 | #8 Marigold St. Carmen, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | [6 empty] | #N/A
MIN1092 | CDO | CDO_020_GPONA_01 | CUGMANCDOMORX CUGMANFHKLNVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4662 | 124.702 | Globe Telecom Alwana Compound Cugman, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1932 | CUGMAN SDH | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4468 | 124.7068 | Malasag, Cugman, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | [6 empty] | #N/A
MIN339 | CUMCOD | NA | GUSACDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4783 | 124.673 | Cagayan Capitol Gen. Hospital Gusa, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | [6 empty] | #N/A
MIN2001 | DAGATKIDVALN | NA | DAGATKIDVALNFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.824 | 125.1315 | DagatKidavao, Bagontaas, Valencia City Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1450 | DAHILA | NA | DAHILAFWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.2006 | 124.8569 | Dahilayan, Manolo Fortich, Bukidnon | CDO NDC | GT | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2384 | DALWNGMALAYBALAYBUK | NA | DALWNGMALAYBALAYBUKFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1994 | 125.0424 | Dalwangan, Malaybalay, Bukidnon, Philippines | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1724 | DAMILAGBUK | NA | DAMILAGBUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DAMILAG |  | Territory 8 | 8.3539 | 124.8125 | Damilag, Manolo Fortich, Bukidnon | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN78 | DAMULO | NA | DAMULOFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DAMULOG |  | Territory 8 | 7.4878 | 124.9412 | Purok 4 Poblacion (New Damulog), Damulog, Bukidnon | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN79 | DANGCA | DNG_001_GPONA_01 | DANGCAFHKLWXY TCFGAP3OSMENADANGCABUKFHKLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DANGCAGAN |  | Territory 8 | 7.6065 | 125.0056 | Osmena St., Purok 3 Dangcagan_Poblacion, Dangcagan, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1802 | DAYAWANVILMISOR | NA | DAYAWANVILMISORFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | VILLANUEVA |  | Territory 8 | 8.5801 | 124.7769 | Coca-Cola BrgyKatipunan, Villanueva, Misamis Oriental, Philippines | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2288 | DOLGNMRAMAGBUK | MRM_002_GPONA_01 | DOLGNMRAMAGBUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8349 | 125.0448 | Dologon, Maramag, Bukidnon | GVALEN | PHILTOWER | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1764 | DOLOGONMARAM | NA | DOLOGONMARAMFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8518 | 125.0478 | Brgy. Dologon, Maramag Bukidnon | GVALEN | GT | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN633 | DONCAR | DCR_001_GPONA_01 | DONCARFHKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS |  | Territory 8 | 7.6699 | 124.9955 | Don Carlos Sur (Pob.), Don Carlos, Bukidnon | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN341 | DUKABY | NA | DUKABYFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MEDINA |  | Territory 8 | 8.9285 | 124.9976 | Duka, Medina, Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1310 | ELSAL2 | NA | ELSAL2FHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | EL SALVADOR CITY |  | Territory 8 | 8.5357 | 124.5477 | Taytay, City of El Salvador, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN729 | ELSALV | ELS_002_GPONA_01 | ELSALVFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | EL SALVADOR CITY |  | Territory 8 | 8.5545 | 124.5256 | ElSalvador_Poblacion, City of El Salvador, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN961 | ESPERNZMISOR | NA | ESPERNZMISORFLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | KINOGUITAN |  | Territory 8 | 9.004 | 124.8224 | Purok 3 Esperanza, Kinoguitan, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1968 | FICOVILLECDO | NA | FICOVILLIPONACDOMORFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4895 | 124.5913 | Canitoan Cagayan de Oro City Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1664 | GALAXYRDCDO | CDO_034_GPONA_01 | GALAXYGUSACDOMORFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.475 | 124.6854 | Cagayan de oroGusa, Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN81 | GANGO | NA | GANGOFKLNVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | LIBONA |  | Territory 8 | 8.4157 | 124.6657 | Brgy. Gango,Libona,Bukidnon | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN360 | GINGO2 | GNG_003_GPONA_01 | GINGO2FHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.813 | 125.1049 | Mercado Ave. GingoogCity_Barangay 26 (Pob.), Gingoog City, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1238 | GINGO3 | GNG_002_GPONA_01 | GINGO3FHLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8256 | 125.0886 | GingoogCity_Barangay 25 (Pob.), Gingoog City, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN823 | GINGOO | GNG_001_GPONA_01 | GINGOOFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.825 | 125.1026 | 22 Delima St., GingoogCity_Barangay 3 (Pob.), Gingoog City, Misamis Oriental | GINGOO | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1825 | GINGOOG NDC | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8212 | 125.11 | 2F 909 Dona Graciana St. Purok 7, Gingoog City Baranggay 20 (Pob.) Misamis Oriental | GINGOO | GT | [6 empty] | #N/A
MIN1371 | GNG-701 | GNG_701_HYB_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8256 | 125.0992 | HUAWEI CABINET CORNER CUERDORIZAL ST., FRONT OF DMS RTW , GINGOOG CITY | GINGOO | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1337 | GNG-702 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8243 | 125.1047 | HUAWEI CABINET FRONT DEP ED, DON RESTITUTO ELEMENTARY SCHOOL, ALONG NATIONAL HIGHWAY, GINGOOG CITY | GINGOO | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1970 | GOLDNGLOWCDO | NA | GOLDNGLOWCDOFHKLMWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4596 | 124.6157 | Golden Glow Village, Carmen, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN656 | GRANDCTYCDO | CDO_011_GPONA_01 | GRANDCITYCDOMORIOFHKLMWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4771 | 124.6445 | Grand City Hotel ApolinarVelez St., CagayandeOroCity_Barangay 2 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN923 | GSCDOA | NA | GAISAN2CDOMORLSFHWY GAISANCDOMORLSFHWY GSCDOAFHKLMWX | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4867 | 124.6498 | Gaisano City Main, Recto Ave CagayandeOroCity_Barangay 24 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN365 | GSLUIS | NA | GSLUISFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8749 | 125.0424 | San Luis, Gingoog City, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1390 | GT STORE NVM VALENCIA REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.905 | 125.092 | G/F NVM Mall Sayre Highway Lumbo, City of Valencia, Bukidnon | GVALEN | GT | [6 empty] | #N/A
MIN635 | GUIHIA | NA | GUIHIAFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUGONG |  | Territory 8 | 8.4043 | 125.0011 | Guihean, Impasugong, Bukidnon | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN80 | GUINOY | NA | GUINOYFHLWXY TCFGAP3GUINOYVALENBUKFHLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8972 | 125.0022 | Purok 3 Guinoyuran, City of Valencia, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN113 | NPOBGUINSICMGN | NA | NPOBGUINSICMGNFWY TCFGANPOBGUINSICMGNFLWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | GUINSILIBAN |  | Territory 8 | 9.0999 | 124.7831 | Guinsiliban_North Poblacion, Guinsiliban, Camiguin | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN824 | GUSA | NA | GUSAFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4722 | 124.6924 | Gusa, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN634 | GVALEN | NA | GVALENFH GVALENIDFKWXY GVALENKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9037 | 125.0903 | Valencia_Poblacion, City of Valencia, Bukidnon | GVALEN | GT | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2512 | HAGPITANBUK | NA | INDULATALAKAGBUKHKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | TALAKAG |  | Territory 8 | 8.0928 | 124.5783 | Brgy. Indulang, Talakag, Bukidnon. | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1353 | HILAND | NA | HILANDZ | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO (Capital) | Soro-soro | Territory 8 | 9.2183 | 124.7281 | HIGHLAND RESORT, MAMBAJAO, CAMIGUIN | CDO NDC | GT | [6 empty] | #N/A
MIN2354 | HUBANGMAHINOCAMGN | NA | HUBANGMAHINOCAMGNFLWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAHINOG |  | Territory 8 | 9.1715 | 124.7852 | Hubangon, Mahinog, Camiguin, Pilipinas | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN342 | IGPIT | OPL_001_GPONA_01 | IGPITFHKWXY TCFGAIGPITOPOLMORFHKWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | OPOL |  | Territory 8 | 8.5116 | 124.5869 | Igpit, Opol, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN827 | IMAGSA | NA | IMAGSAFHKLMWXY MAGSAY17POBCDOMORFKLMVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4868 | 124.6446 | Magsaysay St. CagayandeOroCity_Barangay 9 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN73 | IMBATU | NA | IMBATUFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | BAUNGON |  | Territory 8 | 8.3111 | 124.6911 | Imbatug (Pob.), Baungon, Bukidnon | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN99 | IMPAL | NA | IMPALFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUGONG |  | Territory 8 | 8.2218 | 125.0353 | Impalutao, Impasugong, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2485 | IMPALIMPASUGBUK | NA | IMPALIMPASUGBUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUGONG |  | Territory 8 | 8.2461 | 125.0277 | Impasug-ong, Bukidnon, Philippines | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN636 | IMPASU | NA | IMPASUFHWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUGONG |  | Territory 8 | 8.3019 | 124.9987 | ImpasugOng_Poblacion, Impasugong, Bukidnon | CDO NDC | GT | [6 empty] | #N/A
MIN1665 | INDAHAGCDO | CDO_021_GPONA_01 | INDAHAGCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | BAUNGON |  | Territory 8 | 8.4333 | 124.6675 | Indahag, Cagayan de Oro, Misamis Oriental, Philippines | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN362 | INMMC | NA | NMMCCDOMORIDX | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Lapasan | Territory 8 | 8.485 | 124.6495 | Northern Mindanao Medical Center CagayandeOroCity_Barangay 27 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | [6 empty] | #N/A
MIN1091 | IPONA2 | CDO_005_GPONA_01 | KINASANGIPONACDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4996 | 124.5943 | Sitio Kinasanghan Iponan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN730 | IPONAN | NA | IPONANCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4837 | 124.5977 | Iponan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1381 | JASAA2 | NA | JASAA2FHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | JASAAN |  | Territory 8 | 8.6037 | 124.7648 | Zone 2 Aplaya, Jasaan, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN731 | JASAAN | JSA_001_GPONA_01 | JASAANFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | JASAAN |  | Territory 8 | 8.651 | 124.7556 | Lower Jasaan (Pob.), Jasaan, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1567 | JULMARBALULA | NA | JULMARBALULAFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4639 | 124.6236 | Brgy Carmen, Cagayan de Oro City Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN82 | KADING | NA | KADINGFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | KADINGILAN |  | Territory 8 | 7.605 | 124.9048 | Kadingilan_Poblacion, Kadingilan, Bukidnon | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1533 | KALASUNGAY | NA | KALASUNGAYFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1714 | 125.1055 | Kalasungay, City Of Malaybalay, Bukidnon | MALAY2 | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN83 | KALILA | NA | KALILAFHKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | KALILANGAN |  | Territory 8 | 7.75 | 124.7506 | Poblacion, Kalilangan, Bukidnon, Philippines | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN950 | KAO | NA | KAOFKWX | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | JASAAN |  | Territory 8 | 8.633 | 124.7637 | Pilipinas Kao, Jasaan Misamis Oriental Ecozone Upper Jasaan (Pob.), Jasaan, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2659 | KTPUNANVNUEVAMORSPEM | NA | KTPUNANVNUEVAMORSPEMF | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | VILLANUEVA |  | Territory 8 | 8.5704 | 124.7599 | STEAG Villanueva, Mis. Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN7 | KAUSA | NA | CITRAKAUSWACDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4927 | 124.6323 | Rooftop Citra Mina Bldg. National Highway Kauswagan, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN14 | KAUSWA | CDO_004_GPONA_01 | KAUSWAGANCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5019 | 124.6361 | Kauswagan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1610 | KAUSWAGCDO | NA | Z1KAUSWAGANCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4961 | 124.6431 | Cagayan de Oro CityKauswagan Kauswagan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1423 | KDT-KAI CDO REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4743 | 124.6552 | KDTKai Bldg. Camamanan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN86 | KIBAWE | KIB_001_GPONA_01 | KIBAWEFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | KIBAWE |  | Territory 8 | 7.5654 | 124.9833 | J.P. Rizal St. cor.Datu Manlabao, Purok 5 West Kibawe (Pob.), Kibawe, Bukidnon | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN87 | KIBURI | NA | KIBURIFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.6434 | 125.0934 | Kiburiao, Quezon, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN88 | KIHARO | NA | KIHAROFHLWXY TCFGAKIHAROMRAMAGBUKFHLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8608 | 124.9915 | Kiharong, Maramag, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1741 | KILOMOY SDH | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MAGSAYSAY |  | Territory 8 | 9.0389 | 125.1998 | Villa Felipa, Magsaysay (Linugos), Misamis Oriental | GINGOO | GT | [6 empty] | #N/A
MIN354 | KINOGU | NA | KINOGUFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | KINOGUITAN |  | Territory 8 | 8.9798 | 124.7942 | Purok 1 Kinoguitan_Poblacion, Kinoguitan, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN89 | KISOLN | NA | KISOLNFHLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | SUMILAO |  | Territory 8 | 8.3185 | 124.969 | Kisolon, Sumilao, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN90 | KITAO | KIT_001_GPONA_01 | KITAOFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | KITAOTAO |  | Territory 8 | 7.6422 | 125.0091 | Kitaotao_Poblacion, Kitaotao, Bukidnon | MARAMA | GT | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1669 | KM6BALULACDO | NA | KM6BALULACDOFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4307 | 124.6186 | Cagayan de Oro CityBalulang Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN344 | KNDIIS | NA | KNDIISFHLWXY TCFGACANDIISMAGSAYMORFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MAGSAYSAY |  | Territory 8 | 8.9647 | 125.1859 | Purok 3 Candiis, Magsaysay (Linugos), Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN85 | KPJUAN | NA | KPJUANFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | LANTAPAN |  | Territory 8 | 8.0829 | 125.0277 | Capitan Juan, Lantapan, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1469 | KUKUNHTLCDO | NA | KUKUNHTLCDOMORFH KUKUNHTLCDOMORIDFWXY KUKUNHTLCDOMORKLMVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 7.0895 | 125.6105 | Bounded by CM Recto Ave., Capt. Vicente Roa and Corrales Ave, Brgy. 24, Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN732 | LAGONG | LGG_001_GPONA_01 | LAGONGFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LAGONGLONG |  | Territory 8 | 8.8091 | 124.7858 | Lagonglong_Poblacion, Lagonglong, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN734 | LAGUIN | LGU_001_GPONA_01 | LAGUINFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LAGUINDINGAN |  | Territory 8 | 8.5797 | 124.448 | Poblacion, LAGUINDINGAN, MISAMIS ORIENTAL, REGION X (NORTHERN MINDANAO), MIN | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1453 | LAGUINDAIRPT | NA | LAGUINDAIRPTFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.6052 | 124.4559 | Laguindingan Airport Moog, Laguindingan, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN107 | LALIGA | NA | LALIGAFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8849 | 125.1823 | Purok 3 Laligan, City of Valencia, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN91 | LANTAP | NA | LANTAPFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | LANTAPAN |  | Territory 8 | 7.9991 | 125.0217 | Purok 2 Lantapan_Poblacion, Lantapan, Bukidnon | MALAY2 | PHILTOWER | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN836 | LAPASA | CDO_022_GPONA_01 | LAPASANCDOMORFKLNVWYX | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4789 | 124.6625 | San Miguel Village, Lapasan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10004188 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN355 | LCGCDO | CDO_013_GPONA_01 | LCGCDOFHKLMVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4839 | 124.6533 | Osmeña Extension CagayandeOroCity_Barangay 22 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN71 | LIBONA | NA | LIBONAFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | LIBONA |  | Territory 8 | 8.3245 | 124.7918 | Crossing, Libona, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1515 | LIMKETHTLOD | NA | LIMKETHTLIDFWXYDFHK | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4839 | 124.6567 | Limketkai Luxe Hotel, Limketkai Drv., Lapasan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN736 | LIMKETCDOMORLS | NA | LIMKETCDOMORLSFW LIMKETMALHIGFHKRWXY LIMKETMALLOWFHKRWXY LIMKETMALROBWY LIMKETODFHKLMVW | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4817 | 124.6559 | Limketkai Bldg Lapasan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1534 | LINABOMALAY | NA | LINABOMALAYFHKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.052 | 125.157 | Purok 2 Linabo, City Of Malaybalay, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2664 | LOURDESALUBIJMOR | NA | LOURDESALUBIJMORFLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | ALUBIJID |  | Territory 8 | 8.5234 | 124.4362 | Lourdes, Alubijid, Misamis Oriental, Philippines | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN340 | LOWDAN | NA | LOWDANFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | JASAAN |  | Territory 8 | 8.6959 | 124.7475 | 189 Quezon St. Danao, Jasaan, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN839 | LUMBIA | CDO_024_GPONA_01 | LUMBIACDOMORFKLNVWXY TCFGALUMBIACDOMORVX | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4097 | 124.6127 | Lumbia, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2003 | LUMBOVALN | VLN_002_GPONA_01 | LUMBOVALNFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8988 | 125.0851 | Brgy Lumbo, Valencia City Bukidnon | GVALEN | PHILTOWER | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN367 | LUMCDO | CDO_026_GPONA_01 | STACRUZLUMBIACDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4272 | 124.6084 | Sta Cruz Lumbia, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN959 | LUNAO | GNG_004_GPONA_01 | LUNAOFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8468 | 125.0566 | Lunao, Gingoog City, Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN108 | LUROG | NA | LUROGFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9665 | 125.0488 | Purok 1 Lurogan, City of Valencia, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1848 | MAANASMISOR | NA | MAANASMISORFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MEDINA |  | Territory 8 | 8.8918 | 125.0318 | Brgy Maanas Medina, Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN358 | MACABA | NA | MACABALANCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.499 | 124.6617 | 0825 Piaping Puti Macabalan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN599 | MADONAOD | NA | MADONNACDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4781 | 124.6348 | Madonna Hospital, Carmen, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN840 | MAGSAY | NA | MAGSAYFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MAGSAYSAY |  | Territory 8 | 9.0218 | 125.1829 | Cabubuhan, Magsaysay (Linugos), Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN600 | MAGSYM | NA | MAGSYMWZ | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MAGSAYSAY |  | Territory 8 | 9.0589 | 125.1953 | Sitio Mahayahay, Damayuhan, Magsaysay (Linugos), Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN841 | MAHINO | NA | MAHINOFHKLWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAHINOG |  | Territory 8 | 9.1462 | 124.7979 | Mahinog_Poblacion, Mahinog, Camiguin | GINGOO | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1223 | MAILAG | NA | MAILAGFHLWXY TCFGAP12MAILAGVALENBUKFHLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9734 | 125.1346 | Purok 12 Mailag, City of Valencia, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN353 | MALANA | NA | MALANAFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | OPOL |  | Territory 8 | 8.4888 | 124.5782 | Youngsville Subd Opol_Poblacion, Opol, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN671 | MALAY2 | MYB_001_GPONA_01 | MALAY2FKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1597 | 125.1282 | City of Malaybalay_Barangay 1 (Pob.), City Of Malaybalay, Bukidnon | MALAY2 | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1224 | MALAY3 | NA | MALAY3FHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1486 | 125.1318 | CityofMalaybalay_Barangay 7 (Pob.), City Of Malaybalay, Bukidnon | MALAY2 | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN637 | MALAYB | NA | MALAYBFKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1527 | 125.112 | Camp Bahian, Sumpong, City Of Malaybalay, Bukidnon | MALAY2 | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN104 | MALIPA | NA | MALIPAFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | PANGANTUCAN |  | Territory 8 | 7.6163 | 124.8292 | Malipayon, Pangantucan, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1502 | MALLBERRYCDO | NA | MALLBERRYCDOFD | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4817 | 124.6536 | Mallberry Suites Business Hotel CagayandeOroCity_Barangay 31 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2344 | MALNAOKALILNGNBUK | NA | MALNAOKALILNGNBUKFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | KALILANGAN |  | Territory 8 | 7.7954 | 124.7033 | Brgy. Malinao, Kalilangan, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2260 | MANDABALINGSGMISOR | NA | MANDABALINGSGMISORFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGASAG |  | Territory 8 | 8.7638 | 124.7823 | Man-iso Mandangoa Balingasag 9005, Balingasag, Misamis Oriental, Philippines | CDO NDC | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN359 | MANDUM | CDO_027_GPONA_01 | MNDMACASANDIGCDOMORFKLNVWX TCFGAMCSNDIGCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4639 | 124.6395 | Mandumol Macasandig, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2665 | MANGOKMALYBALAYBUK | NA | MANGOKMALYBALAYBUKFHLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.0269 | 125.1918 | Managok, Malaybalay, Bukidnon, Philippines | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN94 | MANOL2 | MFR_003_GPONA_01 | MANOL2FHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3901 | 124.836 | San Miguel, Manolo Fortich, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN638 | MANOLO | MFR_002_GPONA_01 | MANOLOFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3656 | 124.8616 | Tankulan (Pob.), Manolo Fortich, Bukidnon | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2623 | MANTBUGAOMFORTBUK | NA | MANTBUGAOMFORTBUKFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.4609 | 124.8236 | Mantibugao, Manolo Fortich, Bukidnon, Philippines | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN77 | MARAM2 | MRM_005_GPONA_01 | MARAM2FHKLWXY TCFGACAMP1MRAMAGBUKFHKLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7079 | 125.0199 | Camp I, Maramag, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN662 | MARAMA | MRM_001_GPONA_01 | MARAMAFHKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7581 | 125.0047 | Purok 2, Maramag_North Poblacion, Maramag, Bukidnon | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1313 | Maramag | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7483 | 125.0075 | Purok 6A Maramag_South Poblacion, Maramag, Bukidnon | MARAMA | GT | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1433 | MARCOH | NA | MARCOHTLCDOMORIDFWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4686 | 124.6994 | Marco Hotel Alwana Compound Cugman, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN954 | MARIA REYNA HOSPITAL REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.476 | 124.655 | Maria Reyna Hospital, Msgr. Santiago Hayes St., CagayandeOroCity_Barangay 4 (Pob.), Cagayan De Oro City, Misamis Or | CDO NDC | GT | [6 empty] | #N/A
MIN1648 | MCASANDIGCDO | NA | MCASANDIGCDODFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4635 | 124.6445 | Cagayan de Oro CityMacasandig Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN735 | MEDINA | MED_001_GPONA_01 | MEDINAFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MEDINA |  | Territory 8 | 8.9065 | 125.022 | GingoogCity_Barangay 1 (Pob.), Gingoog City, Misamis Oriental | GINGOO | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2382 | MIARAYDANGBUKDN | NA | MIARAYDANGBUKFHKLVWYX | REGION X (NORTHERN MINDANAO) | BUKIDNON | DANGCAGAN |  | Territory 8 | 7.5738 | 125.0426 | Miaray, Dangcagan, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2418 | MINCOBALINGAMISOR | NA | MINCOBALINGAMISORFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGASAG |  | Territory 8 | 8.768 | 124.7693 | Balingasag, Misamis Oriental, Philippines | CDO NDC | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN356 | MLIBER | LBR_001_GPONA_01 | MLIBERFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LIBERTAD |  | Territory 8 | 8.5591 | 124.3558 | Purok 9 Libertad_Poblacion, Libertad, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN92 | MMALIT | NA | MMALITFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALITBOG |  | Territory 8 | 8.5336 | 124.8832 | Malitbog_ Poblacion, Malitbog, Bukidnon | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN847 | MOLUGA | ELS_001_GPONA_01 | MOLUGAFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | EL SALVADOR CITY |  | Territory 8 | 8.5332 | 124.571 | Molugan, City of El Salvador, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN114 | MPARAS | NA | TCFGAYUMBIMAMBJACMGNFWY/H/V | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2431 | 124.6612 | Paras Beach Resort Yumbing, Mambajao, Camiguin | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN115 | POBSAGAYCMGN | NA | POBSAGAYCMGNFHKLWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | SAGAY |  | Territory 8 | 9.1098 | 124.7218 | Sagay_Poblacion, Sagay, Camiguin | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1832 | MSDSLDBNMANOLOBUK | NA | MSDSLDBNMANOLOBUKFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.2767 | 124.8519 | Lindaban - Dahilayan Road, Manolo Fortich, Bukidnon, Philippines | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN369 | MTALIS | NA | MTALISFKLVWXY TCFGASTAINESTALISAMORFKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TALISAYAN |  | Territory 8 | 8.9648 | 124.9453 | Purok 4 Santa Ines, Talisayan, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN95 | MTVIEWM | NA | MTVIEWMFHLWXDY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9773 | 125.0073 | Mt. View College Mt. Nebo, City of Valencia, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN663 | MUSUAN | NA | MUSUANFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8764 | 125.0698 | Musuan Peak Dologon, Maramag, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1372 | MYB-701 | MYB_701_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1555 | 125.1269 | BESIDE MALAYBALAY CITY CENTRAL SCHOOL AND MALAYBALAY SPORTS COMPLEX, MALAYBALAY CITY | MALAY2 | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1364 | MYB-702 | MYB_702_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1439 | 125.1218 | CORNER IMBALAMBANG ? SAN VICTORES ST., MALAYBALAY CITY | MALAY2 | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1274 | MYB-703 | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1323 | 125.1268 | INFRONT OF CASISANG ELEMENTARY SCHOOL, BRGY. CASISANG, ALONG NATIONAL HIGHWAY | MALAY2 | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN866 | NAZARE | NA | 18STNAZARETHCDOMORFHKLMWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4745 | 124.6465 | 19th St. cor. C. Fernandez St Nazareth Subd. Nazareth, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1608 | NAZARETHCDO | NA | NAZARETHCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4666 | 124.6488 | Cagayan de Oro CityNazareth, Nazareth, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1781 | NORTHPOBMARAM | NA | NORTHPOBMARAMFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7646 | 125.0077 | Maramag_North Poblacion, Maramag, Bukidnon | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN363 | OPOL | OPL_017_GPONA_01 | OPOLFHKLWXY TCFGATABOCOPOLMORFKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | OPOL |  | Territory 8 | 8.5148 | 124.5755 | Sitio Puntakan Taboc, Opol, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN753 | OROSUP | NA | OROSUPZ | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4768 | 124.6489 | Ororama Mega CM Recto National Highway Lapasan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1703 | P2BAGONTAAS | VLN_004_GPONA_01 | P2BAGONTAASFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9588 | 125.1099 | Valencia CityBagontaas Bagontaas, City of Valencia, Bukidnon | MALAY2 | GT | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN364 | PAGAT | NA | CANITOAN2CDOMORFKLNVWXY TCFGACANITOAN2CDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4736 | 124.5941 | Canitoan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2250 | PAGATPATCDOMISOR | NA | PAGATPAT2CDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4592 | 124.586 | Pagatpat, Cagayan de Oro, Misamis Oriental, Philippines | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1857 | PAT01 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4957 | 124.6254 | Between NFA & Police Training Center, PatagMolawan Rd, Patag, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | [6 empty] | #N/A
MIN1378 | PATAG2 | CDO_029_GPONA_01 | BPCBULUACDOMORFHKLWY PATAG2FHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4997 | 124.6173 | Apovel Subdivision Patag, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10004188 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN330 | PATAG3 | NA | Z8CARMENCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4801 | 124.6244 | Zone 8 Carmen, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2257 | PATAGOPOLMISOR | OPL_002_GPONA_01 | PATAGOPOLMISORFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4979 | 124.5567 | Patag, Opol, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN97 | PATPAT | NA | PATPATDFHKLDWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1962 | 125.0644 | Patpat (Lapulapu), City Of Malaybalay, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN956 | PEARLMONT REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.478 | 124.654 | Pearlmont Hotel, Osmena and Florentino Sts., Limketkai Drive Lapasan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2286 | PNADTALNMRAMAGBUK | MRM_003_GPONA_01 | PNADTALNMRAMAGBUKFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8053 | 125.0143 | Panadtalan, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2381 | POBDONCARLOSBUK | NA | POBDONCARLOSBUKFHKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS |  | Territory 8 | 7.6862 | 124.9967 | Prk. 6 Poblacion, Don Carlos, Bukidnon, 8712 Bukidnon, Philippines | MARAMA | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN666 | POBMAMBAJAO | NA | POBMAMBAJAOFHLDWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2439 | 124.7152 | Mambajao_Poblacion, Mambajao, Camiguin | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1839 | POBPANGAN | NA | POBPANGANFKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | PANGANTUCAN |  | Territory 8 | 7.8332 | 124.8241 | Reloc Pangantucan_Poblacion, Pangantucan, Bukidnon | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN943 | POLYGH | NA | POLYGHFWXY POLYGHODFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4983 | 124.6309 | Brgy Kauswagan, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1799 | POLYMEDIC REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.496 | 124.634 | CDO Polymedic General Hospital Velez St, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN607 | PSCMIN | NA | PSCMINFX | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | VILLANUEVA |  | Territory 8 | 8.5704 | 124.769 | Villanueva Poblacion1, Villanueva, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2386 | PUNTIANQUEZONBUK | QZB_003_GPONA_01 | PUNTIANQUEZONBUKFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.6117 | 125.1193 | Purok 5, Puntian, Quezon, Bukidnon, Philippines | GVALEN | PHILTOWER | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1840 | PUNTODCDO | CDO_012_GPONA_01 | PUNTODCDOMORFKLMVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4922 | 124.6551 | Reloc, CagayandeOroCity_Barangay 22 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1419 | PVALEN | NA | PVALENFHKLX | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9131 | 125.0929 | Sayre Highway, Purok 16 Valencia_Poblacion, City of Valencia, Bukidnon | GVALEN | GT | [6 empty] | #N/A
MIN98 | QUEZON | QZB_001_GPONA_01 | QUEZONFHKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON | Poblacion (Kiokong) | Territory 8 | 7.7342 | 125.1018 | Quezon_Poblacion (Kiokong), Quezon, Bukidnon | CDO NDC | GT | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1606 | REYNAXAVCDO | CDO_014_GPONA_01 | REYNAXAVCDOMORFKLMVWXYW | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4763 | 124.6552 | Cagayan de oroCamamanan, Camamanan, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1290 | RKALIL | NA | RKALILFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | KALILANGAN |  | Territory 8 | 7.7409 | 124.7837 | Sitio Pinamsamon Ninoy Aquino, Kalilangan, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN610 | RMALIT | NA | RMALITFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALITBOG |  | Territory 8 | 8.5369 | 124.8223 | Bagong Silang,Brgy. Sta. Inez,Malitbog,Bukidnon | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN101 | RSNFER | NA | RSNFERFKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | SAN FERNANDO |  | Territory 8 | 7.9489 | 125.3199 | Sitio Tuburan Halapitan (Pob.), San Fernando, Bukidnon | GVALEN | GT | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1199 | SACREH | NA | CAPCOMGUSACDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4728 | 124.677 | Capistrano Complex Gusa Campus Gusa, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN105 | SALAWA | NA | SALAWAFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.7003 | 125.1166 | Salawagan, Quezon, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN740 | SALAY | SLY_001_GPONA_01 | SALAYFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | SALAY |  | Territory 8 | 8.8553 | 124.7853 | J. Artadi St., Salay_Poblacion, Salay, Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN957 | SALCEDO REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2522 | 124.7163 | V.O. Salcedo Mamajao_Poblacion, Mambajao, Camiguin | GINGOO | GT | [6 empty] | #N/A
MIN1691 | SANJOSMALAYB | MYB_003_GPONA_01 | SANJOSMALAYBFKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.0995 | 125.1295 | Purok 1 San Jose, City Of Malaybalay, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1975 | SANJUANCDO | NA | SJUANLAPASANCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4863 | 124.6627 | Brgy. Lapasan Cagayan de Oro City Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1969 | SAVALLEYCDO | NA | SAVALLEYCDOFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4558 | 124.61 | Pagatpat(Pedro N Roa),CagayanDeOroCity MisamisOriental, Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN336 | SINALO | NA | SINALOFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | EL SALVADOR CITY |  | Territory 8 | 8.5721 | 124.5078 | Zone 3 Sinaloc, City of El Salvador, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN106 | SINAY | NA | SINAYFHLWXY TCFGASINAYVALENBUKFHLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8785 | 125.1406 | Sinayawan, City of Valencia, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2474 | SMCBALULACDO | NA | SMCBALULACDOVRFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4674 | 124.631 | Balulang, Cagayan de Oro, Misamis Oriental, Philippines | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2486 | SMCBOCBOC | NA | SMCBOCBOCFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS |  | Territory 8 | 7.6385 | 124.9046 | Bocboc, Don Carlos, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2409 | SMCDO1PRMIER | NA | SMCDO1PRMIERFWXY SMCDO2PRMIERFWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4841 | 124.6546 | SM Cagayan De Oro 2 Premier & BPO Tower, CM Recto Avenue, National Highway, Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN860 | SMCDOOD | NA | SMCDOODXYFLVWY SMCITYCDOMORIOFLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.457 | 124.6224 | SM City Cagayan de Oro Upper Balulang, Materson Ave. cor Gran Via St., Carmen, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2550 | SMCKALASMALAYBUK | NA | SMCKALASMALAYBUKFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1722 | 125.0978 | Kalasungay, Malaybalay, Bukidnon, Philippines | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2477 | SMCKIARADC | NA | SMCKIARADCFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS |  | Territory 8 | 7.6433 | 124.8835 | Kiara, Don Carlos, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2480 | SMCKILIWST | NA | SMCKILIWSTFHWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | WAO |  | Territory 8 | 7.7373 | 124.7236 | Kilikili East, WAO, LANAO DEL SUR, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2543 | SMCSANISIDROTALAKBUK | NA | SMCSANISIDROTALAKBUKFKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | TALAKAG |  | Territory 8 | 8.2769 | 124.5899 | Talakag, bukidnon | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2533 | SMCSTNINOTALAKBUK | NA | SMCSTNINOTALAKBUKFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | TALAKAG |  | Territory 8 | 8.1924 | 124.585 | Santo Nino (Lumbayawa), Bukidnon, Philippines | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN100 | SNFERN | NA | TCFGATUBURAN2SFERNBUKFHLWY RSNFERFKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | SAN FERNANDO |  | Territory 8 | 7.9269 | 125.3287 | Halapitan (Pob.), San Fernando, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2293 | SONGCOLANTAPBUK | NA | SONGCOLANTAPBUKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | LANTAPAN |  | Territory 8 | 8.042 | 124.9458 | Songco, Lantapan, Bukidnon, Philippines | MALAY2 | PHILTOWER | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1951 | STACRUZMISOR | NA | STACRUZMISORFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TAGOLOAN |  | Territory 8 | 8.5462 | 124.7599 | Brgy. SantaCruz Tagoloan Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN366 | STAGOL | TGO_002_GPONA_01 | STAGOLFHKLWY TCFGASANTANATAGOLOMORFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TAGOLOAN |  | Territory 8 | 8.5349 | 124.8023 | Zone 2 Santa Ana, Tagoloan, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1995 | STJUDEMALAYB | NA | STJUDEMALAYBBUKIOF | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1549 | 125.1299 | St. Jude Thadeus Hospital, Brgy. 1, Malaybalay, Bukidnon | MALAY2 | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN741 | SUGBON | NA | SUGBONFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | SUGBONGCOGON |  | Territory 8 | 8.9536 | 124.7834 | Sitio Mincape, Sugbongcogon_Poblacion, Sugbongcogon, Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN102 | SUMILA | NA | SUMILAFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | SUMILAO |  | Territory 8 | 8.2926 | 124.9497 | Sitio Mahayahay,,Brgy. Damayuhan Sumilao_Poblacion, Sumilao, Bukidnon | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN368 | TAGBOC | NA | TAGBOCFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TALISAYAN |  | Territory 8 | 8.9804 | 124.9093 | Purok 6 Tagbocboc, Talisayan, Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1072 | TAGOL1 | TGO_001_GPONA_01 | TAGOL1FHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TAGOLOAN |  | Territory 8 | 8.5382 | 124.7523 | Tagoloan_Poblacion, Tagoloan, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN103 | TALAKG | NA | TALAKGFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | TALAKAG |  | Territory 8 | 8.2333 | 124.598 | Talakag_Barangay 3 (Pob.), Talakag, Bukidnon | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1847 | TALISAYMISOR | NA | TALISAYMISORFLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8788 | 125.1773 | Brgy Talisay Gingoog City Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN370 | TALISY | NA | TALISYFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TALISAYAN |  | Territory 8 | 8.9947 | 124.8802 | Purok 1 Talisayan_Poblacion, Talisayan, Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1822 | TELEC CDO | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5084 | 124.6288 | Zone 1, Buara, Bayabas, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN371 | TRINAS | NA | TRINASFHLWXY VILTRINBUGOCDOMORFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5127 | 124.7738 | Gumamela St. Villa Trinitas Subdivision, Phase II, Bugo, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN116 | TUPSAN | NA | TUPSANFHLWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2026 | 124.7769 | Tupsan, Mambajao, Camiguin | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN865 | UCARME | CDO_032_GPONA_01 | UPPERCARMENCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4707 | 124.6286 | Carmen, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1666 | UP9TABLONCDO | NA | UP9TABLONCDOFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4679 | 124.7178 | Pilipinas Shell, Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN664 | VALEN | NA | VALENHKLDXYFWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9095 | 125.0822 | Purok 21, Valencia_Poblacion, City of Valencia, Bukidnon | MARAMAG TELIC | GT | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN743 | VILLAN | VNV_001_GPONA_01 | VILLANFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | VILLANUEVA |  | Territory 8 | 8.5833 | 124.7682 | National Highway Villanueva Poblacion1, Villanueva, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1972 | VIPBLDGCDO | NA | VIPBLDGCDOFHKLMVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4793 | 124.6448 | VIP Hotel Bldg. Don A. Velez C. Pacanas St., Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1362 | VLN-701 | VLN_701_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9043 | 125.0925 | Along Guillermo Lavina St., Corner National Hiway Valencia City | GVALEN | GT | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1285 | VLN-702 | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9308 | 125.0972 | NEAR BEES GARDEN ALONG SUNKIST ROAD , VALENCIA , BUKIDNON | MALAY2 | GT | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1402 | VLN-703 | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8942 | 125.0796 | HUAWEI CABINET BESIDE FIBECO, ALONG EXIT OF SUGARLAND BRGY. LUMBO, VALENCIA, BUKIDNON | GVALEN | GT | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN109 | WAOLDS | NA | WAOLDSFHKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | WAO |  | Territory 8 | 7.6425 | 124.7239 | Poblacion, Wao, Lanao Del Sur | MARAMA | GT | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1153 | XAVIER | CDO_006_GPONA_01 | XAVIERSUBDCDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4376 | 124.6244 | 20 60 Xavier Heights Subd Balulang, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2078 | XAVIERUCDOOD | NA | XAVIERUCDOIDD | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4763 | 124.6485 | 3800 Victory Pkwy, Cincinnati, OH 45207, USA | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1886 | XVR-01 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4447 | 124.6209 | Infront of Xavier Estates Subdivision, Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | [6 empty] | #N/A
MIN1976 | ZON8BULUACDO | NA | Z8BULUACDOMORFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5125 | 124.6139 | BrgyBulua_CagayandeOroCity_MisamisOriental, Cagayan De Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1974 | ZONE4TABLON | CDO_036_GPONA_01 | Z4TABLONCDOMORFHKLVWY ZONE4TABLONFHKLWXYR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4837 | 124.7288 | Brgy Tablon Cagayan de Oro City Misamais Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2132 | ZUBIRI REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7635 | 124.9173 | Brgy. Danggawan, Maramag, Bukidnon | MARAMA | GT | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2033 | George Town Cyber Mall | NA | GTCYBM-LSA01 | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4874 | 124.6389 | Georgetown Building, Vamenta Blvd, Near Sacred HEart Church, Cagayan de oro City | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2034 | LIFESTYLE DISTRICT | NA | LIFESTYLE DISTRICT | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4883 | 124.6484 | LIfestyle District, Corrales Extension Cagayan de oro City | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN960 | SJQUEZONBUKZ | NA | SJQUEZONBUKFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.7267 | 125.0411 | San Jose, QUEZON, BUKIDNON, REGION X (NORTHERN MINDANAO), MIN | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2691 | SANMARTINVNUEVAMOR | NA | SANMARTINVNUEVAMORFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | VILLANUEVA |  | Territory 8 | 8.5606 | 124.7686 | Brgy. San Martin, Villanueva, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN951 | ROBINSONCDO | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4808 | 124.656 | Lapasan, CAGAYAN DE ORO CITY (Capital), MISAMIS ORIENTAL, REGION X (NORTHERN MINDANAO), MIN | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2289 | BASECMPMRAMAGBUK | NA | BASECMPMRAMAGBUKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7738 | 124.981 | Brgy. Base Camp, Maramag, Bukidnon | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2390 | POBLIBONABUK | NA | POBLIBONABUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | LIBONA |  | Territory 8 | 8.3341 | 124.7435 | BrgyPoblacion_Libona_Bukidnon | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2291 | SANJOSEQUEZONBUK | NA | SANJOSEQUEZONBUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.7354 | 125.0695 | BrgySanJose_QUEZON_BUKIDNON | GVALEN | PHILTOWER | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2254 | BAYABSCDOMOR | NA | BAYABASCDOMORFLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5073 | 124.6406 | BrgyBayabas_CagayandeOroCity_MisamisOriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2705 | P7POBELSALVMOR | NA | P7POBELSALVMORFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | EL SALVADOR CITY |  | Territory 8 | 8.5513 | 124.5115 | BrgyCogon_CagayanDeOroCity | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2395 | SANISIDTLAKAGBUK | NA | SANISIDTLAKAGBUKFKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | TALAKAG |  | Territory 8 | 8.2631 | 124.5932 | BrgySanIsidro_Talakag_Bukidnon | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2513 | SMCSERRANVILLWAOLDS | NA | SMCSERRANVILWAOLDSFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | WAO |  | Territory 8 | 7.6866 | 124.7316 | PUROK 4 SERRAN VILLAGE, Kilikili West, WAO, LANAO DEL SUR, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2385 | KIBANGKAY | NA | KIBANGAYLANTAPBUKFLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | LANTAPAN |  | Territory 8 | 8.0518 | 124.8997 | Kibangay, LANTAPAN, BUKIDNON, REGION X (NORTHERN MINDANAO), MIN | MALAY2 | PHILTOWER | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW31 | TABLONCOW | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4782 | 124.726 | Tablon, Cagayan de Oro City | CDO NDC | GT | [6 empty] | #N/A
MIN2523 | ROBVALBUK | NA | ROBVALBUKFWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9343 | 125.1003 | Robinsons Mall, Sayre Highway , Valencia City, Bukidnon | MALAY2 | GT | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1927 | MARAMAG TELIC | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7624 | 125.0031 | North Poblacion, MARAMAG, BUKIDNON, REGION X (NORTHERN MINDANAO), MIN | MALAY2 | GT |  |  |  |  | ROSSI AGA CLAUDE PUERTO
MIN2633 | CDO-710 | CDO_710_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4809 | 124.6486 | Ramon Chavez St, Barangay 24 (Pob.), CAGAYAN DE ORO CITY (Capital), MISAMIS ORIENTAL, REGION X (NORTHERN MINDANAO), MIN | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2658 | CDO-711 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4768 | 124.6608 | Rosario Limketkai Ave., Camaman-an, CAGAYAN DE ORO CITY (Capital), MISAMIS ORIENTAL, REGION X (NORTHERN MINDANAO), MIN | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW57 | KBARITKALILABUKCOW | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | KALILANGAN |  | Territory 8 | 7.8134 | 124.683 | CAMP KIBARITAN, BRGY. MALINAO, KALILANGAN, BUKIDNON | MARAMA | GT | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2145 | POBMAMBAJAO_D | NA | NA | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2436 | 124.7242 | Poblacion, MAMBAJAO (Capital), CAMIGUIN, REGION X (NORTHERN MINDANAO), MIN | GINGOO | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2253 | Z1LUMBIACDOMOR | NA | Z1LUMBIACDOMORFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.3978 | 124.5974 | Cagayan de Oro, Lalawigan ng Misamis Oriental, Pilipinas | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2396 | SANTONIOTLAKAGBUK | NA | SANTONIOTLAKAGBUKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | SAN ANTONIO |  | Territory 8 | 8.2026 | 124.6065 | San Antonio, Baungon, Bukidnon, Philippines | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2710 | LAFORTUNAIMPASBUK | NA | LAFORTUNAIMPASBUKFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUGONG |  | Territory 8 | 8.2064 | 124.9539 | Impasug-ong, Bukidnon, Pilipinas | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2595 | SANNICOLASDCARLSBUK | NA | SANNICOLASDCARLSBUKFHLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS |  | Territory 8 | 7.679 | 124.969 | San Nicolas (Banban), Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2324 | KIBUNGSODMAGSAYMOR | NA | KIBUNGSODMAGSAYMORFKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MAGSAYSAY |  | Territory 8 | 9.0074 | 125.2064 | BrgyKibungsod_Magsaysay_MisamisOriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2596 | MABUHAYSFERNBUK | NA | MABUHAYSFERNBUKXFLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | SAN FERNANDO |  | Territory 8 | 7.9013 | 125.3457 | BrgyMabuhay_SanFernando_Bukidnon | GVALEN | PHILTOWER | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2694 | NICDAOBAUNGNBUK | NA | NICDAOBAUNGBUKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | BAUNGON |  | Territory 8 | 8.3875 | 124.6187 | BrgyNicdao_CagayanDeOroCity | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2876 | SUGBOTAGOLOANMISOR | NA | SUGBONGTAGOLOMORFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TAGOLOAN |  | Territory 8 | 8.5301 | 124.7537 | BrgySugbongcogon_Tagoloan_MisamisOriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2506 | BANGAHANPNGANTBUK | NA | BANGAHANPNGANTBUKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | PANGANTUCAN |  | Territory 8 | 7.6527 | 124.8236 | SMC_R0039_BrgyBangahan_Pangantucan_Bukidnon | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1621 | GTGLASSMALAYBBUKPC | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1559 | 125.1268 | Gaisano Malaybalay | MALAY2 | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2577 | LUMBO2VALN | NA | LUMBO2VALNFHLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8927 | 125.0767 | Lumbo, Valencia City Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3382 | MANGIMADALIRGBUKSPEM | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3753 | 124.8799 | Mangima River, Bukidnon, Philippines | CDO NDC | GT | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW52 | CALAANCOW | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.47 | 124.607 | Zone 6, Calaanan,, Canito-an, CAGAYAN DE ORO CITY (Capital), MISAMIS ORIENTAL, REGION X (NORTHERN MINDANAO) | CDO NDC | GT | [6 empty] | #N/A
MIN3209 | KIORAOKIBAWEBUK | NA | KIORAOKIBAWEBUKFLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | KIBAWE |  | Territory 8 | 7.5355 | 124.9336 | Kibawe, Bukidnon, Philippines | MARAMA | PHILTOWER | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2274 | Z7LINGIONMFORTBUK | NA | LINGIONMFORTBUKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3809 | 124.8833 | Lingion, Manolo Fortich, Bukidnon, Philippines | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2283 | BATANGANVALENBUK | NA | BATANGANVALENBUKFKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9041 | 125.1067 | Pinatilan, Valencia City, Bukidnon, Philippines | GVALEN | PHILTOWER | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW22 | NPOBMARAGBUKCOW | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7655 | 125.0234 | Crystal Sugar Company, Inc., North Poblacion, Maramag, Bukidnon, Philippines | MARAMA | GT | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3253 | BULUACDOMOR | NA | BULUACDOMORFKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4875 | 124.6096 | Bulua near Amaya Subd | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1949 | CONSOLACIONCDOMOR | NA | CONSOLACIONCDOMORFLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4918 | 124.6494 | Manuel Vega St, Cagayan de Oro, Misamis Oriental, Philippines | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3446 | SINAILAGUINMOR | NA | SINAILAGUINMORFKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LAGUINDINGAN |  | Territory 8 | 8.5778 | 124.426 | Butuan - Cagayan de Oro - Iligan Rd, Barangay Sinai, Laguindingan, Cagayan de Oro, 9000 Misamis Oriental, Pilipinas | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3142 | POBIMPASBUK | NA | POBIMPASBUKFKLWX | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUGONG |  | Territory 8 | 8.3034 | 124.9993 | Impasug-ong, Bukidnon, Philippines | CDO NDC | PHILTOWER | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3245 | MACSANDIGCDOMOR | NA | MACSANDIGCDOMORFKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4543 | 124.6399 | Zone 2, Rainbow Drive, Pillar Homes, Tibasak, Macasandig, Cagayan de Oro City | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2358 | DAMPILAGONGMOR | NA | DAMPILAGONGMORFKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LAGONGLONG |  | Territory 8 | 8.826 | 124.7934 | Dampil, Lagonglong, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2281 | MAUSWAGLAGUINMOR | NA | MAUSWAGLAGUINMORFKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5971 | 124.4097 | Brgy. Mauswagon, Laguindingan, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2352 | LUMADPOBMAMBJACMGN | NA | LUMADPOBMAMBJACMGNFLWY | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2516 | 124.7086 | Sitio Lumad, Brgy. Poblacion, Mambajao, Camigiun | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3481 | UMALAGTABLONCDOMOR | NA | UMALAGTABLONCDOMORFKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4778 | 124.7262 | Phase 9-A Linanguhan, Brgy. Tablon, Cagayan de Oro City, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3442 | DOLOGON2MRAMAGBUK | NA | P1DOLOGONMRAMAGBUKFKLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8419 | 125.0426 | Brgy. Dologon, Maramag, Bukidnon | GVALEN | GT | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3353 | P5SUMPONGMALAYBBUK | NA | P5SUMPONGMALAYBBUKFKLVWYKX | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1626 | 125.1239 | Brgy. Sumpong, Malaybalay City, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3246 | Z10BULUACDOMOR | NA | Z10BULUACDOMORFKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4898 | 124.6116 | Soldiers Hill Subdivision, Bulua, Cagayan de Oro City | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2095 | BRGY23CDOMOR | NA | BRGY23CDOMORFKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4886 | 124.6507 | Barangay 23, Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3595 | BRGY1TLAKAGBUK | NA | BRGY1TLAKAGBUKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | TALAKAG |  | Territory 8 | 8.235 | 124.6022 | Barangay 1, Talakag, Bukidnon | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3146 | CALAANCANITOANCDOMOR | NA | CALAANCANITOANCDOMORFKLMNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4703 | 124.6073 | Zone 6, Calaanan,, Canito-an, CAGAYAN DE ORO CITY (Capital), MISAMIS ORIENTAL, REGION X (NORTHERN MINDANAO) | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2540 | SMCNORTHMRAMAGBUK | NA | SMCNORTHMRAMAGBUKFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7666 | 125.0146 | Purok 2A, Brgy. North Poblacion, Maramag, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3700 | IPONAN01CDOMOR | NA | IPONAN01CDOMORFKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4962 | 124.596 | 2019CapSite_BrgyIpona01_CdeO_MisOr | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3698 | SALWAGNQUEZONBUK | NA | SALWAGNQUEZONBUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON | Salawagan | Territory 8 | 7.6945 | 125.1164 | Salawagan, Quezon, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2481 | POBLACIONMFORTBUK | NA | POBLACIONMFORTBUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3658 | 124.8634 | Poblacion, Manolo Fortich, Bukidnon | CDO NDC | GT | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3630 | P6APOBVALENBUK | NA | P6APOBVALENBUKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9112 | 125.0846 | Purok 6A, Brgy. Poblacion, Valencia City, Bukidnon | GVALEN | PHILTOWER | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3256 | CARMEN02CDOMOR | NA | CARMEN02CDOMORFKLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.472 | 124.6346 | Macanhan, Brgy. Carmen, Cagayan deo Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3528 | TCFGAP1BANLANTAPBUK | NA | TCFGAP1BANLANTAPBUKFLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | LANTAPAN |  | Territory 8 | 8.0142 | 125.0716 | Pur0k1A, Bantuanon, Lantapan, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3585 | ROSALCARMENCDOMOR | NA | ROSALCARMENCDOMORFLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.482 | 124.6376 | Yakal St., Zone 1, Carmen, Cagayan De oro City | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3621 | P16POBVALENBUK | NA | P16POBVALENBUKFLVWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9117 | 125.0923 | Purok 16, Poblacion, Valencia City, Bukidnon | GVALEN | GT | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3542 | LAGUITASMALAYBBUK | NA | LAGUITASMALAYBBUKFHKLWXY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.0803 | 125.1319 | Brgy. Laguitas, Malaybalay City, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2700 | BRGY20GINGOOMOR | NA | BRGY20GINGOOMORFLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8252 | 125.1109 | Barangay 20, Gingoog City, Misamis Oriental | GINGOO | PHILTOWER | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3096 | BRGY6CDOMOR | NA | BRGY6CDOMORFKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4776 | 124.6416 | Barangay 6, Cagayan de Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3182 | SARAYSALAYMOR | NA | SARAYSALAYMORFKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | SALAY |  | Territory 8 | 8.8842 | 124.7912 | Brgy. Inobulan, Salay, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3742 | TCFGAIPONAN03CDOMOR | NA | TCFGAIPONAN03CDOMORFLWX | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4937 | 124.6045 | Brgy Iponan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3520 | LAPASAN01CDOMOREM | NA | LAPASAN01CDOMOREMFHR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4832 | 124.6635 | Brgy. Lapasan, Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3518 | KAUSWAGN02CDOMOREM | NA | KAUSWAGN02CDOMOREMFHR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.489 | 124.6402 | Barangay Kauswagan, Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3405 | TCFGADOLOGNMRAMAGBUK | NA | TCFGADOLOGNMRAMAGBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.837 | 125.0323 | Brgy. Dologon, Maramag, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3893 | TCFGABULUA01CDOMOR | NA | TCFGABULUA01CDOMORFLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5056 | 124.6153 | Brgy. Bulua, Cagayan de Oro City | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3910 | TCAICPOBLAVALENBUK | NA | TCAICPOBLAVALENBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.918 | 125.0777 | Barangay Poblacion, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3911 | TCAICSUGODVALENBUK | NA | TCAICSUGODVALENBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9415 | 125.1156 | Barangay Sugod, Valencia City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3549 | TCFGAEXTWAOLDS | NA | TCFGAEXTWAOLDSFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | WAO |  | Territory 8 | 7.6418 | 124.7302 | Brgy Extension, Wao, Lanao Del Sur | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3550 | TCFGAWESTPOBWAOLDS | NA | TCFGAWESTPOBWAOLDSFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | WAO |  | Territory 8 | 7.6385 | 124.7185 | Western Pob. Wao, Lanao Del Sur | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3714 | POBLAELSALVMOR | NA | POBLAELSALVMORFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | EL SALVADOR CITY |  | Territory 8 | 8.5622 | 124.5204 | Brgy Poblacion, El Salvador, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3728 | COGBALINGMOR | NA | COGBALINGMORFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGASAG |  | Territory 8 | 8.7495 | 124.7783 | Brgy Cogon, Balingasag, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3867 | TCAICPINATiLANVALBUK | NA | TCAICPINATILANVALBUKFLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8829 | 125.1117 | Purok 2, Barangay Pinatilan, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3975 | TCAICDALIRIGMFORTBUK | NA | TCAICDALIRIGMFORTBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3749 | 124.9039 | BRGY. DALIRIG, MANOLO FORTICH, BUKIDNON | CDO NDC | UNITY | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3976 | TCAICLUNOCANMFORTBUK | NA | TCAICLUNOCANMFORTBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.4131 | 124.8291 | BRGY. LUNOCAN, MANOLO FORTICH, BUKIDNON | CDO NDC | UNITY | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3977 | TCAICMALUKOMFORTBUK | NA | TCAICMALUKOMFORTBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3741 | 124.9553 | BRGY. MALUKO, MANOLO FORTICH, BUKIDNON | CDO NDC | UNITY | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3980 | TCAICP1SNMARTINMALAYBUK | NA | TCAICP1SNMARTINMALAYBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 7.9952 | 125.1971 | PUROK 1, BRGY. SAN MARTIN, MALAYBALAY CITY, BUKIDNON | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3383 | TCAICP5BCUDMALAYBBUK | NA | TCAICP5BCUDMALAYBBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.0008 | 125.1331 | Purok 5, Bangcud, Malaybalay City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3387 | TCAICP2SJOSMALAYBBUK | NA | TCAICP2SJOSMALAYBBUKF_DFLDW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.104 | 125.1219 | Purok 2, San Jose, Malaybalay City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3391 | TCAICP4CASIMALAYBBUK | NA | TCAICP4CASIMALAYBBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1401 | 125.1241 | Purok 4, Casisang, Malaybalay City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3398 | TCFGAP6SPOBMRAMAGBUK | NA | TCFGAP6SPOBMRAMAGBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7472 | 125.0075 | Purok 6.A, South Poblacion, Maramag, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3662 | TCFGAMOLUGELSALVMOR | NA | TCFGAMOLUGELSALVMORFLW | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | EL SALVADOR CITY |  | Territory 8 | 8.5349 | 124.5605 | Molugan, El Salvador, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3393 | TCAICP5PAT2MALAYBBUK | NA | TCAICP5PAT2MALAYBBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1948 | 125.0508 | Purok 5, Patpat, Malaybalay City, Bukidnon | CDO NDC | UNITY | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3416 | TCAICP4APOBVALENBUK | NA | TCAICP4APOBVALENBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9074 | 125.0761 | Purok 4A, Poblacion, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3418 | TCAICBAGONTSVALENBUK | NA | TCAICBAGONTSVALENBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9501 | 125.1057 | Purok 3, Bagontaas, Valencia City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3541 | TCAICBAROBOVALENBUK | NA | TCAICBAROBOVALENBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9046 | 125.0354 | BrgyBarobo_VALENCIA CITY_BUKIDNON | GVALEN | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3390 | TCAICP2CASIMALAYBBUK | NA | TCAICP2CASIMALAYBBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1444 | 125.123 | Purok 2, Brgy. Casisang, Malaybalay City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3412 | TCAICPOBVALENBUK | NA | TCAICPOBVALENBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9134 | 125.0882 | Brgy. Poblacion, Valencia, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3388 | TCAICP9CASIMALAYBBUK | NA | TCAICP9CASIMALAYBBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1225 | 125.1248 | KM 4, Purok9, Brgy. Casisang, Malaybalay City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3386 | TCAICP2AGLYMALAYBBUK | NA | TCAICP2AGLYMALAYBBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.0599 | 125.1337 | Purok 2B, Brgy. Aglayan, Malaybalay City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3845 | TCAICP6KAHAPUNVALBUK | NA | TCAICP6KAHAPUNVALBUKFLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9188 | 125.1542 | Purok 6, Barangay Kahapunan, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3401 | TCFGAPANALSMRAMAGBUK | NA | TCFGAPANALSMRAMAGBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8603 | 124.9817 | Brgy. Panalsalan, Maramag, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2252 | STACRUZGUSACDOMOR | NA | STACRUZGUSACDOMORFKLMNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4694 | 124.6698 | Brgy. Gusa, Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3523 | BRGY40CDOMOREM | NA | BRGY40CDOMOREMFHR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4764 | 124.649 | Barangay 40 (Pob.), Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4148 | TCISAGYAYNGINGOOMOR | NA | TCISAGYAYNGINGOOMORLY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8567 | 125.0591 | Brgy.Agay-ayan,GINGOOG CITY,MISAMIS ORIENTAL | GINGOO | ISON | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3533 | TCFGALINABUBALINGMOR | NA | TCFGALINABUBALINGMORLY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGASAG |  | Territory 8 | 8.7029 | 124.8498 | Upper Linabu, Balingasag, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4087 | TCAICLUMBOVALENBUK | NA | TCAICLUMBOVALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8875 | 125.0849 | Barangay Lumbo, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4022 | TCAICP4SJOSMALAYBBUK | NA | TCAICP4SJOSMALAYBBUKLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1117 | 125.1284 | Lot No. 26-B, Purok 05, Barangay San Jose, Malaybalay City Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4077 | TCFGAWESTKIBAWEBUK | NA | TCFGAWESTKIBAWEBUKFLWY | REGION X (NORTHERN MINDANAO) | BUKIDNON | KIBAWE |  | Territory 8 | 7.5736 | 124.9881 | Brgy. West, Kibawe, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2391 | TCFGAKINAWELIBONABUK | NA | TCFGAKINAWELIBONABUKLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | LIBONA |  | Territory 8 | 8.3714 | 124.6841 | Brgy.Kinawe,LIBONA,BUKIDNON | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3389 | TCAICP6CASIMALAYBBUK | NA | TCAICP6CASIMALAYBBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1336 | 125.1202 | Purok 6, Casisang, Malaybalay City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3426 | TCFGABRGY1POBQUEZONBUK | NA | TCFGABRGY1POBQUEZONBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.7366 | 125.095 | Brgy. 1-D, Poblacion, Quezon, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3406 | TCAICP5LMBOVALENBUK | NA | TCAICP5LMBOVALENBUKFLW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8865 | 125.0735 | Purok 5, Lumbo, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3432 | TCAICP1MABUHAYVALENBUK | NA | TCAICP1MABUHAYVALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8428 | 125.1371 | Purok 1, Mabuhay, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3423 | TCAICP14LALIGANVALENBUK | NA | TCAICP14LALIGANVALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.878 | 125.1882 | Purok 14, Laligan, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3392 | TCAICBRGY11POBMALAYBBUK | NA | TCAICBRGY11POBMALAYBBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1445 | 125.1159 | Zone 5, Brgy. 11 Poblacion, Malaybalay City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3427 | TCAICMASIGLAQUEZONBUK | NA | TCAICMASIGLAQUEZONBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.705 | 125.114 | Purok Masigla, Brgy. Salawagan, Quezon, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3419 | TCAICP1BAGONTASVALENBUK | NA | TCAICP1BAGONTASVALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9634 | 125.1136 | Purok 1, Brgy. Bagontas, Valencia City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3428 | TCAICP2LIBERTDQUEZONBUK | NA | TCAICP2LIBERTDQUEZONBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.7156 | 125.1126 | P2, Brgy. Libertad, Quezon, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3409 | TCAICBRGYLUMBOVALENBUK | NA | TCAICBRGYLUMBOVALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.894 | 125.0879 | Brgy. Lumbo, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3422 | TCAICP2LUROGANVALENBUK | NA | TCAICP2LUROGANVALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9654 | 125.0425 | Purok 4, Brgy. Lurogan, Valencia City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3420 | TCAICP7MAILAGVALENBUK | NA | TCAICP7MAILAGVALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9722 | 125.1177 | Purok 7, Dabongdabong, Brgy. Mailag, Valencia City, Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3394 | TCAICPOBLAPNGANTBUK | NA | TCAICPOBLAPNGANTBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | PANGANTUCAN |  | Territory 8 | 7.8307 | 124.8343 | Brgy. Poblacion, Pangantucan, Bukidnon | MARAMA | UNITY | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4133 | GUSACDOMOR | NA | GUSACDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4789 | 124.6722 | Gusa, Cagayan De Oro City | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4138 | AIRPTLAGUINMORLS | NA | AIRPTLAGUINMORLSFKWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LAGUINDINGAN |  | Territory 8 | 8.6085 | 124.4583 | Laguindingan Airport Moog, Laguindingan, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4001 | SMCDOMORLS | NA | SMCDOMORLSFHWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4569 | 124.6225 | SM City Cagayan de Oro Upper Balulang, Materson Ave. cor Gran Via St., Carmen, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2091 | USTPCDOMORIO | NA | USTPCDOMORIOFHWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4849 | 124.657 | USTP, Lapasan, Cagayan De Oro City | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2498 | XAVIERESTCDOMORIO | NA | XAVIERESTCDOMORIOWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4456 | 124.6258 | Xavier Sports and Country club, Balulang, Cagayan De Oro City | CDO NDC | GT | [6 empty] | #N/A
MIN2961 | PDLIMBLDGGINGOOMORPC | NA | PDLIMBLDGGINGOOMORPCF | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8224 | 125.1086 | Ground floor, Lim Bldg, Doña Graciana St, Gingoog, 9014 Misamis Oriental | GINGOO | GT | [6 empty] | #N/A
MIN3514 | KAUSWAGN01CDOMOREM | NA | KAUSWAGN01CDOMOREMFHR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.4868 | 124.6389 | Barangay Kauswagan, Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3865 | TCAICP5CASISAMLAYBUK | NA | TCAICP5CASISAMLAYBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY (CAPITAL) |  | Territory 8 | 8.1367 | 125.128 | Purok 5, Brgy. Casisang, Malaybalay City,Bukidnon | MALAY2 | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3535 | TCFGASANISIDBLNGSGMOR | NA | TCFGASANISIDBLNGSGMORFLW | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGASAG |  | Territory 8 | 8.7367 | 124.803 | Brgy San Isidro, Balingasag, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4076 | TCFGAP3MBHAYVALENBUK | NA | TCFGAP3MBHAYVALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8574 | 125.1411 | Purok 3, Mabuhay, Valencia City, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3384 | TCTILINABMALAYBBUK | NA | TCTILINABMALAYBBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY (CAPITAL) |  | Territory 8 | 8.054 | 125.1464 | P-6A Aglayan, Malaybalay City, Bukidnon | CDO NDC | TIGER | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3855 | TCTICAS01MALAYBBUK | NA | TCTICAS01MALAYBBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY (CAPITAL) |  | Territory 8 | 8.138 | 125.1122 | Purok 20, Brgy. Casisang, Malaybalay City, Bukidnon | MALAY2 | TIGER | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3413 | TCFGAPOB04VALENBUK | NA | TCFGAPOB04VALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9209 | 125.0869 | Brgy. Poblacion, Valencia City, Bukidnon | GVALEN | FTAP | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3424 | TCTISINAYWNVALENBUK | NA | TCTISINAYWNVALENBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8667 | 125.1424 | Brgy. Sinayawan, Valencia City, Bukidnon | GVALEN | TIGER | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3982 | TCFGAAGUSANCDOMOR | NA | TCFGAAGUSANCDOMORFW | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.484 | 124.7389 | Brgy Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3944 | TCFGABUGO01CDOMOR | NA | TCFGABUGO01CDOMORFW | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.5075 | 124.7619 | Ilang2 st. Bugo, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2761 | Governor Office | NA | NA | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.2437 | 124.724 | Mambajao Polacion, Camiguin | GINGOO | GT | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2146 | Happy Warehouse | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | Cagayan de Oro City |  | Territory 8 | 8.4578 | 124.6443 | Macasandig,Cagayan de Oro City | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2159 | CDO Corp Office | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | Cagayan de Oro City |  | Territory 8 | 8.4843 | 124.6564 | 6th Floor Gateway Tower, Limketkai Drive,CDO City | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2155 | CEPALCO | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | Cagayan de Oro City |  | Territory 8 | 8.4481 | 124.6233 | CEPALCO Admin Bldg. Balulang , CDO | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2494 | Mountain View Collage Valencia | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | Valencia City |  | Territory 8 | 7.9831 | 125.0078 | Mountain View College, City of Valencia City, Bukidnon | MALAY2 | GT | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2495 | Circa Restaurant, Red Planet Hotel | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | Cagayan de Oro City |  | Territory 8 | 8.4849 | 124.655 | Red Planet Hotel, C.M. Recto Avenue, Brgy. Lapasan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2496 | G9 Distributors | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | Cagayan de Oro City |  | Territory 8 | 8.4782 | 124.6441 | Cruz Taal St., Barangay 11 (Pob.), Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | [6 empty] | #N/A
MIN3522 | LAPASAN02CDOMOREM | NA | LAPASAN02CDOMOREMFHR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.483 | 124.6641 | Brgy. Lapasan, Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4159 | TCISLINGGANBALINGMOR | NA | TCISLINGGANBALINGMORFW | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGASAG |  | Territory 8 | 8.7464 | 124.7837 | Brgy.Linggangao,BALINGASAG,MISAMIS ORIENTAL | CDO NDC | ISON | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4038 | TCISANAHWONMRAMAGBUK | NA | TCISANAHWONMRAMAGBUKLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.783 | 125.0072 | Brgy. Anahawon_Maramag_BUK | MARAMA | ISON | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4039 | TCISPTAGOPOLMOR | NA | TCISPTAGOPOLMORLY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | OPOL |  | Territory 8 | 8.5076 | 124.5637 | Brgy Patag, Opol, Misamis Oriental | CDO NDC | ISON | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4109 | TCISDONCARDCARLSBUK | NA | TCISDONCARDCARLSBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS |  | Territory 8 | 7.6765 | 124.9906 | Brgy.Don Carlos Sur (Pob.),DON CARLOS,BUKIDNON | MARAMA | ISON | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4096 | TCISP6ANPOBMRAMAGBUK | NA | TCISP6ANPOBMRAMAGBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7646 | 124.9974 | Purok 6-A, Brgy. North Poblacion, Maramag, Bukidnon | MARAMA | ISON | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2345 | TCAICDAGATKDVALENBUK | NA | TCAICDAGATKDVALENBUKLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8006 | 125.1429 | Logdeck Street, Barangay Dagatkidavao, Valencia City, Bukidnon | GVALEN | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2284 | TCISP1KUYAMRAMAGBUK | NA | TCISP1KUYAMRAMAGBUKLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8145 | 124.8998 | Purok 1, Kuya Maramag Bukidnon | MARAMA | ISON | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3534 | TCFGANAPILIBALINGMOR | NA | TCFGANAPILIBALINGMORLY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGASAG |  | Territory 8 | 8.7824 | 124.7853 | Brgy. Napaliran, Balingasag, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4164 | TCFGABALULACDOMOR | NA | TCFGABALULACDOMORFLNVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.4614 | 124.6322 | Brgy.Balulang,Cagayan de Oro City (CAPITAL),MISAMIS ORIENTAL | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2392 | TCFGALINGATBAUNGBUK | NA | TCFGALINGATBAUNGBUKLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | Baungon |  | Territory 8 | 8.3337 | 124.6313 | Brgy.Lingating,BAUNGON,BUKIDNON | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3395 | TCFGAP1NPOBMRAMAGBUK | NA | TCFGAP1NPOBMRAMAGBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.768 | 125.0038 | Purok 1, North Poblacion, Maramag, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3430 | TCFGACENTPOBKALILABUK | NA | TCFGACENTPOBKALILABUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | KALILANGAN |  | Territory 8 | 7.7412 | 124.7471 | Central Poblacion, Kalilangan, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2648 | TCFGACARMEN04CDOMOR | NA | TCFGACARMEN04CDOMORFLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.4774 | 124.6386 | Tambo st, Brgy Carmen, Cagayan De Oro City, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3915 | BRGY27CDOMOREM | NA | BRGY27CDOMOREMFHR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.4847 | 124.6498 | Brgy. 27, Cagayan de Oro, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3838 | TCFGAZ2MAMBUYACDOMOR | NA | TCFGAZ2MAMBUYACDOMORLY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.3287 | 124.5967 | ZONE 2A BRGY MAMBUAYA CAGAYAN DE ORO CITY | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4145 | TCISBLUBALCDOMOR | NA | TCISBLUBALCDOMORLY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.4693 | 124.7786 | Brgy.Balubal,CAGAYAN DE ORO CITY (Capital),MISAMIS ORIENTAL | CDO NDC | ISON | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4094 | TCISP2SMGELMRAMAGBUK | NA | TCISP2SMGELMRAMAGBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7786 | 124.9411 | Purok 2B, Brgy. San Miguel, Maramag, Bukidnon | MARAMA | ISON | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4118 | TCAICKLASUNMALAYBBUK | NA | TCAICKLASUNMALAYBBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY (CAPITAL) |  | Territory 8 | 8.1799 | 125.0945 | Brgy.Kalasungay,MALAYBALAY CITY (CAPITAL),BUKIDNON | CDO NDC | UNITY | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3858 | TCAGVIOLEMALAYBBUK | NA | TCAGVIOLEMALAYBBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY (CAPITAL) |  | Territory 8 | 8.0347 | 125.1538 | Purok 2, Brgy. Violeta, Malaybalay City, Bukidnon | MALAY2 | ALT GLOBAL | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3567 | PRK1BRGY24AGINGOOMOR | NA | PRK1BRGY24AGINGOOMORFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8238 | 125.0966 | Purok 1, Barangay 24-A,Gingoog City, Misamis Oriental | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3217 | BUGOCDOMOREM | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5083 | 124.7539 | Butuan-Cagayan De Oro-Iligan Road, Brgy Bugo, Cagayan De Oro City | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3506 | MCASANDIGCDOMOREM | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Macasandig | Territory 8 | 8.4644 | 124.6447 | Brgy. Macasandig, Cagayan de Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4185 | TCISKAUSWAGCDOMOR | NA | TCISKAUSWAGCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.492 | 124.6416 | Brgy.Kauswagan,CAGAYAN DE ORO CITY (CAPITAL),MISAMIS ORIENTAL | CDO NDC | ISON | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4201 | TCISMASCANDIGCDOMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4445 | 124.6417 | Brgy.Macasandig,CAGAYAN DE ORO CITY (CAPITAL),MISAMIS ORIENTAL | CDO NDC | ISON | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4085 | TCISZ4KUYAMRAMAGBUK | NA | None | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8104 | 124.8696 | Zone 4, Sitio Magsaysay Kuya Maramag Bukidnon | MARAMA | ISON | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4172 | TCISBAYANGACDOMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.3566 | 124.601 | Brgy.Bayanga,CAGAYAN DE ORO CITY (Capital),MISAMIS ORIENTAL | CDO NDC | ISON | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4082 | TCISP6DAGUMRAMAGBUK | NA | TCISP6DAGUMRAMAGBUKLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8555 | 124.9268 | Purok 6, Brgy. Dagumba-an, Maramag, Bukidnon | MARAMA | ISON | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4168 | TCISPOBIMPASBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUGONG |  | Territory 8 | 8.3094 | 125.004 | Brgy.Poblacion,IMPASUG-ONG,BUKIDNON | CDO NDC | ISON | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4434 | TCAICPOBMAMBAJAOCMGN | NA | NA | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO |  | Territory 8 | 9.251 | 124.7187 | Brgy.Poblacion,MAMBAJAO (CAPITAL),CAMIGUIN | GINGOO | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4223 | TCAICDMILAGMANFORBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.372 | 124.814 | Brgy.Damilag,MANOLO FORTICH,BUKIDNON | CDO NDC | UNITY | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4446 | TCAICDICLUMMFORTBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH |  | Territory 8 | 8.3771 | 124.8485 | Brgy.Diclum, MANOLO FORTICH, BUKIDNON | CDO NDC | UNITY | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3578 | PRK1BRGY21GINGOOMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY |  | Territory 8 | 8.8197 | 125.1094 | Purok 7, Barangay 21, Gingoog City | GINGOO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3854 | TCFGABRGY01MALAYBBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1654 | 125.1293 | Purok 2, Brgy. 1 Poblacion, Malaybalay City, Bukidnon | MALAY2 | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3410 | TCAGPOB01VALBUK | NA | TCAGPOB01VALBUKFW | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8974 | 125.0929 | Purok 2, Poblacion, Valencia City, Bukidnon | GVALEN | ALT GLOBAL | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3946 | PATAG02CDOMOREM | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Patag | Territory 8 | 8.488 | 124.6294 | Besides Alpha Charlie Tactival Supply, Patag, Cagayan De Oro, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4048 | TCFGALOOCVNUEVAMOR | NA | TCFGALOOCVNUEVAMORFW | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | VILLANUEVA |  | Territory 8 | 8.5944 | 124.7727 | Brgy Looc, Villanueva, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2668 | CDO-713 | CDO_713_HYB_01 | CDO_713_HYB | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4871 | 124.6527 | Mesa Verte Residences, Osmena Ext Agusan, Cagayan De Oro City, Misamis Oriental | CDO NDC | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4406 | TCEDCZ3BONBONOPOLMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | OPOL |  | Territory 8 | 8.5225 | 124.5716 | Gabor St.Zone3 Bonbon Opol MisamisOriental , Opol, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4436 | TCAICPOB2MAMBAJAOCMGN | NA | NA | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO (Capital) |  | Territory 8 | 9.248 | 124.7274 | Brgy. Poblacion, Mambajao, Camiguin | GINGOO | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3399 | TCAICSYRECAMP1MRAMAGBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7127 | 125.0093 | Camp I, Maramag, Bukidnon | MARAMA | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3816 | TCAICP5NPOBMEDINAMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | Medina |  | Territory 8 | 8.9151 | 125.0242 | North Poblacion, Medina Misamis Oriental | GINGOO | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3885 | TCAICBALUARTAGOLOMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TAGOLOAN |  | Territory 8 | 8.541 | 124.7459 | Brgy Baluarte,Tagoloan,Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3397 | TCFGAPRK6POB01MRAMAGBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.7574 | 125.0007 | Brgy. South Pob, Maramag, Bukidnon | MARAMA | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4659 | TCAICZ13ENATUMOTAGOLOMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TAGOLOAN |  | Territory 8 | 8.5324 | 124.7618 | Brgy. Poblacion, Tagoloan, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4544 | TCAICPATAGCDOMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.4925 | 124.6276 | Brgy.Patag, Cagayan de Oro, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4698 | TCEDCTUPSANMHINOGCMGN | NA | NA | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO (CAPITAL) |  | Territory 8 | 9.2122 | 124.7671 | Brgy. Tupsan, Mambajao, Camiguin | GINGOO | EDOTCO | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4705 | TCEDCP7CALAODCARLSBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS |  | Territory 8 | 7.6969 | 124.924 | Brgy. Old Nongnongan, Don Carlos, Bukidnon | MARAMA | EDOTCO | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4706 | TCEDCSANJOSEQUEZONBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.7319 | 125.0526 | Brgy. San Jose, Quezon, Bukidnon | GVALEN | EDOTCO | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4713 | TCEDCTIGNAPOLCDOMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.2545 | 124.572 | Brgy. Tignapoloan, Cagayan de Oro City, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4416 | TCEDCTIKALAANTLAKAGBUK | NA | TCEDCTIKALAANTLAKAGBUKLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | TALAKAG |  | Territory 8 | 8.043 | 124.619 | Brgy. Tikalaan, Talakag, Bukidnon | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2255 | TCEDCBOLOBOLOELSALVMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | El Salvador City |  | Territory 8 | 8.5458 | 124.5372 | Bolobolo, CITY OF EL SALVADOR, MISAMIS ORIENTAL | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2282 | TCAICPOBLACIONVALENBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF VALENCIA |  | Territory 8 | 7.9043 | 125.0934 | Barangay Poblacion, Valencia, Bukidnon | MARAMAG FOC | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2878 | TCEDCBRGY11BMALAYBBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY (CAPITAL) |  | Territory 8 | 8.15 | 125.1245 | Evangelista Lot, Medardo Bello St., Brgy.11, Impalambong, Malaybalay, Bukidnon | MALAY2 | EDOTCO | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3402 | TCFGAPOBLACIONQUEZONBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON |  | Territory 8 | 7.7244 | 125.1056 | Brgy. Poblacion, Quezon, Bukidnon | MARAMAG FOC | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3460 | TCEDCRMAGPOBLAVALENBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9046 | 125.088 | G. Lavina Avenue, Brgy. Poblacion, Valencia City, Bukidnon | MARAMAG FOC | EDOTCO | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3407 | TCFGALUMBO02VALENBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.8932 | 125.0691 | Brgy. Lumbo, Valencia City, Bukidnon | MARAMAG FOC | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4553 | TCFGASOROMAMBJACMGN | NA | NA | REGION X (NORTHERN MINDANAO) | CAMIGUIN | MAMBAJAO (CAPITAL) |  | Territory 8 | 9.2205 | 124.7281 | Orasan, Brgy. Soro-Soro, Mambajao, Camiguin | CAMIGUIN | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4704 | TCAICMATICLAVERMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CLAVERIA |  | Territory 8 | 8.6329 | 124.9873 | Lot No. 013 Mat-I, Claveria Misamis Oriental | GINGOO | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4696 | TCEDCP4MAGSAYKITAOBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | DANGCAGAN |  | Territory 8 | 7.6268 | 125.0106 | Brgy. Lourdes, Dangcagan, Bukidnon | MARAMAG FOC | EDOTCO | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4736 | TCEDCAMOROSELSALVMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | EL SALVADOR CITY |  | Territory 8 | 8.5269 | 124.5461 | Brgy.Amoros, City of Elsavador, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4707 | TCEDCBAYABASONMRAMAGBUK | NA | NA | REGION X (NORTHERN MINDANAO) | BUKIDNON | MARAMAG |  | Territory 8 | 7.8206 | 125.0148 | Brgy. Bayabason (Spring), Maramag, Bukidnon | MARAMAG FOC | EDOTCO | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4709 | TCEDCSANSIMONCDOMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) |  | Territory 8 | 8.4393 | 124.5667 | Brgy. San Simon, Cagayan De Oro, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4723 | TCEDCSANISIDROTLAKAGBUK | NA | TCEDCSANISIDROTLAKAGBUKLY | REGION X (NORTHERN MINDANAO) | BUKIDNON | TALAKAG |  | Territory 8 | 8.2455 | 124.5989 | Brgy. San Isidro, Talakag, Bukidnon | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1739 | ABREEZARES | DVO_708_GPONA_01 | ABREEZA2RESD | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0897 | 125.6112 | HUAWEI CABINET INSIDE GLOBE TELCO ROOM, GROUND FLOOR, ABREEZA RESIDENCE ALONG J.P. LAUREL AVENUE, BRGY. | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1598 | ABREEZEXP | NA | ABREEZEXPDAVAODDSIDFHKWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0913 | 125.6104 | Abreeza Mall JP Laurel St. Acacia, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1424 | ABREEZMALL | NA | ABREEZADAVAODDS1ACFWFWDWXY ABREZ2FKLNVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0907 | 125.6109 | HUAWEI CABINET INSIDE GLOBE TELCO ROOM, GROUND FLOOR, ABREEZA MALL, ALONG J.P. LAUREL AVENUE, BRGY. | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1114 | AGDAO | DVO_038_GPONA_01 | WESUITAGDAODAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0847 | 125.6251 | Wescon Suites Cmpd., R. Castillo, Agdao, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN131 | ALEJAL | CRN_001_GPONA_01 | ALEJALFHLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3846 | 125.6621 | Purok 1 Alejal, Carmen, Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1104 | ANGALA | NA | ANGALAFHKLVWYFH TCFGATAGAKPDAVAODDSFHKLVWYFH | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1201 | 125.4504 | Acacia, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1526 | ANONANGSAMAL | NA | ANONANGSAMALFHKLWY ANONANGSAMALFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.0125 | 125.7414 | Anonang, Island Garden City Of Samal, Davao Del Norte | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN156 | APLAY | DIG_004_GPONA_01, DIG_004_GPONA_02 | APLAYFHKLWY TCFGAAPLAYA2DIGOSDDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7476 | 125.3717 | Digos 2 Aplaya, Digos, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2 | APLAYA | DVO_021_GPONA_01 | MATIAPLAYADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0606 | 125.5372 | New Visayas Village Matina Aplaya, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1225 | APOKON | NA | APOKONFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4102 | 125.839 | Villa Consuelo Apokon, City Of Tagum, Davao Del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1652 | APOKONTAGUM | TGM_014_GPONA_01, TGM_014_GPONA_02 | APOKONTAGUMFHKLVWY APOKONTAGUMFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4381 | 125.8214 | Apokon, Tagum, Davao del Norte, Philippines | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1382 | AREL | NA | ARELLANO11BDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0778 | 125.6109 | Arellano St., Barangay 2A (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1731 | AREL_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0763 | 125.6115 | Sutherland Call Center Office, Jacinto Extension DavaoCity_Barangay 10A (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1986 | ARKCOMMDVO | NA | ARKTIGATTODAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1354 | 125.5862 | Tigatto_DavaoCity_DavaoDelSur, Acacia, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN157 | ASTORG | NA | ASTORGFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.9149 | 125.463 | Astorga, Santa Cruz, Davao del Sur | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN673 | ASUNSI | NA | ASUNSI_DXIFHKLDWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ASUNCION |  | Territory 7 | 7.5393 | 125.7546 | Cambanogoy (Pob.), Asuncion (Saug), Davao Del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN132 | BABAK | NA | BABAKFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.1391 | 125.6935 | Pichon St. Brgy. Babak ( not Adecor) Adecor, Island Garden City Of Samal, Davao Del Norte | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN209 | BACULI | NA | BACULIFHKLVWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BAGANGA |  | Territory 7 | 7.4528 | 126.5806 | Purok Tambis Baculin, Baganga, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN650 | BAGANI | DVO_090_GPONA_01 | BAGANIFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.4773 | 125.2448 | Baganihan Purok 1 Marilog, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN158 | BAGOAP | NA | BAGOAPLAYADAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0417 | 125.5294 | Bago Aplaya, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN236 | BAGOBA | NA | BAGOBAFWYFWY TCFGABAGUMBALUPONDVORFWYFLW | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | LUPON |  | Territory 7 | 6.9282 | 126.0077 | Bagumbayan, Lupon, Davao Oriental | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2468 | BAGOSHIRODVODDS | DVO_096_GPONA_01 | BAGOSHIRODAVAODDSXFKLNPVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0558 | 125.5086 | PRK 1, BRGY. BAGO GALLERA TALOMO | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1111 | BAJADA | BAJADA_LSA04-001-MIN1111 | DJESUBANGOYDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0968 | 125.6195 | J. P. Laurel Ave. GMA Cmpd Buhangin (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1151 | BALIOK | DVO_040_GPONA_01 | TCFGABALIOKDAVAODDSFKLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0451 | 125.4971 | Baliok, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN160 | BALUTA | NA | BALUTAFHWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | HAGONOY |  | Territory 7 | 6.7156 | 125.3519 | Purok 3 Balutakay, Hagonoy, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN212 | BANAY | BNY_001_GPONA_01 | BANAYFHKLWY TCFGAPOBLABANAYDVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BANAYBANAY |  | Territory 7 | 6.9665 | 126.0107 | BanayBanay_Poblacion, Banaybanay, Davao Oriental | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1144 | BANGKA | NA | BANGKAFLWYFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MATANAO |  | Territory 7 | 6.6654 | 125.142 | Bangkal, Matanao, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1100 | BANKAS | DVO_020_GPONA_01 | BANGKASHTSDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0439 | 125.4904 | Bangkas Heights, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN117 | BANKER | NA | BANKERFLWXY TCFGABANKERMONTEVDDOFLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONTEVISTA |  | Territory 7 | 7.7489 | 126.0018 | Purok 6 Bankerohan Sur, Montevista, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN678 | BANSAL | NA | BANSALFKLWY JUDEPOBDOSBANSALDDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | BANSALAN |  | Territory 7 | 6.7838 | 125.2102 | Saint Jude St., Poblacion, Bansalan, Davao del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1311 | BARAY | NA | BARAYFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MAGSAYSAY |  | Territory 7 | 6.783 | 125.1712 | Barayong, Magsaysay, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1286 | BASIAWNSMARIADVOC | NA | BASIAWNSMARIADVOCFHLWY TCFGABASIAWNSMARIADVOCFHLWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.508 | 125.5139 | Basiawan, Santa Maria, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN679 | BATO | SCD_003_GPONA_01 | BATOFHKLWY TCFGABATOSTCRUZDDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.7932 | 125.3896 | Bato, Santa Cruz, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1803 | BAYAN LOCAL EXCHANGE | NA | BAYANIFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1032 | 125.6413 | 2F, Bayantel Bldg., Rafael Castillo, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1298 | BAYTOR | DVO_041_GPONA_01 | PIEDADTORILDAVAODDSFKLNPVW TCFGAPIEDADDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0238 | 125.4915 | Upper Piedad Toril (Pob.), Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1061 | BFACIO | DVO_010_GPONA_01 | BONIFACI33DDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0666 | 125.6145 | 276 A. Bonifacio St., DavaoCity_Barangay 33D (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1658 | BGALLERADVO | NA | BAGOGALLERADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0509 | 125.5169 | Baliok_DAVAO CITY_DAVAO DEL SUR_P15_6 Acacia, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN680 | BOLTON | NA | BOLTONFWYFLVWY TCFGABOLTONMLALAGDDSFLVWYFHK | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MALALAG |  | Territory 7 | 6.5572 | 125.3809 | Sito Lubog, Bolton, Malalag, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3 | BONGUY | NA | PAVILBAGOAPDAVAODDSFKLNPVW TCFGAPAGASAVILDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.042 | 125.5781 | Pagasa Village Matina Aplaya, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1687 | POBBOSTONDVOR | NA | POBBOSTONDVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BOSTON |  | Territory 7 | 7.8613 | 126.3742 | Boston_Poblacion, Boston, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1522 | BRCVILDVOCTY | DVO_022_GPONA_01 | BRCVLCATPEQDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0606 | 125.5372 | Talomo (Pob.)_DAVAO CITY_DAVAO DEL SUR_P15_10 Talomo (Pob.), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1958 | BRDVLBUHANGDAVAODDS | NA | BRDVLBUHANGDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1123 | 125.6068 | BrgyBuhangin(Pob)_DavaoCity_DavaodelSur, Acacia, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN163 | BSHIRE | NA | BRKNSHIRE8ADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0763 | 125.5983 | Circumferencial cor. F. Celga DavaoCity_Barangay 8A (Pob.), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2016 | Bucana-1 MSAN/ DLUISMATINADAVAODDS_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0601 | 125.6119 | Brgy 76A, Bucana Blvd, Bucana, Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2430 | BUCANADVODDS | DVO_085_GPONA_01 | ISIDBUCANADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0466 | 125.6032 | Bucana, Talomo, Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN926 | BUDA | NA | BUDAFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.5212 | 125.2356 | Purok 1, Buda, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN408 | BUDBUD | NA | BUDBUDBUNAWDAVAODDSFKLNPVW TCFGABUNAWDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2241 | 125.6403 | A1 BudBud Bunawan (Pob.), Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN164 | BUHAN2 | NA | KM8CABANTIDAVAODDSFHKLPWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1193 | 125.6281 | Km. 8, Diversion Rd. Cabantian, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN165 | BUHAN3 | DVO_026_GPONA_01 | BUHANGIN02DAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1107 | 125.6173 | Buhangin (Pob.), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1110 | BUHANG | DVO_007_GPONA_01, DVO_007_GPONA_02 | KM5BUHANGINDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1036 | 125.6137 | Km.5 Buhangin Road, Buhangin District, Buhangin (Pob.), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN909 | BUHIS | DVO_088_GPONA_01 | BUHISTIBUNGDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2155 | 125.6433 | Buhisan St Tibungco, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1051 | BULTON | NA | TCFGAMARASIGANDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0655 | 125.6095 | rooftop Marasigan Building Bolton Streeet DavaoCity_Barangay 4A (Pob.), Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN118 | BUNGAB | NA | BUNGABXZFHKLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | PANTUKAN |  | Territory 7 | 7.215 | 125.8759 | Sitio Pagakpak Bongabong, Pantukan, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN166 | CABANT | NA | CABANTFKLNPVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1485 | 125.5987 | Purok 7 Cabantian, Davao City, Davao del Sur | JUNA | FTAP | [6 empty] | #N/A
MIN134 | CABAYA | NA | CABAYAFHLWXY TCFGACABAYBDUJALDDNFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | BRAULIO E. DUJALI |  | Territory 7 | 7.4431 | 125.7212 | Cabayangan, Braulio E. Dujali, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1106 | CABID | NA | CABIDFLWXY TCFGACABIDIANABUNDDOFLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.5726 | 125.9942 | Purok 1 Cabidianan, Nabunturan, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN167 | CABLIG | MAT_001_GPONA_01 | CABLIGFHWYFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MATANAO |  | Territory 7 | 6.7536 | 125.2751 | Km. 67,National Highway Cabligan (Managa), Matanao, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN191 | CABNTI | DVO_075_GPONA_01 | SCHLCABANTDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1348 | 125.6108 | National Highway,Buhangin District Cabantian, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1211 | CAGPAN | PNB_006_GPONA_01 | CAGPANFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2803 | 125.6815 | Cagangohan, Panabo, Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN681 | CALADD | NA | CALINAFHKLVWDY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1841 | 125.421 | Baguio District Malagos, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1999 | CALICLICDDN | NA | CALICLICDDNFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.1032 | 125.6663 | Caliclic, IGACOS, Davao del Norte | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN168 | CALIN2 | DVO_065_GPONA_01 | CALIN2FHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.185 | 125.4541 | Calinan (Pob.), Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN682 | CAMUS | NA | APOVIEWDAVAODDSIDFWXY APOVIEWDAVAODDSODFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0693 | 125.6082 | Apo View Hotel Camus St DavaoCity_Barangay 4A (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1019 | CAP | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0669 | 125.6083 | CAP building JP Rizal St., DavaoCity_Barangay 30C (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5 | POBCARAGADVOR | CRA_001_GPONA_01 | POBCARAGADVORFHLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | CARAGA |  | Territory 7 | 7.3285 | 126.5677 | Caraga_Poblacion, Caraga, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN813 | CARMEN | NA | CARMENFHKLWXY TCFGAGUADACARMENDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3755 | 125.7397 | Guadalupe, Carmen, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN136 | CARMN2 | CRN_002_GPONA_01 | CARMN2FHKLWXY TCFGAISINGPOBCARMENDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3642 | 125.7134 | Purok 2 Ising (Pob.), Carmen, Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1058 | CASTIL | NA | RCASTILGOVDAVAODDSFKLNPVW TCFGACASTILDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0896 | 125.6327 | R. Castillo st. Otero Compund Lapulapu, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1753 | CAT PEQUENO | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0709 | 125.5255 | Wellspring Subd., Phase II, Catalunan Pequeño, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN169 | CATAL2 | DVO_049_GPONA_01, DVO_049_GPONA_02 | TCFGACATALGRANDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0847 | 125.5352 | Catalunan Grande, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2007 | GRNVLCATPEQDAVAODDS | NA | GRNVLCATPEQDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0768 | 125.5261 | Granville Subdivision (fronting Residentia del Rio), Catalunan Pequeno, Davao City, Davao del Sur, Acacia, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1049 | CATALU | NA | CATALUGRANDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0679 | 125.5477 | Seminary Road Catalunan Grande, Talomo Catalunan Grande, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN215 | POBCATEELDVOR | CTL_001_GPONA_01 | POBCATEELDVORFHLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | CATEEL |  | Territory 7 | 7.7888 | 126.4509 | F. Enriquez St. Cateel_Poblacion, Cateel, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1559 | CAWAGSAMAL | NA | CAWAGSAMALFHKLWY CAWAGSAMALFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.0602 | 125.7201 | Cawag, Island Garden City Of Samal, Davao Del Norte | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1411 | CMPSAB | NA | CMPSABFKLVWY KAPATAGANDIGOSDDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.929 | 125.3397 | Purok Mount Apo 1 Kapatagan (Rizal), Digos, Davao del Sur | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1057 | COMMUN | DVO_014_GPONA_01, DVO_014_GPONA_02 | COMMUNALDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.128 | 125.6373 | Diversion road Sasa, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN816 | COMPOS | CMP_001_GPONA_01 | COMPOSFHKLVWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.6655 | 126.0838 | Dagohoy St. Compostela_Poblacion, Compostela, Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN817 | CORONO | SCD_004_GPONA_01 | CORONOFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.8762 | 125.454 | Coronon, Santa Cruz, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN927 | CUAMBO | TGM_015 GPONA-01 | CUAMBOFFKLVWY CUAMBOKLWXYFKL TCFGACUAMBOTAGUMDDNFKLVWYRF | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4968 | 125.7992 | Purok Maharlika Cuambogan, City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2521 | CYBERDELTADVOID | NA | CYBERGATE2DAVAODDSIDFKWDFWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0964 | 125.6176 | Ground Floor,, Robinsons Cybergate Delta,, J. P. Laurel Ave., Buhangin (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN170 | DACUDA | NA | TCFGARGAPACIANODAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0896 | 125.6214 | Amber St. RGA Village Gov. Paciano Bangoy, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN216 | DAHICA | MTI_001_GPONA_01, MTI_001_GPONA_02 | DAHICAFHKDWDY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9454 | 126.2547 | Dahican, Mati, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1227 | DALIAO | DVO_067_GPONA_01 | TCFGABADAKDALIAODAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0107 | 125.5095 | Badak Beach Resort Toril (Pob.), Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1609 | DALIAODVOCTY | DVO_079_GPONA_01 | LIZADADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0039 | 125.4998 | Daliao, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1656 | DASUNCIONVIL | NA | PH7PAMPANGADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1167 | 125.6426 | Doña Asuncion, Buhangin, Davao City, Davao del Sur, Philippines | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN615 | DAVAIR | NA | DVOAIRDAVAODDSIDFWXFHRWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1298 | 125.6447 | New Davao Airport Sasa, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1388 | DAVAO FOC | DVO_047_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0552 | 125.5446 | Ulas Davao City Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1804 | DAVAO NDC | DVO_061_GPONA_01, DONMAR-LSA01-001-MIN1804 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.071 | 125.6104 | 2F, Don Mariano Bldg, C.Bangoy St( former Ponciano Reyes St), DavaoCity_Barangay 34D (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN683 | DAVDOC | NA | DAVDOCDAVAODDSIDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0704 | 125.6048 | Davao Doctors Hospital Quirino St. DavaoCity_Barangay 6A (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2270 | DAWANMATIDVOR | NA | DAWANMATIDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9004 | 126.1504 | Dawan, Davao Oriental, Philippines | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1082 | DCLA | NA | DCLA26CDAVAODDSX DCLAFKLNPVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0738 | 125.6238 | DCLA Bldg Ramon Magsaysay DavaoCity_Barangay 26C (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1794 | DEL MONTE TAMAYONG REPEATER | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1518 | 125.4426 | Brgy Tamayong_DavaoCity_DavaodelSur Tamayong, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1160 | DIG-701 | DIG_701_GPONA_01, DIG_701_HYB_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7558 | 125.3569 | Along First Crumb St. Beside Conpinco Trading Corp. Brgy. Zone I | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1161 | DIG-702 | DIG_702_GPONA_01, DIG_702_GPONA_02 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7449 | 125.3632 | Lapulapu St. cor Corregidor st Front of office of the Prov. Agriculturist Brgy. Zone III | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1162 | DIG-703 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7384 | 125.3609 | Along Dona Aurora Ave. Near Drug Check Phils. Inc Brgy. San Jose | DIGOS | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1163 | DIG-704 | DIG_704_HYB_01, DIG_704_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7435 | 125.3553 | Lim St. cor Rizal St. Beside Gigos City Park Brgy. Zoce III | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1164 | DIG-705 | DIG_705_HYB_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7503 | 125.3408 | Opposite Blk. 25 Lot 02 Beside Emily Homes Covered Court Brgy. Tres De Mayo | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN820 | DIGOS | DIG_001_GPONA_01, DIG_001_GPONA_02 | ZONE2DIGOSDDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7554 | 125.3487 | 6th Estrada St Zone 2 (Pob.), Digos, Davao del Sur | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN903 | DIGOS DOCTOR'S HOSPITAL REPEATER | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.764 | 125.355 | Digos Doctors Hospital McArthur Hiway Zone 2 (Pob.), Digos, Davao del Sur | DIGOS | GT | [6 empty] | #N/A
MIN1426 | TCFGARIZAZONE3DIGOSDDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7461 | 125.3556 | Rizal Avenue Zone 3 (Pob.), Digos, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1632 | DIWATA | NA | DIWATAFHLWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.8182 | 126.1866 | Mt. Diwata, Monkayo Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1268 | DMCDVOOD | NA | SPMCDAVAODDSFDFWXY SPMCDAVAODDSKLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0983 | 125.6203 | Davao Medical Center Buhangin (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN908 | VICTOR_D/ DMSF REPEATER | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.085 | 125.607 | Davao Medical School Foundation Hospital Medical School Drive DavaoCity_Barangay 19B (Pob.), Davao City,Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1668 | DONALUISADVO | NA | DLUISMATINADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0491 | 125.5832 | Dona Luisa, Ph2 Ecoland Davao City Daval del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2748 | DONENRIQUMATIDAVOR | NA | DONENRIQUMATIDAVORFKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9675 | 126.3059 | Brgy Don Enrique Lopez, Mati, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN171 | KINANGADMARCEDVOC | NA | KINANGADMARCEDVOCFWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | DON MARCELINO |  | Territory 7 | 6.1986 | 125.6949 | Kinanga, Don Marcelino, Davao del Sur | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN913 | DUGMAN | NA | DUGMANFHX | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | SAN ISIDRO |  | Territory 7 | 6.8835 | 126.1124 | Puting Bato Dugmanon, San Isidro, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN151 | DUGSO | NA | DUGSOFHKLWXY TCFGADUGSOPANABODDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2993 | 125.7048 | Purok Dugso San Pedro, Panabo, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN133 | DUJALI | NA | DUJALIFHLWXY TCFGADUJABDUJALDDNFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | BRAULIO E. DUJALI |  | Territory 7 | 7.4495 | 125.6883 | Purok 5 Dujali, Braulio E. Dujali, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN153 | DUMABU | NA | DMANLSBUHANDAVAODDSFLPWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.108 | 125.6215 | talisay Ext., Zone 2, Sitio Dumanlas Buhangin (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN162 | DUMOY | DVO_048_GPONA_01 | MACAPLDUMOYDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0355 | 125.5125 | Macapili Subd. Dumoy, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1060 | DURIAN | NA | DURIANHT20BDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0882 | 125.6106 | Durian Hotel JP Laurel St DavaoCity_Barangay 20B (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1015 | DVO-601 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0754 | 125.6116 | E. Jacinto Cor. Quirino St. Inside Nograles Park Barangay Poblacion Downtown Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1016 | DVO-603 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.081 | 125.6067 | Behind Davao City National High School, E. Jacinto St. Cor Surveyor St. Barangay Bajada Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1017 | DVO-605 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0907 | 125.6177 | Along Veloso St. cor. Topaz St., Barangay Obrero, Davao City | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1022 | DVO-607 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0999 | 125.628 | Along J.P. Laurel St. Cor. Carmellite Rd. Between Lady of Victory Enterprises & Prayer House Brgy Bajada Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1023 | DVO-608 | DVO_608_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1087 | 125.6503 | Along J.P. Laurel Ave. Opposite Insular Hotel Waterfront, Barangay Lanang, Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1024 | DVO-615 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.105 | 125.6016 | ALONG C.P. GARCIA AVE., DIVERSION ROAD, COR. BACACA ROAD, BRGY. BUHANGIN, DAVAO CITY | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1032 | DVO-616 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1119 | 125.6323 | near Lifestream Int’l College, along A. Angliongto Sr. Avenue Barangay Damosa, Lanang, Davao City | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1025 | DVO-617 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0797 | 125.583 | ALONG MAA ROAD, OPPOSITE OF BAKEWELL BAKESHOP, BRGY. BUGAC MAA, DAVAO CITY | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1026 | DVO-618 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1031 | 125.582 | ALONG C.P. GARCIA AVE., DIVERSION ROAD, COR. MAA ROAD, BRGY. MAA, DAVAO CITY | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1027 | DVO-619 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1061 | 125.614 | ALONG BUHANGIN ROAD, FRONT OF FIRST BUHANGIN BAPTIST CHURCH INC., | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1028 | DVO-621 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0464 | 125.5675 | Front of Matina Aplaya Elem. School Matina Aplaya Rd. Matina Aplaya Davao City | JUNA | GT | [6 empty] | #N/A
MIN1033 | DVO-622 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0615 | 125.5592 | Along Mc Arthur Hiway, Cor Mabini St. Brgy. Talomo, Beside Mabini Elem. School Bangkal Davao City | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1029 | DVO-623 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.053 | 125.5636 | Cordeliera St. Front of DCPAG Out Post Kadayawan Homes Phase 1 Brgy. Talomo Davao City | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1030 | DVO-624 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0558 | 125.5561 | Corner Sierra Madre & Cordeliera Rd. Dava Central Park Subd. Bangkal, Davao City | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1031 | DVO-625 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.077 | 125.5457 | Cataluna Grande Higway. Brgy.Catalunan Grande Davao City, Beside Brgy. Catalunan Basket ball Gym. | JUNA | GT | [6 empty] | #N/A
MIN1165 | DVO-702 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0674 | 125.6178 | Along Quezon Ave, Beside Brgy Hall, Brgy 31D, Davao | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1166 | DVO-704 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.081 | 125.6067 | Beside Department of Education along F. Torres cor. E Jacinto St. , Davao | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1167 | DVO-706 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0882 | 125.6236 | Beside Assumption College of Davao Along JP Rizal Cabaguio Ave., Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1275 | DVO-709 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0961 | 125.6391 | Jerome st. corner R. Castillo,Barangay LapuLapu Davao | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1168 | DVO-710 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1214 | 125.6451 | Infront of Doña Asuncion Hizon Elementary School,along FDO avenue near corner Balibago St | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1169 | DVO-711 | NA | none | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1252 | 125.6603 | Colocated SASA3DVODDS | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1276 | DVO-712 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1215 | 125.6487 | Saint Peter St. beside Dona Pilar Basketball Covered Court, Dona Pilar Subd. Sasa, Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1170 | DVO-717 | NA | na | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1301 | 125.6209 | Opposite Cabantian National High School near basketball open court | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1171 | DVO-726 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1287 | 125.6188 | Emilyhomes Cabantian, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1172 | DVO-727 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1297 | 125.6176 | Along Revelation cor Joshua St. near Water Tank Emily Homes | JUNA | GT | [6 empty] | #N/A
MIN1174 | DVO-728 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1256 | 125.6336 | Along Pagibig avenue corner Faith st. Pagibig Subd. Bgy. Buhangin | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1173 | DVO-729 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0625 | 125.5703 | Opposite A.P Manzano coco Lumber & Native Products Pres. CP Garcia Highway cor Pangi Ave | JUNA | GT | [6 empty] | #N/A
MIN1175 | DVO-731 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.054 | 125.6019 | Infront PNP Regional Traffic Mgt. OfficeXI Along Dona Candelaria Ave., Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1176 | DVO-733 | DVO_733_GPONA_01, DVO_733_GPONA_02 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.098 | 125.5137 | Near basketball covered court along Uraya Avenue opposite Villegas store | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1177 | DVO-735 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0852 | 125.5086 | Near Southern Mindanao campus opposite A.G. Grekenstrack Ventures along DavaoBukidnon National Highway | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1178 | DVO-736 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0716 | 125.522 | Near Southern Philippine Development Authority along National Highway | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1179 | DVO-738 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0534 | 125.5355 | Infront Providence Primitive Baptist Church corner Acacia st. | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1180 | DVO-739 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.044 | 125.5311 | Infront APO Golf and Country Club opposite Flying V gas station along National Highway | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1181 | DVO-740 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0346 | 125.5112 | Along going to Capili Subdivision opposite barber shop,Purok Kalayaan, Barangay B | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1182 | DVO-741 | DVO_741_HYB_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0133 | 125.4994 | Infront Davao Central College opposite Virgen Del Rosario Parish Church, along Juan Dela Cruz St | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1346 | DVO-742 | DVO_742_HYB_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0649 | 125.5585 | Along C.P. Garcia avenue opposite Loleng Store Countryside Phase 2, Davao | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1403 | DVO-745 | DVO_745_HYB_01, DVO_745_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0591 | 125.528 | HUAWEI CABINET NEAR HOUSE NO. 3 BLK. 1 INSIDE TUSCANA SUBDIVISION, UPPER LIBBY RD. BRGY. BAGO GALLE | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1444 | DVO-746 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0469 | 125.5888 | HUAWEI CABINET ONE OASIS DAVAO ECO WEST DRIVE, BRGY. MATINA DAVAO CITY | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN616 | DVOAIR | DVO_029_GPONA_01 | TCFGADVOAIRSASADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1225 | 125.6535 | Davao International Airport,Catitipan Sasa, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1052 | ECOLAN | NA | ECOLANMTCRODAVAODDSFKLNPVW TCFGAECOLANDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0559 | 125.5872 | No. 143 Jaruda Road, Tulip Drive, Matina Matina Crossing, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN154 | ECOSUB | DVO_011_GPONA_01, DVO_011_GPONA_02 | ECOSUBBUCANDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0498 | 125.5965 | lot 22 blk 3 Ph 7 Ecoland Sudb. Bucana, Davao City, Davao del Sur | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN173 | EDENTO | NA | EDENTOFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0254 | 125.417 | Toril District Eden, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN174 | ELENIT | DVO_016_GPONA_01, DVO_016_GPONA_02 | ELENITADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1064 | 125.5098 | Elenita Height Subd. Purok 18 Mintal, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN155 | ELRIO | NA | ELRIO19BDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1049 | 125.6016 | lot 19 blk 17 Bacaca road El Rio Vista Buhangin (Pob.), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1228 | EMILY | DVO_008_GPONA_01 | EMILYCABANTDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | DAVAO CITY | Territory 7 | 7.1286 | 125.6189 | Emilyhomes Cabantian, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1115 | EPOL | NA | EPOLFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.4526 | 125.2372 | Sitio Epol Marilog Distric Baganihan, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1053 | FARMA | DVO_002_GPONA_01, DVO_002_GPONA_02, DVO_002_GPONA_03 | TCFGASOCVILPANACDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1396 | 125.6498 | Diversion Road, Socorro Village Panacan, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2010 | FTCTOWERDVO | NA | FTCTOWERDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0726 | 125.6056 | FTC Tower, Mt. Apo Street, Malvar St., DavaoCity_Barangay 19B (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN213 | FUENTE | NA | FUENTELOFHL FUENTEPANTUKDDOFHLWXY FUENTEXZ | REGION XI (DAVAO REGION) | DAVAO DE ORO | PANTUKAN |  | Territory 7 | 7.0833 | 125.9435 | Sitio Sarker P. Fuentes, Pantukan, Compostela Valley | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1561 | FULMARDAVAO | NA | SULNHAALFONDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1098 | 125.6273 | Fulmar St. BelisarioBuhangin (Pob.), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1492 | GAIDIGOSOD | DIG_003_GPONA_01 | GAIDIGOSODFHKLWY GAISANZON1DIGOSDDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.758 | 125.353 | Unit 14 G/L Gaisano Grand Mall of Digos Quezon Ave Zone 2 Aplaya, Digos, Davao del Sur | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN914 | GAISANO1DAV | NA | GAISANO1DAVAODDSIDFHWXY GAISANO2DAVAODDSIDFHKWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0779 | 125.6136 | Gaisano Mall, JP Laurel St. Gov. Vicente Duterte, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1391 | GAITAGUMOD | NA | GAIMAGUGTAGUMDDNFHDFKLW GAITAGUMODFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4488 | 125.8122 | Gaisano Mall of Tagum Agusan National Highway Magugpo Poblacion, City Of Tagum, Davao Del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1209 | GOVGE2 | NA | GOVGE2FY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | GOVERNOR GENEROSO |  | Territory 7 | 6.4717 | 126.1225 | Nangan, Governor Generoso, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN217 | GOVGEN | NA | GOVGENFHKLWY TIBANGOVGENDVORFFHKLDWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | GOVERNOR GENEROSO |  | Territory 7 | 6.6325 | 126.0817 | Tibanban, Governor Generoso, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1432 | GPANAB | NA | GPANABFHKLWXY IGPANAFWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3067 | 125.687 | Gaisano Grand Mall of Panabo M. L. Quezon Avenue A. O. Floirendo, Panabo, Davao Del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1109 | GSILUS | NA | GSILUS3ADAVAODDSIDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0693 | 125.6065 | Ilustre St DavaoCity_Barangay 3A (Pob.), Davao City, Davao del Sur | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1418 | GTAGUM | NA | GTAGUMFHKWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4454 | 125.8101 | Gaisano Grand Apokon Road Apokon, City Of Tagum, Davao Del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1229 | GUIHIN | NA | GUIHINFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | HAGONOY |  | Territory 7 | 6.677 | 125.3469 | Sugar St. Guihing, Hagonoy, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN684 | HAGONO | NA | HAGONOFHLWYFHLWY TCFGAPOBHGONOYDDSFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | HAGONOY |  | Territory 7 | 6.6897 | 125.2969 | Sacedo cor. Cavan St., Hagonoy_Poblacion, Hagonoy, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN137 | HIJUMA | NA | HIJUMAFHLWXY TCFGAHIJOMACODDOFHLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MACO |  | Territory 7 | 7.3773 | 125.8398 | Hijo Crossing,Brgy. Hijo,Maco,Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1874 | HRISLU001 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0924 | 125.633 | Belisario Village, R. Castillo St., Rafael Castillo, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1871 | HRISLU002 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0874 | 125.6239 | Assumption College, Cabaguio Ave., Wilfredo Aquino, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1869 | HRISLU003 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0764 | 125.6215 | Lizada Street, Monteverde, DavaoCity_Barangay 27C (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1870 | HRISLU004 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0771 | 125.6169 | Sta Ana Church, LapuLapu St., DavaoCity_Barangay 14B (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1868 | HRISLU005 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0751 | 125.6097 | Near Central Bank, TionkoQurino Street, DavaoCity_Barangay 10A (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1865 | HRISLU006 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0614 | 125.6105 | Almendras Gym, Quimpo Blvd, DavaoCity_Barangay 39D (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1880 | HRISLU009 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1107 | 125.6325 | Victoria Subd, Mamay Road, Alfonso Angliongto Sr., Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1882 | HRISLU010 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1125 | 125.6263 | NHA Buhangin, Buhangin (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1881 | HRISLU011 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1109 | 125.6182 | San Nicolas, Buhangin (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1879 | HRISLU012 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1062 | 125.6133 | PagAsa Subdivision, Buhangin Road, Buhangin (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1876 | HRISLU014 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0975 | 125.6159 | Petron Buhangin, Buhangin (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1877 | HRISLU015 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1004 | 125.6275 | Belisario Subdivision, Lanang, Acacia, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1872 | HRISLU016 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0875 | 125.6106 | Durian Hotel, Acacia, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1867 | HRISLU017 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0748 | 125.6031 | F.Torres Cor. Lopez Jaena Streets, DavaoCity_Barangay 7A (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1883 | HRISLU020 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1172 | 125.6445 | Dona Asuncion Village, Pampanga, Lanang, Acacia, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN1924 | HRISLU021 | DVO_910_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1656 | 125.5754 | Mandug, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1613 | ILANGDVO | NA | ROADILANGDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1779 | 125.6423 | HT Proposed New site_DAVAO CITY_DAVAO DEL SUR_P15_17, Acacia, Davao City, Davao del Sur | JUNA | UNITY | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN176 | INAWAY | SCD_002_GPONA_01 | INAWAYFHKLWY TCFGAINAWAYANSTCRUZDDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.9539 | 125.4714 | Inawayan, Santa Cruz, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1208 | INDAN | DVO_068_GPONA_01, DVO_068_GPONA_02 | MILVILINDANDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1649 | 125.5958 | Millenium Village Indangan, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2013 | Indangan-1 MSAN | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.154 | 125.5968 | Blk. 25 lot 1 & 45 phase 2, Deca Homes, Indangan, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN2014 | Indangan-2 MSAN | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1521 | 125.5967 | Blk. 23 Parks & Playground Phase 1 Deca Homes, Indangan, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN658 | IPANAB | PNB_002_GPONA_01 | IPANABFHKLWXY TCPHTNEWPANPANABODDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2934 | 125.6799 | Purok Atis New Pandan (Pob.), Panabo, Davao Del Norte | JUNA | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN231 | ISIDRO | NA | ISIDROFHLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | SAN ISIDRO |  | Territory 7 | 6.8399 | 126.0893 | Batobato (Pob.), San Isidro, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1050 | JACINT | NA | JACINTFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0692 | 125.6163 | rooftop RCS Bldg., Jacinto St. Davao City DavaoCity_Barangay 32D (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN832 | JUNA | DVO_003_GPONA_01, DVO_003_GPONA_02 | JUNAMATCROSDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0603 | 125.59 | Globe Telecom GT Corp. Center Orchid St., Juna Subd., Matina Crossing, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN660 | KABAN | NA | KABANFLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.9106 | 126.0896 | Pasian (Santa Filomena), Monkayo, Compostela Valley | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN674 | KAPALO | NA | KAPALOFHLVWXY TCFGAMANIKIKPALONDDNFHLVWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG | Maniki (Poblacion) | Territory 7 | 7.5844 | 125.706 | Maniki (Poblacion), Kapalong, Davao Del Norte | DVO-TAGUM | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN675 | KAPUTI | NA | KAPUTIFHKLWXY TCFGAKAPUTISAMALDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 6.9622 | 125.7272 | Poblacion (Kaputian), Island Garden City Of Samal, Davao Del Norte | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN179 | KIBLAW | NA | KIBLAWFKLWY TCPHTPOBLACIONKIBLAWDDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | KIBLAWAN |  | Territory 7 | 6.6124 | 125.2495 | Sitio Acacia Kiblawan_Poblacion, Kiblawan, Davao del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN139 | KIMAMO | NA | KIMAMOFHKLWXY TCFGAKIMAMONSTOMASDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5534 | 125.6904 | Kimamon, Santo Tomas, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN929 | KINABLBAGANGDVOR | NA | KINABLBAGANGDVORFH | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BAGANGA |  | Territory 7 | 7.6901 | 126.549 | Purok Walingwaling Kinablangan, Baganga, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN120 | KING | NA | KINGFHLWXYZ | REGION XI (DAVAO REGION) | DAVAO DE ORO | PANTUKAN |  | Territory 7 | 7.1345 | 125.9543 | Napnapan, Pantukan, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN180 | KINUSK | NA | KINUSKFHKLWY TCFGAKINUSBANSALDDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | BANSALAN |  | Territory 7 | 6.851 | 125.1626 | Kinuskusan Road Bansalan_Poblacion Dos, Bansalan, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2438 | KM7MPANGIDVODDS | NA | KM7MPANGIDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.076 | 125.5676 | Matina Pangi Rd, Talomo, Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2472 | KM8MPANGIDVODDS | NA | KM8MATINAPADAVAODDSFHKLPWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0793 | 125.5601 | Km 8 Matina Pangi Rd, Purok 5-A Matina Pangi, Talomo District, Davao City, 8000 Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1769 | KNAMAYANDVO | NA | KNAMAYANDVOFHLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5004 | 125.6743 | Kinamayan, Santo Tomas, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1470 | KUKUNDVO | NA | SEDAHTLDAVAODDSIDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0918 | 125.6108 | J.P.Laurel Ave., Barangay 20B (Pob)., West Bajada, Davao City Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN121 | LAAK | NA | LAAKHL | REGION XI (DAVAO REGION) | DAVAO DE ORO | LAAK |  | Territory 7 | 7.8162 | 125.7878 | P6 Laac (Pob.), Laak (San Vicente), Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN182 | LACARONMALITADVOC | NA | LACARONMALITADVOCFLWYFLWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.4515 | 125.5721 | Lacaron, Malita, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1309 | LACCAL | DVO_091_GPONA_01 | LACCALFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2091 | 125.4422 | Lacson, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN138 | LADIA | TGM_010_GPONA_01 | LADIAFHKLWYF TCFGAP6MADAUMTAGUMDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.3831 | 125.8068 | Ladia St. Purok 6 Madaum, City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN220 | LAFILI | NA | LAFILIFHKLWXY TCFGALAFILIPINATAGUMDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4743 | 125.8072 | Castrence St. La Filipina, City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1354 | LAMBAJONDVOR | NA | LAMBAJONBAGANGDVORFHKLWDY LAMBAJONDVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BAGANGA |  | Territory 7 | 7.6101 | 126.5692 | Lambajon, Baganga, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1651 | LANSOVISVIL | NA | LANSOVISVILFHKLWXY LANVISVILTAGUMDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4235 | 125.7902 | Tagum CityLakans Place (indoor/outdoor of full outdoor), Apokon, City Of Tagum, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2373 | LANUROHAGONDDS | NA | LANUROHAGONDDSFLY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | HAGONOY |  | Territory 7 | 6.7286 | 125.273 | Brgy. Lanuro, Hagonoy, Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN896 | LAPANDAY AGRI REPEATER | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | NEW CORELLA |  | Territory 7 | 7.677 | 125.829 | La Panday Agri, Macgum, New Corella, Davao Del Norte | TAGUM FOC | GT | [6 empty] | #N/A
MIN1308 | LASANG | NA | ALEJANDRANVDAVAODDSFLWY LASANGFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2652 | 125.6636 | Alejandra Navarro (Lasang), Davao City, Davao del Sur | JUNA | FTAP | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1452 | LAUREL/SMLANANG1DAVAODDSID/SMLANANG2DAVAODDSID | NA | SMLANANG1DAVAODDSFDFWXYKLWXY SMLANANG1DAVAODDSFDFWXYKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1004 | 125.6324 | J.P. Laurel Avenue, SM Lanang, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1684 | LICANANCROS | DVO_092_GPONA_01 | LICANACROSDAVAODDSFLWY LICANANCROSFHKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2601 | 125.6496 | Purok Virgo, Licanan, Brgy. Lasang, San Isidro (Licanan), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN123 | LINOAN | NA | LINOANFWFLWY TCFGALINOANMONTEVDDOFLWYSF | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONTEVISTA |  | Territory 7 | 7.6643 | 125.9766 | Linoan, Montevista, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1659 | LUBOGANDVO | DVO_095_GPONA_01 | STIOLUBOGANDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0332 | 125.5002 | Crossing Bayabas, Davao City Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1140 | LUNA | DVO_033_GPONA_01 | JLUNA29CDAVAODDSDFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0725 | 125.616 | Divine Dorm Juan Luna St. Leon Garcia, Sr., Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN699 | LUPON | LPN_001_GPONA_01 | LUPADDNFHVX POBLACION2LUPONDVORRFHX | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | LUPON |  | Territory 7 | 6.9033 | 126.0175 | Lupon_Poblacion, Lupon, Davao Oriental | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1054 | MAA | DVO_028_GPONA_01, DVO_028_GPONA_02 | JIREHLNDMAADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0847 | 125.5918 | Unit 17, Jireh Land , Maa Riverside Maa, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1959 | MAADAVAODDS | NA | MAADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0728 | 125.5817 | BrgyMaa_DavaoCity_DavaodelSur, Maa, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1263 | MABCV2 | MAI_001_GPONA_01 | MABCV2FHLWXY TCFGAANITAPMABINIDDOFHLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MABINI |  | Territory 7 | 7.3117 | 125.8547 | Purok Mauswagan Anitapan, Mabini (Dona Alicia), Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN124 | MABICV | NA | MABICVHKLXYZ TCFGAPINDASMABINIDDOHKLXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MABINI |  | Territory 7 | 7.2844 | 125.8536 | Pindasan, Mabini (Dona Alicia), Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN221 | MACANG | NA | MACANGFHLWY TCFGAMACANGLUPONDVORFHLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | LUPON |  | Territory 7 | 6.8953 | 126.0751 | Purok Mangga Macangao, Lupon, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN667 | MACO | MCO_001_GPONA_01 | MACOFHX | REGION XI (DAVAO REGION) | DAVAO DE ORO | MACO |  | Territory 7 | 7.3707 | 125.86 | Maco Poblacion, Maco, Compostela Valley | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN226 | MADANG | NA | MADANGFHKLVWY TCFGACNTRALPOBMATIDVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9606 | 126.2119 | Mati Municipal Hall, Golden Valley Central (Pob.), Mati, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN230 | MADAS | NA | MADASFLWYFLVWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.8698 | 126.3274 | Purok Madasigon, Bobon, Mati, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN222 | MADAUM | TGM_012_GPONA_01 | MADAUMFHKLWXY TCFGAISIDROTAGUMDDNFHKLWYDF | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.3987 | 125.7756 | Madaum, City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN223 | MAGCAR | NA | MAGCARFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3992 | 125.6373 | Purok 4 Magsaysay, Carmen, Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN152 | MAGDUM | TGM_017_GPONA_01 | MAGDUMFHKLWXY TCFGAMAGDUMTAGUMDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4743 | 125.843 | Magdum, City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2671 | MAGDVOTEMP | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0648 | 125.6074 | City Hall Drive,cor., 152 San Pedro St., Poblacion District, DavaoCity_Barangay 9A (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN183 | MAGSY | NA | MAGSYFHLWY TCFGAPOBMAGSAYDDSFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MAGSAYSAY |  | Territory 7 | 6.7543 | 125.1519 | Purok 2 Magsaysay_Poblacion, Magsaysay, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN686 | MAGTUO | DVO_055_GPONA_01, DVO_055_GPONA_02 | LWRDPMAGTUODAVAODDSFKLNPVW TCFGAMAGTUODAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1062 | 125.5819 | Lower Dampa, Magtuod, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2791 | MAGUGPOEASTTAGUMDDN | NA | MAGUGPOEASTAGUMDDNFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4488 | 125.8191 | Magugpo East, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1721 | MAGUGPOTAGUM | TGM_001_GPONA_01 | MAGUGPOSOUTAGUMDDNFHKLDWYX | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4507 | 125.8015 | Mankilam, City of Tagum, Davao del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1763 | MAGUGPWSTDVO | TGM_004_GPONA_01 | MAGUGPOWESTAGUMDDNFHKLWY MAGUGPWSTDVOFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4623 | 125.8028 | Magugpo West, City Of Tagum, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN142 | MAGUPO | TGM_011_GPONA_01, TGM_011_GPONA_02 | MAGUPOFKLWXY TCFGAMAGUPOTAGUMDDNFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4584 | 125.8213 | Senangote Village 2 Magugpo East, City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN161 | MALABO | NA | MALABOFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.3255 | 125.4632 | Malabog, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN842 | MALALA | NA | MALALAFHLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MALALAG |  | Territory 7 | 6.5209 | 125.368 | New Baclayon, Malalag, Davao del Sur | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN218 | MALATI | NA | MALATIFLVWXY TCFGAMALATIVPANABODDNFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3057 | 125.5592 | Purok 2 Malativas, Panabo, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN184 | POBMALITADVOC | NA | POBMALITADVOCF_DFHKLVDWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.411 | 125.6124 | Benwang Road Malita_Poblacion, Malita, Davao del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2433 | MAMAYVILDVODDS | DVO_036_GPONA_01 | MAMAYVILDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1097 | 125.6319 | Mamay Rd, Buhangin, Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN237 | HCROSSMANAYDVOR | NA | HCROSSMANAYDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MANAY |  | Territory 7 | 7.1265 | 126.5124 | Holy Cross, Manay, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN225 | POBMANAYDVOR | NA | POBMANAYDVORFHLDWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MANAY |  | Territory 7 | 7.2107 | 126.5313 | Central (Pob.), Manay, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN185 | MANDUG | NA | TCFGAMANDUGDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.162 | 125.5812 | Mandug, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1774 | MANIKIDVO | NA | MANIKIDVOFHLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG |  | Territory 7 | 7.5941 | 125.712 | Pagasa, Kapalong, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1226 | MANKLM | TGM_003_GPONA_01, TGM_003_GPONA_02 | MANKLMFKLVWXY TCFGAMANKILAMTAGUMDDNFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4608 | 125.7844 | Mankilam, City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN140 | MANPAN | NA | MANPANFHKLWXY TCFGAMANAYPANABODDNFLWFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3431 | 125.5803 | Manay, Panabo, Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN911 | MAPUTIDVO | NA | MAPUTIDVOFHKLWY TCFGAMAPUTISIDRODVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BANAYBANAY |  | Territory 7 | 7.0209 | 125.9853 | Sitio Mapagba, Brgy. Maputi, Banaybanay, Davao Oriental | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN126 | MARAGU | NA | MARAGUFHLWY TCFGAPOB01MARAGUDDOFHLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MARAGUSAN |  | Territory 7 | 7.3178 | 126.122 | P. Sambang Maragusan (Pob.), Maragusan (San Mariano), Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1292 | MARAGUSANRLY | NA | KATIPUNANMARAGUDDOFHLWY MARAGUSANRLYFHLFHWYB | REGION XI (DAVAO REGION) | DAVAO DE ORO | MARAGUSAN |  | Territory 7 | 7.4131 | 126.1459 | New Negros Katipunan, Maragusan (San Mariano), Compostela Valley | DIGOS | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN687 | MARCO | NA | MARCOPOLODAVAODDSIDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0723 | 125.6109 | Marco Polo Hotel, Roxas Ave. cor CM Recto St., DavaoCity_Barangay 34D (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN602 | MARILO | NA | MARILOFHKLWYR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2827 | 125.3059 | Santo Niño, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1 | MASCOW | NA | NA | REGION XI (DAVAO REGION) | DAVAO DE ORO | MACO |  | Territory 7 | 7.3867 | 126.0328 | Masara COW, Theresa Crew Mining Masara, Maco, Compostela Valley | DIGOS | GT | [6 empty] | #N/A
MIN688 | MATANA | NA | MATANAFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MATANAO |  | Territory 7 | 6.709 | 125.2172 | Matanao_Poblacion, Matanao, Davao del Sur | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN187 | MATCRO | DVO_019_GPONA_01 | SMVMATCROSDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0544 | 125.5742 | 10 San Miguel Village Matina Crossing, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN843 | MATI | NA | MATIFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9523 | 126.2254 | Capitol Hills Central (Pob.), Mati, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2008 | MATIAODAVOR | NA | MATIAODAVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9443 | 126.2392 | Matiao Highway, Brgy Dahican, Mati City Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN186 | MATIAP | NA | BONGUYMATAPDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0475 | 125.5666 | Bonguyan Compound Matina Aplaya, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1108 | MATINA | DVO_086_GPONA_01 | SHRMATCROSDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0678 | 125.5775 | Shrine Hills Matina Crossing, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN188 | MATTI | DIG_005_GPONA_01 | MATTIFHKLWY TCFGAMATTIDIGOSDDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7691 | 125.3113 | Matti, Digos, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN668 | MAWAB | NA | MAWABFHLWDY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MAWAB |  | Territory 7 | 7.5045 | 125.9332 | Mawab_Poblacion, Mawab, Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN603 | MAWABR | NA | MAWABRFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MAWAB |  | Territory 7 | 7.5154 | 125.8958 | Sitio Mahayahay Tuboran, Mawab, Compostela Valley | DIGOS | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN238 | MAYO | MTI_005_GPONA_01 | MAYOFKLWYFKLWY TCFGAMAYOMATIDVORFKLVWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 7.0067 | 126.334 | Mayo, Mati, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN604 | MBUCAN | DVO_074_GPONA_01 | 76ABUCANADAVAODDSFKLNPVW TCFGABUCANDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0517 | 125.6094 | 76A St. John, Bucana, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN175 | MENSNG | NA | MENSENGDAVAODDSIDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0642 | 125.6063 | Grand Menseng Hotel DavaoCity_Barangay 2A (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1046 | MERCU2 | NA | MERCU2FKLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1037 | 125.641 | Grand Regal Hotel(Mercure Hotel) J.P. Laurel Ave Pampanga, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN125 | MGNAGA | NA | MGNAGAFHLWXYF TCFGAMAGNAPANTUKDDOFHLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | PANTUKAN |  | Territory 7 | 7.169 | 125.8948 | Magnaga, Pantukan, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1427 | MHAYAG | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2229 | 125.6186 | Mahayag Bunawan (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN619 | MINTAL | DVO_083_GPONA_01 | MINTALDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0856 | 125.497 | Bago Oshiro, Tugbok District Mintal, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1752 | MINTALDVO | NA | PALMINTALDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0921 | 125.5055 | Doña AuroraPalm St., Mintal, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN617 | MINTL2 | DVO_052_GPONA_01 | CATALPEQDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0774 | 125.5149 | Km 12.5, Talomo Dist Catalunan Pequeño, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN208 | MLALAG | NA | MLALAGFHKWY TCFGAPOBLACIONMLALAGDDSFHKWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MALALAG |  | Territory 7 | 6.5976 | 125.4014 | Malalag_Poblacion, Malalag, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN669 | MONKAY | MNK_001_GPONA_01 | MONKAYFHKLVWXY POBMONKAYDDOFHKLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.8236 | 126.0512 | Bonifacio St. Monkayo_Poblacion, Monkayo, Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1056 | MONTEV | NA | MONTEV27CDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0753 | 125.6216 | rooftop Tanyu Bldg., Monteverde cor. Lizada St DavaoCity_Barangay 27C (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN605 | MRAHAN | NA | MRAHANFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.5212 | 125.2356 | 3rd District, Marahan Marilog, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN127 | MRMZCOM | NA | MRMZCOMFLVWXYDF TCFGAPOB02MARAGUDDOFLVWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MARAGUSAN |  | Territory 7 | 7.3167 | 126.137 | Maragusan (Pob.), Maragusan (San Mariano), Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1464 | MTI-701 | MTI_701_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.5445 | 126.1344 | Beside Philippine National Bank along Rizal Ext, Brgy. Madang, Mati | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1465 | MTI-702 | MTI_702_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9459 | 126.2292 | Outside SSS, National, Highway,Bgy. Matiao, Mati. | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1074 | MUDIAN | DVO_035_GPONA_01 | ILANGDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1648 | 125.6566 | Ilang, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN851 | MVISTA | MON_001_GPONA_01 | MVISTAFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONTEVISTA |  | Territory 7 | 7.7012 | 125.9867 | San Jose (Pob.), Montevista, Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN670 | NABUN | NBN_001_GPONA_01, NBN_001_GPONA_02 | NABUNFHKLWXY POBNABUNDDOFHKLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.6027 | 125.9667 | Osmeña Ave., Nabunturan_Poblacion, Nabunturan, Compostela Valley | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN227 | NANYO | CRN_003_GPONA_01 | NANYOFLVWXY TCFGATUBODCARMENDDNFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3723 | 125.6175 | Purok 5C Tubod, Carmen, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1059 | NCCC | NA | NCCCB27DAVAODDSIDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0746 | 125.6217 | NCCC, R.Magsaysay Ave DavaoCity_Barangay 27C (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1034 | NCCCPT | DVO_018_GPONA_01 | NCCCMTINADAVAODDSFDFWXYKL | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0591 | 125.5695 | 3rd NCCC Centerpoint Matina Crossing, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN228 | NCCCTA | TGM_006_GPONA_01, TGM_006_GPONA_02 | NCCCMAGUGPOTAGUMDDNFHKLWYFK NCCCTAHKLFKWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4518 | 125.8138 | NCCC Department Store National highway Magugpo Poblacion, City Of Tagum, Davao Del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN128 | NEWBAT | NA | NEWBATDFLWXY TCFGAP2POBNBATANDDOFFKLVWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | NEW BATAAN |  | Territory 7 | 7.5534 | 126.1398 | Purok II Cabinuangan (Pob.), New Bataan, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN141 | NEWCOR | NA | NEWCORFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | NEW CORELLA |  | Territory 7 | 7.5879 | 125.8211 | Purok 1 NewCorella_Poblacion, New Corella, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN924 | NEWSIBUNGA | NA | NEWSIBUNGAFHLWXY TCFGANEWSIBNABUNDDOFHLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.561 | 125.9286 | Purok 6, Brgy. New Sibonga, Nabunturan, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN229 | NEWVIS | PNB_001_GPONA_01, PNB_001_GPONA_02 | NEWVISFHKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2998 | 125.6708 | Cabaluna St Purok 5 New Visayas, Panabo, Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN143 | NMALIT | PNB_007_GPONA_01 | NMALITFHKLWXY TCFGANEWMALPANABODDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3378 | 125.6127 | Purok 2 New Malitbog, Panabo, Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN190 | OBALDE | DVO_025_GPONA_01 | UBALDEDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0938 | 125.6361 | 208 R. Castillo St. Ubalde, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1494 | OBRERO | NA | OBRERODAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0831 | 125.6156 | Corner Palma Gil & Cervantes St. Davao City Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN130 | OLAYCO | NA | TCFGAOLAYCONMONKAYDDOFLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.7877 | 126.0228 | Purok1 Olaycon, Monkayo, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2790 | P12SMGUELTAGUMDDN | NA | P12SMGUELTAGUMDDNFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4348 | 125.776 | Capitol Rd, Tagum, Davao del Norte, Philippines | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2431 | P2COMMBUHANDVO | NA | P2COMMUNDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1341 | 125.6321 | Communal, Buhangin, Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN689 | PADADA | PDA_001_GPONA_01 | PADADAFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | PADADA |  | Territory 7 | 6.6459 | 125.3451 | Southern Paligue, Padada, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1937 | Padada Relay | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MALALAG |  | Territory 7 | 6.521 | 125.3705 | Malabakid Hills, Malaag, Malalag (Pob.), Davao del Sur | DIGOS | GT | [6 empty] | #N/A
MIN899 | PAG-ASA FARMS REPEATER | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG |  | Territory 7 | 7.576 | 125.68 | Pagasa Farms Pagasa, Kapalong, Davao Del Norte | TAGUM FOC | GT | [6 empty] | #N/A
MIN219 | PAGSA | NA | PAGSAFHKLWXY TCFGAPAGSABANGTAGUMDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4803 | 125.751 | Purok Pagkakaisa Pagsabangan, City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN135 | PANAB2 | PNB_004_GPONA_01 | PANAB2FHKLWXY TCFGASTONINOCARMENDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3237 | 125.6894 | Purok 1C Santo Niño, Carmen, Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN856 | PANABO | PNB_005_GPONA_01, PANABO-LSA01-001-MIN856 | PANABOFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2903 | 125.6756 | Cagangohan, Panabo, Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN193 | PANAC3 | NA | TCFGADIVRDPANACDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1498 | 125.6584 | Km. 14, Diversion Rd. Panacan, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN690 | PANACA | DVO_069_GPONA_01 | PANACANDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1624 | 125.6476 | Malagamot Road, Panacan, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN194 | PANGI | NA | ULATALOMPOBDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0573 | 125.5488 | Talomo River, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN672 | PANTUK | PNT_001_GPONA_01 | PANTUKFHKLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | PANTUKAN |  | Territory 7 | 7.1282 | 125.8981 | Kingking (Pob.), Pantukan, Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2879 | PARDSEMBACDVODDS | NA | PARDSEMBACDVODDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.3486 | 125.5292 | Paradise Embak, Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2643 | PBATOPROPDVODDS | NA | PBATOPROPDVODDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.3722 | 125.4962 | Paquibato, Calinan District, Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN195 | PBUNAW | DVO_093_GPONA_01 | TCFGABUNAWANDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2383 | 125.642 | Villarosa St. Purok 2 Bunawan (Pob.), Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN144 | PEARLFARMDVO | NA | PEARLFARMDVOFHKLWXY PFARMADECORSAMALDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.0024 | 125.7259 | Pearl Farm Beach Adecor, Island Garden City Of Samal, Davao Del Norte | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1647 | PECMATINADAV | NA | PECMATCROSDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0603 | 125.582 | Matina Crossing, P15, 21 Acacia, Davao City Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN192 | PNACA2 | DVO_070_GPONA_01 | TCFGAHIWAYPANACDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1544 | 125.6568 | Nstional Highway Panacan, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1185 | PNB-701 | PNB_701_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3112 | 125.6767 | Opposite from ACES College, Tadeco Rd, Panabo, Davao del Norte, Philippines | JUNA | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1340 | PNB-702 | PNB_702_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3085 | 125.6847 | Panabo Wharf Rd & Quezon St, Panabo, Davao del Norte, Philippines | JUNA | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1195 | PNB-703 | PNB_703_HYB_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2982 | 125.6824 | Back of Poblacion Daycare Center Quezon st. corner Roxas st. Barangay New Pandan, Panabo City | JUNA | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1339 | PNB-704 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2966 | 125.6744 | Infront Panabo City National High School along Purok Everlasting st., Barangay Gredu, Panabo City | JUNA | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN159 | POBBAG | NA | POBBAGFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1997 | 125.4082 | P. Durian Ave. Baguio (Pob.), Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1955 | POBCOMPOSCVLY | NA | POBCOMPOSCVLYFHKLVWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.6753 | 126.0835 | BrgyPoblacion_Compostella_CompostellaValley, Aurora, Compostela, Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN196 | POHAS | NA | POHAS30CDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0762 | 125.6169 | 412 Narra St. DavaoCity_Barangay 30C (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1601 | PRK28SILADVO | DVO_076_GPONA_01 | SILAMAADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0916 | 125.5824 | Maa, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1783 | PRKMAITUMDVO | MTI_006_GPONA_01 | PRKMAITUMDVOFKLVWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.932 | 126.2574 | Dahican, Mati, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN197 | PUAN | NA | NVLBAGOGALDAVAODDSFKLNPVW TCFGABAGOGLDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.061 | 125.5215 | Nievel Road Bago Gallera, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1694 | PUR4EDENDVO | NA | PUR4EDENDVOFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0326 | 125.3985 | Davao CityToril (Pob.) Toril (Pob.), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN145 | RABE | NA | IPILVISVILTAGUMDDNFKLVWY RABEFKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4346 | 125.8057 | Purok Ipilipil Visayan Village, City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1597 | RADISSONDAV | NA | RADISSONDAVAODDSIDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.097 | 125.63 | J. P. Laurel Avenue Lanang, San Antonio, Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN912 | RBADAS | NA | RBADASFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9123 | 126.1723 | Brgy. Badas, Mati City Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN210 | POBBAGANGDVOR | BGN_001_GPONA_01 | POBBAGANGDVORFHW | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BAGANGA |  | Territory 7 | 7.5687 | 126.5609 | Central (Pob.), Baganga, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1681 | BANAOBAGANGDVOR | NA | BANAOBAGANGDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BAGANGA |  | Territory 7 | 7.7272 | 126.5312 | Brgy Banao, Baganga, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN122 | RLAAK | NA | RLAAKFLWXYZ | REGION XI (DAVAO REGION) | DAVAO DE ORO | LAAK |  | Territory 7 | 7.7897 | 125.8161 | Sitio San Isidro Banbanon, Laak (San Vicente), Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1231 | RLUPON | NA | CALAPAGLUPONDVORFHKLVWYFL | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | LUPON |  | Territory 7 | 7.1286 | 126.1945 | Calapagan, Lupon, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1793 | ROB1TAGUMDDN | NA | ROB1TAGUMDDNFWYZNFWYZ | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4276 | 125.7958 | 4F, Robinsons Place Tagum, Canocotan, City Of Tagum, Davao Del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1428 | ROBDVO | DVO_030_GPONA_01 | ROBCYBERDAVAODDSIDFWXY ROBDVOFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0997 | 125.6243 | Robinsons Cybergate Acacia, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1481 | ROBDVO_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0991 | 125.6242 | Davao City Water District (Bajada Branch) AtanAwe, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1603 | ROLLINGHDVO | DVO_080_GPONA_01 | ROLLING19BDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1 | 125.6053 | Davao CityBuhangin (Pob.), Buhangin (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN915 | ROYALM | NA | ROYALMANDAVAODDSIDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.069 | 125.6057 | Royal Mandaya Hotel, Palma Palma Gil St., DavaoCity_Barangay 34D (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN233 | SANTICARAGADVOR | NA | SANTICARAGADVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | CARAGA |  | Territory 7 | 7.2726 | 126.5742 | Purok Balete Santiago, Caraga, Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN146 | RVRMED | NA | RVRMDPOBPANABODDNIOFHKLWYH RVRMEDHFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3128 | 125.6854 | 7302 Panabo Rivera Medical Cntr Inc San Francisco (Pob.), Panabo, Davao Del Norte | JUNA | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN16 | SAMALM | NA | SAMALMFHKLWY TCPHTPENAPLATASAMALDDNFFHKLDWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.0767 | 125.7102 | Peñaplata (Pob.), Island Garden City Of Samal, Davao Del Norte | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1055 | SANDAW | DVO_023_GPONA_01 | SANDAWBUCANDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0557 | 125.5991 | Quimpo Blvd. Bucana, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2015 | Sandawa-1 MSAN | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0605 | 125.6019 | Pag asa St., SIR Elementary School, Davao City | JUNA | GT | [6 empty] | #N/A
MIN1611 | SANJOSEDIGOS | DIG_002_GPONA_01 | SANJOSEDIGOSDDSFHKLWY SANJOSEDIGOSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.735 | 125.357 | Purok Gemelina San Jose (Balutakay), Digos, Davao del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN611 | POBSMARIADVOC | NA | POBSMARIADVOCFHLWY TCFGAPOBS2MARIADVOCFHLWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | SANTA MARIA |  | Territory 7 | 6.5564 | 125.47 | Santa Maria_Poblacion, Santa Maria, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1582 | SANMIGDIGOS | DIG_007_GPONA_01 | GLUNASANMIGDIGOSDDSFHKLVWY SANMIGDIGOSFHKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7481 | 125.3394 | Luna Ext. San Miguel (Odaca), Digos, Davao del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1780 | SANMIGUELDVO | TGM_007_GPONA_01, TGM_007_GPONA_02 | P3DSANMIGTAGUMDDNFKLVWY SANMIGUELDVOFKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.442 | 125.789 | PRK. 30, DOMINGO COMPOUND, VILLA VERDE SUBD., BRGY. SAN MIGUEL, TAGUM CITY, DAVAO DEL NORTE | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1230 | SANPED | NA | SANPED2APOBDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0669 | 125.6046 | Melagros Bldg., Illustre St. DavaoCity_Barangay 2A (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN178 | SANTOS | NA | SANTOSFFC | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | JOSE ABAD SANTOS |  | Territory 7 | 5.9124 | 125.6417 | Sitio Agdao Caburan Small (Pob.), Jose Abad Santos, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN691 | SASA | DVO_005_GPONA_01, DVO_005_GPONA_02, SASADV-LSA06-001-MIN691 | BRPAMPASASADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1077 | 125.651 | Beach Side Resort, Barrio Pampanga, Sasa, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1489 | SASA_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.107 | 125.651 | Waterfront Insular Hotel, Lanang Acacia, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1078 | SASA2 | DVO_082_GPONA_01 | KM11SASADAVAODDSFKLNPVW TCFGASASADAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1342 | 125.6607 | Km. 11 Sasa, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2424 | SASA3DVODDS | DVO_032_GPONA_01, DVO_032_GPONA_02 | KM10SASADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1254 | 125.6604 | Km. 11, Barangay Sa-Sa, Buhangin District, Davao City, 8000 Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN181 | SASA5 | NA | KM9SASADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1145 | 125.6544 | Km. 9 Sasa, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1262 | SAWATA | NA | SAWATAFHWXYFH TCFGASAWATAISIDRODDNFHWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SAN ISIDRO |  | Territory 7 | 7.7524 | 125.7307 | Sawata, San Isidro, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN147 | SEMONG | NA | SEMONGFHWXY TCFGASEMONGKPALONDDNFHWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG |  | Territory 7 | 7.6352 | 125.6527 | Semong, Kapalong, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN148 | SFPANA | PNB_003_GPONA_01 | SFPANAFHKLWXY TCFGAQUEZONPANABODDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3263 | 125.6676 | Zone 6, National Hiway Quezon, Panabo, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN224 | SIBAJAYBOSTONDVOR | NA | SIBAJAYBOSTONDVORFHX | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BOSTON |  | Territory 7 | 7.8144 | 126.4129 | Sitio Manat Sibajay, Boston, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2372 | SINAWIMATANADDS | NA | SINAWIMATANADDSFHKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MATANAO |  | Territory 7 | 6.7547 | 125.2306 | Sinawilan, Matanao, Davao del Sur, Philippines | DIGOS | UNITY | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1699 | SIRAWANDVO | DVO_078_GPONA_01 | SIRAWANDVOFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 6.98 | 125.4792 | Purok 2, Sirawan, Toril, Davao City Sirawan, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1655 | SIRPHASE2DVO | NA | SIRPH2BUCANDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.062 | 125.5995 | Brgy SIR Sandawa, Davao City Acacia, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2457 | SITORILCATGRANDVO | DVO_031_GPONA_01 | CATALGRANDEDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0793 | 125.5601 | SITIO TORIL BRGY CATALUNAN GRANDE DAVAO CITY | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2484 | SMCAPOKONDDNZ | TGM_008_GPONA_01 | P5APOKONTAGUMDDNFKLVWY SMCAPOKONDDNXFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4252 | 125.8306 | Apokon Rd, Tagum, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN199 | SMCDS | NA | SMCDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.9309 | 125.4781 | Purok Mannga Larding Darong, Santa Cruz, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2553 | SMCLAFILITAGUMDDN | NA | SMCLAFILITAGUMDDNFHKWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4795 | 125.8042 | Tagum-New Corella Highway, La Filipina, Tagum City, 8100, Davao del Norte, Tagum, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2478 | SMCMARSCON | NA | SMCMARSCONFHLWXY TCPHTSMCMAGWASTOMASDDNFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5052 | 125.6235 | Santo Tomas - Carmen Rd, Santo Tomas, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2482 | SMCPOBSULOP | NA | SMCPOBSULOPFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SULOP |  | Territory 7 | 6.5956 | 125.3445 | Sulop, Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2397 | SMCSHILLSDAV | NA | SMCSHILLSDAVFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0814 | 125.5739 | Shrine Hills Rd, Talomo, Davao City, Davao del Sur, Philippines | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2479 | SMCTIBALOG | NA | SMCTIBALOGFHLWXY SMCTIBALSTOMASDDNFLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5436 | 125.6226 | Tibal-og, Santo Tomas, Davao del Norte, Philippines | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN692 | SMDVAO | NA | SMBUCANDAVAODDSIDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0511 | 125.5885 | SM Davao Mall Quimpo Boulevard, Matina Aplaya, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1800 | SMDVAOEXT | NA | SMANNEXDAVAODDS1LSFKFKDFWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0511 | 125.5885 | Ext Building SM Davao Mall Quimpo Boulevard, Matina Aplaya, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN149 | SMGUEL | TGM_009_GPONA_01 | SMGUELFHKLWXY TCFGASANMIGUELTAGUMDDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4431 | 125.7751 | Purok 6 San Miguel (Camp 4), City Of Tagum, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2000 | SNAGUSTINDDN | NA | SANAGUSTINSAMALDDNFHKLWY SNAGUSTINDDNFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.122 | 125.7081 | SanAgustin_SamalCity_DavaoDelNorte, Adecor, Island Garden City Of Samal, Davao Del Norte | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN232 | SANIGNAMANAYDVOR | NA | SANIGNAMANAYDVORFHLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MANAY |  | Territory 7 | 7.1167 | 126.4834 | San Ignacio, Manay, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1468 | SPAC REPEATER | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MATANAO |  | Territory 7 | 6.751 | 125.261 | SPAC Cabligan (Managa), Matanao, Davao del Sur | DIGOS | GT | [6 empty] | #N/A
MIN1500 | SPEDHOSPDAV | NA | SPEDHOSPDAVAODDSIDFWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0787 | 125.6148 | San Pedro Hospital, Guzman St., Brgy. Gov. Vicente Duterte, Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1429 | SPRVI | NA | SPRINGMAADAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0792 | 125.5834 | Compound 7, Brgy. Maa, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN861 | STACRU | SCD_001_GPONA_01 | STACRUFHKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.848 | 125.4087 | Sitio Luay Tagabuli, Santa Cruz, Davao del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1136 | STAMARIARLY | NA | STAMARIARLYFLWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | SANTA MARIA |  | Territory 7 | 6.5558 | 125.4537 | Caputian, Malalag, Davao del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2535 | STONINOBANSLNDDS | NA | STONINOBANSLNDDSFHLWY TCPHTSTNINOBANSALDDSFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | BANSALAN |  | Territory 7 | 6.8181 | 125.1766 | Bansalan, Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN693 | SULOP | NA | SULOPFHKWY TCFGAPOBLACIONSULOPDDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SULOP |  | Territory 7 | 6.6048 | 125.3433 | National Road, Purok9 Sulop_Poblacion, Sulop, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN200 | TACUL | NA | TACULFHWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MAGSAYSAY |  | Territory 7 | 6.8052 | 125.0878 | Tacul, Magsaysay, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1985 | TACUNANDAV | DVO_051_GPONA_01 | TACUNANDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1064 | 125.5098 | Matina Crossing, Talomo, Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1499 | TADECOPANABO | NA | TADECOPANABOFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3968 | 125.5801 | TADECO Centrale Brgy. A. O. Floirendo, CITY OF PANABO, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1273 | TAGUM FOC | TGUMAB-LSA01-001-MIN1273 | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4434 | 125.8037 | A. Bonifacio St. Magugpo Poblacion Tagum City Davao del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN677 | TAGUM2 | TGM_005_GPONA_01 | TAGUM2FHKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4449 | 125.8019 | Sison Subd., San Isidro, City Of Tagum, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN150 | TALAIN | NA | TALAINFHLWXY TCPHTSTNINOTALAINDDNFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TALAINGOD |  | Territory 7 | 7.6286 | 125.6221 | Santo Niño, Talaingod, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1084 | TALOM2 | DVO_027_GPONA_01 | TALOM2POBDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0507 | 125.541 | Lloueras Bldg., Mc Arthur Highway Talomo (Pob.), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN694 | TALOMO | DVO_060_GPONA_01 | TALOMOPOBDAVAODDSDFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0636 | 125.5559 | San Isidro (Licanan), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1646 | TALOMOPOBDAV | NA | SDRTALOMPOBDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0437 | 125.5422 | Salakot drive, Davao CityTalomo (Pob.), Acacia, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2449 | TALOMRIVERDVODDS | DVO_094_GPONA_01 | TALOMRIVERDVODDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1852 | 125.4704 | Campo Tres, Talomo Riverside, Calinan Dist., Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1578 | TAMACALINDAVAODDS | NA | TAMACALINDAVAODDSFWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1338 | 125.3808 | Garden of Eden Tamayong, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN234 | TAMISA | NA | TAMISAFHLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.8455 | 126.2959 | Tamisan, Mati, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1293 | TAMUGAN RELAY | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1997 | 125.4082 | Gumalang, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1698 | TAMUGANDVO | DVO_077_GPONA_01 | TAMUGANDVOFHKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2495 | 125.3907 | Lower Tamugan, Tamugan, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN235 | TARRAG | NA | TARRAGFHRFH TCFGACNTRALPOBTARRADVORFHFLW | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | TARRAGONA |  | Territory 7 | 7.0558 | 126.4449 | Central (Pob.), Tarragona, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1294 | TARRAGONARLY | NA | TARRAGONARLYFHWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | TARRAGONA |  | Territory 7 | 7.0665 | 126.466 | Jovellar, Tarragona, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN201 | TBUNG2 | NA | TCFGAP2TIBUNGDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1893 | 125.6443 | Purok II Tibungco, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1342 | TGM-701 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4452 | 125.8019 | Beside Globe Tower Sison St, Tagum City | TAGUM FOC | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1344 | TGM-702 | TGM_702_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4416 | 125.8056 | National Highway, Visayan Village Tagum City, 8100 Davao del Norte, Philippines | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1159 | TGM-703 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4361 | 125.8227 | Infront San Lorenzo Ruiz Academy, along Apokon Road, Tagum | TAGUM FOC | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1341 | TGM-704 | TGM_704_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4557 | 125.8159 | Infront Saint Mary College along National Highway, Tagum | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1284 | TGM-705 | TGM_705_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4502 | 125.8049 | Across Jollibee Pioneer St cor Suaybaguio St Tagum City | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1343 | TGM-706 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4571 | 125.7922 | Infront Aces Tagum College Near Union Elementary School, Tagum | TAGUM FOC | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN695 | TIBUNG | NA | ILANGTIBUNGDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1865 | 125.6479 | Barrio Ilang Tibungco, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1585 | TIBUNG_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.206 | 125.647 | Km. 20, Buhisan, Tibungco, Pan-Philippine Hwy, Bunawan, Dabaw, 8000 Lalawigan ng Davao del Sur, Philippines | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1956 | TIBUNGDVODDS | NA | P15TIBUNGDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2037 | 125.6459 | Km. 21 Buhisan, Bunawan, Davao City, 8000 Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1398 | TICULONMALITADVOC | NA | TCFGATICULONMALITADVOCFLWYFLWY TICULONMALITADVOCFLWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.3005 | 125.6027 | Ticulon, Malita, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1306 | LAPUANDMARCEDVOC | NA | LAPUANDMARCEDVOCFLWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.3127 | 125.6498 | Brgy. Bisang, Malita, Davao Occidental | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2011 | TIG02 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1384 | 125.5861 | Holy St., near cor Azalea St, Deca Homes Subdivision Ph2, Mandug, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN696 | TIGATO | DVO_024_GPONA_01, DVO_024_GPONA_02 | TIGATTODAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1157 | 125.6009 | Tigatto, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1943 | Tigatto-1 MSAN | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1384 | 125.5894 | Cattleya St., Deca Homes Subdivision Ph3, Mandug, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN2012 | Tigatto-3 MSAN | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1394 | 125.5862 | Jade Street, Deca Homes Subdivision Ph1, Mandug, Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN202 | TITOGO | DVO_081_GPONA_01 | TCFGAMALAMBADAVAODDSFKLVWY TITOGOFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2532 | 125.3529 | Malamba, Marilog District, Davao City, Davao del Sur, Philippines | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN676 | TOMAS | STM_001_GPONA_01 | TIBALOGPOBSTOMASDDNFLWYFHKLTOMADDFWYSFHKL | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5274 | 125.6214 | Along FD Road II, Tibalog (Pob.), Santo Tomas, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN203 | TORCRO | NA | TORCROFKLNPVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0157 | 125.4973 | Agton St. Toril (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN697 | TORIL | DVO_006_GPONA_01 | MCLEODDALIAODAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0211 | 125.5068 | Macleod St. Toril (Pob.), Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN204 | TORIL2 | NA | LAOLIZADADAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0076 | 125.4867 | Sitio Curvada Lizada, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN205 | TORRES | DVO_072_GPONA_01, DVO_072_GPONA_02 | TCFGA9ADAVAODDPSFKLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0759 | 125.604 | Torres St. DavaoCity_Barangay 9A (Pob.), Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1152 | TRESDE | DIG_008_GPONA_01, DIG_008_GPONA_02 | TRESDEFHKLFHK TRESDEMAYO01DIGOSDDSFHKLWYWY TRESDEWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7633 | 125.3362 | Villadares Compound Tres De Mayo, Digos, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN206 | TUBALANMALITADVOC | NA | TCFGATUBALANMALITADVOCFHLWYFLWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.4814 | 125.5716 | Tubalan, Malita, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN207 | TUGBOK | DVO_034_GPONA_01 | TCFGATUGBOKDAVAODDSFKLNPVW TUGBOKDAVAODDSFKLNPVW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1077 | 125.4867 | Tugbok (Pob.), Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1081 | UDACA | DIG_009_GPONA_01 | TCFGASANMIGUELDIGOSDDSFHKLWY UDACAFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7362 | 125.3448 | San Miguel (Odaca), Digos, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN698 | VICTOR | DVO_089_GPONA_01 | VICTOMALLDAVAODDSIDFHKWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0843 | 125.6101 | Victoria Plaza Mall J.P.Laurel Ave., DavaoCity_Barangay 20B (Pob.), Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1538 | VISVILTAGUM | TGM_002_GPONA_01, TGM_002_GPONA_02 | SAGVISVILTAGUMDDNFKLVWY VISVILTAGUMFKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4348 | 125.7989 | Purok Saging Visayan Village, City Of Tagum, Davao Del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1540 | ZONE1DIGOS | NA | ZONE1DIGOSDDSFHKLWY ZONE1DIGOSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7533 | 125.3649 | BrgyZone3(Pob)_Digos_DavaodelSur Zone 3 (Pob.), Digos, Davao del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1312 | GAISANO DIGOS REPEATER | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7553 | 125.3542 | Gaisano Digos City, Davao del Sur Aplaya, Digos, Davao del Sur | DIGOS | GT | [6 empty] | #N/A
MIN1376 | PLAZA LUISA REPEATER | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0602 | 125.5903 | Jacinto Extension, Barangay 20-B (Pob.), DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | [6 empty] | #N/A
MIN2359 | MANIKISIDRODVOR | NA | MANKLINGSNISDRODAVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | SAN ISIDRO |  | Territory 7 | 6.8791 | 126.0866 | Brgy. Manikling, San Isidro, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2269 | POBCENTRALMATIDVOR | MTI_002_GPONA_01 | POBCENTRALMATIDVORFHKLVWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9533 | 126.219 | Central (Pob.), CITY OF MATI (Capital), DAVAO ORIENTAL | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2784 | BGRHOMDAHIMATIDVOR | NA | BGRHOMDAHIMATIDVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.949 | 126.2638 | BGR EXEC Homes Dahican, Mati City, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2786 | SUDCNTRALMATIDVOR | NA | SUDCNTRALMATIDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9666 | 126.1974 | Sudlon, Brgy. Central, Mati, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2898 | ROXASDVO01AS | NA | ROXAS33DDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0694 | 125.6143 | Roxas Avenue, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2782 | ROCASAINZMATIDVOR | NA | ROCASAINZMATIDAVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9689 | 126.2257 | Rabat-Rocamora Sainz, Mati City, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2360 | BITAUGISIDRODVOR | NA | BITAUGISIDRODVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | SAN ISIDRO |  | Territory 7 | 6.7672 | 126.0816 | BrgyBitaogan_SAN_ISIDRO_DAVAO_ORIENTAL | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2802 | CECILIA2DVODDS02FWH | NA | CECILIA2DAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1298 | 125.6249 | Brgy Cabantian Priscilla_H2A-1 | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2899 | TORRESDVO01FW | NA | TORRES01DAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0795 | 125.608 | (A) Torres – E. Jacinto intersection , Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2536 | P4SDVOPANABODDN | NA | P4SDVOPANABODDNFHLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3307 | 125.6606 | Brgy Southern Davao, Panabo City, Davao del Norte | JUNA | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2787 | TAMBOSAINMATIDVOR | NA | TAMBOSAINZMATIDAVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9839 | 126.2316 | BrgySainz_MatiCity_DavaoOriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2781 | BIL2CNTRALMATIDVOR | NA | BIL2CNTRALMATIDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9548 | 126.1955 | Purok_lower_Bilawan_MatiCity_DavaoOriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2900 | TORRESDVO02FW | NA | TORRESDVO02EMFH | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0817 | 125.6107 | (B) Torres St. (fronting Yellow Fin) | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2807 | USEPOBREDVO01FWH | NA | USEPOBREDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0855 | 125.6143 | USEP Obrero_H2A-2 | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2804 | KM5LADIDVODDS01FWF/H | NA | KM5LADIDVODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1145 | 125.6135 | Buhangin-Cabantian Road_H2A-2 infront of Church | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2805 | KM6BUHADVODDS02FWH/F | NA | KM6BUHADVODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1092 | 125.6145 | Pan- Philippine Hwy Underpass | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2371 | SANTONIOCATEELDVOR | NA | SANTONIOCATEELDVORFKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | CATEEL |  | Territory 7 | 7.7354 | 126.4987 | San Antonio, CATEEL, DAVAO ORIENTAL, REGION XI (DAVAO REGION), MIN | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2039 | DPWHPNACDAVAODDSSPEM | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1497 | 125.6617 | DPWH, Km14, Panacan,, Panacan, DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2801 | BRGY19BDVODDSEM | NA | BRGY19BDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0986 | 125.6138 | Barangay 19-B (Pob.)_H2A-2 near Mcdo and Ladislawa subd. | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3083 | CMRECTODVODDS01FW / CMRECTODVODDS02FW | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0739 | 125.6125 | Roxas Avenue_H2A-1 beside Phoenix | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2070 | FELCRIS CENTRALE | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0597 | 125.6091 | Felcris Centrale, Quimpo Boulevard,, Bucana, DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1443 | DAVAO ORIENTAL PROVINCIAL HOSPITAL REPEATER | NA | NA | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9445 | 126.2429 | Davao Oriental Provincial Hospital, Matiao, CITY OF MATI (Capital), DAVAO ORIENTAL, REGION XI (DAVAO REGION), MIN | MATI | GT | [6 empty] | #N/A
MIN1873 | BRGY19BYNDAV | NA | CIRCUMCR19BDAVAODDSFKLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0903 | 125.6089 | CIRCUMFERENCIAL COR. BACACA ROAD, DAVAOCITY_BARANGAY 19-B (POB.), DAVAO CITY, DAVAO DEL SUR | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2009 | DVO_001 | DVO_001_GPONA_01, DVO_001_GPONA_02 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0912 | 125.6134 | Abreeza Ayala Business Park, J. P. Laurel Ave.,, Barangay 10-A (Pob.), DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1377 | MSDDN JUNA MIN832 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0602 | 125.5903 | MATINA CROSSING, DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2134 | DVOFINANCECTRDDSID | NA | FINANCECTRDAVAODDSIDFHWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.096 | 125.629 | DAKUDAO AVENUE CORNER MEGAWORLD AVENUE AGDAO DAVAO CITY, DAVAO | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2169 | P1DLUISADAVAODDSSPEM | NA | P1DLUISADAVAODDSSPEM_DXFWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0602 | 125.5903 | DUTERTE, DONA LUISA SUBD PH2, DAVAO CITY | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2466 | DIAMONDVILDAVAODDS | NA | DIAMONDVILDAVAODDSFKLMVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1096 | 125.6372 | DIAMOND VILLAGE, BRGY. ANGLIONGTO, DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2493 | DAHICA_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9678 | 126.261 | Don Martin Marundan, Mati, Davao Oriental, Philippines | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2499 | LUNA_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0738 | 125.6185 | DSWD Region XI Head Office, Ramon Magsaysay Ave., cor. Suazo Street,, Acacia, DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2518 | SNOCDAV2PC | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0594 | 125.5509 | SNOC POP OFFICE, ULAS, DAVAO CITY, DAVAO CITY | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2532 | AVIDA | DVO_009_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.07 | 125.6113 | Brgy. 34 D Poblacion Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2636 | NCCCBUHANDAVAODDSLS | NA | NCCCBUHANDAVAODDSLSFWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1104 | 125.6121 | BUHANGIN, DAVAO CITY, DAVAO DEL SUR | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2742 | JUNADAVPC | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0603 | 125.59 | GLOBE TELECOM GT CORP. CENTER ORCHID ST., JUNA SUBD., MATINA (Co-located with MIN832-JUNA | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2753 | P4APOKONTAGUMDDN | NA | P4APOKONTAGUMDDNFVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4217 | 125.8249 | APOKON, TAGUM CITY, DAVAO DEL NORTE | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3205 | 10IDMAWABCVLYCOW | NA | NA | REGION XI (DAVAO REGION) | DAVAO DE ORO | MAWAB |  | Territory 7 | 7.5074 | 125.8879 | BRGY. TUBORAN, MAWAB, COMPOSTELA VALLEY | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MINCOW51 | Z3RIZALDIGOSDDSCOW | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7435 | 125.3554 | RIZAL AVE., BRGY. ZONE 3 (POB.), DIGOS CITY, DAVAO DEL SUR | DIGOS | GT | [6 empty] | #N/A
MIN2031 | Davao SLTE | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0556 | 125.5468 | McArthur Highway, Brgy Ulas, Davao City, Ula, DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2032 | Davao PFE | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0556 | 125.5468 | Brgy. Talomo, Davao City, Talomo (Pob.), DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2151 | CALINA_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1904 | 125.4287 | Malagos Garden Resort,, Calinan (Pob.), DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | [6 empty] | #N/A
MIN2071 | MATOSQ | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0644 | 125.597 | Matina Town Square, Gen. Douglas McArthur Hwy, Acacia, DAVAO CITY, DAVAO DEL SUR, REGION XI (DAVAO REGION), MIN | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2780 | CABAYBADMATIDVOR | MTI_003_GPONA_01 | CABAYBADMATIDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9474 | 126.1912 | Cabaybad, Brgy. Badas, Mati, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2622 | P1BPOBMACOCVLY | NA | P1BPOBMACOCVLYFLWXY | REGION XI (DAVAO REGION) | COMPOSTELA VALLEY | MACO | Mapaang | Territory 7 | 7.3576 | 125.8638 | Brgy. Langgam, Maco, Davao de Oro, Philippines | DVO-TAGUM | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2810 | MANKLMTAGUMDDN | NA | MANKLMTAGUMDDNFHKVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4647 | 125.7943 | Mankilam, Tagum, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3061 | POBGOVGENDVOR | NA | POBGOVGENDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | GOVERNOR GENEROSO |  | Territory 7 | 6.6569 | 126.0732 | Catada St., Tibanban, Sigaboy, Governor Generoso, Davao Oriental, Philippines | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2783 | MARSUBDAHIMATIDVOR | NA | MARSUBDAHIMATIDVORFHKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9368 | 126.2519 | Martinez Subd, Mati, Davao Oriental, Philippines | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2549 | CABLIG2MTANAODDS | NA | CABLIG2MTANAODDSFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MATANAO |  | Territory 7 | 6.7511 | 125.2666 | Manga, Matanao, Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2747 | ROSALBUSOMATIDVOR | NA | ROSALBUSOMATIDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 7.0078 | 126.2347 | Buso, Mati, Davao Oriental, Philippines | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2745 | TAGUIBOMATIDAVOR | NA | TAGUIBOMATIDAVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 7.0345 | 126.2072 | Taguibo, Mati, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3088 | PAGASA1MATIDVOR | NA | PAGASA1MATIDVORFKLVWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9493 | 126.2342 | Purok Matulungin, Mati City | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3116 | DURIANVISVILTAGUMDDN | NA | DURIANVISVILTAGUMDDNFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4239 | 125.8075 | Brgy. Durian, Visayan Village, Tagum City, Davao del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3117 | P3ACANOCOTAGUMDDNZ | NA | P3ACANOCOTAGUMDDNFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4211 | 125.7769 | Purok 3A, Brgy Canocotan, Tagum City, Davao del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2471 | COMMUNROADAVAODDS | NA | COMMUNROADAVAODDSFKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1457 | 125.6208 | Baluarte_BrgyCommunal_DavaoCity_DavaodelSur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2800 | DLPCBANKERDVO01EM | NA | DLPCBANK01DAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0664 | 125.6021 | Bankerohan Public Market-1 | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3079 | DLPCBANKERDVO02EM | NA | DLPCBANK02DAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0668 | 125.6022 | Bankerohan Public Market-2 | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2749 | COGONTAMISAMATIDVOR | NA | COGONTAMISAMATIDVORFWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.8587 | 126.3071 | Purok Cogon, Brgy Tamisan, Mati City, Davao Oriental | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2706 | SFRANCISCOPANABODDN | NA | SFRANCISCOPANABODDNFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3152 | 125.6761 | BrgySanFrancisco (Pob.)_PanaboCity | JUNA | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2462 | DECAINDANGDAVAODDS | NA | DECAINDANGDAVAODDSLXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1557 | 125.5993 | DecaHomesIndangan_DavaoCity_DavaoDelSur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3465 | DLPCIGNATALOMODVOEM | NA | DLPCTALOMDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0497 | 125.5508 | SmallCell_BrgyTalomo01_DavaoCity_DavaoDelSur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3467 | DLPCTALOMPOBDVOEM | NA | DLPCTAPOBDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0526 | 125.5479 | SmallCell_BrgyTalomo02_DavaoCity_DavaoDelSur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3263 | DLPCNHABUHANDVOEM | NA | DLPCNHABUDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1141 | 125.6228 | 2019CapSite_BrgyCabantian_DAVAOCITY_DAVAODELSUR_B | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3260 | DLPCSDAMBUHANDVOEM | NA | DLPCSDACBDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1124 | 125.6204 | SmallCell_2019CapSite_BrgyCabantian_DAVAOCITY_DAVAODELSUR_A | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3461 | DLPCGTECHCABANDVOEM | NA | DLPCGTECHCABANDVOEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1162 | 125.6251 | 2019CapSite_BrgyCabantian_DAVAOCITY_DAVAODELSUR_C | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3265 | DLPCHCCDBUHANDVOEM | NA | DLPCHCCDBDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1201 | 125.6228 | Baluarte_BrgyBuhangin(Pob.)_DavaoCity_DavaoDelSur_C | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3264 | DLPCMPARKBUHADVOEM | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1167 | 125.6148 | Baluarte_BrgyBuhangin(Pob.)_DavaoCity_DavaoDelSur_B | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3266 | DLPCJEHOBUHANDVOEM | NA | DLPCJEHOCDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1193 | 125.6209 | Baluarte_BrgyBuhangin(Pob.)_DavaoCity_DavaoDelSur_D | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3267 | DLPCKM5BUHADVOSEM | NA | DLPCKM5BDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.098 | 125.6148 | SmallCell_Baluarte_BrgyLadislawaBuhangin_DavaoCity_DavaodelSur_A | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3269 | DLPCPAGSABUHADVOEM | NA | DLPCPAGSADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.105 | 125.618 | SmallCell_2019CapSite_BrgyBuhangin(Pob.)_DAVAOCITY_DAVAODELSUR_C | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3463 | DLPCBELIALFONDVOEM | NA | DLPCALFONDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1067 | 125.6326 | SmallCell_BelisarioHeights02_Buhangin(Pob.)_DavaoCity_DavaoDelSur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3464 | DLPCBELENHIZONDVOEM | NA | DLPCHIZONDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.112 | 125.6478 | SmallCell_BrgyVicenteHizon01_DavaoCity_DavaodelSur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3471 | DLPCORQUI11BPODVOEM | NA | DLPCJP11BDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0764 | 125.6132 | SmallCell_Barangay11-B(Pob)_DavaoCity | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3462 | DLPCSPCGUZMAN14BDVOEM | NA | DLPCSP14BDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0782 | 125.615 | SmallCell_GuzmanSt_DavaoCity_A | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2855 | BFACIDAVAODDS | NA | BFACIDAVAODDSFKLMVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0665 | 125.6152 | Bonifacio St, Poblacion District, Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3084 | JACINTEXTDVODDS02FWH | NA | JACINTEXTDVODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0756 | 125.6112 | Roxas Avenue_H2A-3 near DVO601 | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3080 | PRISCILLA2DVODDSFWH | NA | PRISCILLA2DVODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1299 | 125.627 | Cabantian, Buhangin, Davao City, Davao del Sur, Philippines | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3086 | PICHONSTDVODDS01FW | NA | PICHONSTDVODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0651 | 125.6063 | Barangay 1-A (Pob.)_H2A Infront of Menseng Hotel | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3085 | BRGY19BDVO01FWFH | NA | DACUDA20BDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0817 | 125.6127 | Barangay 19-B (Pob.)_H2A-1 near Bajada underpass | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3082 | CBANGOYDVODDS02EM | NA | CBANGOYDAVAODDS02EMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0738 | 125.6125 | Roxas Avenue_H2A-2 near Rotonda | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3123 | TANGLAWDUJALIDDN | NA | TANGLAWDUJALIDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | BRAULIO E. DUJALI |  | Territory 7 | 7.4462 | 125.6523 | Brgy. Tanglaw, Dujali, Davao del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3613 | TIMOGVISVILTAGUMDDN | NA | TIMOGVISVILTAGUMDDNY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4206 | 125.8025 | Timog Ave, Tagum, Davao del Norte, Philippines | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3473 | DLPBANKEMAR5ADVOEM | NA | DLPBANKEMAR5ADVOEMFH | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.068 | 125.6007 | Bankerohan Market | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3495 | BOMBELTIGUMAN | NA | BOMBELTIGUMDIGOSDDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.6954 | 125.3502 | Tiguman, Digos City, Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3491 | C7APLAYA | NA | C7APLAYADIGOSDDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7385 | 125.3692 | Baragay of, P9QC+QG7, Digos City, 8006 Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3434 | P5COLORADO | NA | AZUPOBDOSBANSALDDSFLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | BANSALAN |  | Territory 7 | 6.787 | 125.2164 | Sto Niño Village, Azucena St., Bansalan, Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3490 | TALISASANJODIGOSDDS | NA | TALISASANJODIGOSDDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7282 | 125.353 | Purok Talisay, Brgy. San Jose, Digos City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2806 | CBANGOYDVODDS01FW / CBANGOYDVODDS02FW | NA | CBANGOYDAVAODDS01EMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0739 | 125.6124 | Roxas Avenue_H2A-1 | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3475 | DLPCBKTRADE27CDVOEM | NA | DLPCTR27CDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0758 | 125.6248 | Monteverde st | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3268 | DLPCLADISBUHANDVOEM | NA | DLPCLADIBDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0979 | 125.6059 | Ladislawa Clubhouse, Zinnia Avenue, Ladislawa Garden Village, Brgy. Buhangin Proper, Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2799 | ABREEZ20BDAVAODDSEM | NA | ABREEZ20BDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0923 | 125.6117 | Abreeza Ayala Mall Complex, JP Laurel Ave., Pob. Dist., Brgy 20-B, Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2803 | OPMARF10ADAVAODDSEM | NA | OPMARF10ADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0813 | 125.6023 | Ruby st, marfori, davao city | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3081 | TORQUOISTDVODDSFW | NA | TOMARF10ADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0821 | 125.6016 | Turquoise st., marfori, davao city | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3213 | WILFREAQUIDAVAODDSEM | NA | WILFREAQUIDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0977 | 125.6208 | Brgy. Buhangin Proper, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3237 | KAPTOMAMONDAVAODDSEM | NA | KAPTOMAMONDAVAODDSEMFH | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0801 | 125.6245 | Barangay Kap. Tomas Monteverde, Sr., Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3238 | MAGALLA2ADAVAODDSEM | NA | MAGALLA2ADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0662 | 125.6049 | DAVAO | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3239 | SHMCROS74ADAVAODDSEM | NA | SHMCROS74ADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0591 | 125.5673 | Barangay Matina Crossing, Davao City, Davao Del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3230 | MATIAPLAYADAVAODDSEM | NA | MATIAPLAYADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0407 | 125.5761 | Matina Aplaya Road, Brgy. 75-A Matina Aplaya, Shanghai II, Davao City | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3507 | SHQUIRIN4ADAVAODDSEM | NA | SHQUIRIN4ADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.075 | 125.6101 | Barangay 4-A (Pob.), Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3469 | DLPCNORTHCRESTDVOEM | NA | DLPCNCRESDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1207 | 125.6133 | Northcrest Subdivision, Cabantian Road, Buhangin, Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3270 | DLPCDDCMALVAR6ADVOEM | NA | DLPCDDC6ADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0717 | 125.6034 | Malvar st | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3147 | P6APOKONTAGUMDDN | NA | P6APOKONTAGUMDDNFWX | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4101 | 125.8389 | Purok 6, Villa Consuelo, Apokon, Tagum City, Davao del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2432 | FDMBOLTONSTDAVAODDS | NA | FDMBOLTONSTDAVAODDSNV | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0614 | 125.6075 | FDM Building, #59 Bolton Ext., Brgy. 1-A, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2437 | P26MAADAVAODDS | NA | P26MAADAVAODDSFKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0997 | 125.59 | Country side road, maa | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2454 | CATGRANDEDAVAODDS | NA | CATGRANDEDAVAODDSFKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0922 | 125.5247 | Catalunan Grande, Talomo, Davao City, Davao del Sur, Philippines | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2444 | PRK4COMMUNALDAVAODDS | NA | PRK4COMMUNALDAVAODDSFKLMWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1457 | 125.6215 | Purok 4 Communal, Buhangin, Davao City | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2785 | SANFRANDAHIMATIDVOR | NA | SANFRANDAHIMATIDVORFKLVWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9313 | 126.2768 | San Francisco, DAHICAN, Mati, Davao Oriental, Philippines | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2401 | UMMATINAMAADAVAODDS | NA | UMMATINAMAADAVAODDSFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0691 | 125.5954 | UM Matina Campus, Purok 4, Brgy. Ma-a, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2467 | RIVERSIDEDAVAODDS | NA | RIVERSIDEDAVAODDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1685 | 125.4726 | Brgy. Riverside Calinan District, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2464 | SMITPRK18BATDAVAODDS | NA | SMITPRK18BATDAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.027 | 125.4826 | SMIT Compound, Purok 18, Upper Piedad, Brgy. Bato, Toril District, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3257 | MESAOYNEWCORDDN | NA | MESAOYNEWCORDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | NEW CORELLA |  | Territory 7 | 7.5317 | 125.7934 | Brgy. Mesaoy, New Corella, Davao del Norte, Philippines | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3112 | SALVACIONSTOMASDDN | NA | SALVACIONSTOMASDDNFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.4859 | 125.7158 | Brgy Salvacion, Sto Tomas, Davao del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3115 | BUNGAVISVILTAGUMDDN | NA | BUNGAVISVILTAGUMDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4332 | 125.7874 | Purok Bunga, Visayan Village, Tagum, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3122 | TINGOLOMALITADVOC | NA | TINGOLOMALITADVOCFKLVWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.3624 | 125.6375 | Tingolo, Malita, Davao Occidental, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3126 | TIBALOG1STOMASDDN | NA | TIBALOG1STOMASDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5324 | 125.6271 | Feeder Rd 3, Santo Tomas, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3165 | CRUZMANKILTAGUMDDN | NA | CRUZMANKILTAGUMDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4556 | 125.7923 | Mankilam, Tagum, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2460 | ELBAJADADAVAODDS | NA | ELBAJADADAVAODDSFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0835 | 125.6125 | El Bajada Hotel, Brgy. 18-B, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3178 | CADENAVISTAGUMDDN | NA | CADENAVISTAGUMDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4321 | 125.8133 | Purok Dalia, Visayan Village, Tagum, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3312 | P4CANOCOTANTAGUMDDN | NA | P4CANOCOTANTAGUMDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.409 | 125.7784 | Purok 4, Brgy Canocotan, Tagum City, Davao del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3314 | BAGANCUAMBOTAGUMDDN | NA | BAGANCUAMBOTAGUMDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4955 | 125.786 | Cuambogan, Tagum, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3222 | SHELLPOBMONKAYOCVLY | NA | SHELLPOBMONKAYOCVLYFLVWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.829 | 126.0559 | Shell Gasoline Station, Poblacion Monkayo, Compostela Valley, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3240 | CERVPOBMONKAYOCVLY | NA | CERVPOBMONKAYOCVLYFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.817 | 126.0538 | Cervantes Rd, Monkayo, Compostela Valley, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3167 | STONINOCARMENDDN | CRN_004_GPONA_01 | STONINOCARMENDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3381 | 125.6955 | Santo Nino, Carmen, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3486 | P1SANVICENPANABODDN | NA | P1SANVICENPANABODDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3124 | 125.6986 | San Vicente, Panabo, Davao del Norte, Philippines | JUNA | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2429 | LOSAMIGOSDAVAODDS | NA | LOSAMIGDAVAODDSFKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1405 | 125.4804 | Los Amigos, Tugbok, Davao City, Davao del Sur, Philippines | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3321 | P2ALIMBAANTAGUMDDN | NA | P2LIMBAANNEWCORDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | NEW CORELLA |  | Territory 7 | 7.624 | 125.838 | Prk. 2A, Limba-an, New Corella, Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3494 | P5SINARAMATANODDS | NA | P5SINARAMATANAODDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MATANAO |  | Territory 7 | 6.7518 | 125.2851 | Sinaragan, Matanao, Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3303 | BENHILSPANACDAVAODDS | NA | BENHILSPANACDAVAODDSFHKLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1536 | 125.6507 | Benjamin Hills | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3591 | P3APOKONTAGUMDDN | NA | P3APOKONTAGUMDDNFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4291 | 125.8264 | Purok 3 Apokon Rd, Tagum, 8100 Davao del Norte, Philippines | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2451 | FARLANDUMOYDAVAODDS | NA | FARLANDUMOYDAVAODDSFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0381 | 125.5035 | Farlandville Subdivision, Brgy. Dumoy, Talomo District, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3704 | TRESDEMAYODIGOSDDS | NA | TCFGATRESDEDIGOSDDSFLVWY TRESDEMAYODIGOSDDSFKLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7551 | 125.3361 | Tres de Mayo, Digos City, Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3705 | ZONE3DIGOSDDS | NA | ZONE3DIGOSDDSFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7424 | 125.3619 | Zone III, Digos City, Davao del Sur, Philippines | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2883 | LAWIGANMATIDVOR | NA | LAWIGANMATIDVORFKLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.8238 | 126.2962 | Brgy_Lawigan_Mati_City_Davao_Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3214 | MALAGPANACDAVAODDSEM | NA | MALAGPANACDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1571 | 125.6572 | SC_ShellMalagamot_BrgyPanacan_DavaoCity | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3259 | P28MADAUMTAGUMDDN | NA | P28MADAUMTAGUMDDNFHKLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4146 | 125.7964 | Madaum, Tagum, Davao del Norte, Philippines | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3511 | DLPCQUEZ39DAVAODDSEM | NA | DLPCQUEZ39DAVAODDSEMFH | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.063 | 125.611 | SmallCell_Barangay39-D(Pob)_DavaoCity | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3703 | NEWPANDANPANABOAS | NA | NEWPANDANPANABOASFWFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2982 | 125.6798 | SmallCell_BrgyNewPandan(Pob)_Panabo_DDN | JUNA | GT | [6 empty] | #N/A
MIN3510 | DLPCJPAMPADAVAODDSEM | NA | DLPCJPAMPADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1133 | 125.6516 | SmallCell_BrgyVicenteHizon02_DavaoCity_DavaodelSur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3367 | MERCEDESUBDAVAODDS | NA | MERCEDESUBDAVAODDSFKLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1291 | 125.6595 | Mercedes Subd. Sasa Davao City | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3571 | P7POBCOMPOSCVLY | NA | P7POBCOMPOSCVLYFKLVWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.6698 | 126.0885 | Purok 7, Poblacion Compostela, Davao de Oro | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3702 | ISINGCARMENAS | NA | ISINGCARMENASFWFH | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3555 | 125.7044 | SmallCell_BrgyIsing(Pob)_Carmen_DDN | JUNA | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3688 | TCFGABINCUTAGUMDDN | NA | TCFGABINCUTAGUMDDNFHLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.3873 | 125.761 | Bincungan, Tagum, Davao del Norte, Philippines | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2885 | TCFGAGREDUPANABODDN | NA | TCFGAGREDUPANABODDNFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2941 | 125.6683 | Purok Maharlika, Brgy. Gredu Panabo | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3579 | SMCMAGDUMTAGUMDDN | NA | SMCMAGDUMTAGUMDDNFHLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4687 | 125.8359 | National Highway, Brgy Magdum, Tagum City, Davao del Norte | TAGUM FOC | UNITY | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3674 | TCFGAMANGALCARMENDDN | NA | TCFGAMANGALCARMENDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3601 | 125.665 | PUROK 6 BRGY.MANGALCAL, CARMEN,DAVAO DEL NORTE | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3679 | TCFGATABACARMENDDN | NA | TCFGATABACARMENDDNFHLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3501 | 125.7225 | BRGY. TABA, CARMEN, DAVAO DEL NORTE | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3689 | TCFGAMABINIDIGOSDDS | NA | TCFGAMABINIDIGOSDDSFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7402 | 125.3515 | MABINI EXT., ANINON DRIVE, DIGOS CITY, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3690 | TCFGAALEJALCARMENDDN | NA | TCFGAALEJALCARMENDDNFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3908 | 125.6465 | Purok 9A Brgy. Alejal, Carmen, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3693 | TCFGAAPLAYAHGONOYDDS | NA | TCFGAAPLAYAHGONOYDDSFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | HAGONOY |  | Territory 7 | 6.6813 | 125.372 | Purok 5, Aplaya, Hagonoy, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3754 | TCFGACEBLACARMENDDN | NA | TCFGACEBLACARMENDDNFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3428 | 125.6778 | Brgy. Cebulano, Carmen, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3760 | TCFGADATUAPANABODDN | NA | TCFGADATUAPANABODDNFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3106 | 125.6607 | Purok Mangga, Brgy. Datu Abdul Dadaia, Panabo City | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3797 | TCFGATUBANSTCRUZDDS | NA | TCFGATUBANSTCRUZDDSFLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.8202 | 125.3907 | BrgyTuban_SANTACRUZ_DDS | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3798 | TCFGAPOBSMARIADVOC | NA | TCFGAPOBSMARIADVOCFLVWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | SANTA MARIA |  | Territory 7 | 6.5411 | 125.4798 | Sitio Culibao,, Poblacion, SANTA MARIA, DAVAO OCCIDENTAL | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3660 | TCFGACOGONDIGOSDDS | NA | TCFGACOGONDIGOSDDSFHLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7545 | 125.3859 | Punta Biao, Cogon, Digos City, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3677 | TCFGAANIBONCARMENDDN | NA | TCFGAANIBONCARMENDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3977 | 125.7147 | BRGY. ANIBONGAN, CARMEN,DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3319 | PRK2ACACIADAVAODDS | NA | PRK2ACACIADAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1935 | 125.6062 | 2019CapSite_Acacia02_DAVAO CITY_DAVAO DEL SUR | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3676 | TCFGAPOB1BANSALDDS | NA | TCFGAPOB1BANSALDDSFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | BANSALAN |  | Territory 7 | 6.7794 | 125.2171 | Purok Liwanag, Poblacion Uno, Bansalan, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3795 | TCFGAKIAGOTDIGOSDDS | NA | TCFGAKIAGOTDIGOSDDSFHLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7819 | 125.363 | Coordinates 6.7819; 125.3632. BrgyKiagot_DIGOS | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3673 | TCFGALAPAZCARMENDDN | NA | TCFGALAPAZCARMENDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3177 | 125.7169 | BRGY. LAPAZ,CARMEN, DAVAO DEL NORTE | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3722 | MAGSAYSAYNABUNCVLY | NA | MAGSAYSAYNABUNCVLYFLVWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.6255 | 125.9729 | Purok 1, Brgy. Magsaysay, Nabunturan, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3723 | PANGUTOSNABUNCVLY | NA | PANGUTOSNABUNCVLYFLWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.604 | 125.9946 | Purok 1, Brgy. Pangutosan, Nabunturan, Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3796 | TCFGAMABUBANSALDDS | NA | TCFGAMABUBANSALDDSFLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | BANSALAN |  | Territory 7 | 6.7685 | 125.2258 | Brgy Mabuhay, Bansalan Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3675 | TCFGANEWVISSTOMASDDN | NA | TCFGANEWVISSTOMASDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.511 | 125.6074 | BRGY. NEW VISAYAS, STO. THOMAS, DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3691 | TCFGAMESOYNEWCORDDN | NA | TCFGAMESOYNEWCORDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | NEW CORELLA |  | Territory 7 | 7.5159 | 125.7934 | Purok 18 Mesaoy, New Corella, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3687 | TCFGAMONCADSAMALDDN | NA | TCFGAMONCADSAMALDDNFLWX | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.1297 | 125.6918 | Brgy. Kinawitnon, Villarica, Moncado, Igacos, Davao del Norte | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3286 | ALAMSANISIDTAGUMDDN | NA | ALAMSANISIDTAGUMDDNFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.3909 | 125.7924 | San Isidro, Tagum, Davao del Norte, Philippines | TAGUM FOC | FRONTIER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2746 | DALIATAGUMATIDVOR | NA | DALIATAGUMATIDVORFW | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 7.0149 | 126.2101 | Taguibo, CITY OF MATI (Capital), DAVAO ORIENTAL | MATI | PHILTOWER | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3457 | AZUPOB2BANSALANDDS | NA | AZUPOB2BANSALANDDSFHKLWXYY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7619 | 125.2953 | Brgy. Colorado, Digos City, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3298 | TCFGAP11CLNDAVAODDS | NA | TCFGAP11CLNDAVAODDSFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2026 | 125.4447 | Purok 11, Brgy Calinan, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3454 | TCFGAP5TBOKDAVAODDS | NA | TCFGAP5TBOKDAVAODDSFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1118 | 125.4815 | Purok 5, Brgy Tugbok, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3546 | MABINSANMIGDIGOSDDS | NA | MABINSANMIGDIGOSDDSFHKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7417 | 125.3386 | MABINI EXTENSION BRGY. SAN MIGUEL, DIGOS, DAVAO DEL SUR | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3701 | P8ISINGCARMENDDN | NA | P8ISINGCARMENDDNFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.35 | 125.704 | Brgy. Ising, Carmen, Davao del Norte | JUNA | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3726 | P16POBNABUNCVLY | NA | P16POBNABUNCVLYFLVWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.6014 | 125.9612 | Purok 16, Brgy. Poblacion, Nabunturan, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3727 | P14POBNABUNCVLY | NA | P14POBNABUNCVLYFLWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.6094 | 125.9679 | Purok 14, Brgy. Poblacion, Nabunturan, Compostela Valley | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3749 | TCFGABBONGSTOMASDDN | NA | TCFGABBONGSTOMASDDNFLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.4869 | 125.5945 | Brgy Bobongon, SANTO TOMAS, DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3778 | TCFGACORONSTCRUZDDS | NA | TCFGACORONSTCRUZDDSFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.8926 | 125.4526 | Coronon, SANTA CRUZ, DAVAO DEL SUR | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3765 | TCFGAGBUYAKPALONDDN | NA | TCFGAGBUYAKPALONDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG |  | Territory 7 | 7.61 | 125.6595 | Gabuyan, KAPALONG, DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3766 | TCFGASMPAOKPALONDDN | NA | TCFGASMPAOKPALONDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG |  | Territory 7 | 7.5863 | 125.6586 | Purok 5, Sampao, KAPALONG, DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3769 | TCFGASANJOSTOMASDDN | NA | TCFGASANJOSTOMASDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5426 | 125.6017 | San Jose, SANTO TOMAS, DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3692 | TCFGAPOBLAMLALAGDDS | NA | TCFGAPOBLAMLALAGDDSFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MALALAG |  | Territory 7 | 6.5862 | 125.4044 | Purok Acacia 1, Poblacion, Malalag, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3657 | TCFGAP1CAMUDSAMALDDN | NA | TCFGAP1CAMUDSAMALDDNFLWX | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.1749 | 125.697 | Purok 1, Brgy Camudmud, Sitio Basao, IGACOS, Davao del Norte | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3658 | TCFGACTAGMASAMALDDN | NA | TCFGACTAGMASAMALDDNFLW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.0758 | 125.6873 | Brgy. Catagman, District 2, IGACOS,Davao del Norte | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3678 | TCFGATALICODSAMALDDN | NA | TCFGATALICODSAMALDDNFLW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 6.9357 | 125.7148 | Purok Ilang-Ilang, Sta. Cruz, Kaputian District, Talicud Island, IGACOS | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3680 | TCFGAMRANDASAMALDDN | NA | TCFGAMRANDASAMALDDNFLW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.1489 | 125.6929 | Purok 5, Brgy. Tambo, Miranda,IGACOS, Davao del Norte | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3755 | TCFGAFLISMALITADVOC | NA | TCFGAFLISMALITADVOCFLVWXY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.4049 | 125.6015 | San Roque, POB, Malita, Davao Occidental | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3761 | TCFGAMUDIPANADVODDS | NA | TCFGAMUDIPANADVODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1711 | 125.6292 | Purok Bongbong Brgy.Mudiang, Panacan, Davao City | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3880 | TCFGAISIN3CARMENDDN | NA | TCFGAISIN3CARMENDDNFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3766 | 125.682 | Brgy Ising, Carmen,Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3768 | TCFGANAMYASTOMASDDN | NA | TCFGANAMYASTOMASDDNFLWX | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5228 | 125.6491 | BRGY. TIBALOG, STO. TOMAS, DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3900 | TCFGADAPNBAGANGDVOR | NA | TCFGADAPNBAGANGDVORFLVWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BAGANGA |  | Territory 7 | 7.6188 | 126.5615 | BLK. 4 LAMBAJON, BAGANGA DAVAO ORIENTAL | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3866 | TCFGAKATIPUPANBODDN | NA | TCFGAKATIPUPANBODDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2998 | 125.6386 | Purok 6, Little Panay, Panabo City Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3848 | TALOM3DAVAODDSEM | NA | TALOM3DAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0492 | 125.5451 | San Lorenzo Ruiz Church, Brgy Talomo Proper, Davao City, Davao Del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3336 | TCFGAMARAPADAVAODDS | NA | TCFGAMARAPADAVAODDNSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0191 | 125.4856 | Purok 9, Brgy. Marapangi 3, Toril, Davao City | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3455 | TCFGACATGRNDAVAODDS | NA | TCFGACATGRNDAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0887 | 125.5387 | Sitio Sta. Filomena, Brgy. Catalunan Grande, Davao City | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3962 | TCFGAVISVILTAGUMDDN | NA | TCFGAVISVILTAGUMDDNFLWX | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4294 | 125.7964 | VISAYAS VILLAGE, BESIDE ROBSON MALL,, Visayan Village, CITY OF TAGUM (Capital), DAVAO DEL NORTE, | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2450 | TCFGANVDUMODAVAODDS | NA | TCFGANVDUMODAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0276 | 125.5099 | Sto. Niño Village, Brgy Dumoy, Talomo District, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3597 | TCFGALINDANABUNCVLY | NA | TCFGALINDANABUNCVLYFLW | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.5887 | 125.9414 | Purok 1, Brgy. Linda, NABUNTURAN, COMPOSTELA VALLEY | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3598 | TCFGASANRONABUNCVLY | NA | TCFGASANRONABUNCVLYFLW | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.5927 | 125.9519 | Purok 3, Brgy. San Roque, NABUNTURAN, COMPOSTELA VALLEY | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3599 | P5LAFILITAGUMDDN | NA | P5LAFILITAGUMDDNFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4826 | 125.8143 | Purok 5, La Filipina, Tagum City, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2683 | TCFGAPR7ULADAVAODDS | NA | TCFGAPR7ULADAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1215 | 125.4957 | Mintal Road, Purok 7, Brgy Ula, Tugbok District, Davao City | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3644 | TCFGALIND1NABUNCVLY | NA | TCFGALIND1NABUNCVLYFLW | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.581 | 125.9351 | Purok 2, Brgy. Linda, Nabunturan, Davao de Oro | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3661 | TCFGABTUGBODAVAODDS | NA | TCFGABTUGBODAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1195 | 125.481 | Purok 13, Bongato Compound Quarry, Barangay Tugbok Proper, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3664 | TCFGASTAMANABUNCVLY | NA | TCFGASTAMANABUNCVLYFLWX | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.5879 | 125.9842 | Purok 3, Bgry. Santa Maria, NABUNTURAN, COMPOSTELA VALLEY | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2463 | TCFGACGRANDAVAODDS | NA | TCFGACGRANDAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0847 | 125.5519 | Purok 3, Sitio Toril, Catalunan Grande, Talomo District, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3806 | TCFGAP1TBOKDAVAODDS | NA | TCFGAP1TBOKDAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1024 | 125.4907 | Purok 1, Tugbok Pob., Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3870 | TCFGAFTUBKDAVAODDS | NA | TCFGAFTUBKDAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1085 | 125.4952 | Deca Homes Phase 3, Tugbok, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3808 | TCFGASINDANDAVAODDS | NA | TCFGASINDANDAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1611 | 125.5956 | Brgy. Indangan, Sitio Sta. Cruz Davao City | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3810 | SHMINTALDVODDSEM | NA | SHMINTALDVODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0897 | 125.505 | Brgy. Mintal, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3882 | TCFGAMAGNORTAGUMDDN | NA | TCFGAMAGNORTAGUMDDNFLW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4648 | 125.8151 | Purok C, Suaybaguio District, Brgy. Magugpo North, Tagum City, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3369 | TCFGABANKADAVAODDS | NA | TCFGABANKADAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.053 | 125.4845 | Purok 2, Brgy. Bankas Heights, Toril, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3368 | TCFGAP4ULADAVAODDS | NA | TCFGAP4ULADAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1313 | 125.4925 | Purok 4, Brgy. Ula, Tugbok District, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3894 | TCFGAHIJOMACOCVLY | NA | TCFGAHIJOMACOCVLYFLWXY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MACO |  | Territory 7 | 7.3958 | 125.8372 | Hijo, Maco, Compostela Valley, Hijo, MACO, COMPOSTELA VALLEY | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3897 | TCFGAP1BIAODAVAODDS | NA | TCFGAP1BIAODAVAODDSFLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1498 | 125.4987 | Purok 1, Brgy. Biao Guianga, Tugbok District, Davao City | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3901 | TCFGAMANATNABUNCVLY | NA | TCFGAMANATNABUNCVLYFLW | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN |  | Territory 7 | 7.5474 | 126.0251 | Purok 6, Brgy. Manat, Nabunturan Davao De Oro | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3904 | TCFGATIBNGOVGENDVOR | NA | TCFGATIBNGOVGENDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | GOVERNOR GENEROSO |  | Territory 7 | 6.6256 | 126.0803 | Purok 3 Dalia 1, Brgy. Tibanban | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3913 | TCFGAGUMALDAVAODDS | NA | TCFGAGUMALDAVAODDSFLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2171 | 125.4112 | Purok 4A, Upper Lacson, Brgy. Gumalang, Baguio District, Davao City | JUNA | FRONTIER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3313 | TCFGATACUNDAVAODDS | NA | TCFGATACUNDAVAODDSFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1134 | 125.5158 | Purok 1, Brgy. Tacunan, Davao City | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3923 | TCFGAMATIAOMATIDVOR | NA | TCFGAMATIAOMATIDVORFLVWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9563 | 126.2401 | Brgy. Mahayahay, Matiao, Mati City | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3987 | QBLDBRG22CDVODDSEM | NA | QBLDBRG22CDVODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0697 | 125.62 | Quezon Boulevard, Barangay 22-C (Pob.), Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3492 | STONINPAGSATAGUMDDN | NA | STONINPAGSATAGUMDDNFKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4728 | 125.7587 | Purok Sto. Nino, Brgy. Pagsabangan, Tagum City, Davao del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3739 | TCFGAORDPOPADADADDS | NA | TCFGAORDPOPADADADDSFLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | PADADA |  | Territory 7 | 6.6346 | 125.3482 | Purok 1 ,Maria mendez, Upper Limonzo, Padada, DDS | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3864 | TCFGAAPLAYADIGOSDDS | NA | APLAYADIGOSDDSFHKLWY TCFGAAPLAYADIGOSDDSFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7382 | 125.3789 | Cadilig St., Corner Obenza, Aplaya, Digos City | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3960 | TCFGAMANAYPANABODDN | NA | TCFGAMANAY2PANABODDNFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3555 | 125.6076 | Purok 14 Brgy. Manay, Panabo City Davao Del Norte | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3592 | TCFGAMAGUWETAGUMDDN | NA | TCFGAMAGUWETAGUMDDNFLW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4582 | 125.8086 | Purok Pag-Asa, Semininary Drive, Brgy. Magugpo West, Tagum City, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2678 | TCFGAP1ANGLDAVAODDS | NA | TCFGAP1ANGLDAVAODDSFLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1183 | 125.4643 | Purok 1-Molave, Brgy Angalan, Tugbok, District, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3355 | TCFGAWANGANDAVAODDS | NA | TCFGAWANGANDAVAODDSFLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1676 | 125.4384 | Purok 10, Sitio Curvada, Brgy Wangan, Calinan District, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3656 | TCFGAINDANDAVAODDS | NA | TCFGAINDANDAVAODDSFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1705 | 125.6088 | Purok Sto Niño, Barangay Indangan, Buhangin District, Davao City | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3884 | TCFGAMANKITAGUMDDN | NA | TCFGAMANKITAGUMDDNFLW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4682 | 125.7737 | Purok Magkindong, Brgy. Mankilam, Tagum City, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3905 | TCFGALIBERSTOMASDDN | NA | TCFGALIBERSTOMASDDNLY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.478 | 125.6586 | Purok 7A, La Libertad Sto. Tomas_DDN | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3447 | BLK16NHABUHADAVAODDS | NA | BLK16NHABUHADAVAODDSFKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.106 | 125.6166 | Lot 28, Block 16, Buhangin NHA-ICD, Brgy. Buhangin , Davao City , Davao Del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3373 | DPLEXRCASTILDAVAODDS | NA | DPLEXRCASTILDAVAODDSFKLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0982 | 125.6361 | Duplex Subdivision, Brgy. Rafael Castillo, Davao City , Davao Del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4162 | P2APOKONTAGUMDDN | NA | P2APOKONTAGUMDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4206 | 125.8178 | Purok 2, Brgy. Apokon, Tagum City, Davao del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1570 | TCFGALBINUGDAVAODDS | NA | TCFGALBINUGDAVAODDSFLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 6.9653 | 125.4772 | Sitio Lower Brgy Binugao, Toril, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3548 | KM8TIGATTODAVAODDS | NA | KM8TIGATTODAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1212 | 125.5995 | Purok 5 KM 8, Brgy Tigatto, Buhangin District, Davao City, Davao Del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3545 | TCFGAZONE3DIGOSDDS | NA | TCFGAZONE3DIGOSDDSFHKLWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7465 | 125.3465 | LAPU LAPU EXTENSION, BRGY. ZONE 3, DIGOS CITY, DAVAO DEL SUR | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3330 | MALADTAGAKNDAVAODDS | NA | MALADTAGAKNDAVAODDSFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1261 | 125.4282 | Purok Maladaya, Tagakpan, Tugbok District, Davao City | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3631 | P1LIMTORILDAVAODDS | NA | P1LIMTORILDAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0163 | 125.4969 | Purok 1 Lim St., Barangay Toril Proper, Davao City | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3725 | SAMPAGBINCUTAGUMDDN | NA | SAMPAGBINCUTAGUMDDNFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.3763 | 125.7535 | Purok Sampaguita, Brgy. Bincungan, Tagum, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3750 | TCFGAFLORIKPALONDDN | NA | TCFGAFLORIKPALONDDNFLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG |  | Territory 7 | 7.6795 | 125.6721 | Brgy Florida, Kapalong, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3748 | TCFGALUNGASTOMASDDN | NA | TCFGALUNGASTOMASDDNFLWY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5283 | 125.6944 | BRGY. LUNGAOG, STO. TOMAS, DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3694 | TCFGABAGUMMLALAGDDS | NA | TCFGABAGUMMLALAGDDSFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MALALAG |  | Territory 7 | 6.6005 | 125.3863 | BAGUMBAYAN, MALALAG, DAVAO DEL SUR | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3753 | TCFGACULAMALITADVOC | NA | TCFGACULAMALITADVOCFLVWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.3827 | 125.6211 | Brgy new argao, Malita, Davao Occidental | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3756 | TCFGAMANALITADVOC | NA | TCFGAMANALITADVOCFLVWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | MALITA |  | Territory 7 | 6.3418 | 125.6426 | Mana, Malita | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3763 | TCFGAP2TACUMIDVODDS | NA | TCFGAP2TACUMIDVODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1097 | 125.5244 | Purok 2 Brgy. Tacunan, Mintal, Davao City | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3903 | TCFGAPALIGHGONOYDDS | NA | TCFGAPALIGHGONOYDDSFLVWY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | HAGONOY |  | Territory 7 | 6.6594 | 125.3476 | Northern Paligue, Padada, Davao Del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3731 | TCLBSMHAYAGDAVAODDS | NA | TCLBSMHAYAGDAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2225 | 125.6178 | Purok 1, Barangay Mahayag, Bunawan District, Davao City, Davao Del Sur | JUNA | LDIC | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3837 | TCFGAKPATAGLAAKCVLY | NA | TCFGAKPATAGLAAKCVLYFLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | LAAK |  | Territory 7 | 7.7183 | 125.8025 | Prk. 11, Kapatagan, Laak | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3937 | MABINITAGUMDDNEM | NA | MABINITAGUMDDNEMFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4473 | 125.8051 | Mabini Street, Purok Sunflower, Brgy Poblacion, Tagum City, Davao Del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3978 | TCFGANGANCOMPOSCVLY | NA | TCFGANGANCOMPOSCVLYFLWY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.697 | 126.1316 | Brgy. Ngan, Compostella, Davao De Oro | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3963 | TCFGAPOBLAMAWABCVLY | NA | TCFGAPOBLAMAWABCVLYFW | REGION XI (DAVAO REGION) | DAVAO DE ORO | MAWAB |  | Territory 7 | 7.5197 | 125.9181 | Mawab Poblacion, Mawab, Compostela Valley | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3593 | TCFGADONSEPADADADDS | NA | TCFGADONSEPADADADDSFLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | PADADA |  | Territory 7 | 6.6431 | 125.3367 | PUROK 5 BRGY DON SERGIO OSMENA SR., PADADA DAVAO DEL SUR | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3717 | SAPHOAPANACDAVAODDS | NA | SAPHOAPANACDAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1618 | 125.6407 | Bunawan-Panacan, SAPAMA HOA, Brgy Panacan, Davao City, Davao Del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3317 | PRK14BUNAWDAVAODDS | NA | PRK14BUNAWDAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2365 | 125.6282 | Purok 14, Bunawan Crossing Mahayag Road, Bunawan, Davao City, Davao Del Sur | PRK14BUNAWDAVAODDS | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3671 | TCFGAPOBLUPONDVOR | NA | TCFGAPOBLUPONDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | LUPON |  | Territory 7 | 6.8954 | 126.008 | Palma Gil-Yabut St., Brgy. Poblacion, Lupon, Davao Oriental | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3647 | TCFGAMNDANDAVAODDS | NA | TCFGAMNDANDAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1769 | 125.5963 | Purok St. Joseph, Molave Homes, Brgy Indangan, Buhangin District, Davao City, Davao Del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2707 | TCFGAGANGADAVAODDS | NA | TCFGAGANGADAVAODDSFLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1616 | 125.4908 | Sitio Dimiao, Brgy Guianga, Tugbok District, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3649 | REDOBLEAPOKTAGUMDDN | NA | REDOBLEAPOKTAGUMDDNFLW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4267 | 125.8186 | PUROK 3B PHASE 1 REDOBLE COMPOUND BRGY APOKON TAGUM CITY | TAGUM FOC | UNITY | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3370 | TCFGALOSAMDAVAODDS | NA | TCFGALOSAMDAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1306 | 125.4794 | Lot 3967-F1, Davao Bukdnon National Highway, Tugbok, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3752 | P6BRACATANDVODDS | NA | P6BRACATANDVODDSFLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 6.972 | 125.4264 | Purok 6, Brgy. Baracatan, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3775 | TCFGAMCAMBOMATIDVOR | NA | TCFGAMCAMBOMATIDVORFLW | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.8338 | 126.1961 | Prk. Site, Macambol, Mati City | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3557 | TCFGAP9TBOKDAVAODDS | NA | TCFGAP9TBOKDAVAODDSFLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0965 | 125.4801 | Purok 9, Brgy. Tugbok Proper, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3899 | TCFGACALAPLUPONDVOR | NA | TCFGACALAPLUPONDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | LUPON |  | Territory 7 | 7.1152 | 126.1738 | Purok Nagkahiusa, Calapagan | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3902 | TCFGANUECOMAWABCVLY | NA | TCFGANUECOMAWABCVLYFW | REGION XI (DAVAO REGION) | DAVAO DE ORO | MAWAB |  | Territory 7 | 7.4997 | 125.9534 | Purok 4-A, Nuevo Iloco, Mawab, Davao de Oro | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3909 | TCFGASANJOSAMALDDN | NA | TCFGASANJOSAMALDDNFLW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.034 | 125.7237 | Purok 6, Brgy. San Jose, IGACOS, Davao del Norte | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3736 | P1INDANGANDAVAODDS | NA | P1INDANGANDAVAODDSFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1482 | 125.5998 | Purok 1, Indangan, Davao City, Davao del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2452 | TCLBSDALIAODAVAODDS | NA | TCLBSDALIAODAVAODDSFLVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0121 | 125.5013 | Don Juan Dela Cruz, Toril (Pob.), Davao City | JUNA | LDIC | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3996 | SANPEDDAVAODDS | NA | SANPEDDAVAODDSFLNPVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0678 | 125.6052 | San Pedro St. Brgy. Poblacion, Davao City | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4035 | TCISPOBMONKAYCVLY | NA | TCISPOBMONKAYCVLYFW | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.8222 | 126.0442 | Brgy,Poblacion,Monkayo,Davao de Oro | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4010 | TCISDELPIMABINICVLY | NA | TCISDELPIMABINICVLYFW | REGION XI (DAVAO REGION) | DAVAO DE ORO | MABINI |  | Territory 7 | 7.2997 | 125.8567 | Brgy. Del Pilar, Mabini, Davao De Oro | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4012 | TCISMAKUPMONKAYCVLY | NA | TCISMAKUPMONKAYCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.7441 | 126.0619 | P-1A Brgy.Makupa ,Monkayo davao de Oro | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4088 | TCISMARAPCOMPOSCVLY | NA | TCISMARAPCOMPOSCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.6867 | 126.0487 | Prk. 4, Brgy Maparat, Compostela valley, Davao de Oro | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4019 | TCISOSMENCOMPOSCVLY | NA | TCISOSMENCOMPOSCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.6676 | 126.1032 | Brgy. Osmena Compostela,DDO | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4120 | TCISTAMIACOMPOSCVLY | NA | TCISTAMIACOMPOSCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.7016 | 126.1042 | Brgy. Tamia Compostela,DDO | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4027 | TCISUNION2MONKAYCVLY | NA | TCISUNION2MONKAYCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.8001 | 126.0723 | P-Seniorita, Barangay,Union,Monkayo,Davao de Oro | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4018 | TCFGAMANGUIDAVAODDS | NA | TCFGAMANGUIDAVAODDSLY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1052 | 125.4131 | Brgy. Manuel Guianga, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4020 | TCFGARIVCALDAVAODDS | NA | TCFGARIVCALDAVAODDSLY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1571 | 125.4769 | Purok Puting Bato, Brgy. Riverside, Calinan, Davao City | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4025 | TCFGATALRIVDAVAODDS | NA | TCFGATALRIVDAVAODDSLY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.193 | 125.4799 | Purok 2, Talomo River, Calinan, Davao City | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4156 | TCFGARBALIODAVAODDS | NA | TCFGARBALIODAVAODDSFVWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0399 | 125.5108 | Blk 62 Lot 10 Rosalina Village 3 Baliok, Talomo Dist., D.C | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3328 | TCFGATBALIODAVAODDS | NA | TCFGATBALIODAVAODDSFVWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0503 | 125.4955 | Purok 2, Brgy. Tisa, Baliok, Toril, Davao City | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3179 | TCFGAP5SANJOSTOMASDDN | NA | TCFGAP5SANJOSTOMASDDNFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5328 | 125.6144 | Purok 5, Brgy. San Jose, Santo Tomas, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3581 | TCFGAVILILANGAYLUPONDVOR | NA | TCFGAVILILANGAYLUPONDVORFLWY | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | LUPON |  | Territory 7 | 6.8905 | 126.021 | Purok Villareiz, Brgy. Ilangay, LUPON, DAVAO ORIENTAL | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3582 | TCFGACENTRAMATIDVOR | NA | TCFGACENTRAMATIDVORFW | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.957 | 126.2064 | Purok Dona Rosa-1, Madang, Brgy. Cental, Mati, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2398 | TCAGMALAGOSDAVAODDS | NA | TCAGMALAGOSDAVAODDSF_DLDY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1902 | 125.4266 | Malagos Garden Resort, Purok 2B Malagos, Baguio District, Davao City, Davao Del Sur | JUNA | ALT GLOBAL | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3600 | TCFGAP10MANIKIKPALONDDN | NA | TCFGAP10MANIKIKPALONDDNFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG | MANIKI | Territory 7 | 7.5954 | 125.8143 | PUROK 10B NATIONAL HIGHWAY BRGY MANIKI KAPALONG DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3601 | TCFGAP13ISINGCARMENDDN | NA | TCFGAP13ISINGCARMENDDNFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3553 | 125.708 | PUROK 13, POBLACION CARMEN, DAVAO DEL NORTE | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3715 | TCLBSMAADAVAODDS | NA | TCLBSMAADAVAODDSFLWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0874 | 125.5814 | Purok 23, Lot 5, Plariza Compound, Barangay Ma-a, Davao City, Davao Del Sur | JUNA | LDIC | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3651 | TCFGAP3GUADALCARMENDDN | NA | TCFGAP3GUADALCARMENDDNFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3881 | 125.7427 | Purok 3, Guadalupe, Carmen, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3807 | KM5MATICROSDVODDS | NA | KM5MATICROSDVODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0639 | 125.5716 | Km.5 Guadalupe St., Matina Crossing, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3859 | P5MAGDUMTAGUMDDN | NA | P5MAGDUMTAGUMDDNFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4632 | 125.8279 | PUROK 5-A BRGY MAGDUM TAGUM CITY DAVAO DEL NORTE | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3942 | TCLBSCALINADAVAODDS | NA | TCLBSCALINADAVAODDSFW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1827 | 125.4633 | LOT 1 M 2 A DAVAO BUKIDNON NATIONAL HIGHWAY CALINAN DISTRICT DAVAO CITY | JUNA | LDIC | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3956 | TCLBSYTALOMDAVAODDS | NA | TCLBSYTALOMDAVAODDSFVWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0505 | 125.5702 | Poly Subdivision, 702,Timdalo St, corner Acacia, Davao City | JUNA | LDIC | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3939 | TCLBSMTUGBODAVAODDS | NA | TCLBSMTUGBODAVAODDSFVWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0922 | 125.4988 | LOT 149, DAVAO-BUKIDNON NAT’L HIGHWAY, BRGY. MINTAL, TUGBOK DISTRICT , DAVAO CITY, DAVAO DEL SUR | JUNA | LDIC | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3158 | DAMOSTWRDAVAODDSID | DVO_066_GPONA_01 | DAMOSTWRDAVAODDSIDFHKWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1037 | 125.634 | Damosa IT Park, J.P. Laurel Ave, Lanang, Davao City, Davao del Sur 8000 | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4033 | DASUCOGONDIGOSDDS | NA | DASUCOGONDIGOSDDSFX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7598 | 125.367 | Brgy. Cogon, Digos City, Davao del Sur | DIGOS | FRONTIER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3759 | P1BRACATANDVODDS | NA | P1BRACATAN02DVODDSLYF | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 7.004 | 125.3831 | Purok 1, Brgy. Baracatan, Toril Dist., Davao City | JUNA | PHILTOWER | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3157 | VISTAMALLDAVAODDSID | NA | VISTAMALLDAVAODDSIDFHWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0865 | 125.5079 | Camella Cerritos, Sto Nino Mintal, Davao City, Davao del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3638 | ALBANORESDVOPNP | NA | ALBANORESDVOPNPFFWXRFKL | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0949 | 125.6138 | BRGY. BUHANGIN (POB.),DAVAO CITY,DAVAO DEL SUR | JUNA | GT | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MINCOW54 | MAHAYAGDAVAODDSCOW | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.222 | 125.6187 | Mahayag Bunawan (Pob.), Davao City, Davao del Sur | JUNA | GT | [6 empty] | #N/A
MIN2957 | ANDRADAMATIDVORPC | NA | NA | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY |  | Territory 7 | 6.9528 | 126.217 | Andrada Building 2, Mati City Davao Oriental | MATI | GT | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2860 | DVO-749 | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0619 | 125.6078 | Centro Spatial, Boltom Ext., Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1952 | BUDIONGAVISTAGUMDDN | NA | BUDIONGAVISTAGUMDDNFHLWXY | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4407 | 125.8124 | Purok Budiongan, Brgy. Visayan Village, Tagum City, Davao del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4023 | TCISP1MIGCOMPOSCVLY | NA | TCISP1MIGCOMPOSCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.6383 | 126.1179 | Purok 1 Brgy. San Miguel Compostela,DDO | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4026 | TCISUNION1MONKAYCVLY | NA | TCISUNION1MONKAYCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.8083 | 126.0973 | P-Kawayan, Barangay,Union,Monkayo,Davao de Oro | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4154 | TCFGAECABANDAVAODDS | NA | TCFGAECABANDAVAODDSFVWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1287 | 125.6139 | Blk 3 Lot 4 Mark st., Phase 1 Emily homes Cabantian, Davao City | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3335 | TCFGACOGONDAVAODDS | NA | TCFGACOGONDAVAODDSFLW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 6.9992 | 125.4613 | PUROK 8, BRGY. COGON SIRAWAN, DAVAO CITY | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3716 | BUDBUDTBUNGDAVAODDS | NA | BUDBUDTBUNGDAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1908 | 125.6366 | Bunawan, Budbud Road, Brgy Tibungco, Davao City, Davao Del Sur | JUNA | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3452 | TCFGAMATCRODAVAODDS | NA | TCFGAMATCRODAVAODDSFLWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0621 | 125.5613 | Lot 18-A, Talomo NAFCO (Bangkal), Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2158 | Catigan - DU30 resthouse | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0064 | 125.3951 | Davao City | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2751 | ASUNSI_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ASUNCION |  | Territory 7 | 7.6028 | 125.7534 | 60IB Philippine Army Asuncion | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3734 | PANTUK_D | NA | NA | REGION XI (DAVAO REGION) | DAVAO DE ORO | PANTUKAN |  | Territory 7 | 7.1941 | 125.907 | 48IB, Pantukan, Davao de Oro | TAGUM FOC | GT | [6 empty] | #N/A
MIN3526 | 28th IB PA, Mawab | NA | NA | REGION XI (DAVAO REGION) | DAVAO DE ORO | MAWAB |  | Territory 7 | 7.4927 | 125.9387 | 28th IB PA, Mawab | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3625 | 66IB 10ID PA, Brgy. Cabinuangan, New Bataan, Davao de Oro | NA | NA | REGION XI (DAVAO REGION) | DAVAO DE ORO | NEW BATAAN |  | Territory 7 | 7.5437 | 126.1457 | 66IB 10ID, Brgy. Cabinuangan, New Bataan, Davao de Oro | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4157 | TCISKINGPANTUKCVLY | NA | TCISKINGPANTUKCVLYFW | REGION XI (DAVAO REGION) | DAVAO DE ORO | PANTUKAN |  | Territory 7 | 7.1397 | 125.8955 | Brgy. Kingking, Pantukan, Davao De Oro | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4227 | TCFGAPANDANPANABODDN | NA | TCFGAPANDANPANABODDNFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2974 | 125.6811 | Mabini St., New Pandan, Panabo City | JUNA | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4011 | TCISARORACOMPOSCVLY | NA | TCISARORACOMPOSCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.6581 | 126.053 | Purok 5, Brgy. Aurora Compostela,DDO | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4021 | TCISSANJOCOMPOSCVLY | NA | TCISSANJOCOMPOSCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.6473 | 126.0754 | Brgy. San Jose Compostela,DDO | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4193 | TCFGAP6BALUTHGONOYDDS | NA | TCFGAP6BALUTHGONOYDDSFW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7172 | 125.366 | Purok 6, Lower Balutakay, Hagonoy, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4116 | TCISMENZTIBSTOMASDDN | NA | TCISMENZTIBSTOMASDDNFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5177 | 125.6231 | Purok. 1 Menzi Brgy. Tibal-og, Sto. Tomas Davao del Norte | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4161 | TCISP2SALVAPANABODDN | NA | TCISP2SALVAPANABODDNFW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3182 | 125.686 | P-2,Brgy.Salvacion,Panabo City | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4013 | TCISGABICOMPOSCVLY | NA | TCISGABICOMPOSCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.61 | 126.0581 | Purok 6, Brgy. Gabi Compostela,DDO | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4024 | TCISSIOCOCOMPOSCVLY | NA | TCISSIOCOCOMPOSCVLYLY | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.6458 | 126.0318 | Purok 1 Brgy. Siocon Compostela,DDO | TAGUM FOC | ISON | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4222 | TCFGAP8TIBUNDAVAODDS | NA | TCFGAP8TIBUNDAVAODDSFLNVWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.197 | 125.6258 | Prk. 8 ,Communal, Brgy.Tibungco,DAVAO CITY,DAVAO DEL SUR | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3297 | DUSNAIDUMODAVAODDS | NA | DUSNAIDUMODAVAODDSFLNVWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0355 | 125.5266 | Purok Dusnai, Brgy Dumoy, Talomo District, Davao City, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3650 | TCFGAVERSANISISAMALDDN | NA | TCFGAVERSANISISAMALDDNFLW | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 6.9493 | 125.734 | Brgy. San Isidro, Kaputian District Island Garden City of Samal, Davao Del Norte | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3292 | EVISSA | DVO_063_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0752 | 125.571 | Evissa Subdivision, Matina Pangi, Diversion Road, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3291 | PRESTIGE | DVO_064_GPONA_01 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1413 | 125.6035 | Forestal Road, Cabantian, Buhangin, Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3004 | TCISCALINADAVAODDS | NA | TCISCALINADAVAODDSFW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1928 | 125.4526 | Brgy. Calinan, Davao City, Davao del Sur | JUNA | ISON | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3989 | ILLUBRG4ADVODDSEM | NA | ILLUBRG4ADVODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0702 | 125.6069 | Ilustre St., Barangay 4-A (Pob.), Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4219 | TCISZONE4STCRUZDDS | NA | TCISZONE4STCRUZDDSFW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.8356 | 125.4068 | BRGY. ZONE 4, SANTA CRUZ | DIGOS | ISON | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2507 | TCAGMAYADAWISDIGOSDDS | NA | TCAGMAYADAWISDIGOSDDSFW | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY |  | Territory 7 | 6.7326 | 125.3635 | P-Maya-maya, Brgy. Dawis, Digos City | DIGOS | ALT GLOBAL | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4225 | DLPCLTSMAADAVAODDSEM | NA | DLPCLTSMAADAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0865 | 125.5722 | Las Terrazas Subd., Brgy. Maa, ,Davao CITY,DAVAO DEL SUR | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3509 | BUHANPOBDAVAODDSEM | NA | BUHANPOBDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1139 | 125.615 | Brgy Buhangin, Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4611 | LEONGARDAVAODDSEM | NA | LEONGARDAVAODDSEMFHR | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0759 | 125.6262 | Fronting B & K Trading, Barangay 27-C (Pob.), Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3327 | PR49JPMIMAADAVAODDS | NA | PR49JPMIMAADAVAODDSFVWX | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0856 | 125.5868 | Purok 49, JPMI, Brgy Maa, Davao City, Davao Del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2600 | LANDCO-PDCP Corporate Center | LAPDCP-LSA01-001-MIN2600-A1 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0843 | 125.6117 | Landco Pdcp Corporate Center, J.P. Laurel Ave, Bajada, 19-B Poblacion, Davao City, 8000 Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4163 | TCFGACROSSBDAVAODDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0279 | 125.4944 | Purok 1, Birhen de los Remedios, Brgy. Crossing Bayabas, Davao City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3508 | QUIMBUCANDAVAODDSEM | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0505 | 125.5864 | Beside Mandaue Foam, Quimpo Boulevard, Brgy. Bucana, Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2439 | TCEDCGHS19BDAVAODDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0903 | 125.6056 | Gregorio Caneda Road, Garcia Heights Subdvision, Brgy. 19-B, Davao City, Davao del Sur | JUNA | EDOTCO | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3308 | TCEDCDJRMAADAVAODDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0968 | 125.5756 | LOT 3-C-3-B, DON JULIAN RODRIGUEZ AVENUE, BRGY. MA-A, TALOMO DISTRICT, DAVAO CITY | JUNA | EDOTCO | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4506 | TCAGCABANTIADAVAODDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1438 | 125.5985 | BrgyCabantian, DavaoCity | JUNA | ALT GLOBAL | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3114 | TULALIANSTOMASDDN | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.4589 | 125.5847 | Purok 13, District 4, Brgy. Tulalian, Sto. Tomas, Davao del Norte | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3359 | CALVILTBUNGDAVAODDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1947 | 125.6453 | Purok 4, CAL Village 2, Tibungco, Davao City, Davao Del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4008 | DLPCB3ADAVAODDSEM | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0681 | 125.6092 | Barangay 3-A (Pob.), Davao City, Davao Del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3991 | DLPCTIBALSTOMASDDNAS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.5245 | 125.6235 | FD Road1, Brgy. Tibal-og, Sto. Tomas, Davao del Norte | TAGUM FOC | GT | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4236 | TCPHTMALBATOSTCRUZDDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.7867 | 125.3823 | Purok Maligaya, Brgy. Bato, Santa Cruz, Davao Del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3606 | GAIBUHANDAVAODDSLS | DVO_099_GPONA_01 | GAIBUHANDAVAODDSLSFHWXY | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.11 | 125.6128 | Buhangin, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2857 | DVO-748 | DVO_748_HYB_01, DVO_748_HYB_02 | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0678 | 125.5914 | 8 SPATIAL DAVAO BLDG 2, Ma-a Rd, Talomo, Davao City, Davao del Sur | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2959 | PD Gaisano Mall Toril - Telecom Works | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0169 | 125.4935 | Gaisano Mall of Toril, McArthur Highway, Davao City, 8000 Davao Del Sur | JUNA | GT | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4032 | TCFGAMAGUPOBTAGUMDDN | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY |  | Territory 7 | 7.4443 | 125.8064 | Brgy. Magugpo Pob.,Tagum City, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4009 | TCCREKM8TIGAT02DAVAODDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1113 | 125.5894 | KM 8 Sitio Uyanguren, Tigatto, Davao City, Davao del Sur | JUNA | CREI | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4520 | TCPHTP4AWAOMONKAYDDO | NA | NA | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONKAYO |  | Territory 7 | 7.9458 | 126.0036 | Purok 4, Barangay Awao, Monkayo, Davao De Oro | TAGUM FOC | PHILTOWER | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4631 | TCISTORILPOBDAVAODDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0155 | 125.5011 | Brgy. Toril, Davao City, Davao del Sur | JUNA | ISON | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4653 | TCEDCSOMOGREDUPANABODDN | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3043 | 125.6774 | Brgy. New Visayas, City Of Panabo, Davao Del Norte | JUNA | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4237 | TCPHTZONE1STCRUZDDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 6.8696 | 125.4386 | Patulangon, Brgy Zone 1, Santa Cruz, Davao del Sur | DIGOS | PHILTOWER | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4686 | TCEDCQUEZONPOBKIBLAWDDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | KIBLAWAN |  | Territory 7 | 6.619 | 125.2557 | Brgy. Poblacion ,Kiblawan ,Davao Del Sur | DIGOS | EDOTCO | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4507 | TCIS8APOBDAVAODDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0728 | 125.6002 | 51-1 FR. Selga St., Brgy. 8-A (Pob.), Davao City | JUNA | ISON | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3800 | TCAICKINABLANBAGANGDVOR | NA | NA | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | BAGANGA |  | Territory 7 | 7.5884 | 126.5581 | Purok Malinawon, Brgy. Saoquegue, Baganga, Davao oriental | MATI | UNITY | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4646 | TCEDCMALAGAPANACADVODDS | NA | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1619 | 125.6317 | Brgy. Panacan, Davao City, Davao Del Sur | JUNA | EDOTCO | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN404 | ACHARO | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1084 | 125.1765 | Mabuhay Enterprises Bldg. , Mansanitas St. Dadiangas South, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | [6 empty] | #N/A
MINCOW32 | AFPCMPMALABALDSCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MALABANG |  | Territory 7 | 7.625 | 124.0689 | MALABANG AFP CAMP, LANAO SUR | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2350 | AFUSTBOLISCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | T'BOLI |  | Territory 7 | 6.1869 | 124.8337 | Afus, T'BOLI, SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN746 | ALABEL | NA | ALABELHVXZRHVX | REGION XII (SOCCSKSARGEN) | SARANGANI | ALABEL |  | Territory 7 | 6.1045 | 125.2805 | Sitio Maharlika Poblacion (Alabel), Alabel, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1244 | ALAESP | NA | ALAESPFHKLWXYTCFGADUKAYESPERSKUDFHKLWY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ESPERANZA |  | Territory 7 | 6.681 | 124.5584 | Dukay, Esperanza, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN372 | ALAMAD | NA | ALAMADFHKLWXY TCFGAKITACUBALMADANCOTFHKLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALAMADA |  | Territory 7 | 7.3867 | 124.5584 | Purok 13 Kitacubong (Pob.), Alamada, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2045 | ALAMADASKUDMGDN | NA | ALAMADASKUDMGDNDFLWYZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | ALAMADA |  | Territory 7 | 7.2479 | 124.3503 | Barangay Alamada, Sultan Kudarat, 9805 Maguindanao, Philippines | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN373 | ALEOSN | NA | ALEOSNFHWXY SANMATEOALEOSNNCOTFHLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALEOSAN |  | Territory 7 | 7.1526 | 124.5826 | San Mateo, Aleosan, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1710 | ALIPDATUPA | NA | ALIPDATUPAFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU PAGLAS |  | Territory 7 | 6.7456 | 124.8679 | Brgy. Madidis Datu Paglas Maguindanao | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN932 | ALSON | NA | ALSONYPFLWYZG | REGION XII (SOCCSKSARGEN) | SARANGANI | ALABEL |  | Territory 7 | 6.1055 | 125.2558 | Alcantara and Sons Poblacion (Alabel), Alabel, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN379 | AMAS | NA | AMASFKLVWXY TCFGAAMASKIDAPNCOTFKLVWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0659 | 124.9698 | Matalam Rd, corner Capitol Homes Amas, City Of Kidapawan, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN270 | AMPATU | NA | AMPATUFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | AMPATUAN |  | Territory 7 | 6.8327 | 124.4557 | Dicalongan (Pob.), Ampatuan, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3573 | ANASLAGAOGENSANSCOT | NA | ANASLAGAOGENSANSCOTFWX | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1359 | 125.1962 | Anas Subdivision, Brgy. Lagao (1st & 3rd), General Santos City, South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN418 | ANDRAD | NA | ANDRADFHKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1188 | 125.1273 | Lanton St. Andrada Subd., Apopong, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN374 | ANTIPA | NA | ANTIPAHZTH | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ANTIPAS |  | Territory 7 | 7.25 | 125.055 | Antipas_Poblacion, Antipas, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 13 | COTABATO 2 | KIDAPAWAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN648 | APOPON | NA | APOPONFLWY TCFGAAPOPONGENSANSCOTFKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1325 | 125.1427 | National Highway, Apopong, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1992 | APOPONGENSAN | NA | APOPONGENSANFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1265 | 125.1178 | Brgy Apopong, General Santos City, South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN375 | ARAKAN | NA | ARAKANFHKLWXY TCFGAGREENFARAKANNCOTFHKLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ARAKAN |  | Territory 7 | 7.3515 | 125.129 | Edsor St Poblacion (Greenfield), Arakan, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 13 | COTABATO 2 | KIDAPAWAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1069 | ARINGA | NA | ARINGAFHKLWY TCFGAPRKARINGAKBACANNCOTFHKLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN |  | Territory 7 | 7.1288 | 124.8322 | Purok Pagasa Aringay, Kabacan, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1239 | AROMAN | NA | AROMANFHKLWXY TCFGAP2AROMANCARMENNCOTFHKLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CARMEN |  | Territory 7 | 7.29 | 124.7873 | Purok 2, Aroman, Carmen, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3352 | ARTSNROQUEKNADALSCOT | NA | ARTSNROQUEKNADALSCOTFKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4432 | 124.9036 | CapSite_SanRoque01_KORONDAL | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3194 | AVANCENAKNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5404 | 124.8692 | Purok Gumamela, Brgy. Avancena, Koronadal City, South Cotabato | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2110 | AWANGTEMPO | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | AMPATUAN |  | Territory 7 | 7.1599 | 124.215 | 61D Awang Military Camp, Dicalongan Poblacion, Ampatuan, Maguindanao | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN283 | BAGGUA | CTT_005_GPONA_01 | BAGGUAFHKLXZ TCFGABAGGUACOTABMGDNFHKL | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | COTABATO CITY |  | Territory 7 | 7.2277 | 124.2354 | Bagua II, Cotabato City, Cotabato City | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN376 | BAGTAP | NA | BAGTAPFKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MLANG |  | Territory 7 | 6.8866 | 124.8961 | Bagontapay, M'Lang, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2569 | BAGUA2COTABMGDN | NA | BAGUA2COTABMGDNFKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2197 | 124.2339 | Bagua, COTABATO CITY, COTABATO CITY (Not a Province), REGION XII (SOCCSKSARGEN), MIN | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2570 | BAGUACOTABMGDN | NA | BAGUACOTABMGDNFKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2261 | 124.2435 | Bagua, COTABATO CITY, COTABATO CITY (Not a Province), REGION XII (SOCCSKSARGEN), MIN | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN377 | BAGUER | PGK_002_GPONA_01 | BAGUERFHLWXY TCFGAUPBAGUERPIGKAWNCOTFHLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIGKAWAYAN |  | Territory 7 | 7.2716 | 124.4656 | Upper Baguer (Baguer), Pigkawayan, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2542 | BAGUERLIBUNGNCOT | NA | BAGUERLIBUNGNCOTFHLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | LIBUNGAN |  | Territory 7 | 7.28 | 124.4688 | Baguer, Libungan, Cotabato, Philippines | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN651 | BAGUMB | NA | BAGUMBFHKLWXY POBBAGUMBSKUDFHKLWY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | BAGUMBAYAN |  | Territory 7 | 6.5302 | 124.5622 | Bagumbayan_Poblacion, Bagumbayan, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN259 | BALABA | NA | BALABAFHKLVWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | BALABAGAN | Poblacion (Balabagan) | Territory 7 | 7.5157 | 124.1235 | Lorenzo, Balabagan, Lanao Del Sur | COTABATO | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2277 | BALINDOGKIDAPNCOT | NA | BALINDOGKIDAPNCOTFLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0308 | 125.0634 | BrgyManongol_KidapawanCity_NORTHCOTABATO | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2336 | BALITONGLANSAR | NA | BALITONGLANSARFKLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.7545 | 125.2307 | Baliton, GLAN, SARANGANI, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1355 | BAMBAD | NA | BAMBADFHXZDFHX | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.5704 | 124.603 | Bambad, Isulan, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2562 | BANABDULSANGKIMGDN | NA | BANABDULSANGKIMGDNFLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ABDULLAH SANGKI |  | Territory 7 | 6.7971 | 124.5344 | Banaba, Datu Abdul Sangki Maguindanao | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN747 | BANATE | NA | TCFGABANATEMALUNGSARFWYNFH | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON |  | Territory 7 | 6.481 | 125.326 | National Hiway, Banate, Malungon, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN754 | BANGA | BNG_001_GPONA_01 | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.4204 | 124.7776 | Benitez (Pob.), Banga, South Cotabato | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN652 | BANISI | NA | BANISIFHLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | BANISILAN |  | Territory 7 | 7.5098 | 124.6943 | Banisilan Poblacion, Banisilan, Cotabato (North Cotabato) | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2276 | BANNAWAGKABACANNCOT | NA | BANNAWAGKABACANNCOTFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN |  | Territory 7 | 7.1544 | 124.8697 | Kabacan, Cotabato, Philippines | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN273 | BARIRA | NA | BARIRADDFHLWXYZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BARIRA |  | Territory 7 | 7.5093 | 124.3296 | Barira (Pob.), Barira, Maguindanao | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN274 | BARONG | NA | BARONGFLWXY TCFGABARURAOBARONGMGDNFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN SA BARONGIS |  | Territory 7 | 6.8776 | 124.6024 | Barurao, Sultan Sa Barongis (Lambayong), Maguindanao | COTABA | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2187 | BATULAWANPIKITCOT | NA | BATULAWANPIKITCOTFLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.0618 | 124.6727 | Fort Pikit, Pikit, Cotabato (North Cotabato) | MIDSAY | GT | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN755 | BATUTI | NA | BATUTIFLWYFHLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.2226 | 125.2474 | Tinagacan, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3150 | BFLORTACUROSKUD | NA | BFLORTACUROSKUDFW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6877 | 124.6713 | Brgy. Buenaflor,Tacurong City,Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2796 | BITUSPOBALABELSAR | NA | BITUSPOBALABELSARFL | REGION XII (SOCCSKSARGEN) | SARANGANI | ALABEL |  | Territory 7 | 6.0963 | 125.2861 | Poblacion (Alabel), ALABEL (Capital), SARANGANI, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3719 | BNISTAMBLRGENSANSCOT | NA | BNISTAMBLRGENSANSCOTFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0578 | 125.1428 | Purok Banisil, Brgy. Tambler, General Santos City, South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN406 | BOLOL | NA | BOLOLFHKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TUPI |  | Territory 7 | 6.3758 | 124.9632 | Purok PagAsa II Cebuano, Tupi, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN275 | BONGO | NA | BONGOFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PARANG |  | Territory 7 | 7.3404 | 124.032 | Bongo Island (Litayen), Parang, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3371 | BRARANGGALMGDN | NA | BRARANGGALMGDNFWX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.014 | 124.3248 | Brgy. Brar, Datu Angal Midtimbang, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2149 | Brgy Burias Sarangani | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.7147 | 125.2771 | Brgy Burias, Sarangani province | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2148 | Brgy Cablalan BSR ( repeater changeout) | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.7761 | 125.2191 | BRGY CABLALAN SARANGANI PROVINCE | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3588 | Brgy. Kapatan, Glan, Saranggani Province | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8971 | 125.2389 | Brgy. Kapatan, Glan, Saranggani Province | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3589 | Brgy. Lago, Glan, Saranggani Province | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8902 | 125.2304 | Brgy. Lago, Glan, Saranggani Province | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3590 | Brgy. Tango, Glan, Saranggani Province | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8712 | 125.2239 | Brgy. Tango, Glan, Saranggani Province | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN407 | BUAYAG | GSN_012_GPONA_01 | BUAYAGFKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1205 | 125.2268 | Buayan, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2202 | BUAYANDATUPIMGDN | NA | BUAYAN1DATUPIMGDNKLY BUAYAN2DATUPIMGDNFW BUAYANDATUPIMGDNFKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU PIANG |  | Territory 7 | 7.0318 | 124.4943 | Datu Piang, Maguindanao, Philippines | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN756 | BULA | GSN_002_GPONA_01 | BULAFHKLMVWY BULAWYFHKLMV | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1116 | 125.1895 | Bula Road Bula, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN419 | BULA2 | NA | BULA2FHKLWY TCFGAAMOARDGENSANSCOTFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1039 | 125.1991 | Amoa Road, Bula, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN276 | BULALO | NA | BULALOFHKLWXY TCFGABULALONULINGMGDNFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2332 | 124.2569 | Bulalo, Sultan Kudarat (Nuling), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN277 | BULDON | NA | BULDONFHKLWXY TCFGACALAANBULDONMGDNFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BULDON |  | Territory 7 | 7.5145 | 124.3714 | Calaan (Pob.), Buldon, Maguindanao | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN278 | BULUAN | NA | BULUANFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BULUAN |  | Territory 7 | 6.7126 | 124.7959 | Buluan_Poblacion, Buluan, Maguindanao | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2206 | BULUANMGDN | NA | BULUANMGDNFKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BULUAN |  | Territory 7 | 6.7265 | 124.7909 | Buluan, Maguindanao, Maguindanao, Philippines | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2243 | BUNGKONGLUTYNSKUD | NA | NA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LUTAYAN |  | Territory 7 | 6.5704 | 124.8826 | Brgy. Blingkong, lutayan, Sultan Kudarat (Nuling), Maguindanao | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1210 | BURIAS | NA | BURIASDFLWXDYZ | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.7235 | 125.2531 | Burias, Glan, Sarangani | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2299 | CABLINGBANGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.389 | 124.803 | Cabuling, Banga, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3193 | CARPENTERKNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | CITY OF KORONADAL (Capital) | Carpenter Hill | Territory 7 | 6.5246 | 124.8424 | BrgyCarpenterHill_KORONADAL_SOUTHCOTABATO | GENSAN | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3562 | CALOOCKNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5134 | 124.8392 | Caloocan, CITY OF KORONADAL (Capital), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2004 | CALSADASKUD | NA | CALSADASKUDFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2313 | 124.2447 | Bulalo, Nuling, Sultan Kudarat | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1527 | CALUMGENSAN | NA | CALUMGENSANFKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0828 | 125.1241 | BrgyLabangal_GenSan_Scotab Labangal, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3287 | CALUMGENSANSCOT | NA | CALUMGENSANSCOTFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.087 | 125.1492 | CapSite_BrgyCalumpang03_GeneralSantosCity | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2510 | CALUMPANGENSANSCOT | NA | CALUMPANGENSANSCOTFLX | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0787 | 125.1514 | CALUMPANG ROAD,, Calumpang, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2769 | Camp Pigcalagan, Sultan Kudarat, Maguindanao | NA | NA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | Maguindanao |  | Territory 7 | 7.2617 | 124.3558 | Camp Pigcalagan, Sultan Kudarat, Maguindanao | COTABA | GT | [6 empty] | #N/A |  | DECOM
MIN410 | CANERY | PLM_002_GPONA_01 | CANERYFHKLXZFH TCFGACANERYPOLOMOSCOTFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2423 | 125.093 | Dole_Phils, Cannery Site, Polomolok, South Cotabato | GENSAN | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3172 | CAPITONDINAIGMGDN | NA | CAPITONDINAIGMGDNFLX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.156 | 124.2298 | Capiton, DATU ODIN SINSUAT (DINAIG), MAGUINDANAO, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2767 | Cargill OILMILL ( repeater changeout) | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.025 | 125.1413 | Cargill Oilmill Tambler, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN380 | CARMNC | CMN_001_GPONA_01 | CARMNCFHLWXY TCFGAP9MOLAVECARMENNCOTFKLVWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CARMEN |  | Territory 7 | 7.2057 | 124.7945 | Molave st Purok 9 Carmen_Poblacion, Carmen, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3332 | CARPENTERKNADALSCOT | NA | TLUNGATU02ZAMBOAZDSFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.453 | 124.8777 | BrgyCarpenterHill_KORONADAL_SOUTHCOTABATO | KORONADAL FOC | GT | [6 empty] | #N/A |  | DECOM
MIN3555 | CENTERTOPKNADALSCOT | NA | CENTERTOPKNADALSCOTFLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4902 |  | CapSite_BrgyZulueta02_KoronadalCity | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1242 | CENTRA | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.3592 | 124.7564 | Centrala, Surallah, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2370 | CENTRASURALLSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.3242 | 124.7614 | Brgy. Centrala, Surallah, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2298 | CINCOBANGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.3933 | 124.7693 | Liwanay (Barrio 1), South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1455 | CLUMP2 | NA | CLUMP2FHKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0828 | 125.1435 | Purok Maunlad, Lanoy Subd., Brgy. Calumpang, General Santos City(Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN409 | CLUMPA | NA | CLUMPAFHKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0703 | 125.1461 | Purok Estrella Block Calumpang, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN751 | COGON | NA | COGONFHKLWY TCFGAMALALAGMALUNGSARFHKLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON |  | Territory 7 | 6.4156 | 125.3025 | Malalag Cogon, Malungon, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2295 | COLONGULOSURALLSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.3453 | 124.7221 | Colongulo, SURALLAH, SOUTH COTABATO | KORONADAL FOC | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN445 | COLUMB | NA | COLUMBFHKLWYZ | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | COLUMBIO |  | Territory 7 | 6.6849 | 124.9577 | Columbio_Poblacion, Columbio, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1574 | CONCEPKORDAL | NA | CONCEPKORDALFHLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.476 | 124.8864 | BrgyNewPangasinan_ Koronadal_ SCotab New Pangasinan (Bo. 4), Koronadal, South Cotabato | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3484 | CONELGENSANSCOT | NA | CONELGENSANSCOTFKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.2058 | 125.1859 | CapSite_BrgyConel01_GeneralSantosCity | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN818 | COTABA | NA | COTABAFHKLWX ICOTABDXAFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.22 | 124.244 | PC Hill Rosary Heights II, Cotabato City, Cotabato City | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN972 | COTABATO ICON | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | COTABATO CITY |  | Territory 7 | 7.2225 | 124.249 | 3/F F.A. Tan Bldg. SK Pendatun Street Rosary Heights IV, Cotabato City, Cotabato City | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1148 | CRORUB | NA | CRORUBFHLWXY TCFGACROSRUBTUPISCOTFHLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TUPI |  | Territory 7 | 6.3636 | 124.9197 | Crossing Rubber, Tupi, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2541 | CROSSINGNULINGMGDN | NA | CROSSINGNULINGMGDNFKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2788 | 124.3103 | Crossing Simuay, Nuling Maguindanao, Philippines | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1580 | CTYHTSGENSAN | NA | CTYHTSGENSANFHKLMWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1279 | 125.1722 | Paparon St. City Heights, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3497 | CTYHTSGENSANSCOTAS | NA | CTYHTS1GENSANSCOTASFKFK | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.119 | 125.1702 | City Heights, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN265 | CURAHA | NA | CURAHAFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MALABANG |  | Territory 7 | 7.5943 | 124.0696 | Corahab, Malabang, Lanao Del Sur | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2181 | DADOALAMADNCOT | NA | DADOALAMADNCOTFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALAMADA |  | Territory 7 | 7.5089 | 124.5222 | LOWER DADO, Alamada, Cotabato, Philippines | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2228 | DAGUMABAGUMBSKUD | NA | DAGUMABAGUMBSKUDFHKLVWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | SULTAN KUDARAT |  | Territory 7 | 6.5962 | 124.5441 | BrgyBiwang_BAGUMBAYAN_S, Alamada, Sultan Kudarat (Nuling), Maguindanao | TACURO | GT | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2303 | DAJAYSURALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.3734 | 124.7205 | Brgy. Dajay, surallah, south cotabato | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2221 | DALUMANGSKUD | NA | DALUMANGSKUDFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2648 | 124.2856 | Dalumangcob (Pob.), Sultan Kudarat (Nuling), Maguindanao | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN282 | DATUOD | NA | DATUODFHKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.0225 | 124.3151 | Dalican Poblacion, Datu Odin Sinsuat (Dinaig), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN280 | DATUPA | NA | DATUPAFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU PAGLAS |  | Territory 7 | 6.7387 | 124.8618 | Hilltop DatuPaglas_Poblacion, Datu Paglas, Maguindanao | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN281 | DATUPI | NA | DATUPIFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU PIANG |  | Territory 7 | 7.0274 | 124.5054 | Datu Piang_Poblacion (Dulawan), Datu Piang, Maguindanao | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2752 | DDIANGASTHGENSANSCOT | NA | DDIANGASTHGENSANSCOTFHKLMWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1095 | 125.1783 | ACHARON, BRGY. DADIANGAS SOUTH, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3498 | DDIANRTHGENSANSCOTAS | NA | DDIANRTH1GENSANSCOTASFHFH | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1128 | 125.1702 | Dadiangas North, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3499 | DDIASTH1GENSANSCOTAS | NA | DDIASTH11GENSANSCOTASFK | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1075 | 125.1743 | Dadiangas South, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3501 | DDIASTH3GENSANSCOTAS | NA | DDIASTH31GENSANSCOTASFFF | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1075 | 125.1768 | Dadiangas South, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3502 | DDIASTH4GENSANSCOTAS | NA | DDIASTH41GENSANSCOTASFFF | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1111 | 125.1794 | Lagao (1st & 3rd), GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3503 | DDIAWESTGENSANSCOTAS | NA | DDIAWEST1GENSANSCOTASFKFK | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1072 | 125.1715 | Dadiangas South, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN269 | DELCAN | CTT_002_GPONA_01 | DELCANFKLVWXY TCFGADELCANACOTABMGDNFKLVWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | COTABATO CITY |  | Territory 7 | 7.2055 | 124.2396 | Delcana St. Rosary Heights X, Cotabato City, Cotabato City | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2347 | DENLAGLSEBUSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | LAKE SEBU |  | Territory 7 | 6.1568 | 124.7775 | BrgyLaconon_TBOLI_SOUTHCOTABATO, Laconon, T'BOLI, SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | KORONADAL FOC | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2524 | DERILONBANGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.3093 | 124.847 | Lamian Barangay Plaza, Banga, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2196 | DIGALBULUANMGDN | NA | DIGALBULUANMGDNFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PANDAG |  | Territory 7 | 6.732 | 124.8284 | Digal, BULUAN, MAGUINDANAO | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN271 | DINAIG | NA | DINAIGFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.1747 | 124.2186 | Oblates of Mary Immaculate Compound Tamontaka, Datu Odin Sinsuat (Dinaig), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN423 | DINUGA | GSN_017_GPONA_01 | DINUGAFHKLMWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1249 | 125.1833 | Dinuga Subdivision Lagao (1st & 3rd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2201 | DULANGDINAIGMGDN | NA | DULANGDINAIGMGDNFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.1554 | 124.264 | Tanuel, Datu Odin Sinsuat (Dinaig), Maguindanao | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2309 | DUMAGUILNORALASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | NORALA |  | Territory 7 | 6.5492 | 124.6797 | Dumaguil | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1380 | DUMDLG | NA | DUMDLGFHLWXY TCFGADMADLIGTANTANSCOTFHLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TANTANGAN |  | Territory 7 | 6.5845 | 124.7542 | Dumadalig, Tantangan, South Cotabato | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3316 | DUNGOANMLANGNCOT | NA | DUNGOANMLANGNCOTFKLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MLANG |  | Territory 7 | 6.9497 | 124.8707 | CapSite_BrgyDungo-an_Mlang_NorthCotabato | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2195 | EDCORBULDONMGDN | NA | EDCORBULDONMGDNFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BULDON |  | Territory 7 | 7.4425 | 124.3981 | BrgyEdcor_(Gallego_Edcor)_Buldon_Maguindanao | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2330 | EDWARDSTBOLISCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | T'BOLI |  | Territory 7 | 6.241 | 124.8132 | Edwards (Pob.), T'BOLI, SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN655 | ESPERA | ESR_002_GPONA_01 | ESPERAFHKLVWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ESPERANZA |  | Territory 7 | 6.7238 | 124.5194 | Purok Paglaung Esperanza_Poblacion, Esperanza, Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1853 | FAT01 | GSN_910_GPONA_01 | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0723 | 125.1176 | Employees Village, Fatima, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1625 | FATIMAGENSANSCOTLS | NA | FATIMAGENSANSCOTLSFHKWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0576 | 125.1002 | Fatima, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN413 | FMARTK | NA | FMARTK | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4886 | 124.86 | Fitmart Mall of Marvel Gensan Drive Santo Niño (Bo. 2), Koronadal, South Cotabato | GENSAN | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2194 | GADUNGBARIRAMAG | NA | GADUNGBARIRAMAGFLWYNX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BARIRA |  | Territory 7 | 7.397 | 124.323 | Korosoyan, BARIRA, MAGUINDANAO | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3318 | GANSINGTACUROSKUD | NA | GANSINGTACUROSKUDFLVWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.7018 | 124.6727 | CapSite_BrgyGansing_TacurongCity | TACURO | GT | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1612 | GENPAUSANTOS | KRN_003_GPONA_01 | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5128 | 124.8538 | Purok Maharlika, Capunda Subd. General Paulino Santos (Bo. 1), Koronadal, South Cotabato | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN420 | GENSA2 | NA | GENSA2FHKLX TCFGAP1CONELGENSANSCOTFHKLX | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1971 | 125.1858 | Purok 1 Conel, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN758 | GENSAN | GSN_001_GPONA_01 | GENSANFHKLMVDWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1166 | 125.167 | J.P. Laurel cor. Bayabas St., Dadiangas North, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1805 | GENSAN CO | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1161 | 125.1753 | JPLaurel East near corner Quirino Street, Dadiangas East (Pob.), GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1314 | GENSAN FOC | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | City Heights | Territory 7 | 6.1197 | 125.163 | Lot 46 Mercury Cor Earth St. Villa Consuelo Sub. Brgy. City Heights, Gen. Santos City South Cotabato | GENSAN | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN937 | GENSHP | NA | GENSHPFLWYZ | REGION XII (SOCCSKSARGEN) | SARANGANI | MAASIM |  | Territory 7 | 5.9555 | 125.1019 | Gensan Ship Yard and Machine Works, Tinoto, Maasim, Sarangani | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1446 | GFATIM | GSN_016_GPONA_01 | GFATIMFKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0711 | 125.1127 | Lot 25 Blk 34 Employees Village Apopong, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN414 | GLAMAN | PLM_003_GPONA_01 | GLAMANFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.1658 | 125.1141 | National Highway, Glamang, Polomolok, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN748 | GLAN | NA | GLANFHWXYZ | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8165 | 125.1902 | Glan_Poblacion, Glan, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3624 | Glan, Saranggani Province | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8128 | 125.2275 | Glan, Saranggani Province | GENSAN FOC | GT | [6 empty] | #N/A
MIN1466 | GLAN2 | NA | GLAN2FHLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8133 | 125.2097 | GLAN WATER DISTRICT RESERVOIR SITE Purok Banahao, Sumbang Calabanit, Glan, Sarangani | GENSAN FOC | GT | [6 empty] | #N/A |  | DECOM
MIN1730 | GLAN2A | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8133 | 125.2097 | GLAN WATER DISTRICT RESERVOIR SITE Purok Banahao, Sumbang Calabanit, Glan, Sarangani | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2139 | GLIPIKITNCOT | NA | GLIPIKITNCOTFHKLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.0261 | 124.672 | Pikit, Cotabato, Philippines | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2760 | Globe Business Center ( repeater changeout)) | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2236 | 124.2475 | Cotabato City | COTABA | GT | [6 empty] | #N/A
MIN2143 | GREENLEAFHTL | NA | GREENLEAFHTLFHKLMVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1148 | 125.1825 | Green Leaf Hotel, J. Catolico Sr. Ave., General Santos City, South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1707 | GRINOTACUR | NA | GRINOTACURFHKLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.7238 | 124.6674 | Buenaflor, Tacurong, Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1858 | GSC001 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1161 | 125.1754 | MLQuezon Ave., corner Daproza Street, Dadiangas North, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | [6 empty] | #N/A
MIN1854 | GSC002 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0854 | 125.1495 | Calumpang Hiway, Purok Malinawon, Calumpang, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | [6 empty] | #N/A
MIN1856 | GSC003 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1091 | 125.1486 | Makar Highway, Espina Village Entrance, Labangal, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | [6 empty] | #N/A
MIN1860 | GSC005 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1257 | 125.1715 | Aparente Avenue corner Pula Street, City Heights, City Heights, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | [6 empty] | #N/A
MIN1863 | GSC006 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1363 | 125.1708 | Aparente Avenue, (near New Era Univ.) Purok Malakas, San Isidro (Lagao 2nd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | [6 empty] | #N/A
MIN1861 | GSC007 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1322 | 125.1811 | Leon Llido Street, beside Trade School, Lagao (1st & 3rd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | [6 empty] | #N/A
MIN1859 | GSC009 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1178 | 125.188 | Bula Road, back of NFA, Lagao (1st & 3rd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | [6 empty] | #N/A
MIN1855 | GSC010 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1067 | 125.1873 | P Acharon Blvd, (Near Bula Police Station), Bula, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | [6 empty] | #N/A
MIN1035 | GSN-602 | GSN_602_GPONA_01 | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1155 | 125.1389 | ALONG DIAMOND AVE., PH 2, DOεA SOLEDAD, BRGY. LABANGAL, GENERAL SANTOS CITY | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1036 | GSN-603 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1131 | 125.1414 | ALONG E. AGUINALDO ST., DONA SOLEDAD, LABANGAL, GSC | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1037 | GSN-604 | GSN_604_GPONA_01 | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1263 | 125.1945 | ALONG TIONGSON STREET, LAGAO, GENERAL SANTOS CITY | GENSAN FOC | GT | [6 empty] | #N/A
MIN1038 | GSN-605 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1187 | 125.1893 | ALONG BULA AVE., CORNER ARRADAZA ST., BRGY LAGAO , GENERAL SANTOS CITY | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1277 | GSN-706 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.116 | 125.176 | ALONG QUIRINO ST. NEAR COR JP LAUREL ST FRONT NEW CHED BLDG., GENERAL SANTOS CITY | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1278 | GSN-707 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1382 | 125.1662 | BRGY. SAN ISIDRO, GENERAL SANTOS CITY, ALONG NUNEZ ROAD FRONT NUNEZ COMPOUND, BGY, GENERAL SANTOS C | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1366 | GSN-708 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0963 | 125.1539 | BRGY. MAKAR, GENERAL SANTOS CITY, ALONG MAKAR NATIONAL HIGHWAY FRONTING SUPER FERRY AND SULPICIO LIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1326 | GSN-709 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1073 | 125.1924 | BRGY. BULA, GENERAL SANTOS CITY, ALONG BULA ROAD NEAR STO NINO PARISH CHURCH, BULA DISTRICT, GENERA | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1532 | HWAYLANAOKID | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0266 | 125.0884 | Lanao_Kidapawan City Lanao, City Of Kidapawan, Cotabato (North Cotabato) | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2208 | IDTIGPENDAMAG | NA | IDTIGPENDAMAGFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | GEN. SK. PENDATUN |  | Territory 7 | 6.7959 | 124.7653 | Lower Idtig, General S.K. Pendatun, Maguindanao, Philippines | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN761 | IGENSA | NA | IGENSAF_D IGENSAFKLMVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1175 | 125.1764 | Kadulasan St Dadiangas East (Pob.), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN438 | ISIDGS | GSN_005_GPONA_01 | ISIDGSFKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1363 | 125.1582 | Purok Kaunlaran San Isidro (Lagao 2nd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1589 | ISLAJARDIN | NA | ISLAJARDINWDY | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.7892 | 125.1886 | Isla Jardin del Mar Resort, Gumasa, Glan, Sarangani | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN446 | ISULA2 | ISU_001_GPONA_01 | ISULA2FHKLWY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6216 | 124.61 | Kalawag I (Pob.), Isulan, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1749 | ISULANCPITOL | NA | ISULANCPITOLFHKLWY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6445 | 124.6099 | IsulanTacurong City Road Sampao, Isulan Sultan Kudarat | TACURO | GT | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN744 | KABACA | KBC_001_GPONA_01 | KABACAFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN |  | Territory 7 | 7.1097 | 124.8249 | Matala St. Kabacan_Poblacion, Kabacan, Cotabato (North Cotabato) | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2327 | KABATIOLMAASIMSAR | NA | KABATIOLMAASIMSARFL | REGION XII (SOCCSKSARGEN) | SARANGANI | MAASIM |  | Territory 7 | 5.864 | 124.9784 | Kabatiol, MAASIM, SARANGANI, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN716 | KABING | NA | KABINGFLXZFL TCFGAKABENGISAUDIAMGDNFL | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU SAUDIAMPATUAN |  | Territory 7 | 6.9243 | 124.4148 | Kabengi, Datu SaudiAmpatuan, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1459 | KABLACANRLY | NA | KABLACANRLYFLW | REGION XII (SOCCSKSARGEN) | SARANGANI | MAASIM |  | Territory 7 | 5.8564 | 124.9524 | Kablacan, Maasim, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN415 | KABLON | NA | KABLONFHLWXY TCFGAKABLONTUPISCOTFHLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TUPI |  | Territory 7 | 6.3157 | 125.0122 | Purok Maligaya Kablon, Tupi, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN284 | KABUNT | NA | KABUNTFHKLWY TCFGAPOBTUMBAOMGDNFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | KABUNTALAN |  | Territory 7 | 7.1172 | 124.3846 | Kabantalan(Tumbao)_Poblacion, Kabuntalan (Tumbao), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN447 | KALAMA | NA | KALAMAFHKLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | KALAMANSIG |  | Territory 7 | 6.556 | 124.056 | Kalamansig_Poblacion, Kalamansig, Sultan Kudarat | COTABA | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2240 | KALANAWESKUD | NA | KALANAWESKUDFHLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.7501 | 124.6842 | Tacurong City, Sultan Kudarat, Philippines | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1068 | KALAND | NA | KALANDFHLWXY TCFGAKALANDTACUROSKUDFHLWY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6559 | 124.7018 | Kalandagan, Tacurong, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3489 | KALAWAG2ISULANSKUD | NA | KALAWAG2ISULANSKUDFW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6313 | 124.6027 | Brgy. Kalawag II, Isulan, Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3480 | KALAWAG3ISULANSKUD | NA | KALAWAG3ISULANSKUDFHKLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6392 | 124.5999 | Kalawag III (Pob.), ISULAN (Capital), SULTAN KUDARAT, REGION XII (SOCCSKSARGEN), MIN | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3092 | KALAWISULANSKUDCOW | NA | NA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6383 | 124.5999 | KALAWAGIII, ISULAN, SULTAN KUDARAT | TACURO | GT | [6 empty] | #N/A
MIN411 | KALSAN | NA | KALSANFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.295 | 125.1005 | DOLE Kalsangi Polo, Polomolok, South Cotabato | KORONADAL FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN421 | KATANG | NA | KATANGFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1843 | 125.2244 | Purok 3 Katangawan, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2246 | KATICOSKUD | NA | KATICOSKUDFLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | PRESIDENT QUIRINO |  | Territory 7 | 6.758 | 124.7292 | Roger Perono , Katico, President Quirino, Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1149 | KATID | NA | KATIDFHLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN |  | Territory 7 | 7.0979 | 124.8598 | Katidtuan, Kabacan, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1457 | KATUBAORLY | NA | KATUBAORLYFLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | MAASIM |  | Territory 7 | 5.883 | 124.854 | Lumasal, Maasim, Sarangani | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2239 | KATUNGTACUR | NA | KATUNGTACURFHLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6525 | 124.6605 | BrgyRajah Nuda_TACURONG CITY_, Rajah Nuda, Tacurong, Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN416 | KAURAN | NA | KAURANFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | AMPATUAN |  | Territory 7 | 6.7785 | 124.4799 | Purok 2 Kauran, Ampatuan, Maguindanao | TACURO | FTAP | AREA 13 | COTABATO 2 | TACURONG | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2197 | KAYADASMGND | NA | KAYADASMGNDFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ABDULLAH SANGKI |  | Territory 7 | 6.8538 | 124.5426 | Kayakaya, Datu Abdullah Sangki, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2200 | KAYAGAKBAKNCOT | NA | KAYAGAKBAKNCOTFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN |  | Territory 7 | 7.1118 | 124.8059 | Kayaga, Kabacan, Cotabato (North Cotabato) | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN417 | KCCGEN | NA | KCCGENFHWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1156 | 125.1859 | KCC Gensan Lagao (1st & 3rd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN760 | KCCMARBEL | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4992 | 124.8467 | KCCKoronadal Mall Gensan Drive,National Highway Zone II (Pob.), Koronadal, South Cotabato | GENSAN | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN399 | KIAMBA | NA | KIAMBAFHKLW TCFGAPOBKIAMBASARFHKLW | REGION XII (SOCCSKSARGEN) | SARANGANI | KIAMBA |  | Territory 7 | 5.9951 | 124.6257 | National Hway Kiamba_Poblacion, Kiamba, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN833 | KIDAP2 | NA | KIDAP2FHLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CITY OF KIDAPAWAN (Capital) | Benoligan | Territory 7 | 7.0389 | 125.0256 | Benoligan, City Of Kidapawan, Cotabato (North Cotabato) | KIDAPAWAN | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN381 | KIDAP3 | NA | KIDAP3FHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 6.9986 | 125.081 | Phase 1 Apo Sandawa Homes Junction, City Of Kidapawan, Cotabato (North Cotabato) | KIDAP2 | GT | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1240 | KIDAP4 | NA | KIDAP4FHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CITY OF KIDAPAWAN (Capital) | Poblacion | Territory 7 | 7.0133 | 125.0897 | Jose Abad Santos Ave CitiofKidapawan_Poblacion, City Of Kidapawan, Cotabato (North Cotabato) | KIDAPAWAN | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN834 | KIDAPA | KPW_001_GPONA_01 | KIDAPAFHKLWYZ TCFGAPOBKIDAPNCOTFHKLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0063 | 125.0947 | Cotelco Village CitiofKidapawan_Poblacion, City Of Kidapawan, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN933 | KIDAPAWAN DOCTORS REPEATER | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.009 | 125.0898 | Kidapawan Doctors Hospital Inc. CitiofKidapawan_Poblacion, City Of Kidapawan, Cotabato (North Cotabato) | KIDAP2 | GT | [6 empty] | #N/A
MIN1823 | KIDAPAWAN NDC | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0123 | 125.0922 | Marasigan Building,, CitiofKidapawan_Poblacion, City Of Kidapawan, Cotabato (North Cotabato) | KIDAP2 | GT | [6 empty] | #N/A
MIN2526 | KILAGAKBACANCOT | NA | KILAGAKBACANCOTFLX | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN |  | Territory 7 | 7.0894 | 124.8203 | Kilagasan, Kabacan, Cotabato, Philippines | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2183 | KIMADZILCARMENCOT | NA | KIMADZILCARMENCOTFHKLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CARMEN |  | Territory 7 | 7.3232 | 124.7809 | Kimadzil, Carmen, Cotabato, Philippines | KIDAP2 | PHILTOWER | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN442 | KIPAL | NA | KIPALHWYZHWY TCFGAKIPALBGTAMPAKSCOTHWYFHKL | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TAMPAKAN |  | Territory 7 | 6.4075 | 124.927 | Kipalbig, Tampakan, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN382 | KISANT | NA | KISANTFLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MAKILALA |  | Territory 7 | 6.9225 | 125.1417 | Kisante, Makilala, Cotabato (North Cotabato) | KIDAP2 | GT | [6 empty] | #N/A
MIN1448 | KLING | NA | KLINGFLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | KIAMBA |  | Territory 7 | 5.9454 | 124.731 | Kling (Lumit), Kiamba, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2234 | KLWAGISULANSKUD | ESR_001_GPONA_01 | KLWAGISULANSKUDFHKLVWY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6245 | 124.5968 | Brgy. Kalawag, Isulan, Sultan Kudarat | TACURO | GT | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2163 | KM17NULINGMGDNCOW | NA | KM17NULINGMGDNCOW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2617 | 124.3558 | KM 17 SULTAN KUDARAT, MAGUINDANAO | COTABA | GT | [6 empty] | #N/A |  | DECOM
MIN762 | KORON2 | NA | KORON2FKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.481 | 124.8646 | Zone III Purok Santos Zone III (Pob.), Koronadal, South Cotabato | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN639 | KORON3 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4924 | 124.8425 | Maranion Village Zone III (Pob.), Koronadal, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1070 | KORON4 | KRN_002_GPONA_01 | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5039 | 124.8373 | Paras Bldg National Highway Zone II (Pob.), Koronadal, South Cotabato | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN763 | KORONA | KRN_001_GPONA_01 | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4965 | 124.8506 | Osita Subd Osmena St., Zone II (Pob.), Koronadal, South Cotabato | KORONADAL FOC | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1271 | KORONADAL FOC | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4817 | 124.8661 | KM.3 Gensan Drive. Purok Silangan Sto Niño (Bo. 2), Koronadal, South Cotabato | KORONADAL FOC | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN704 | KPATAG | NA | KPATAGFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | KAPATAGAN |  | Territory 7 | 7.5412 | 124.2132 | Kapatagan, Kapatagan, Lanao Del Sur | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1830 | KRAANSKUD | NA | KRAANSKUDFLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | PALIMBANG |  | Territory 7 | 6.1235 | 124.3279 | Kraan, Palimbang, Sultan Kudarat | GENSAN FOC | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1445 | KRN-701 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4851 | 124.842 | HUAWEI CABINET ALONG BLK 2 AMURAO ST., AMURAO SUBD., KORONADAL CITY, SOUTH COTABATO | KORONADAL FOC | GT | [6 empty] | #N/A
MIN1359 | KRN-702 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5042 | 124.8482 | HUAWEI CABINET ALONG ROXAS ST. CORNER BALMORES ST. KORONADAL CITY, SOUTH COTABATO | KORONADAL FOC | GT | [6 empty] | #N/A
MIN1361 | KRN-703 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4895 | 124.8579 | HUAWEI CABINET ALONG GENERAL SANTOS DRIVE, FRONT NFA COMPOUND, KORONADAL CITY, SOUTH COTABATO | KORONADAL FOC | GT | [6 empty] | #N/A
MIN448 | KULAMA | NA | KULAMAFWYFWY TCFGABUENFLORAQUINOSKUDFWLY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | SEN. NINOY AQUINO |  | Territory 7 | 6.4452 | 124.3305 | Buenaflores, Sen. Ninoy Aquino, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2300 | KUSANBANGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.4108 | 124.7331 | Kusan (Barrio 8), BANGA, SOUTH COTABATO | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2220 | LABUSHRFAGQKMGND | NA | LABUSHRFAGQKMGNDFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SHARIFF AGUAK |  | Territory 7 | 6.8474 | 124.4526 | Labu-labu, Maguindanao, Philippines | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1834 | LADIASKUDMGDN | NA | LADIASKUDMGDNFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2625 | 124.335 | Ladia, Maguindanao, Philippines | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2188 | LADTINGPIKITCOT | NA | LADTINGPIKITCOTFHKLZ | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.052 | 124.6408 | Ginatilan, Pikit, Cotabato (North Cotabato) | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2027 | LAG-01 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1415 | 125.1998 | Beside Alpine Subd. Nursery Road General Santos City | GENSAN FOC | GT | [6 empty] | #N/A
MIN2028 | LAG-02 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1324 | 125.1991 | Nursery Road General Santos City | GENSAN FOC | GT | [6 empty] | #N/A
MIN764 | LAGAO | GSN_009_GPONA_01 | LAGAOFHKLWY TCFGANHIWAYGENSANSCOTFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1409 | 125.2058 | National Highway Lagao (1st & 3rd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN759 | LAGAO2 | GSN_003_GPONA_01 | LAGAO2FHKLMWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1321 | 125.1886 | Sto. Rosario St.. Purok 5 Lagao (1st & 3rd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3504 | LAGAO3GENSANSCOTAS | NA | LAGAO1GENSANSCOTASFFF | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.119 | 125.1817 | Lagao (1st & 3rd), GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1548 | LAGAOGENSAN | GSN_004_GPONA_01 | LAGAOGENSANF_DFHKLDWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1188 | 125.197 | BrgyBaluan_GenSan_Scotab Baluan, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2235 | LAGUILAYANISULANSKUD | NA | LAGUILAYANISULANSKUDFHLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6723 | 124.5289 | Brgy.Laguilayan_Esperanza_, Alamada, Sultan Kudarat (Nuling), Maguindanao | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN403 | LAHAK | NA | LAHAKFHLWYZ | REGION XII (SOCCSKSARGEN) | SARANGANI | MALAPATAN |  | Territory 7 | 5.969 | 125.293 | Sitio Lahak, Poblacion (Malapatan), Malapatan, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN774 | LAMBAY | NA | LAMBAYFHLWXY TCFGAPOBLAMBAYSKUDFHLWY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | SULTAN SA BARONGIS |  | Territory 7 | 6.7978 | 124.6337 | Poblacion (Lambayong), Lambayong (Mariano Marcos), Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2329 | LAMBAYONGTAMPAKSCOT | NA | LAMBAYONGTAMPAKSCOTFL | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TAMPAKAN |  | Territory 7 | 6.4352 | 124.9768 | Maltana, TAMPAKAN, SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN750 | LAMCAN | NA | LAMCANXZ | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON |  | Territory 7 | 6.2761 | 125.2567 | National Highway Malandag, Malungon, Sarangani | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2304 | LAMDALASEBUSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | LAKE SEBU |  | Territory 7 | 6.2042 | 124.7311 | Lamdalag, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1067 | LAMSUG | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.291 | 124.7925 | Lamsugod, Surallah, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2203 | LAPOKSHRFAGQKMGND | NA | LAPOKSHRFAGQKMGNDFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SHARIFF AGUAK |  | Territory 7 | 6.9108 | 124.4839 | BrgyDaleBong_ShariffSaydona_Mustapha, Abilan, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2308 | LAPUZNORALASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | NORALA |  | Territory 7 | 6.529 | 124.6301 | Barangay Lapuz, Mabini St, Norala, Timog Cotabato, Philippines | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2199 | LAYOGPAGALUMGDN | NA | LAYOGPAGALUMGDNFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PAGALUNGAN |  | Territory 7 | 7.0748 | 124.7214 | Linandangan, Pagalungan, Maguindanao | MIDSAY | FTAP | AREA 13 | COTABATO 2 | KABACAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3505 | LBANGALGENSANSCOTAS | NA | LBANGAL1GENSANSCOTASFKFKFK | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.119 | 125.1453 | Labangal, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3356 | LBERTADTOPKNADALSCOT | NA | LBERTADTOPKNADALSCOTFHLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4766 | 124.9449 | CapSite_BrgyZulueta03_KoronadalCity | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN449 | LEBAK | NA | LEBAKFHKLVWXYF | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LEBAK |  | Territory 7 | 6.6398 | 124.066 | Lebak_Poblacion III, Lebak, Sultan Kudarat | COTABA | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN383 | LIBUNG | LBU_001_GPONA_01 | LIBUNGFHKLWXY TCFGASINGAYAOLIBUNGNCOTFHKLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | LIBUNGAN |  | Territory 7 | 7.2435 | 124.5221 | Singayao St. Libungan_Poblacion, Libungan, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2204 | LIBUTANMMSAPAMGDN | NA | LIBUTANMMSAPAMGDNFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | MAMASAPANO |  | Territory 7 | 6.9518 | 124.497 | Libutan, Mamasapano, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN422 | LIGAYA | NA | LIGAYAFHKLWY TCFGAP5LIGAYAGENSANSCOTFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1582 | 125.2278 | Purok 5 Ligaya, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2182 | LILIONGCARNCOT | NA | LILIONGCARNCOTX LLIONGCARNCOTFHKLWYTF | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CARMEN |  | Territory 7 | 7.3689 | 124.7992 | Liliongan, Carmen, Cotabato, Philippines | KIDAP2 | UNITY | AREA 13 | COTABATO 2 | KIDAPAWAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1463 | LIMBO | NA | LIMBOFLWXDY TCFGALIMBONULINGMGDNFLWDY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.24 | 124.2651 | Brgy. Limbo, Sultan Kudarat (Nuling), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1421 | LIMBO_D | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Poblacion I | Territory 7 | 7.2 | 124.244 | World Food Program Agency Back of Albert Einstein School CotabatoCity_Poblacion, Cotabato City, Cotabato City | COTABATO | GT | [6 empty] | #N/A
MIN2198 | LINAMUNANTLAYANMGDN | NA | LINAMUNANTLAYANMGDNFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | TALITAY |  | Territory 7 | 7.0204 | 124.4048 | BRGY. MANGGAY TALITAY | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2417 | LKATUNGALTACUROSKUD | NA | LKATUNGALTACUROSKUDFHKLVWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6791 | 124.6569 | Upper Katungal, Tacurong, Sultan Kudarat | TACURO | GT | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN765 | LONDON | NA | LONDON_DZDFHKLDWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 5.9918 | 125.1184 | Tambler, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1422 | LONDON_D | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.025 | 125.1413 | Cargill Oilmill Tambler, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN285 | LUMADI | NA | LUMADIFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.1793 | 124.1957 | Sitio Luma Dinaig Proper, Datu Odin Sinsuat (Dinaig), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2365 | LUNMLAPATSAR | NA | LUNMLAPATSARFL | REGION XII (SOCCSKSARGEN) | SARANGANI | MALAPATAN |  | Territory 7 | 6.0375 | 125.2959 | Lun Padidu, MALAPATAN, SARANGANI, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN450 | LUTAYA | NA | NA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LUTAYAN |  | Territory 7 | 6.561 | 124.8578 | Purok Bougainvilla Tamnag (Pob.), Lutayan, Sultan Kudarat | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN400 | MAASIM | NA | MAASIMFHWYZ | REGION XII (SOCCSKSARGEN) | SARANGANI | MAASIM |  | Territory 7 | 5.8623 | 124.9979 | St. Louie St., Poblacion (Maasim), Maasim, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN426 | MABGEN | GSN_010_GPONA_01 | MABGENFHKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1878 | 125.1409 | Purok 1 Mabuhay, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3325 | MABINIKNADALSCOT | NA | MABINIKNADALSCOTFKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5288 | 124.9093 | Brgy. Mabini, Koronadal, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2222 | MACABISOMGDN | NA | MACABISOMGDNFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2831 | 124.2796 | Sittio Payong 1, Macabico (Macabiso), Sultan Mastura, Maguindanao | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2212 | MACAGUILNGNULINGMGDN | NA | MACAGUILNGNULINGMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2563 | 124.2692 | Salimbao, SULTAN KUDARAT (NULING), MAGUINDANAO, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1784 | MADIADSAUDI | NA | MADIADSAUDIFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU SAUDIAMPATUAN |  | Territory 7 | 6.9685 | 124.4701 | Madia, Datu SaudiAmpatuan, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2364 | MADRIDPOBKIDAPNCOT | NA | MADRIDPOBKIDAPNCOTFLX | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.013 | 125.0943 | 236W+H64, Datu Ingkal St, Kidapawan City, Cotabato, Philippines | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN286 | MAGONO | SFA_001_GPONA_01 | MAGONOFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SHARIFF AGUAK |  | Territory 7 | 6.8637 | 124.4389 | ShariffAguak(Maganoy),Poblacion, Shariff Aguak (Maganoy), Maguindanao | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN384 | MAGPET | NA | MAGPETDFHLVDWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MAGPET |  | Territory 7 | 7.1048 | 125.1271 | Magpet_Poblacion, Magpet, Cotabato (North Cotabato) | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | KIDAPAWAN | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1595 | MAGSAYKIDAP | NA | MAGSAYKIDAPFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0135 | 125.0737 | National Highway Lanao, City Of Kidapawan, Cotabato (North Cotabato) | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3225 | MAGSAYKNADALSCOT | NA | MAGSAYKNADALFLWY/K/V | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.467 | 124.9056 | CapSite_BrgyMagsaysay01_KoronadalCity | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1843 | MAGSAYPOLSCO | PLM_004_GPONA_01 | MAGSAYPOLSCOFHKWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.215 | 125.063 | 13Reloc National Highway, Magsaysay, POLOMOLOK, SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3326 | MAIBOTANTANSCOT | NA | MAIBOTANTANSCOTFKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TANTANGAN |  | Territory 7 | 6.5534 | 124.783 | BrgyMaibo_TANTANGAN_SOUTH COTABATO | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN427 | MAITUM | NA | MAITUMFHKZRFHK | REGION XII (SOCCSKSARGEN) | SARANGANI | MAITUM |  | Territory 7 | 6.0601 | 124.4937 | Malalag (Pob.), Maitum, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN766 | MAKAR | GSN_008_GPONA_01 | MAKARFHKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0922 | 125.1497 | Nutimix Compound. Brgy. Makar,General Santos City,South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN428 | MAKAR2 | GSN_019_GPONA_01 | MAKAR2FHKLWY TCFGAMASGASIGGENSANSCOTFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.069 | 125.1362 | Airport Rd. Purok Masigasig Tambler, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN9 | MAKIL2 | NA | MAKIL2FHLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MAKILALA |  | Territory 7 | 6.9596 | 125.0836 | Beauville Resort Makilala_Poblacion, Makilala, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN8 | MAKILA | NA | MAKILAFHLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MAKILALA |  | Territory 7 | 6.9513 | 125.099 | Makilala_Poblacion, Makilala, Cotabato (North Cotabato) | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3204 | MALADIPICONGLDSCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | PICONG |  | Territory 7 | 7.6692 | 123.967 | Brgy maladi picong lanao del sur | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN429 | MALAK3 | NA | MALAK3FHKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1325 | 125.2054 | Zone 4 Blk 2 Lagao (1st & 3rd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN783 | MALAKA | GSN_006_GPONA_01 | MALAKAFHKLVWXYZ | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1438 | 125.1649 | Purok Malakas, Dadiangas Heights San Isidro (Lagao 2nd), Gen. Santos City (Dadiangas), South Cotabato | KORONADAL FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN749 | MALAPA | NA | MALAPAFWYFWY TCFGALUNMASLAMLAPATSARFWYDFH | REGION XII (SOCCSKSARGEN) | SARANGANI | MALAPATAN |  | Territory 7 | 6.0233 | 125.2969 | National Highway Lun Masla, Malapatan, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN386 | MALAPG | NA | MALAPGFHKLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CARMEN |  | Territory 7 | 7.4071 | 124.809 | Malapag, Carmen, Cotabato (North Cotabato) | KIDAP2 | PHILTOWER | AREA 13 | COTABATO 2 | KIDAPAWAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN385 | MALASI | NA | MALASIFLWYZ | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MAKILALA |  | Territory 7 | 6.9409 | 125.1437 | Purok Nangka Malasila, Makilala, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN387 | MALAT | NA | MALATFLWXYFLWY TCFGAMALATADANTPASNCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ANTIPAS |  | Territory 7 | 7.3057 | 125.0446 | Malatab, Antipas, Cotabato (North Cotabato) | TCFGAISIN3CARMENDDN | FTAP | AREA 13 | COTABATO 2 | KIDAPAWAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2326 | MALBANGMAASIMSAR | NA | MALBANGMAASIMSARFLX | REGION XII (SOCCSKSARGEN) | SARANGANI | MAASIM |  | Territory 7 | 5.8551 | 125.0294 | Malbang, MAASIM, SARANGANI, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN397 | MALDAG | MLU_001_GPONA_01 | MALDAGFHKLWYDF TCFGAMALANDAGMALUNGSARFFHKLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON |  | Territory 7 | 6.307 | 125.2525 | ok | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2301 | MALTANATAMPAKSCOT | NA | MALTANATAMPAKSCOTFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TAMPAKAN |  | Territory 7 | 6.4243 | 124.9358 | Maltana, South Cotabato, Philippines | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN430 | MALUK | GSN_014_GPONA_01 | MALUKFHKLWY TCFGAACHARONGENSANSCOTFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1033 | 125.1624 | Purok Acharon Labangal, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN873 | MALUNG | MLU_002_GPONA_01 | MALUNGFHLWY TCFGAPOBLACIONMALUNGSARFHLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON |  | Territory 7 | 6.3766 | 125.275 | Malungon_Poblacion, Malungon, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1300 | MAMASP | NA | MAMASPFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | MAMASAPANO |  | Territory 7 | 6.8939 | 124.4993 | Bagumbong, Mamasapano, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1776 | MANARAPANCOT | NA | MANARAPANCOTFHKLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CARMEN | Manarapan | Territory 7 | 7.2423 | 124.7922 | Manarapan, Carmen, Cotabato (North Cotabato) | MLANG | PHILTOWER | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2571 | MANAULPIKITNCOT | NA | MANAULPIKITNCOTFKLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.042 | 124.6047 | BRGY. MANAULANAN, PIKIT, NORTH COTABATO | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2363 | MANONGOLKIDAPNCOT | NA | MANONGOLKIDAPNCOTFHLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0245 | 125.1274 | Manongol, CITY OF KIDAPAWAN (Capital), COTABATO (NORTH COTABATO) | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1994 | MARCOSRDKDAL | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4882 | 124.8482 | Brgy. Gen. Paulino Santos, Assumption (Bulol) Koronadal City South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN401 | MARIBU | NA | MARIBUFLWYFLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | ALABEL |  | Territory 7 | 6.1255 | 125.2689 | Maribulan, Alabel, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3438 | MASAGZON3KNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4824 | 124.8564 | Purok Masagana II, Brgy. Zone III, Koronadal City, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN745 | MATALA | MTL_001_GPONA_01 | MATALAFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MATALAM |  | Territory 7 | 7.0827 | 124.9006 | Matalam_Poblacion, Matalam, Cotabato (North Cotabato) | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 2 | MLANG | GILSON A. NAVARRA | JUN MARLO M. CASTRODES | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN287 | MATANO | NA | MATANODFHKLWX TCFGABAYANGAMTANOGMGDNF_DFHKLWDY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | MATANOG |  | Territory 7 | 7.4876 | 124.2473 | Bayanga Sur, Matanog, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2490 | Mayor Yap's Residence | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8119 | 125.2277 | Mayor Yap's Residence Glan Sarangani Province | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN451 | MBARAS | NA | MBARASFHKLVWXYTCFGABARASTACUROSKUDFHKLVWYXA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6714 | 124.6366 | Baras, Tacurong, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1573 | MBUHAYGENSAN | NA | MBUHAYGENSANFKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1658 | 125.1603 | Purok New Mabuhay Mabuhay, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3324 | MBUHAYGENSANSCOT | NA | MBUHAYGENSANSCOTFKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1682 | 125.1502 | CapSite_BrgyMabuhay02_GeneralSantosCity | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2219 | METAUNSAYMGDN | NA | METAUNSAYMGDNFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SHARIFF AGUAK |  | Territory 7 | 6.8891 | 124.4327 | Datu Unsay, Maguindanao, Philippines | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN647 | MIDSA2 | NA | MIDSA2FHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.1896 | 124.5345 | Sto.Nino cor Mallanes St., Midsayap_Barangay Poblacion 1, Midsayap, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN845 | MIDSAY | MDS_001_GPONA_01 | MIDSAYFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.2032 | 124.5432 | National Highway, Midsayap_Barangay Poblacion 5, Midsayap, Cotabato (North Cotabato) | MIDSAY | GT | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2539 | MLALAGCOGMLUNGONSAR | NA | MLALAGCOGMLUNGONSARFLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON |  | Territory 7 | 6.4042 | 125.289 | Malalag Cogon, Malungon, Sarangani, Philippines | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN846 | MLANG | NA | MLANGFKVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MLANG |  | Territory 7 | 6.9464 | 124.8808 | Del Pilar cor Anque Sts., M'lang_Poblacion, M'Lang, Cotabato (North Cotabato) | KIDAP2 | GT | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1272 | MLANG FOC | MLN_001_GPONA_01 | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MLANG |  | Territory 7 | 6.945 | 124.8826 | Porras cor. JP Laurel Sts. Mlang Poblacion North Cotabato | KIDAP2 | GT | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1505 | MLANGAIRPT | NA | MLANGAIRPTFHLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MLANG |  | Territory 7 | 6.93 | 124.9 | Mlang Airport Tawantawan, M'Lang, Cotabato (North Cotabato) | KIDAP2 | GT | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2544 | MLIPAYONPOBESPERSKUD | NA | MLIPAYONPOBESPERSKUDFHKLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ESPERANZA |  | Territory 7 | 6.7182 | 124.5155 | Esperanza, Sultan Kudarat, Philippines | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN938 | MNUANG | NA | MNUANGFLWXYFLWY TCFGASMNUANGPIGKAWNCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIGKAWAYAN |  | Territory 7 | 7.2705 | 124.3988 | South Manuangan, Pigkawayan, COTABATO (NORTH COTABATO) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN388 | MOECAN | NA | MOECANFLWXY TCFGAMEOCANARAKANNCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ARAKAN |  | Territory 7 | 7.2921 | 125.1835 | Meocan, Arakan, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 13 | COTABATO 2 | KIDAPAWAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2236 | MPANTIGISULANSKUD | NA | MPANTIGISULANSKUDFHLWY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.666 | 124.5939 | Mapantig, Isulan, Sultan Kudarat, Philippines | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3554 | MSPAGSTCRUKNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4713 | 124.8439 | Purok Masipag, Brgy. Sta. Cruz, Koronadal City, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MINCOW20 | MSUTEMPO | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.0147 | 124.3209 | Mindanao State University, Brgy Dalican, Datu Odin Sinsuat, Maguindanao | COTABA | GT | [6 empty] | #N/A
MIN3920 | MUNDOGMAGSAYKIDAPCOT | NA | MUNDOGMAGSAYKIDAPCOTFLW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0123 | 125.0814 | Brgy. Magsaysay, Kidapawan City | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN752 | NAGPAN | NA | NAGPANFLWYFLWY TCFGANAGPANMALUNGSARFLWYPZFL | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON |  | Territory 7 | 6.3459 | 125.264 | Nagpan, Malungon, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2331 | NALUSKIAMBASAR | NA | NALUSKIAMBASARFLWYDDD | REGION XII (SOCCSKSARGEN) | SARANGANI | KIAMBA |  | Territory 7 | 6.018 | 124.5715 | Linek, Brgy. Nalus, Kiamba, Sarangani Province | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2348 | NDUMANGSTBOLISCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | T'BOLI |  | Territory 7 | 6.1874 | 124.787 | New Dumangas, T'Boli, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2244 | NEWISABELATACUROSKUD | NA | NEWISABELATACUROSKUDFKLVWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6789 | 124.6784 | BrgyNewIsabela_CITY OF TACURONG_, Alamada, Sultan Kudarat (Nuling), Maguindanao | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2233 | NEWPANAYSKUD | NA | NEWPANAYSKUDFHLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ESPERANZA |  | Territory 7 | 6.7364 | 124.5572 | Purok Malipayon, New Panay, Esperanza, Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2249 | NEWPNGISULANSKUD | NA | NEWPNGISULANSKUDFHLVWY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.637 | 124.5542 | BRGYNEWPANGASINAN_ISULAN_, Alamada, Sultan Kudarat (Nuling), Maguindanao | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2186 | NEWPNYALEOSNCOT | NA | NEWPNYALEOSNCOTFHKLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALEOSAN |  | Territory 7 | 7.2198 | 124.6581 | BrgyNewPanay_Aleosan_, Dicalongan (Pob.), Ampatuan, Maguindanao | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN435 | NINOSC | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SANTO NIÑO |  | Territory 7 | 6.4174 | 124.7038 | Purok Bagong Lipunan Teresita, Santo Nino, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1212 | NORAL2 | NA | TCFGASANMIGNORALASCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | NORALA |  | Territory 7 | 6.4914 | 124.7192 | San Miguel, Norala, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN431 | NORALA | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | NORALA |  | Territory 7 | 6.5216 | 124.6622 | Norala_Poblacion, Norala, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN288 | NOTRED | CTT_003_GPONA_01 | NOTREDFHLXZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2173 | 124.2537 | 32 Dona Teresa St. CotabatoCity_Poblacion III, Cotabato City, Cotabato City | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2191 | NUNGUANPIKITNCOT | NA | NUNGUANPIKITNCOTFKLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.0903 | 124.6854 | Pikit, Cotabato, Philippines | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2516 | NUROPOBUPIMGDN | NA | NUROPOBUPIMGDNFHKWYZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | UPI |  | Territory 7 | 7.0069 | 124.1628 | Purok 7, Sinsuat Avenue, Nuro Poblacion, Upi, Maguindanao | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3553 | OSMENROTONKNADALSCOT | NA | OSMENROTONKNADALSCOTFHLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5157 | 124.8868 | CapSite_BrgyRotonda_KoronadalCity | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1991 | P24MABUHAY | NA | P24MABUHAYFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1764 | 125.153 | Brgy Mabuhay, Gen Santos City South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3892 | P4CENTRALSURALLSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.3507 | 124.7548 | PUROK 4, BRGY. CENTRALA, SURALLAH, SOUTH COTABATO | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2736 | P4GLAMANPOLOMOSCOT | NA | P4GLAMANPOLOMOSCOTFHKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.1626 | 125.0867 | Purok 3, Provincial Road Glamang, Glamang, Polomolok, 9504 Timog Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3487 | P4LIGAYAGENSANSCOT | NA | P4LIGAYAGENSANSCOTFLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1686 | 125.2326 | Purok 4, Brgy. Ligaya, General Santos City, South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2337 | P4POBGLANSAR | NA | P4POBGLANSARFKLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8214 | 125.2025 | Poblacion, GLAN, SARANGANI, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3485 | P7KTANGGENSANSCOT | NA | P7KTANGGENSANSCOTFKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1749 | 125.2217 | CapSite_BrgyKatangawan_GeneralSantosCity | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2335 | PADIDUGLANSAR | NA | PADIDUGLANSARFLWYFKLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8391 | 125.2202 | BrgyPoblacion_GLAN_SARANGANI_2 | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN289 | PAGAGA | NA | PAGAGAFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU MONTAWAL |  | Territory 7 | 7.0764 | 124.7494 | Datu Montawal, Maguindanao | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN290 | PAGALU | NA | PAGALUFHLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PAGALUNGAN |  | Territory 7 | 7.0609 | 124.6993 | Pagalungan_Poblacion, Pagalungan, Maguindanao | MIDSAY | FTAP | AREA 13 | COTABATO 2 | KABACAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1241 | PAGANG | NA | PAGANGFLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALEOSAN |  | Territory 7 | 7.1123 | 124.6034 | Pagangan, Aleosan, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2216 | PAGDTUMONTMGDN | NA | PAGDTUMONTMGDNFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PAGAGAWAN |  | Territory 7 | 7.1104 | 124.7735 | Pagagawan, Pagagawan, Maguindanao | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1415 | PAGLAT | NA | PAGLATFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | GEN. SK. PENDATUN |  | Territory 7 | 6.7808 | 124.7843 | Paglat, Paglat, Maguindanao | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2872 | PAGLUNGPOLOMOSCOT | NA | PAGLUNGPOLOMOSCOTFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2318 | 125.046 | Pagalungan, Polomolok, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1434 | PALIMB | NA | PALIMBFLXDFLX TCFGAPOBPLIMBASKUDFLXOFHK | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | PALIMBANG |  | Territory 7 | 6.2152 | 124.1922 | Palimbang_Poblacion, Palimbang, Sultan Kudarat | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN882 | PALKAN | NA | PALKANFHKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2564 | 124.9677 | Sumbakil, South Cotabato, Philippines | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2213 | PANATANSKUD | NA | PANATANSKUDFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2196 | 124.3551 | Kakar, Sultan Kudarat (Nuling), Maguindanao | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2357 | PANAYSTONINOSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SANTO NIÑO |  | Territory 7 | 6.4914 | 124.6319 | Panay, sto niño, south cotabato | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1207 | PANGYA | NA | PANGYAFLWY TCFGAPANGYAGLANSARFLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.6942 | 125.2922 | Brgy. Pangyan, Glan, Sarangani Pangyan, Glan, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN432 | PARAIS | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4805 | 124.8129 | Paraiso, Koronadal, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN711 | PARANG | PRN_001_GPONA_01 | PARANGDFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PARANG | Poblacion | Territory 7 | 7.3716 | 124.2681 | Parang_Poblacion, Parang, Maguindanao | COTABATO | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN390 | PIGKAW | PGK_001_GPONA_01 | PIGKAWFHKLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIGKAWAYAN |  | Territory 7 | 7.2788 | 124.4258 | Magsaysay St. Pigkawayang_Poblacion III, Pigkawayan, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN857 | PIKIT | PIK_001_GPONA_01 | PIKITFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.05 | 124.6739 | Pikit_Poblacion, Pikit, Cotabato (North Cotabato) | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1942 | Pikit Relay | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.0617 | 124.6772 | Port, Pikit_Poblacion, Pikit, Cotabato (North Cotabato) | MIDSAY | GT | [6 empty] | #N/A
MIN391 | PIKIT2 | NA | PIKIT2FLWYFLWY TCFGADALINGAOENPIKITNCOTFLWYFLWF | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.0797 | 124.662 | Dalingaoen (Lalingaon), Pikit, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1375 | PLM-701 | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2218 | 125.0628 | HUAWEI CABINET PIONEER AVE., CORNER ZENAS ST., PUROK PAYAPA, BRGY. POBLACION, POLOMOLOK, SOUTH COTA | KORONADAL FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1374 | PLM-702 | PLM_702_HYB_01 | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2304 | 125.08 | HUAWEI CABINET POLOMOLOK CANARY ROAD CORNER SAPPHIRE ST., PUROK KAUNLARAN, POLOMOLOK, SOUTH COTABAT | KORONADAL FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN392 | PNOCKI | NA | PNOCKIH | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0099 | 125.2296 | PNOC Kidapawan Ilomavis, City Of Kidapawan, Cotabato (North Cotabato) | KIDAP2 | GT | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2378 | PNONGRANDEBNGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.4571 | 124.7458 | Punong Grande (Barrio 2), Banga, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2209 | POBPRANGMGND | NA | POBPRANGMGNDFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PARANG |  | Territory 7 | 7.0274 | 124.5054 | Making, Parang, Maguindanao | COTABA | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN393 | POBPREROXAS | NA | POBPREROXASFHKLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS |  | Territory 7 | 7.1544 | 125.055 | Purok 3 PresidentRoxasPoblacion, President Roxas, Cotabato (North Cotabato) | KIDAP2 | GT | AREA 12 | COTABATO 1 | KIDAPAWAN | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN198 | POBSARANGGDVOC | NA | POBSARANGGDVOCFKLVWY TCFGAPOBSARANGGDVOCFKLVWY | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | BALOT ISLAND |  | Territory 7 | 5.4118 | 125.4242 | Mabila (Pob.), Saranggani, Davao del Sur | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3479 | POBTACURSKUDCOW | NA | POBTACURSKUDCOWAFLWXYD | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6882 | 124.6707 | Buenaflor, CITY OF TACURONG, SULTAN KUDARAT, REGION XII (SOCCSKSARGEN), MIN | TACURO | GT | [6 empty] | #N/A
MIN2346 | POBTBOLISCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | T'BOLI |  | Territory 7 | 6.2091 | 124.8335 | Barangay Kematu Road, T'Boli, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN710 | POLLOC | PRN_002_GPONA_01 | POLLOCFHKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PARANG |  | Territory 7 | 7.3382 | 124.2396 | Landasan (Sarmiento), Parang, Maguindanao | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN767 | POLOMO | PLM_001_GPONA_01 | POLOMOFHKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2283 | 125.0736 | Polomolok_Poblacion, Polomolok, South Cotabato | KORONADAL FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN433 | POLONU | NA | POLONUDFHLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TUPI |  | Territory 7 | 6.3044 | 124.9758 | Polonuling, Tupi, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1701 | PRK2LANAOKID | NA | PRK2LANAOKIDFKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.025 | 125.076 | National Highway Lanao, Kidapawan City, North Cotabato | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3349 | PRK2POBTUPISCOT | NA | PRK2POBTUPISCOTFLWXYH TCFGAPRK2POBTUPISCOTH | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TUPI |  | Territory 7 | 6.3394 | 124.9432 | Purok 2, Brgy. Poblacion, Tupi, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2242 | PROPRLUTAYNSKUD | NA | NA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LUTAYAN |  | Territory 7 | 6.5933 | 124.8513 | Lutayan, Sultan Kudarat, Philippines | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1700 | PUR14KATANG | NA | PUR14KATANGFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1657 | 125.1974 | Katangawan, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN261 | PURAKA | NA | PURAKAFWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | BALABAGAN | Purakan | Territory 7 | 7.5571 | 124.1228 | Purakan, Balabagan, Lanao Del Sur | COTABATO | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW58 | PURASINSUAMGDNCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU BLAH SINSUAT |  | Territory 7 | 7.2047 | 124.2321 | BRGY. PURA, DATU BLAH SINSUAT, MAGUINDANAO | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN775 | QUIRIN | NA | QUIRINFHLVWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | PRESIDENT QUIRINO |  | Territory 7 | 6.6983 | 124.7255 | Poblacion (Sambulawan), President Quirino, Sultan Kudarat | TACURO | GT | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3441 | QZONBLVDKIDAPNCOTAS | NA | QZONBLVD1KIDAPNCOTASFFFFW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0101 | 125.0907 | Poblacion, CITY OF KIDAPAWAN (Capital), COTABATO (NORTH COTABATO), REGION XII (SOCCSKSARGEN), MIN | KIDAP2 | GT | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3539 | R1LAGAOGENSANSCOTAS | NA | R1LAGAOGENSANSCOTASFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1212 | 125.1893 | Pendatun Ave., Brgy. Dadiangas North, General Santos City, South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN291 | RABAGO | NA | RABAGOXZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.214 | 124.2386 | Rabago St. Rosary Heights II, Cotabato City, Cotabato City | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN378 | RBANIS | NA | RBANISFLXZ | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALAMADA |  | Territory 7 | 7.4902 | 124.5657 | Rangayen, Alamada, Cotabato (North Cotabato) | MIDSAY | PHILTOWER | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1297 | RCOLMB | NA | RCOLMB | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU PAGLAS |  | Territory 7 | 6.726 | 124.9183 | Salendab, Datu Paglas, Maguindanao | TACURO | GT | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN434 | RDFISH | NA | RDFISHFWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Bula | Territory 7 | 6.0808 | 125.1553 | RD Fishing Calumpang, Gen. Santos City (Dadiangas), South Cotabato | GENSAN | GT | [6 empty] | #N/A
MIN398 | RGLAN | NA | RGLANFLWYF | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8009 | 125.1799 | Taluya, Glan, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN609 | RKALAM | NA | RKALAMFLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LEBAK |  | Territory 7 | 6.7394 | 124.1091 | Bolebok, Lebak, Sultan Kudarat | COTABA | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1135 | RMAHAY | NA | RMAHAYFKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS |  | Territory 7 | 7.1976 | 125.0634 | Sitio Mahayag Greenhill, President Roxas, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | KIDAPAWAN | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1406 | ROBGEN | NA | ROBGENFWZ | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1205 | 125.1903 | Robinsons Place Lagao (1st & 3rd), Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1530 | ROSARYH10COT | CTT_007_GPONA_01 | ROSARYH10COTFKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | COTABATO CITY |  | Territory 7 | 7.1986 | 124.2367 | Rosary Heights VI, Cotabato City, Cotabato City | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1761 | ROSARYHT4COT | CTT_001_GPONA_01 | ROSARYHT4COTFKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2127 | 124.248 | Gen. Luna St, Cotabato City, Maguindanao, Philippines | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1529 | ROSARYHT5COT | CTT_006_GPONA_01 | ROSARYHT5COTFKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Rosary Heights V | Territory 7 | 7.2072 | 124.247 | 5th Street, Sero Compound, Rosary Heights V, Cotabato City, Cotabato City | COTABATO | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2225 | ROSARYHT7COTABMGDN | NA | ROSARYHT7COTABMGDNFHKWXY ROSARYHT7COTFHK | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2016 | 124.2462 | BrgyRosaryHeightsVI_CotabatoCity_Maguindanao | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2223 | ROSARYHTXICOTABMGDN | NA | ROSARYHTXICOTABMGDNFKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2025 | 124.2335 | Cotabato City, Maguindanao, Philippines | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2227 | ROXASNINOSCOT (GLIPIKITNCOT) | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 6.4417 | 124.6337 | BrgyBaiSarifinang_BAGUMBAYAN_, Alamada, SULTAN KUDARAT (NULING), MAGUINDANAO, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | KORONADAL FOC | PHILTOWER | AREA 13 | COTABATO 2 | KORONADAL | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1064 | RSOUPI | NA | RSOUPIFLWYZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | UPI |  | Territory 7 | 6.8694 | 124.171 | South Upi Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1458 | RTALTAKGLAN | NA | RTALTAKGLANFLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.612 | 125.337 | Mt. Taltak Cross, Glan, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN859 | RUFINO | CTT_004_GPONA_01 | RUFINOFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | COTABATO CITY |  | Territory 7 | 7.224 | 124.2487 | Rufino Alonzo St Bagua, Cotabato City, Cotabato City | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2232 | SALABACAESPERSKUD | NA | SALABACAESPERSKUDFHKVWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ESPERANZA |  | Territory 7 | 6.6838 | 124.5692 | Brgy.Salabaca,, Esperanza, Sultan Kudarat, Philippines | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1953 | SALIMBAOSKUDMGDN | NA | SALIMBAOSKUDMGDNFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2289 | 124.2592 | Salimbao, Maguindanao, Philippines | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN394 | SALUNA | NA | SALUNAFHKLWXY TCFGASALUNAYMIDSAYNCOTFKLVWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.1554 | 124.4991 | Purok Mauswagon Salunayan, Midsayap, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2733 | SANAGPOBPOLOMOSCOT | NA | SANAGPOBPOLOMOSCOTFKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2183 | 125.075 | Polomolok, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2248 | SANEMANTACUR | NA | SANEMANTACURFHLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6962 | 124.7041 | San Emmanuel, Tacurong, Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN437 | SANFE | TAN_001_GPONA_01 | SANFEFLVWXY TCFGAP2FELIPETANTANSCOTFLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TANTANGAN |  | Territory 7 | 6.5281 | 124.8102 | Purok2 San Felipe, Tantangan, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1404 | SANGEN | NA | SANGENFHLWY TCFGASANJOSEGENSANSCOTFHLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0714 | 125.0247 | San Jose, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1547 | SANISIDROGENSAN | GSN_015_GPONA_01 | SANISIDROGENSANFHKLMWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1425 | 125.1871 | Conel Road, San Isidro Lagao General Santos City South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3433 | SANISIDROKNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.463 | 124.8625 | Purok Mabinuligon, Brgy. San Isidro, Koronadal City, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2302 | SANISIDTAMPAKSCOT | NA | SANISIDTAMPAKSCOTFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TAMPAKAN |  | Territory 7 | 6.4584 | 124.9678 | San Isidro, Tampakan, South Cotabato, Philippines | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2297 | SANJOSBANGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.3522 | 124.8097 | San Jose (Barrio 7), Banga, South Cotabato, Philippines | KORONADAL FOC | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2307 | SANJOSENORALASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | NORALA |  | Territory 7 | 6.5534 | 124.6425 | San Jose | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN444 | SANJSE | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5514 | 124.9054 | Brgy. San Jose,Koronodal City,South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3594 | SANTEASTGENSANSCOTAS | NA | SANTEASTGENSANSCOTASFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.116 | 125.1793 | SC_Shell_BrgyDadiangasEast_GenSanCity | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1562 | SANTONGENSAN | GSN_911_GPONA_01 | SANTONGENSANFHKLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1325 | 125.1315 | San Antonio Village Apopong, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1831 | SAPAKANBUAYANMGDN | NA | SAPAKANBUAYANMGDNFHKLVWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SHARIFF AGUAK |  | Territory 7 | 6.8768 | 124.6029 | Rajah Buayan, Maguindanao, Philippines | COTABA | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1213 | SAPALA | NA | SAPALAFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.0709 | 124.3227 | Sapalan, Datu Odin Sinsuat (Dinaig), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2367 | SAPUMLAPATSAR | NA | SAPUMLAPATSARFL | REGION XII (SOCCSKSARGEN) | SARANGANI | MALAPATAN |  | Territory 7 | 5.9164 | 125.2722 | Sapu Masla, MALAPATAN, SARANGANI, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3195 | SARABIAKNADALSCOT | NA | SARABIAKNADALSCOTFKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4395 | 124.881 | CapSite_BrgySarabia01_KoronadalCity | GENSAN | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN436 | SARAUL | NA | SARAULFHLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4033 | 124.8828 | Purok Maunlad Sarabia (Bo. 8), Koronadal, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN425 | SEBU | NA | SEBUFLHK | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | LAKE SEBU |  | Territory 7 | 6.2287 | 124.7159 | Sitio Dekolon LakeSebu_Poblacion, Lake Sebu, South Cotabato | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2735 | SILWAY7POLOMOSCOT | NA | SILWAY7POLOMOSCOTFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.1773 | 125.1214 | BrgySilway7_ Polomolok_SouthCotabato | KORONADAL FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3604 | SILWAY7POLOMOSCOTEM | NA | SILWAY7POLOMOSCOTEMFHWX | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.16 | 125.1265 | Silway7, Polomolok, South Cotabato | KORONADAL FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1066 | SILWY8 | PLM_005_GPONA_01 | SILWY8FLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.1953 | 125.0848 | Silway 8, Polomolok, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3572 | SINAWALGENSANSCOT | NA | SINAWALGENSANSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1426 | 125.1359 | Brgy. Sinawal, General Santos City, South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2375 | SINGAOKIDAPNCOT | NA | SINGAOKIDAPNCOTFHLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 6.9984 | 125.0603 | Barangay Singao, Kidapawan City, Cotabato, Philippines | KIDAP2 | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2245 | SINOLONTBOLISCOT | NA | SINOLONTBOLISCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | T'BOLI |  | Territory 7 | 6.2628 | 124.809 | Barangay Sinolon, T'Boli, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN292 | SKPEND | NA | SKPENDFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | GEN. SK. PENDATUN |  | Territory 7 | 6.8264 | 124.7523 | Badak, Gen. S. K. Pendatun, Maguindanao | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2224 | SKPENDATUNABCOT | NA | SKPENDATUNABCOTFKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2186 | 124.2574 | Salipada K. Pendatun Ave Ext, Cotabato City, Maguindanao, Philippines | TACURO | PHILTOWER | AREA 13 | COTABATO 2 | TACURONG | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2483 | SMCROXASGSAN | NA | SMCROXASGSANFHKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0557 | 125.1358 | Tambler, General Santos City, South Cotabato, Philippines | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1451 | SMGEN | NA | GTSMSANMIGENSANFNZ2FZFZ SMGENFZ SMGEN2FZ | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1158 | 125.1814 | San Miguel,General Santos City, South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3351 | SNROQUEKNADALSCOT | NA | SNROQUEKNADALSCOTFHKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4622 | 124.8951 | Brgy. San Roque, Koronadal City, South Cotabato | GENSAN | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN279 | SNSUAT | DOS_001_GPONA_01 | SNSUATFHKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.1544 | 124.2202 | Marian Heights Subd., Awang, Datu Odin Sinsuat (Dinaig), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN715 | SOUPI | NA | SOUPIHZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | UPI |  | Territory 7 | 6.8544 | 124.1435 | Pilar, South Upi, Maguindanao | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN395 | SOUSEA | NA | SOUSEAFKWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2231 | 124.2484 | South Seas Complex Don Rufino Alonzo St., CotabatoCity_Poblacion, Cotabato City, Cotabato City | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3730 | SPERVLGAOGENSANSCOT | NA | SPERVLGAOGENSANSCOTFLW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1252 | 125.2041 | Balayo Avenue, Superville Subdivision, Brgy Lagao, General Santos CIty | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1828 | SROQUESKDRAT | NA | SROQUESKDRATFLWXYF | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | PALIMBANG |  | Territory 7 | 6.1625 | 124.272 | San Roque, Palimbang, Sultan Kudarat | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3439 | STACRUZKNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4881 | 124.8366 | CapSite_BrgySantaCruz01_KoronadalCity | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2238 | STCLARAKALAMSKUD | NA | STCLARAKALAMSKUDFLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | KALAMANSIG |  | Territory 7 | 6.5559 | 124.056 | BrgyPagasa_KALAMANSIG_, Alamada, SULTAN KUDARAT (NULING), MAGUINDANAO, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | COTABA | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN768 | STONIN | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SANTO NIÑO |  | Territory 7 | 6.4385 | 124.6716 | SantoNino_Poblacion, Santo Nino, South Cotabato | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3437 | STONINOKNADALSCOT | NA | TCPHTSTONINOKNADALSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4998 | 124.876 | CapSite_BrgySantoNiño_KoronadalCity | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1085 | SUDAPI | NA | SUDAPIFHKLWXYF TCFGASUDAPINKIDAPNCOTFHKLWYFHK | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0256 | 125.1028 | Sudapin, City Of Kidapawan, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN441 | SULIT | NA | SULITFHLWXYZ SULITFHLWXYZH | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2362 | 125.0227 | Sulit, Polomolok, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN293 | SULTAN | NA | SULTANFKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT |  | Territory 7 | 7.2834 | 124.3031 | Simuay/Seashore, Sultan Kudarat (Nuling), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3160 | SUMHTLGENSANSCOTID | NA | SUMHTLGENSANSCOTIDFWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1196 | 125.1907 | Honorio Arriola Street,, Summit Hotels General Santos, Dadiangas East (Pob.), GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN769 | SURALL | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.3792 | 124.7457 | Libertad (Pob.), Surallah, South Cotabato | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1243 | SVBANG | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.4473 | 124.7911 | San Vicente (Barrio 6), Banga, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1556 | SYDNEYHOTEL | NA | SYDNEYHOTELFHKLMWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1059 | 125.1886 | Brgy Lagao (1st & 3rd), General Santos City, South Cotabato | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN452 | TACUR2 | NA | POBTACURSKUDCOWXAFLWXYA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6938 | 124.6827 | Buenaflor, Tacurong, Sultan Kudarat | TACURO | GT | [6 empty] | #N/A
MIN862 | TACURO | TCR_002_GPONA_01 | TACUROFHKLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.694 | 124.6787 | Tacurong Pilot School Tacurong_Poblacion, Tacurong, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2192 | TAKIPNPIKITNORTHCOT | NA | TAKIPNPIKITNORTHCOTFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.094 | 124.6358 | Takipan, Pikit, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN294 | TALAYA | NA | TALAYAFHKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | TALAYAN |  | Territory 7 | 6.9851 | 124.3564 | Midtimbang (Pob.), Talayan, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1498 | TALITAY | NA | TALITAYFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | TALITAY |  | Territory 7 | 7.0359 | 124.3743 | Brgy. Poblacion, Talitay, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN405 | TAMBER | NA | TAMBERFHKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0549 | 125.1023 | Airport Comp., Tambler, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN770 | TAMBLE | NA | TAMBLEFHKLVWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0515 | 125.1367 | Tambler, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2205 | TAMBONANAGDULUNMGDN | GUL_001_GPONA_01 | TAMBONANAGDULUNMGDNFKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | TALAYAN |  | Territory 7 | 6.9754 | 124.3861 | Damablac, Talayan, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2226 | TAMONTAKACOT | NA | TAMONTAKACOTFHKLVWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.1889 | 124.2328 | Tamontaka, Cotabato City, Maguindanao, Philippines | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3221 | TAMONTAKADINAIGMGDN | NA | TAMONTAKADINAIGMGDNFKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT |  | Territory 7 | 7.1673 | 124.2207 | Tamontaka, DATU ODIN SINSUAT (DINAIG), MAGUINDANAO, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN771 | TAMPAK | NA | TAMPAKFHWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TAMPAKAN |  | Territory 7 | 6.4435 | 124.927 | Camagong St. corner Narra Ave., Tampakan_Poblacion, Tampakan, South Cotabato | GENSAN | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN864 | TAMUNT | NA | TAMUNTFHKLVWY | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Tamontaka | Territory 7 | 7.1816 | 124.2243 | Concepcion St. Tamontaka, Cotabato City, Cotabato City | COTABATO | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN772 | TANTAN | NA | TANTANFHKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TANTANGAN |  | Territory 7 | 6.6253 | 124.7473 | Tantangan_Poblacion, Tantangan, South Cotabato | TACURO | GT | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN941 | TAPAYA | NA | TAPAYAFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN MASTURA |  | Territory 7 | 7.3071 | 124.2791 | Tapayan, Sultan Mastura, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN942 | TAVIRAN | NA | TAVIRANFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | KABUNTALAN |  | Territory 7 | 7.1235 | 124.3218 | Lower Taviran, Kabuntalan (Tumbao), Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN439 | TBOLI | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | T'BOLI |  | Territory 7 | 6.2217 | 124.8213 | Lugan Village T'boli_Poblacion, T'Boli, South Cotabato | KORONADAL FOC | PHILTOWER | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2546 | TCAGP8KTANGENSANSCOT | NA | TCAGP8KTANGENSANSCOTLY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1629 | 125.2143 | Purok 8, Brgy. Katangawan, General Santos City, South Cotabato | GENSAN FOC | ALT GLOBAL | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3934 | TCAICLIPPARANGMGDN | NA | TCAICLIPPARANGMGDNFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BARIRA |  | Territory 7 | 7.4693 | 124.3547 | Brgy. Lipawan, Barira, Maguindanao | COTABA | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3936 | TCAICMAKPARANGMGDN | NA | TCAICMAKPARANGMGDNFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PARANG |  | Territory 7 | 7.3852 | 124.2638 | Brgy. Making, Parang, Maguindanao | COTABA | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3931 | TCAICNITPARANGMGDN | NA | TCAICNITPARANGMGDNFLW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PARANG |  | Territory 7 | 7.372 | 125.4526 | Brgy Nituan, Parang, Maguindanao | COTABA | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4187 | TCAICROSARY9COTABMGDN | NA | TCAICROSARY9COTABMGDNFW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.1924 | 124.2383 | Brgy. Rosary Heights IX, Cotabato City, Maguindanao | COTABA | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3771 | TCFGAACMONATUPISCOT | NA | TCFGAACMONATUPISCOTFLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TUPI |  | Territory 7 | 6.3224 | 124.9617 | PUROK 8, BRGY.ACMONAN, TUPI, SOUTH COTABATO | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3926 | TCFGABAGUMIDSAYCOT | NA | TCFGABAGUMIDSAYCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.1894 | 124.4893 | Purok-6, Bagumba,Midsayao, Ncot | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3641 | TCFGABALINDOGKIDAPNCOT | NA | TCFGABALINDOGKIDAPNCOTFW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY | DAPITAN CITY | Territory 7 | 7.0134 | 125.0574 | Purok 7, Brgy. Balindog, Kidapawan City, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3860 | TCFGABANUAGENSANSCOT | NA | TCFGABANUAGENSANSCOTFLW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0396 | 125.1385 | Zone 1, Upper banualan, Brgy Tambler, General Santos City | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3668 | TCFGABLASATACUROSKUD | NA | TCFGABLASATACUROSKUDFLW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6914 | 124.6876 | Belasa Subdivision, Brgy. San Pablo, Tacurong City, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3642 | TCFGABNOLIGANKIDAPCOT | NA | TCFGABNOLIGANKIDAPCOTFLW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0423 | 125.0077 | Km.11, Purok 4, Brgy. Binoligan, Kidapawan City, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3821 | TCFGABUENAFLORTACUROSKUD | NA | TCFGABUENAFLORTACUROSKUDFW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6937 | 124.6674 | Lot 552-G-7. Brgy, Buenaflor, Tacurong City, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3789 | TCFGABULANMIDSAYCOT | NA | TCFGABULANMIDSAYCOTFLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.1586 | 124.5404 | P-1, Central Bulanan, MIDSAYAP, COTABATO | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3786 | TCFGABULOLPIKITCOT | NA | TCFGABULOLPIKITCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.0034 | 124.6906 | Sitio Proper, Bulol, PIKIT, COTABATO | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3898 | TCFGACABALIBUNGCOT | NA | TCFGACABALIBUNGCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | LIBUNGAN |  | Territory 7 | 7.2607 | 124.5385 | Brgy Cabaruyan, Libungan, North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3683 | TCFGACANRYPOLOMOSCOT | NA | TCFGACANRYPOLOMOSCOTFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2441 | 125.0831 | Purok Pagasa Phase 1 Brgy. Cannery, Polomolok, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3889 | TCFGACAPOBTANTANSCOT | NA | TCFGACAPOBTANTANSCOTFLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TANTANGAN |  | Territory 7 | 6.6108 | 124.75 | PUROK CADEN DE AMOR, POBLACION, TANTANGAN, SOUTH COTABATO | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3669 | TCFGACARMETACUROSKUD | NA | TCFGACARMETACUROSKUDFLW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6711 | 124.6851 | Purok Saranay, Brgy. Carmen, Tacurong City, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3774 | TCFGACARPKNADALSCOT | NA | TCFGACARPKNADALSCOTFLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4708 | 124.8758 | Near Santo Nino (Bo. 2), Koronadal City, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3818 | TCFGACNELGENSANSCOT | NA | TCFGACNELGENSANSCOTFLW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1677 | 125.1842 | Brgy. Colonel, General Santos City, South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3888 | TCFGACUYAPTANTANSCOT | NA | TCFGACUYAPTANTANSCOTFLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TANTANGAN |  | Territory 7 | 6.6431 | 124.7384 | PUROK RANG-AY, BRGY. NEW CUYAPO, TANTANGAN, SOUTH COTABATO | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3787 | TCFGADAGUPKBACANCOT | NA | TCFGADAGUPKBACANCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN |  | Territory 7 | 7.122 | 124.8657 | Brgy Dagupan Kabacan North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3877 | TCFGADJAYSURALLSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.3687 | 124.7353 | Brgy. Dajay, Surallah, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3665 | TCFGADLOTILISULANSKUD | NA | TCFGADLOTILISULANSKUDFW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6633 | 124.5554 | Brgy. D'Lotilla, Isulan City, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3958 | TCFGAEDWARTBOLISCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | T'BOLI |  | Territory 7 | 6.2299 | 124.8184 | Brgy Lugan 3, T’BOLI, SOUTH COTABATO | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3776 | TCFGAGENPKNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5029 | 124.8617 | TO FOLLOW | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3758 | TCFGAHARYALKIDAPCOT | NA | TCFGAHARYALKIDAPCOTFLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0075 | 125.0847 | Blk 3, Pendatun St. Pob. Kidapawan City | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3841 | TCFGAILOTANTANSCOT | NA | TCFGAILOTANTANSCOTFLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TANTANGAN |  | Territory 7 | 6.5386 | 124.7978 | BRGY. NEW ILO-ILO, TANTANGAN, SOUTH COTABATO | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3891 | TCFGAILSRAKNADALSCOT | NA | TCFGAILSRAKNADALSCOTFLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4172 | 124.8816 | ILANG-ILANG, BRGY. SARABIA, KORONADAL CITY, SOUTH COTABATO | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4014 | TCFGAINUGUGPIKITCOT | NA | TCFGAINUGUGPIKITCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT | Inug-ug | Territory 7 | 7.0508 | 124.6894 | Brgy. Inug-ug, Pikit, Cotabato (NORTH COTABATO) | MLANG | FTAP | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3729 | TCFGAKALASUYKIDAPNCOT | NA | TCFGAKALASUYKIDAPNCOTFW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0364 | 125.0937 | Purok 2, Brgy Kalasuyan, Kidapawan City,North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3666 | TCFGAKALAW1ISULANSKUD | NA | TCFGAKALAW1ISULANSKUDFW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6184 | 124.6024 | Brgy. Kalawag I (Pob.), Isulan City, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3876 | TCFGAKALAW2ISULANSKUD | NA | TCFGAKALAW2ISULANSKUDFW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ISULAN |  | Territory 7 | 6.6373 | 124.6123 | Capitol East, Kalawag 2, Isulan, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3930 | TCFGAKATAGENSANSCOT | NA | TCFGAKATAGENSANSCOTFLWX | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1514 | 125.2102 | Purok 12, Brgy. Katangawan, General Santos City | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3791 | TCFGAKIGANGMIDSAYCOT | NA | TCFGAKIGANGMIDSAYCOTFHLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.2154 | 124.5636 | Coordinates 7.215325, 124.5636 BrgyKimagango Midsayap | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3747 | TCFGAKRONPOLOMOSCOT | NA | TCFGAKRONPOLOMOSCOTFLW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2486 | 124.9898 | Purok 1−B, Brgy. Koronadal Proper, Polomolok, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3686 | TCFGAKYAGAKBACANCOT | NA | TCFGAKYAGAKBACANCOTFLVWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN | Kayaga | Territory 7 | 7.1156 | 124.7853 | LOT#58, BULIT, DATU MUNTAWAL, Kabacan,NORTH COTABATO | MLANG | FTAP | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3932 | TCFGALAG2GENSANSCOT | NA | TCFGALAG2GENSANSCOTFLWX | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1354 | 125.18 | Brgy. San Isidro, General Santos City | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3320 | TCFGALANAOKIDAPNCOT | NA | TCFGALANAOKIDAPNCOTFW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0342 | 125.0721 | Purok 6F Mangosteen, Brgy. Lanao, Kidapawan City, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3681 | TCFGALIKAMLANGCOT | NA | TCFGALIKAMLANGCOTFLW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | M'LANG |  | Territory 7 | 6.9877 | 124.8911 | P-1,Brgy. Lika, M'lang, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3790 | TCFGALIWAYBANGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.3986 | 124.7596 | Brgy Liwanay Barrio 1, Banga, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3682 | TCFGALNDANPOLOMOSCOT | NA | TCFGALNDANPOLOMOSCOTFLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.3094 | 125.1395 | Purok 5, DAM, Brgy. Landan, Polomolok, South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3847 | TCFGALOOYSTHUPIMGDN | NA | TCFGALOOYSTHUPIMGDNFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SOUTH UPI |  | Territory 7 | 6.9321 | 124.1565 | Brgy. Looy, South Upi, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3906 | TCFGALUMAPOLOMOSCOT | NA | TCFGALUMAPOLOMOSCOTFLW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2133 | 125.0389 | Brgy. Lumakil, Polomolok, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3822 | TCFGALUPOBSURALLSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.3754 | 124.756 | Lubaton Subd, Poblacion, Surallah, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3935 | TCFGAMABUGENSANSCOT | NA | TCFGAMABUGENSANSCOTFLW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1822 | 125.1496 | Brgy. Mabuhay, General Santos City, South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3785 | TCFGAMACABUPIKITCOT | NA | TCFGAMACABUPIKITCOTFHLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.0339 | 124.6379 | Brgy. Balong | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3781 | TCFGAMACASMIDSAYCOT | NA | TCFGAMACASMIDSAYCOTFLW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.0357 | 124.5216 | Brgy Macasendeg, Midsayap North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3792 | TCFGAMALAYBANGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.4723 | 124.7499 | Barrio 9 BrgyMalaya Banga South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3757 | TCFGAMANAULPIKITCOT | NA | TCFGAMANAULPIKITCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.0462 | 124.6188 | Sitio Mahad, Brgy. Manaulanan, Pikit, North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3350 | TCFGAMASUNGENSANSCOT | NA | TCFGAMASUNGENSANSCOTFLW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1438 | 125.1742 | Purok Masunurin, San Isidro, General Santos City | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3372 | TCFGAMAUNPOLOMOSCOT | NA | TCFGAMAUNPOLOMOSCOTFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.1916 | 125.0965 | Purok Maunlad Brgy. Silway8, Polomolok, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4017 | TCFGAMBUHYGENSANSCOT | NA | TCFGAMBUHYGENSANSCOTFLW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1549 | 125.1484 | Brgy. Mabuhay, GENERAL SANTOS CITY (DADIANGAS), SOUTH COTABATO | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3773 | TCFGAMIDP1PIGKAWCOT | NA | TCFGAMIDP1PIGKAWCOTFLW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIGKAWAYAN |  | Territory 7 | 7.2973 | 124.4272 | Midpapan 1, Pigcawayan, North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3782 | TCFGAMLAMOKBACANCOT | NA | TCFGAMLAMOKBACANCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN |  | Territory 7 | 7.0672 | 124.8679 | Malamote KABACAN, COTABATO (NORTH COTABATO) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3780 | TCFGAMOLYSURALLSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH |  | Territory 7 | 6.3649 | 124.706 | Brgy Moloy, Surallah South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3732 | TCFGAMORAKNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5224 | 124.8161 | TO FOLLOW | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3772 | TCFGANAMNKNADALSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.5229 | 124.8616 | TO FOLLOW | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3784 | TCFGANOANGMIDSAYCOT | NA | TCFGANOANGMIDSAYCOTFKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.2457 | 124.5568 | Brgy Anonang, Midsayap North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3346 | TCFGANUANGANKIDAPNCOT | NA | TCFGANUANGANKIDAPNCOTFW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0111 | 125.1061 | Purok 5, Brgy Nuangan, Kidapawan City, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3670 | TCFGANWISATACUROSKUD | NA | TCFGANWISATACUROSKUDFLW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6753 | 124.6699 | Purok Sampaguita, Brgy. New Isabela, Tacurong City, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3663 | TCFGAP17MAGENSANSCOT | NA | TCFGAP17MAGENSANSCOTFLWX | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1758 | 125.1445 | Purok 17, Brgy. Mabuhay, General Santos City, South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3751 | TCFGAP2POBCARMENCOT | NA | TCFGAP2POBCARMENCOTFLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CARMEN |  | Territory 7 | 7.1982 | 124.795 | Purok 2, Poblacion, Carmen, North Cotabato | KIDAP2 | FTAP | AREA 13 | COTABATO 2 | KIDAPAWAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3643 | TCFGAP5BALINKIDAPCOT | NA | TCFGAP5BALINKIDAPCOTFLW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.021 | 125.0656 | Purok 5B, Brgy. Balindog, Kidapawan City, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3744 | TCFGAPACOKIDAPCOT | NA | TCFGAPACOKIDAPCOTFLWX | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0329 | 125.0495 | Purok Pomelo,Brgy. Paco, Kidapawan City | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3745 | TCFGAPAGASAMLANGCOT | NA | TCFGAPAGASAMLANGCOTFHLWX | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | M'LANG |  | Territory 7 | 6.9198 | 124.969 | Purok 2-A, PAG-ASA,MLANG,NORTHCOTABATO | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3907 | TCFGAPALKPOLOMOSCOT | NA | TCFGAPALKPOLOMOSCOTFLW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2946 | 125.0357 | Purok 5, Palkan, Polomolok, SCOT | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3843 | TCFGAPOB1NORALASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | NORALA |  | Territory 7 | 6.5131 | 124.6577 | PUROK BLESS, BRGY. POBLACION, NORALLAH, SOUTH COTABATO | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3684 | TCFGAPOB1POLOMOSCOT | NA | TCFGAPOB1POLOMOSCOTFLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2315 | 125.0649 | Purok Malinawon, Brgy. Poblacion, Polomolok, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3824 | TCFGAPOB2MIDSAYCOT | NA | TCFGAPOB2MIDSAYCOTFLW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.1851 | 124.5399 | 3762-Z-5-B-1 , Poblacion, Midsayap, North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3890 | TCFGAPOB2NORALASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | NORALA |  | Territory 7 | 6.5255 | 124.654 | BRGY. POBLACION, SOUTH COTABATO | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3685 | TCFGAPOB2POLOMOSCOT | NA | TCFGAPOB2POLOMOSCOTFLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2277 | 125.0841 | Purok Immaculate Brgy. Poblacion, Polomolok, South Cotabato | KORONADAL FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3823 | TCFGAPOB4MIDSAYCOT | NA | TCFGAPOB4MIDSAYCOTFLW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.1886 | 124.5286 | 3904-B, Poblacion, Midsayap, North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4183 | TCFGAPOB8MIDSAYCOT | NA | TCFGAPOB8MIDSAYCOTLY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.2119 | 124.5381 | Brgy. Poblacion 8, Midsayap, North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4167 | TCFGAPOBALABELSAR | NA | TCFGAPOBALABELSARFW | REGION XII (SOCCSKSARGEN) | SARANGANI | ALABEL |  | Territory 7 | 6.1038 | 125.2952 | Brgy. Poblacion, Alabel, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3959 | TCFGAPOBLASNIÑOSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SANTO NIÑO |  | Territory 7 | 6.4312 | 124.6755 | Purok Lapu-lapu, Sto. Niño, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3924 | TCFGAPOBMAGPETCOT | NA | TCFGAPOBMAGPETCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MAGPET |  | Territory 7 | 7.0985 | 125.1167 | Purok Maligaya, Poblacion, Magpet, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | KIDAPAWAN | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3783 | TCFGAPULAPIKITCOT | NA | TCFGAPULAPIKITCOTFLW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.0193 | 124.567 | Sitio Bliss, Paidu Pulangi, PIKIT, COTABATO | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3440 | TCFGAREYPOBBANGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.4297 | 124.7698 | Brgy. Reyes (Pob.), Banga, South Cotabato | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3793 | TCFGASADANMIDSAYCOT | NA | TCFGASADANMIDSAYCOTFHLWX | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.1901 | 124.549 | Brgy Sadaan, Midsayap North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3721 | TCFGASAGU2MKLALANCOT | NA | TCFGASAGU2MKLALANCOTFW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MAKILALA |  | Territory 7 | 6.9914 | 125.0814 | Brgy. Saguing, Makilala, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3743 | TCFGASANGATMLANGCOT | NA | TCFGASANGATMLANGCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | M'LANG |  | Territory 7 | 6.9278 | 124.8864 | P-5, Sangat, Mlang, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3794 | TCFGASJOSEBANGASCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA |  | Territory 7 | 6.3695 | 124.8105 | Purok Magsaysay, San Jose (Barrio 7), BANGA, SOUTH COTABATO, REGION XII (SOCCSKSARGEN), MIN | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3746 | TCFGASMBAGMLANGCOT | NA | TCFGASMBAGMLANGCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | M'LANG |  | Territory 7 | 6.8979 | 124.9323 | Purok Sambag, New Rizal, Mlang, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3925 | TCFGATAKUNLSEBUSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | LAKE SEBU |  | Territory 7 | 6.2137 | 124.6975 | SITIO T’BONG, BRGY. TAKUNEL, LAKE SEBU, SOUTH COTABATO | KORONADAL FOC | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3788 | TCFGATLANPIKITCOT | NA | TCFGATLANPIKITCOTFLWY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT |  | Territory 7 | 7.141 | 124.692 | Brgy Tinutulan, Pikit North Cotabato | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3667 | TCFGAZ6SPATACUROSKUD | NA | TCFGAZ6SPATACUROSKUDFLW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.7016 | 124.6881 | Zone 6, Purok Liwayway, Brgy. San Pablo, Tacurong City, Sultan Kudarat | TACURO | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4151 | TCISBUSOKBAGUMBSKUD | NA | TCISBUSOKBAGUMBSKUDLY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | BAGUMBAYAN |  | Territory 7 | 6.4914 | 124.6004 | Brgy. Busok, Bagumbayan, Sultan Kudarat | TACURO | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4184 | TCISCALUMGENSANSCOT | NA | TCISCALUMGENSANSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.0756 | 125.1398 | Brgy. Calumpang, General Santos City, South Cotabato | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4124 | TCISCANRY1POLOMOSCOT | NA | TCISCANRY1POLOMOSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2375 | 125.0981 | Brgy. Cannery Site, Polomolok, South Cotabato | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4196 | TCISCTYHTS1GENSANSCOT | NA | TCISCTYHTS1GENSANSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1253 | 125.1669 | Brgy. City Heights, General Santos City, South Cotabato | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4197 | TCISCTYHTS2GENSANSCOT | NA | TCISCTYHTS2GENSANSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1299 | 125.1599 | Brgy. City Heights, General Santos City, South Cotabato | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4083 | TCISKAPAYBAGUMBSKUD | NA | TCISKAPAYBAGUMBSKUDLY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | BAGUMBAYAN |  | Territory 7 | 6.5699 | 124.563 | Purok Dalisay, Brgy. Kapaya, Bagumbayan, Sultan Kudarat | TACURO | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4186 | TCISLBANGALGENSANSCOT | NA | TCISLBANGALGENSANSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1014 | 125.1564 | Brgy. Labangal, General Santos City, South Cotabato | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4165 | TCISMALDAGMALUNGSAR | NA | TCISMALDAGMALUNGSARFW | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON |  | Territory 7 | 6.3127 | 125.2449 | Brgy. Malandag, Malungon, Sarangani | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4199 | TCISSANISI2GENSANSCOT | NA | TCISSANISI2GENSANSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1532 | 125.1664 | Brgy. San Isidro (Lagao 2nd), General Santos City, South Cotabato | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4153 | TCISSEPAKABAGUMBSKUD | NA | TCISSEPAKABAGUMBSKUDLY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | BAGUMBAYAN |  | Territory 7 | 6.4198 | 124.6532 | Brgy. South Sepaka, Bagumbayan, Sultan Kudarat | TACURO | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3995 | TCLBSKISANTMKLALACOT | NA | TCLBSKISANTMKLALACOTFW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MAKILALA |  | Territory 7 | 6.9211 | 125.1579 | Brgy. Kisante, Makilala, North Cotabato | KIDAP2 | LDIC | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3895 | TCTISANIELKIDAPCOT | NA | TCTISANIELKIDAPCOTFW | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0181 | 125.0866 | Saniel Subd., Poblacion, Kidapawan, North Cotabato | KIDAP2 | TIGER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2231 | TELAFASCOLOMSKUD | NA | TELAFASCOLOMSKUDFHKLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | COLUMBIO |  | Territory 7 | 6.6318 | 124.9736 | Telafas, Columbio, Sultan Kudarat, Philippines | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN440 | TIBAO | NA | TCFGATIBAOMLANGNCOTFHKLWY TIBAOFHKLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MLANG |  | Territory 7 | 7.0219 | 124.8939 | Tibao, M'Lang, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2325 | TINOTOMAASIMSAR | NA | TINOTOMAASIMSARFLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | MAASIM |  | Territory 7 | 5.8987 | 125.0758 | BRGY. TINOTO, MAASIM, SARANGANI | GENSAN FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN424 | TNAGACGENSAN | NA | TCFGAP3TNAGCNGENSANSCOTFHLWY TNAGACGENSANFHLWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.2091 | 125.2407 | Purok 3 Tinagacan, Gen. Santos City (Dadiangas), South Cotabato | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN443 | TOPLAN | NA | TCFGATOPLANKNADALSCOTFHKLWY TOPLANFHKLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4813 | 124.9365 | Zulueta (Bo. 7), Koronadal, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3436 | TOPLANDKNADALSCOT | NA | TOPLANDKNADALSCOTFKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | KORONADAL CITY |  | Territory 7 | 6.4836 | 124.9178 | CapSite_BrgyZulueta01_KoronadalCity | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1456 | TUKARLY | NA | TUKARLYFHKWY | REGION XII (SOCCSKSARGEN) | SARANGANI | KIAMBA |  | Territory 7 | 5.9906 | 124.6109 | Communal Planters MPC Tuka area Badtasan, Kiamba, Sarangani | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2229 | TUKASKUD | NA | TUKASKUDFLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | BAGUMBAYAN |  | Territory 7 | 6.5189 | 124.5875 | Hon. Louie Gilo Purok Santan, Tuka, Bagumbayan, Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN396 | TULUNA | TUL_001_GPONA_01 | TULUNAFHLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | TULUNAN | Sibsib | Territory 7 | 6.8241 | 124.8834 | Sibsib, Tulunan, Cotabato (North Cotabato) | MLANG | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2241 | TUMIAOSKUD | NA | TUMIAOSKUDFHLWXY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LAMBAYONG |  | Territory 7 | 6.7576 | 124.6698 | Purok 2, Tumiao (Tinaga), Lambayong (Mariano Marcos), Sultan Kudarat | TACURO | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN773 | TUPI | TUP_001_GPONA_01 | TUPIFKLVWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TUPI |  | Territory 7 | 6.3321 | 124.9532 | Tupi_Poblacion, Tupi, South Cotabato | KORONADAL FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2368 | TUYANMALAPATSAR | NA | TUYANMALAPATSARFLWY | REGION XII (SOCCSKSARGEN) | SARANGANI | MALAPATAN |  | Territory 7 | 5.9988 | 125.2926 | Brgy Tuyan, Malapatan, Sarangani Province | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2185 | UGALINGANCARNCOT | NA | UGALINGANCARNCOTFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CARMEN |  | Territory 7 | 7.1471 | 124.8017 | Sayre Hwy, Carmen, Cotabato, Philippines | KIDAP2 | PHILTOWER | AREA 13 | COTABATO 2 | KIDAPAWAN | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN717 | UPI | NA | UPIFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | UPI |  | Territory 7 | 7.0142 | 124.1585 | Nuro Poblacion, Upi, Maguindanao | COTABA | PHILTOWER | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN295 | UPI2 | NA | UPI2FLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | UPI |  | Territory 7 | 7.0546 | 124.1471 | Kibleg, Upi, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2734 | UPPERKLNANPOLOMOSCOT | NA | UPPERKLNANPOLOMOSCOTFHLWXY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.211 | 125.1181 | Upper Klinan Road, Polomolok, South Cotabato, Philippines | KORONADAL FOC | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN389 | VAVIDA | NA | VAVIDAFHLWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MLANG |  | Territory 7 | 6.9286 | 124.994 | Nueva Vida, M'Lang, Cotabato (North Cotabato) | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1637 | VERANZAMALL | NA | VERANZAMALLFKWY | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1161 | 125.188 | VeranzaMall BulaLagao Road, Gen. Santos City, South Cotabato | GENSAN FOC | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1299 | VLRICA | MDS_003_GPONA_01 | TCFGAVLRICAMIDSAYNCOTFLVWY VLRICAFHKLVWXY | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP |  | Territory 7 | 7.2236 | 124.5314 | Abaga, Libungan, Cotabato (North Cotabato) | MIDSAY | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN296 | ZENAID | NA | TCFGAZENAIDCOTABMGDNFLVWY ZENAIDFKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.1932 | 124.2457 | Moon St. Notre Dame Village, Tamontaka, Cotabato City, Cotabato City | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3347 | POB3LEBAKSKUD | NA | POB3LEBAKSKUDFW | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | Lebak |  | Territory 7 | 6.6317 | 124.0658 | Brgy. Poblacion III, Lebak, Sultan Kudarat | COTABA | FTAP | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4084 | TCISKEYTOLEBAKSKUD | NA | TCISKEYTOLEBAKSKUDLY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LEBAK |  | Territory 7 | 6.6651 | 124.2613 | Brgy. Keytodak, Lebak, Sultan Kudarat | COTABA | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4179 | TCISSANPABTACUROSKUD | NA | TCISSANPABTACUROSKUDLY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6842 | 124.6913 | Brgy. San Pablo, City of Tacurong, Sultan Kudarat | TACURO | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4275 | TCISILAYAGLANSAR | NONE | TCISILAYAGLANSARFW | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN |  | Territory 7 | 5.8203 | 125.2256 | Brgy. Ilaya, Glan, Sarangani | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4122 | TCAICPOBBULUANMGDN | NA | TCAICPOBBULUANMGDNFW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BULUAN |  | Territory 7 | 6.7145 | 124.7824 | Brgy. Poblacion, Buluan, Maguindanao | TACURO | UNITY | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4198 | TCISFATIMAGENSANSCOT | NA | TCISFATIMAGENSANSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) |  | Territory 7 | 6.0767 | 125.1192 | Brgy. Fatima, General Santos City, South Cotabato | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4200 | TCISSANISI3GENSANSCOT | NA | TCISSANISI3GENSANSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) |  | Territory 7 | 6.1358 | 125.1661 | Brgy. San Isidro (Lagao 2nd), General Santos City, South Cotabato | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3720 | TCFGASAGUINGMKLALANCOT | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | Makilala |  | Territory 7 | 6.9783 | 125.0812 | Brgy. Saguing, Makilala, Cotabato | KIDAP2 | FRONTIER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4127 | TCEDCP1SANISGENSANSCOT | NA | TCEDCP1SANISGENSANSCOTFW | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) |  | Territory 7 | 6.1446 | 125.1534 | Purok 1, Brgy.San Isidro (Lagao 2nd),GENERAL SANTOS CITY (DADIANGAS),SOUTH COTABATO | GENSAN FOC | EDOTCO | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2525 | TCAICHEIGHTS2COTABMGDN | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2188 | 124.2466 | Rosary Heights II, COTABATO CITY, COTABATO CITY (Not a Province) | COTABA | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2689 | KIGANSTHUPIMGDN | NA | KIGANSTHUPIMGDNFW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SOUTH UPI |  | Territory 7 | 6.8599 | 124.2519 | Brgy. Kigan, Upi, Maguindanao | COTABA | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4195 | TCISDDIAWESGENSANSCOT | NA | TCISDDIAWESGENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) |  | Territory 7 | 6.1071 | 125.1676 | Brgy. Dadiangas West, General Santos City, South Cotabato | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4652 | TCAICPOBPOLOMOSCOT | NA | TCAICPOBPOLOMOSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2233 | 125.0617 | Brgy. Poblacion, Polomolok, South Cotabato | GENSAN FOC | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4620 | TCAICLABANGGENSANSCOT | NA | TCAICLABANGGENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) |  | Territory 7 | 6.1107 | 125.1418 | Lot 4 Blk 3, Doña Soledad Subd, Brgy Labangal, General Santos City | GENSAN FOC | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4259 | KLANGANCOTABMGDNLEGO_D | NA | KLANGANCOTABMGDNLEGO_D | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2019 | 124.1669 | Grand Mosque, Brgy. Kalanganan II, Cotabato City, Maguindanao | TAMONTAKA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3840 | TCFGAPOBLAKIDAPCOT | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KIDAPAWAN CITY |  | Territory 7 | 7.0011 | 125.0881 | Poblacion, Kidapawan, North Cotabato | KIDAP2 | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4146 | TCISBARURAOLEBAKSKUD | NA | TCISBARURAOLEBAKSKUDLY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LEBAK |  | Territory 7 | 6.6589 | 124.0727 | Brgy. Barurao, Lebak, Sultan Kudarat | COTABA | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4080 | TCISBASAKLEBAKSKUD | NA | NA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LEBAK |  | Territory 7 | 6.7191 | 124.1467 | Brgy. Basak, Lebak, Sultan Kudarat | COTABA | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4150 | TCISKAYUPOKIAMBASAR | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | KIAMBA |  | Territory 7 | 5.9299 | 124.754 | Brgy. Kayupo, Kiamba, Sarangani | GENSAN FOC | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4090 | TCISPURIKLEBAKSKUD | NA | NA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LEBAK |  | Territory 7 | 6.6868 | 124.0773 | Brgy. Purikay, Lebak, Sultan Kudarat | COTABA | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4091 | TCISSALAMLEBAKSKUD | NA | TCISSALAMLEBAKSKUDLY | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LEBAK |  | Territory 7 | 6.6071 | 124.0655 | Brgy. Salaman, Lebak, Sultan Kudarat | COTABA | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4158 | TCISCALEANTACUROSKUD | NA | NA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | TACURONG CITY |  | Territory 7 | 6.6632 | 124.666 | Brgy. Calean, Tacurong City, Sultan Kudarat | TACURO | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4614 | TCAICMATINEZCOTABMGDN | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.2209 | 124.252 | #4 Notre Dame Ave., Brgy Martinez, Cotabato City, Maguindanao | COTABA | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3819 | TCLDCMASIAGBAGUMBSKUD | NA | NA | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | BAGUMBAYAN |  | Territory 7 | 6.4431 | 124.4498 | Sitio San Vicente, Masiag, Bagumbayan, Sultan Kudarat | TACURO | LDIC | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3354 | TCAGTAMBILKIAMBASAR | NA | NA | REGION XII (SOCCSKSARGEN) | SARANGANI | KIAMBA |  | Territory 7 | 5.9688 | 124.6736 | Brgy. Tambilil, Kiamba, Sarangani | GENSAN FOC | ALT GLOBAL | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3857 | TCLDCPOB2PARANGMGDN | NA | TCLDCPOB2PARANGMGDNFW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PARANG |  | Territory 7 | 7.3755 | 124.2617 | BRGY POBLACION 02 PARANG MAGUINDANAO | COTABA | LDIC | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4131 | TCFGAAPOPON4GENSANSCOT | NA | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.127 | 125.1341 | Brgy.Apopong,GENERAL SANTOS CITY (DADIANGAS),SOUTH COTABATO | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4132 | TCFGABALUANGENSANSCOT | Na | NA | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1299 | 125.2191 | Brgy.Baluan,GENERAL SANTOS CITY (DADIANGAS),SOUTH COTABATO | GENSAN FOC | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4248 | TCEDCWADYABANINCOT | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | BANISILAN |  | Territory 7 | 7.5469 | 124.6938 | Wadya, BANISILAN, COTABATO (NORTH COTABATO) | MIDSAY | EDOTCO | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4249 | TCEDCNEWCEBPROXASNCOT | NA | NA | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS |  | Territory 7 | 7.098 | 125.0415 | New Cebu, PRESIDENT ROXAS, COTABATO | KIDAP2 | EDOTCO | AREA 12 | COTABATO 1 | KIDAPAWAN | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3830 | MAROGONGLDSCOW | NA | MAROGONGLDSTEMP | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MAROGONG | Marogong Proper (Pob.) | Territory 8 | 7.6775 | 124.1502 | Marogong Proper (Pob.), MAROGONG, LANAO DEL SUR, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | COTABATO | GT | [6 empty] | #N/A
MIN4359 | KLANGANCOTABMGDNLEGO | NA | KLANGANCOTABMGDNLEGO | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | COTABATO CITY |  | Territory 7 | 7.193 | 124.217 | Brgy. Kalanganan II, Cotabato City, Maguindanao | COTABA | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3030 | RUMIBARIRAMGDN | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BARIRA | Rominimbang | Territory 7 | 7.409 | 124.3517 | Brgy. Ruminimbang, Barira, Maguindanao | COTABATO | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN1697 | AGUADAMISOCC | NA | AGUADAMISOCCFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1523 | 123.8508 | Circumferencial Rd, Brgy. Aguada, Ozamis City Misamis Occidental | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1643 | AGUADAOZAMIS | NA | AGUADAOZAMISFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.152 | 123.8445 | Aguada Poblacion 50th District, Ozamis City Misamis Occidental | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN618 | ALICIA | NA | ALICIAFHLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | ALICIA |  | Territory 8 | 7.5068 | 122.9424 | Alicia_Poblacion, Alicia, Zamboanga Sibugay | MIMELD | GT | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN297 | ALORAN | ALR_001_GPONA_01 | ALORANFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | ALORAN |  | Territory 8 | 8.4183 | 123.8214 | Dalisay, Aloran, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN790 | AURORA | AUR_001_GPONA_01, AUR_001_GPONA_02 | AURORAFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | AURORA |  | Territory 8 | 7.9503 | 123.586 | Zamora St. Aurora_Poblacion, Aurora, Zamboanga Del Sur | TUBOD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1183 | BA2SI | NA | BA2SIFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | SIAY |  | Territory 8 | 7.7505 | 122.8298 | Batu, Siay, Zamboanga Sibugay | IPIL FOC | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN649 | BACOLD | BCO_001_GPONA_01 | BACOLDFHLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | BACOLOD |  | Territory 8 | 8.1903 | 124.0182 | Poblacion Bacolod, Bacolod, Lanao Del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN530 | BACUNG | NA | BACUNGFHKLWXY TCFGAPOBBCUNGAZDNFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | BACUNGAN |  | Territory 8 | 8.1556 | 122.9262 | Bacungan (Pob.), Bacungan (Leon T. Postigo), Zamboanga Del Norte | DAPITAN | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 63 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN309 | BAGAKY | OZA_007_GPONA_01 | BAGAKYFLWYFLWY TCFGABAGAKAYOZAMISMOCCFLWYLYFL | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1452 | 123.8026 | Bagakay, Ozamis City, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1592 | BALANGASAN | PGD_010_GPONA_01 | BALANGASANFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8223 | 123.4305 | HDMF Balangasan, Pagadian City Zamboanga del Sur | TUBOD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN298 | BALIA | NA | BALIAFLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | BALIANGAO |  | Territory 8 | 8.6509 | 123.6064 | Sitio Napiot Misom, Baliangao, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN576 | BALINT | PGD_015_GPONA_01 | BALINTFHLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8263 | 123.416 | Purok Salinsing Balintawak, Pagadian City, Zamboanga Del Sur | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN700 | BALOI | NA | BALOIFHKLVWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | BALOI |  | Territory 8 | 8.1097 | 124.2272 | Nangka, Baloi, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1332 | BALSIAORLY | NA | BALSIAORLYFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | BALIGUIAN |  | Territory 8 | 7.767 | 122.156 | Sitio 12 Nonoyan, Baliguian, Zamboanga Del Norte | IPIL | PHILTOWER | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1696 | BANADERMISOR | OZA_006_GPONA_01 | BANADERMISORFHKLWDY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1483 | 123.8309 | Purok 1 Banadero (Pob.), Ozamis City, Misamis Occidental | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1519 | BANALEPGDIAN | NA | BANALEPGDIANFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8352 | 123.422 | Banale, Pagadian City, Zamboanga Del Sur | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN701 | BAROY | BRY_001_GPONA_01 | BAROYFHLVWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | BAROY |  | Territory 8 | 8.0222 | 123.7862 | Baroy_Poblacion, Baroy, Lanao Del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1232 | BAUYA | NA | BAUYAFHKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | SULTAN NAGA DIMAPORO |  | Territory 8 | 7.726 | 123.7867 | Bauyan, Sultan Naga Dimaporo (Karomatan), Lanao Del Norte | TUBOD | GT | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN542 | BAYOG | NA | BAYOGFHLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | BAYOG |  | Territory 8 | 7.8543 | 123.0466 | Bayog_Poblacion, Bayog, Zamboanga Del Sur | MIMELD | PHILTOWER | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1504 | BIASONGDIPOL | NA | BIASONGDIPOLFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5898 | 123.3447 | Dipolog Airport Biasong (Pob.), Dipolog City, Zamboanga Del Norte | DAPITAN | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1845 | BIGAMISOR | NA | BIGAMISORFLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LUGAIT |  | Territory 8 | 8.3551 | 124.261 | Brgy Biga, Lugait Misamis Oriental | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN640 | BIGONG | NA | BIGONGFHWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | TIGBAO |  | Territory 8 | 7.8313 | 123.3137 | Begong, Tigbao, Zamboanga Del Sur | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN260 | BINIDA | NA | BINIDAFLWFLW TCFGARANAOBINIDALDSFLWFWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | BINIDAYAN |  | Territory 8 | 7.7999 | 124.1565 | BubongaRanao, Binidayan, Lanao Del Sur | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1782 | BINONIZDN | NA | BINONIZDNFLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | GODOD |  | Territory 8 | 8.0636 | 122.8012 | Baluno, Godod, Zamboanga Del Norte | DAPITAN | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 64 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN346 | BLGIAN | NA | BLGIANFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | BALIGUIAN |  | Territory 8 | 7.8062 | 122.1457 | Baliguian_Poblacion, Baliguian, Zamboanga Del Norte | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN300 | BOCATO | NA | BOCATOFHKLWY TCFGAP3BOCATANGUIBMOCCFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TANGUB CITY |  | Territory 8 | 8.048 | 123.6751 | Purok 3 Bocator, Tangub City, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1708 | BOGOPAGZDS | NA | BOGOPAGZDSFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.866 | 123.429 | Bogo Bogo, Pagadian City, Zamboanga Del Sur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1204 | BPINES | NA | BPINESFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY |  | Territory 8 | 8.4486 | 123.8061 | Purok No 5 Pines, Oroquieta City, Misamis Occidental | CLAMBA | GT | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2266 | DISUDSINDANZDN | NA | DISUDSINDANZDNFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SINDANGAN |  | Territory 8 | 8.2472 | 122.9997 | Brgy. Disud, Sindangan, Zamboanga del Norte, Philippines | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 65 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN299 | BTIBOT | NA | BTIBOTFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | SAPANG DALAGA |  | Territory 8 | 8.5751 | 123.5866 | Purok 2 Bitibut, Sapang Dalaga, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2321 | BUALANTUBODLDN | NA | BUALANTUBODLDNFKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | TUBOD |  | Territory 8 | 7.9868 | 123.924 | Brgy. Bualan,, Tubod, Lanao del Norte, Philippines | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2717 | BUENAVSTAPGDIANZDS | NA | BUENAVSTAPGDIANZDSFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8236 | 123.3929 | Pagadian City, Zamboanga del Sur, Philippines | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1777 | BULAWANZSIB | NA | BULAWANZSIBFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | PAYAO |  | Territory 8 | 7.6493 | 122.8214 | Bulawan, Payao, Zamboanga Sibugay | MIMELD | GT | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1205 | BURUUN | NA | BURUUNFHKLWXY TCFGABURUUNILIGANLDNFHKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1845 | 124.1765 | Buruun, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN811 | BUUG | BUG_001_GPONA_01 | BUUGFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | BUUG |  | Territory 8 | 7.7324 | 123.0559 | Purok 6 Manlin, Buug, Zamboanga Sibugay | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN543 | BUUG2 | NA | BUUG2FLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | BUUG |  | Territory 8 | 7.7097 | 123.0709 | Buug_Poblacion, Buug, Zamboanga Sibugay | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1099 | BVILLA | NA | BVILLAFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY |  | Territory 8 | 8.4724 | 123.7808 | Villaflor, Oroquieta City, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2320 | CABASAGNLALALDN | NA | CABASAGNLALALDNFLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | LALA |  | Territory 8 | 7.9615 | 123.8019 | Napolan,Pagadian City | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN267 | CABILI | NA | TCFGACEANURILIGANLDNFKLVDWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2144 | 124.2257 | Camague Highway, Ceanuri Subd., Tubod, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN653 | CAMPAU | NA | CAMPAUFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | AURORA |  | Territory 8 | 7.9837 | 123.5488 | Campo Uno, Aurora, Zamboanga Del Sur | TUBOD | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1725 | CAWACAWAPOB | DPT_001_GPONA_01 | CAWACAWAPOBFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.664 | 123.4266 | Sinonoc, Dapitan City, Zamboanga Del Norte | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN718 | CLAMBA | CBA_001_GPONA_01 | CLAMBAFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | CALAMBA |  | Territory 8 | 8.5609 | 123.6462 | Calamba_Northern Poblacion, Calamba, Misamis Occidental | CLAMBA | GT | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN719 | CLARIN | CLR_001_GPONA_01, CLR_001_GPONA_02 | CLARINFHKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | CLARIN |  | Territory 8 | 8.2015 | 123.8632 | Clarin_Poblacion II, Clarin, Misamis Occidental | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1184 | COMLOY | NA | COMLOYZ | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LILOY |  | Territory 8 | 8.089 | 122.6739 | Maigang, Liloy, Zamboanga Del Norte | IPIL | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 66 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN348 | COMPRA | NA | COMPRAFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LILOY |  | Territory 8 | 8.0459 | 122.6886 | Compra, Liloy, Zamboanga Del Norte | IPIL | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 67 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN302 | CONCEP | NA | CONCEPFSFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | CONCEPCION |  | Territory 8 | 8.4218 | 123.6071 | Concepcion_Poblacion, Concepcion, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2317 | CONCEPKBASALZS | NA | CONCEPKBASALZSFKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | KABASALAN |  | Territory 8 | 7.7773 | 122.8009 | Concepcion (Balungis), Kabasalan, Zamboanga Sibugay, Philippines | MIMELD | PHILTOWER | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN570 | CROSMO | NA | CROSMOFHKLWXY TCFGABOBONGANLIARGOZDSFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.9913 | 123.4864 | Eastern Bobongan, Ramon Magsaysay (Liargo), Zamboanga Del Sur | TUBOD | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN303 | DAKAK | NA | DAKAKF_D DAKAKFHKLWY DAKAKW_D | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6964 | 123.3964 | Dakak Park and Beach Resort Taguilon, Dapitan City, Zamboanga Del Norte | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1688 | DANLUGANPAG | PGD_005_GPONA_01 | DANLUGANPAGFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8836 | 123.4058 | Pagadian CityDanlugan Danlugan, Pagadian City, Zamboanga Del Sur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN963 | DANSLR | NA | DANSLRFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LABASON |  | Territory 8 | 8.0344 | 122.5771 | San Isidro, Labason, Zamboanga Del Norte | IPIL | GT | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 68 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1269 | DAO | PGD_003_GPONA_01 | DAOFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8406 | 123.4341 | Dao, Pagadian City, Zamboanga Del Sur | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2718 | DAOPGDIANZDS | NA | DAOPGDIANZDSFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8559 | 123.4306 | Purok Curvada, Brgy Dao Pagadian City | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN819 | DAPITA | DPT_002_GPONA_01 | DAPITAFHKLDWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6524 | 123.4245 | Banunong St, Linabo (Pob.), Dapitan City, Zamboanga Del Norte | DAPITA | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN654 | DIGIO | NA | DIGIOXZ | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1371 | 123.8197 | Malaubang HillBagakay, Ozamis City, Misamis Occidental | OZAMIS | GT | [6 empty] | #N/A
MIN304 | DIMALU | NA | DIMALUFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.121 | 123.8002 | Dimaluna, Ozamis City, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN545 | DIMATA | NA | DIMATAFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | DIMATALING |  | Territory 8 | 7.499 | 123.3412 | Kagawasan, Dimataling, Zamboanga Del Sur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN546 | DINAS | NA | DINASFLVWXY TCFGADONJOSEDINASZDSFLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | DINAS |  | Territory 8 | 7.6178 | 123.3359 | Don Jose, Dinas, Zamboanga Del Sur | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN598 | DIPLA2 | NA | DIPLA2FKLVWXY TCFGASANTACRUZDIPLAZSIBFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | DIPLAHAN |  | Territory 8 | 7.7088 | 122.9943 | Santa Cruz, Diplahan, Zamboanga Sibugay | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN821 | DIPOLO | DPL_002_GPONA_01 | DIPOLOFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.58 | 123.3431 | Carlos P. Garcia St.,(formerly Revolution St.) Central (Pob.), Dipolog City, Zamboanga Del Norte | DAPITA | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN241 | DONGOA | NA | DONGOAFLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KAPATAGAN |  | Territory 8 | 7.9085 | 123.7187 | Donggoan, Kapatagan, Lanao Del Norte | TUBOD | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN305 | DONVIC | NA | DONVICFY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | DON VICTORIANO CHIONGBIAN |  | Territory 8 | 8.2577 | 123.5646 | Lalud, Don Victoriano Chiongbian (Don Mariano Marcos), Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN547 | DPLAHN | DPN_001_GPONA_01 | DPLAHNFHKLVWXY TCFGAPOBDIPLAZSIBFHKLVWYRF | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | DIPLAHAN |  | Territory 8 | 7.6899 | 122.9837 | Poblacion (Diplahan), Diplahan, Zamboanga Sibugay | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN792 | DUMALI | DUM_001_GPONA_01 | DUMALIHWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | DUMALINAO |  | Territory 8 | 7.8169 | 123.3712 | Pagasa (Pob.), Dumalinao, Zamboanga Del Sur | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN306 | DUMING | NA | DUMINGFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | DUMINGAG |  | Territory 8 | 8.1549 | 123.3482 | Lapulapu St. San Pablo (Pob.), Dumingag, Zamboanga Del Sur | TUBOD | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN313 | EPOBLJAENA | LPJ_001_GPONA_01 | EPOBLJAENAFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | LOPEZ JAENA |  | Territory 8 | 8.551 | 123.7663 | LopezJaena_Eastern Poblacion, Lopez Jaena, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN242 | FILOM2 | NA | FILOM2FHLWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.3245 | 124.2648 | Sitio Balacanas Santa Filomena, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN822 | FILOME | ILG_005_GPONA_01 | FILOMEFKL FILOMEVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2597 | 124.2575 | Santa Filomena, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN891 | GALAS | DPL_006_GPONA_01 | GALASFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5589 | 123.3396 | Alex Lim Compound, Galas, Dipolog City, Zamboanga Del Norte | DAPITA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN597 | GANDIA | NA | GANDIAFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IMELDA |  | Territory 8 | 7.676 | 122.9048 | Gandiangan, Imelda, Zamboanga Sibugay | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1103 | GANGOS | OZA_004_GPONA_01 | GANGOSFKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1801 | 123.8591 | Gango, Ozamis City, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN885 | GANYANGAN RELAY | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IMELDA |  | Territory 8 | 7.6888 | 122.9375 | Little Baguio, Imelda, Zamboanga Sibugay | MIMELD | GT | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN702 | GICMAL | NA | GICMALFKDFHLWXY GICMALODFHLWXY GICMALWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2313 | 124.2395 | Gaisano Super City Mall IliganCity_Poblacion, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2374 | GMANGPANGINITAOMOR | NA | GMANGPANGINITAOMORFLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | INITAO |  | Territory 8 | 8.477 | 124.2967 | Gimangpang, Initao, Misamis Oriental, Philippines | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW17 | GNPOWERLEG | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KAUSWAGAN |  | Territory 8 | 8.1816 | 124.1099 | GN Power Kauswagan, Lanao del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN349 | GODOD | NA | GODODFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | GODOD |  | Territory 8 | 8.0062 | 122.8455 | Godod_Poblacion, Godod, Zamboanga Del Norte | DAPITAN | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 69 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN307 | GOZAMI | NA | GOZAMIFHWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1432 | 123.8448 | Gaisano Ozamis Rizal Ave cor Zamora Ext Baybay Triunfo, Ozamis City, Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1488 | GSILGN | NA | GSILGNFDFWXY GSILGNLVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2294 | 124.2341 | Gaisano Mall IliganCity_Poblacion, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1786 | GUINIMANAZDS | NA | GUINIMANAZDSFL | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MARGOSATUBIG |  | Territory 8 | 7.5538 | 123.1359 | Guinimanan, Margosatubig, Zamboanga Del Sur | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN550 | GUIPOS | NA | GUIPOSFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | GUIPOS |  | Territory 8 | 7.7355 | 123.3292 | Poblacion (Guipos), Guipos, Zamboanga Del Sur | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN350 | GUTALC | NA | GUTALCFKLWXY TCFGASALVADORGUTALCZDNFKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | GUTALAC |  | Territory 8 | 7.9834 | 122.4073 | Salvador, Gutalac, Zamboanga Del Norte | IPIL | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 70 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN918 | HTLGUILLER | PGD_001_GPONA_01 | HTLGUILLERFHLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8243 | 123.4401 | Hotel Guillermo Rizal Ave. Santiago (Pob.), Pagadian City, Zamboanga Del Sur | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN577 | IBTRD | PGD_016_GPONA_01 | IBTRDFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8421 | 123.456 | IBT Road, Tiguma, Pagadian City, Zamboanga Del Sur | TUBOD | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN993 | ILG-601 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2146 | 124.2432 | SOUTH 1 A CENTRAL SCHOOL, TUBOD, ILIGAN CITY | ILIGAN | GT | [6 empty] | #N/A
MIN990 | ILG-602 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.212 | 124.2265 | ALONG MACAPAGAL AVE., TOMAS CABILI, BRGY. TUBOD, ILIGAN CITY | ILIGAN | GT | [6 empty] | #N/A
MIN991 | ILG-603 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1965 | 124.2137 | SOUTH II CENTRAL SCHOOL, SUAREZ, ILIGAN CITY | ILIGAN | GT | [6 empty] | #N/A
MIN989 | ILG-604 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2265 | 124.2554 | BESIDE DOεA JUANA ACTUB LLUCH MEMORIAL ELEMENTARY SCHOOL, BRGY. PALAO, ILIGAN CITY | ILIGAN | GT | [6 empty] | #N/A
MIN994 | ILG-605 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2426 | 124.2482 | NEAR MINDANAO SANITARIUM HOSPITAL, BRGY. DEL CARMEN, ILIGAN CITY | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN987 | ILG-606 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2458 | 124.2684 | BAHAYAN ROAD, BRGY LUINAB, ILIGAN CITY | ILIGAN | GT | [6 empty] | #N/A
MIN1194 | ILG-701 | ILG_701_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1964 | 124.1868 | NEAR MVC PIER GATE, ALONG NATIONAL ROAD, BRGY. BURUUN, ILIGAN CITY | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1193 | ILG-702 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1955 | 124.2269 | STEEL TOWN SUBD., BRGY. STA. ELENA, ILIGAN CITY, LANAO DEL NORTE | ILIGAN | GT | [6 empty] | #N/A
MIN1336 | ILG-703 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2174 | 124.2403 | HUAWEI CABINETALONG MACAPAGAL AVENUE NATIONAL HIGHWAY BRGY. TUBOD ILIGAN CITY | ILIGAN | GT | [6 empty] | #N/A
MIN1335 | ILG-704 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.229 | 124.2392 | BESIDE ST. MICHAEL CATHEDRAL, ALONG OBACH STREET, BRGY. POBLACION, ILIGAN CITY | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1186 | ILG-705 | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2448 | 124.2554 | BESIDE SKYWALK, ALONG A. BONIFACIO AVENUE, BRGY. HINAPLANON, ILIGAN CITY | ILIGAN | GT | [5 empty] | 10009375 | 9175880728
MIN1279 | ILG-706 | ILG_706_HYB_01 | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2689 | 124.2602 | ALONG NATIONAL HIGHWAY, BRGY. STA. FELOMINA, BESIDE FIRE STATION, ILIGAN CITY | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1280 | ILG-707 | ILG_707_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.3015 | 124.2584 | ALONG DALIPUGA BRGY. ROAD, NEAR JUNK SHOP, BRGY. DALIPUGA, ILIGAN CITY | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN703 | ILIGA2 | NA | ILIGA2FHKLWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1743 | 124.1873 | Ditucalan, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN825 | ILIGA3 | NA | ILIGA3FKLVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2328 | 124.2427 | Villa Verde, Iligan City, Lanao Del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN826 | Iligan | ILG_001_GPONA_01, ILG_001_GPONA_02 | ILIGANFKLVWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2231 | 124.2429 | 875 Globe Telecom Iligan Host Exchange DBP road DBP Subd. Mahayhay, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1810 | POBILIGANLDNCOW | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2288 | 124.2387 | 3F, Dypico Building, Quezon Ave. cor Ramiro Street, IliganCity_Poblacion, Iligan City, Lanao Del Norte | ILIGAN | GT | [6 empty] | #N/A
MIN657 | IMINSH | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2412 | 124.247 | Mindanao Sanitarium & Hospital Tibanga, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN343 | INITAO | NA | INITAOFHLWXY TCFGAPOBLACIONINITAOMORFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | INITAO |  | Territory 8 | 8.4973 | 124.3038 | Initao_Poblacion, Initao, Misamis Oriental | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN795 | IPIL | IPI_003_GPONA_01 | IPILFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.7887 | 122.5749 | Ipil_Poblacion, Ipil, Zamboanga Sibugay | IPIL | GT | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1389 | IPIL FOC | NA | IPIL REGEN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.7976 | 122.6101 | Lower Pangi, Ipil, Zamboanga Sibugay | IPIL | GT | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1620 | ISABELDPOLOG | DPL_007_GPONA_01 | ISABELDPOLOGFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5729 | 123.3465 | Santa Isabel, Dipolog City, Zamboanga Del Norte | DAPITAN | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2256 | JAMPASONINTAOMISOR | NA | JAMPASONINTAOMISORFKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | INITAO |  | Territory 8 | 8.5168 | 124.3103 | Jampason, Initao, Misamis Oriental, Philippines | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN351 | JDLMAN | NA | JDLMANFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | JOSE DALMAN |  | Territory 8 | 8.4434 | 123.0209 | Poblacion (Ponot), Jose Dalman (Ponot), Zamboanga Del Norte | DAPITAN | GT | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 71 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN831 | JIMENE | JIM_001_GPONA_01 | JIMENEFHKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | JIMENEZ |  | Territory 8 | 8.3362 | 123.8373 | Rizal (Pob.), Jimenez, Misamis Occidental | CLAMBA | PHILTOWER | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN308 | JOSEFI | NA | JOSEFIFWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | JOSEFINA |  | Territory 8 | 8.2161 | 123.5459 | Upper Bagong Tudela (Pob.), Josefina, Zamboanga Del Sur | OZAMIS | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN796 | KABASA | KBS_001_GPONA_01 | KABASAFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | KABASALAN |  | Territory 8 | 7.8007 | 122.7563 | Calubihan, Kabasalan, Zamboanga Sibugay | MIMELD | PHILTOWER | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2744 | KAHYAGANPGDIANZDS | NA | KAHYAGANPGDIANZDSFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | KAHAYAGAN |  | Territory 8 | 7.8655 | 123.4023 | Kahayagan, Pagadian City, Zamboanga del Sur, Philippines | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN532 | KALAW | NA | KALAWFHKLWXY TCFGAPOBKLAWITZDNFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | KALAWIT |  | Territory 8 | 7.9055 | 122.5227 | Kalawit (Pob.), Kalawit, Zamboanga Del Norte | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN614 | KALAWI | NA | KALAWIFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TITAY |  | Territory 8 | 7.8601 | 122.5403 | Dalangin, Titay, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN708 | KAPATA | KAP_001_GPONA_01 | KAPATAFKLVWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KAPATAGAN |  | Territory 8 | 7.897 | 123.7676 | Kapatagan_Poblacion, Kapatagan, Lanao Del Norte | TUBOD | GT | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN720 | KATIPU | KAT_001_GPONA_01 | KATIPUFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | KATIPUNAN |  | Territory 8 | 8.5142 | 123.2835 | Katipunan_Barangay Dos (Pob.), Katipunan, Zamboanga Del Norte | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 72 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN552 | KBASAL | NA | KBASALFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | KABASALAN |  | Territory 8 | 7.8094 | 122.7425 | Sininan Rd. Purok C Sininan, Kabasalan, Zamboanga Sibugay | IPIL FOC | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN243 | KIWALA | NA | KIWALAFKLVDWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2794 | 124.2688 | Purok 1 Kiwalan, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1510 | KIWALA_D | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.288 | 124.264 | LaFarge/ Iligan Cement Kiwalan, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN244 | KOLAMB | NA | KOLAMBFHWY2FHWY TCFGAAGUSTINKOLAMBLDNFHWYSFKL | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KOLAMBUGAN |  | Territory 8 | 8.1116 | 123.9028 | Agustin Heights Kolambugan_Poblacion, Kolambugan, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN835 | KSWAGN | NA | KSWAGNFHKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KAUSWAGAN |  | Territory 8 | 8.1917 | 124.0889 | Kauswagan_Poblacion, Kauswagan, Lanao Del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN556 | KUMAL2 | NA | KUMAL2JXZ | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | KUMALARANG |  | Territory 8 | 7.7699 | 123.1417 | Secade, Kumalarang, Zamboanga Del Sur | MIMELD | GT | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN555 | KUMALA | NA | KUMALAFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | KUMALARANG |  | Territory 8 | 7.7516 | 123.149 | Purok Makiangayon Kumalarang_Poblacion, Kumalarang, Zamboanga Del Sur | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN788 | LABASO | NA | LABASOFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LABASON |  | Territory 8 | 8.0684 | 122.5219 | Antonino (Pob.), Labason, Zamboanga Del Norte | IPIL | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 73 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN310 | LABTAB | NA | LABTABFHLWY TCFGATABIDOZAMISMOCCFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1057 | 123.7821 | Tabid, Ozamis City, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN884 | LACAUAN RELAY | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | ROSELLER LIM |  | Territory 8 | 7.6708 | 122.4429 | Surabay, Roseller Lim, Zamboanga Sibugay | IPIL | GT | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN560 | LAKEWD | NA | LAKEWDFHLWXY TCFGAPOBLWOODZDSFHLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LAKEWOOD |  | Territory 8 | 7.8542 | 123.1518 | Poblacion (Lakewood), Lakewood, Zamboanga Del Sur | MIMELD | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN705 | LALA | NA | LALAFLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | LALA |  | Territory 8 | 7.9729 | 123.7474 | Lala Proper (Pob.), Lala, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1145 | LAMACMISOCC | NA | LAMACMISOCCFKLVWY TCFGALAMACLOWOROQUIMOCCFKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY |  | Territory 8 | 8.4842 | 123.7952 | Lamac Lower, Oroquieta City, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1233 | LAMBA | NA | LAMBAFHKLVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2627 | 124.2703 | Sitio Lambagohon San Roque, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1234 | LANIPA | NA | LANIPAFHLWY TCFGALANIPAOLALALDNFHLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | LALA |  | Territory 8 | 7.9595 | 123.777 | Lanipao, Lala, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1076 | LANTAWAN RELAY | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | BUUG |  | Territory 8 | 7.7073 | 123.079 | Lantawan, Buug, Zamboanga Sibugay | MIMELD | GT | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN561 | LAPUYA | NA | LAPUYAFLWXY TCFGAPOBLPUYANZDSFLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LAPUYAN |  | Territory 8 | 7.6366 | 123.1998 | Lapuyan_Poblacion, Lapuyan, Zamboanga Del Sur | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1251 | LARAYA | NA | LARAYAFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6165 | 123.3806 | Larayan, Dapitan City, Zamboanga Del Norte | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN312 | LAWIS | NA | LAWISFHKLWY TCFGAHWAYPANALPLARIDMOCCFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | PLARIDEL |  | Territory 8 | 8.575 | 123.731 | Purok Highway Panalsalan, Plaridel, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN558 | LBANG2 | LAB_001_GPONA_01 | LBANG2FHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LABANGAN |  | Territory 8 | 7.855 | 123.4988 | Upper Sangan, Labangan, Zamboanga Del Sur | PAGADIAN ICON | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN797 | LBANGA | NA | LBANGAFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LABANGAN |  | Territory 8 | 7.8611 | 123.5173 | Lower Campo Islam (Pob.), Labangan, Zamboanga Del Sur | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1394 | LEEPL | NA | LEEPLFWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5817 | 123.3387 | G/F Unit 110 Lee Plaza Mall, Quezon Avenue, Dipolog City, Zamboanga del Norte | DAPITAN | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1235 | LIANG | NA | LIANGFLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | BACOLOD |  | Territory 8 | 8.1773 | 123.9934 | Liangan East, Bacolod, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN562 | LIARGO | NA | LIARGOFHWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 8.0066 | 123.4842 | Purok 2 RamonMagsaysay(Liargo)_Poblacion, Ramon Magsaysay (Liargo), Zamboanga Del Sur | TUBOD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN880 | LILOBO | NA | LILOBOFHKLWY TCFGALILOBONIFAMOCCFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | BONIFACIO |  | Territory 8 | 8.0519 | 123.5648 | Liloan, Bonifacio, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN837 | LILOY | LLY_001_GPONA_01 | LILOYFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LILOY |  | Territory 8 | 8.1185 | 122.6825 | Baybay (Pob.), Liloy, Zamboanga Del Norte | IPIL | GT | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 74 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN838 | LINABO | NA | LINABOFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.5888 | 123.3927 | Linabo (Pob.), Dapitan City, Zamboanga Del Norte | DAPITAN | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN706 | LINAMO | LIN_001_GPONA_01 | LINAMOFHLWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | LINAMON |  | Territory 8 | 8.186 | 124.1615 | Linamon_Poblacion, Linamon, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN661 | LJAENA | NA | LJAENAFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | LOPEZ JAENA |  | Territory 8 | 8.483 | 123.6731 | Macalibre Alto, Lopez Jaena, Misamis Occidental, Philippines | CLAMBA | PHILTOWER | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN311 | LLIBER | NA | LLIBERFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LA LIBERTAD |  | Territory 8 | 8.4668 | 123.5227 | LaLibertad_Poblacion, La Libertad, Zamboanga Del Norte | CLAMBA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1683 | LORENZOTAN | NA | LORENZOTANFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TANGUB CITY |  | Territory 8 | 8.0578 | 123.7054 | Pangabuan, Tangub City, Misamis Occidental | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN874 | LTUNGA | NA | LTUNGAFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | VITALI |  | Territory 8 | 7.5121 | 122.3611 | Lower Tungawan, Tungawan, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN357 | LUGAIT | NA | LUGAITFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LUGAIT |  | Territory 8 | 8.3376 | 124.2568 | Purok Bonifacio seaside Lugait_Poblacion, Lugait, Misamis Oriental | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN239 | MACRIS | NA | MACRISFHLWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1975 | 124.196 | Purok 23, Zone 9 Maria Cristina, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN314 | MAHAYA | NA | MAHAYAFLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MAHAYAG |  | Territory 8 | 8.1248 | 123.4351 | Mahayag_Poblacion (Upper Mahayag), Mahayag, Zamboanga Del Sur | OZAMIS | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN246 | MAIGO | MGO_001_GPONA_01 | MAIGOFKLVWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | MAIGO |  | Territory 8 | 8.1602 | 123.9609 | Nationa Highway Maigo_Poblacion, Maigo, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN642 | MALANG | NA | MALANGFHWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | MALANGAS |  | Territory 8 | 7.6309 | 123.031 | Malangas_Poblacion, Malangas, Zamboanga Sibugay | MIMELD | PHILTOWER | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1261 | MALING | NA | MALINGFHLWY TCFGAMALINGAOTUBODLDNFHLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | TUBOD |  | Territory 8 | 7.9766 | 123.866 | Malingao, Tubod, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2726 | MANGAPGDIANZDS | PGD_014_GPONA_01 | MANGAPGDIANZDSFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8583 | 123.4454 | Vitalea Sudb. Brgy. Manga, Pagadian City | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1642 | MANINGCOLOZM | NA | MANINGCOLOZMFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1707 | 123.8477 | Ozamis CityBacolod, 50th District (Pob.), Ozamis City, Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN721 | MANOKA | MKA_001_GPONA_01 | MANOKAFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | MANOKAN |  | Territory 8 | 8.5167 | 123.0897 | Manukan_East Poblacion, Manukan, Zamboanga Del Norte | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 75 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1935 | Manticao Relay | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MANTICAO |  | Territory 8 | 8.3777 | 124.407 | Dunqui Hill, Manticao_Poblacion, Manticao, Misamis Oriental | ILIGAN | GT | [6 empty] | #N/A
MIN601 | MARAND | LAA_001_GPONA_01 | MARANDFHLVWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | LALA |  | Territory 8 | 7.923 | 123.7759 | Maranding, Lala, Lanao Del Norte | TUBOD | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN262 | MARANT | NA | MARANTFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARANTAO |  | Territory 8 | 7.9736 | 124.2671 | Tuca Kialdan, Marantao, Lanao Del Sur | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN920 | MARAWI | MRW 002 GPONA 01 | MARAWIFKLVWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY |  | Territory 8 | 8.0092 | 124.2887 | Camp Ranao Lilod Madaya (Pob.), Marawi City, Lanao Del Sur | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN798 | MARGOS | NA | MARGOSFHLXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MARGOSATUBIG |  | Territory 8 | 7.5742 | 123.1697 | Margosatubig_Poblacion, Margosatubig, Zamboanga Del Sur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN247 | MARGS | NA | MARGSFHKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KAPATAGAN |  | Territory 8 | 7.9276 | 123.6701 | Margos, Kapatagan, Lanao Del Norte | TUBOD | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN964 | MAYOR HILARION HOSPITAL REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1695 | 123.8584 | Mayor Hilarion A. Ramiro Sr. Regl Training Teaching Hospital Maningcol, Ozamis City, Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN240 | MBALIN | NA | MBALINFLWYFLWY TCFGAPAGAYBLINDOLDSFLWYSFLW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | BALINDONG |  | Territory 8 | 7.9219 | 124.204 | Pagayawan, Balindong (Watu), Lanao Del Sur | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN301 | MBONIF | BNI_001_GPONA_01 | MBONIFFHKLWY TCFGAPOBLABONIFAMOCCFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | BONIFACIO |  | Territory 8 | 8.0563 | 123.6134 | Purok 4 Bonifacio_Poblacion (Centro), Bonifacio, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN564 | MBUHAY | NA | MBUHAYFHLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | MABUHAY |  | Territory 8 | 7.415 | 122.8358 | Mabuhay_Poblacion, Mabuhay, Zamboanga Sibugay | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN955 | MERCY HOSPITAL REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.215 | 124.231 | Mercy Community Hospital Inc IliganCity_Poblacion, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN569 | MIDSAL | NA | MIDSALFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MIDSALIP |  | Territory 8 | 8.0254 | 123.3128 | Rizal, Midsalip, Zamboanga Del Sur | TUBOD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN551 | MIMELD | IML_001_GPONA_01 | MIMELDFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IMELDA |  | Territory 8 | 7.6463 | 122.9316 | Poblacion (Santa Fe), Imelda, Zamboanga Sibugay | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN245 | MMAGSY | NA | MMAGSYFLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | MAGSAYSAY |  | Territory 8 | 8.0333 | 123.916 | Lapulapu St. Poblacion (BagoAIngud), Magsaysay, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1127 | MMCOZAMIS | NA | MMCOZAMISFHKLY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1454 | 123.8486 | Medina Medical Center 50th District (Pob.), Ozamis City, Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1649 | MOBODMISOC | NA | MOBODMISOCFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY |  | Territory 8 | 8.4972 | 123.7902 | Purok 6, Brgy. Canubay City Mobod, Oroquieta City, Misamis Occidental | CLAMBA | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1254 | MOLAV2 | MOL_001_GPONA_01 | MOLAV2FHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MOLAVE |  | Territory 8 | 8.0958 | 123.4824 | Magsaysay St. Makuguihon (Pob.), Molave, Zamboanga Del Sur | OZAMIS | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN722 | MOLAVE | NA | MOLAVECFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MOLAVE |  | Territory 8 | 8.0811 | 123.4923 | Maloloyon (Pob.), Molave, Zamboanga Del Sur | OZAMIS | GT | [6 empty] | #N/A
MIN1644 | MONCKADMAR | NA | MONCKADMARFKLVWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY |  | Territory 8 | 8.0011 | 124.3026 | Ambolong, Marawi City, Lanao Del Sur | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN320 | MRIZAL | NA | MRIZALXZ | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | RIZAL |  | Territory 8 | 8.5189 | 123.5419 | South Mapang, Rizal, Zamboanga Del Norte | CLAMBA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN917 | MSU | NA | MSUFHKLWY TCFGACADAYMARAWILDSFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY |  | Territory 8 | 7.9922 | 124.265 | Cadayonan, Marawi City, Lanao Del Sur | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN848 | MTANG2 | TGB_001_GPONA_01 | MTANG2FHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TANGUB CITY |  | Territory 8 | 8.0644 | 123.743 | Maloro, Tangub City, Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN849 | MTANGU | NA | MTANGUFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TANGUB CITY |  | Territory 8 | 8.0867 | 123.755 | Purok 3 Minsubong, Tangub City, Misamis Occidental | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1301 | MUKAS | NA | MUKASFHKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KOLAMBUGAN |  | Territory 8 | 8.0981 | 123.8429 | Mukas, Kolambugan, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN958 | MUMC REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY | Banadero (Pob.) | Territory 8 | 8.1477 | 123.8185 | Misamis University Medical Center, Bagakay Bagakay, Ozamis City, Misamis Occidental | OZAMIS | GT | [6 empty] | #N/A
MIN248 | MUNAI | NA | MUNAIFKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | MUNAI |  | Territory 8 | 8.1111 | 124.0508 | North Cadulawan, Munai, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1506 | MURICAY | NA | MURICAYFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8305 | 123.4628 | Pagadian Airport Tiguma Muricay, Pagadian City, Zamboanga Del Sur | TUBOD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN361 | NAAWAN | NA | NAAWANFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | NAAWAN |  | Territory 8 | 8.4297 | 124.2957 | Purok 7 Naawan_Poblacion, Naawan, Misamis Oriental | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN571 | NAGAZ2 | NA | NAGAZ2FHKLWXY TCFGALAPAZNAGAZSIBFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | NAGA |  | Territory 8 | 7.81 | 122.6682 | La Paz, Naga, Zamboanga Sibugay | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN852 | NAGAZS | NA | NAGAZSFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | NAGA |  | Territory 8 | 7.7975 | 122.6887 | Naga_Poblacion, Naga, Zamboanga Sibugay | MIMELD | PHILTOWER | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN595 | NAPOL | NA | NAPOLFHKLWXY NAPOLWXYIFHKL | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8096 | 123.4168 | Napolan, Pagadian City, Zamboanga Del Sur | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN533 | NEWCAL | NA | NEWCALFHWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | KALAWIT |  | Territory 8 | 7.939 | 122.618 | New Calamba, Kalawit, Zamboanga Del Norte | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN249 | NSCILG | NA | NSCIL2GFHKLVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2026 | 124.214 | National Steel Corp, Staff House ILigan Global Steel Suarez, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN315 | OLINGA | DPL_004_GPONA_01 | OLINGAFKLVWXY TCFGAPRKFARMERDPOLOGZDNFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5346 | 123.3263 | Purok Farmers Olingan, Dipolog City, Zamboanga Del Norte | DAPITA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN572 | OLUTAN | NA | OLUTANFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | OLUTANGA |  | Territory 8 | 7.3124 | 122.8457 | Purok 6 Solar (Pob.), Olutanga, Zamboanga Sibugay | MIMELD | PHILTOWER | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN853 | OROQUI | ORQ_001_GPONA_01, ORQ_001_GPONA_02 | OROQUIFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY |  | Territory 8 | 8.4799 | 123.8072 | Taboc Norte, Oroquieta City, Misamis Occidental | CLAMBA | PHILTOWER | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN316 | OSMENM | NA | OSMENMFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SERGIO OSMEÑA SR. |  | Territory 8 | 8.2983 | 123.5082 | SergioOsmenaSr_Poblacion Alto, Sergio Osmena Sr., Zamboanga Del Norte | DAPITA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1356 | OZA-701 | OZA_701_HYB_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1456 | 123.8417 | GALLARDO STREET, IN FRONT OF WINSTON MARKETING, BRGY. 58, OZAMIS CITY | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1360 | OZA-702 | OZA_702_HYB_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1487 | 123.8434 | ALONG AGUADAS STREET, CORNER C. M. RECTO, OZAMIS CITY | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1357 | OZA-703 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1504 | 123.8426 | BESIDE KNIGHTS OF COLUMBUS BUILDING, BONIFACIO STREET CORNER LAPULAPU STREET, OZAMIS CITY | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1373 | OZA-704 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1467 | 123.8468 | ALONG DON ANSELMO BERNAD ST. BESIDE JOLLIBEE DRIVE THRU, BRGY. ANNEX, OZAMIS CITY | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1281 | OZA-705 | OZA_705_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1486 | 123.8373 | ALONG LAMAN HIGHWAY, BESIDE UCCP CHURCH, BRGY. LAMAN, OZAMIZ CITY | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1282 | OZA-706 | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.167 | 123.8568 | NEAR FMCMA SCHOOL, BACOLOD STREET, BRGY. MANINGCOL, OZAMIS CITY | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1283 | OZA-707 | OZA_707_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1803 | 123.8595 | FACING LINGLING STORE, AIRPORT ROAD, BRGY. GANGO, OZAMIS CITY | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN854 | OZAMI2 | NA | OZAMI2FHKLDWXY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1453 | 123.8395 | Bay Avenue, Tinago, Ozamis City, Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN855 | OZAMIS | OZA_003_GPONA_01, OZA_003_GPONA_02 | OZAMISFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1576 | 123.8551 | ICC Village Maningcol, Ozamis City, Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1495 | OZAMIS FOC | OZA_002_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1522 | 123.851 | Circumferential Road Aguada Ozamis City Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1813 | OZAMIS NDC | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.146 | 123.8415 | 3F, Junjing Building, Gallardo Street, 50th District (Pob.), Ozamis City, Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN800 | PAGAD2 | PGD_002_GPONA_01 | PAGAD2FHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.825 | 123.4378 | Marasigan Bldg F. Pajares Ave., San Francisco (Pob.), Pagadian City, Zamboanga Del Sur | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN799 | PAGADI | NA | PAGADIFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8431 | 123.3811 | Globe Telecom Tower Mt.Palpalan Palpalan, Pagadian City, Zamboanga Del Sur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN966 | PAGADIAN ICON | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8248 | 123.4385 | GF Sagun Bldg Cabrera St., San Francisco (Pob.), Pagadian City, Zamboanga Del Sur | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1814 | PAGADIAN NDC | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8257 | 123.4385 | 0318 J. Ariosa cor Sanson Streets, San Francisco (Pob.), Pagadian City, Zamboanga Del Sur | TUBOD | GT | [6 empty] | #N/A
MIN738 | PAGAHA | NA | PAGAHAFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | INITAO |  | Territory 8 | 8.4623 | 124.2858 | Pagahan, Initao, Misamis Oriental | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1449 | PAGAIS | PGD_011_GPONA_01 | GAISCAP1PGDIANZDSIDFKSF | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8241 | 123.4415 | Rizal Ave. San Pedro (Pob.), Pagadian City, Zamboanga Del Sur | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN251 | PALAO | NA | PALAOFKLVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2315 | 124.2556 | Del Carmen, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2314 | SANTONIOTITAY | NA | SANTONIOTITAYZSFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TITAY |  | Territory 8 | 7.8275 | 122.4892 | Titay - San Antonio Rd, Titay, Zamboanga Sibugay, Philippines | IPIL | UNITY | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1080 | PANAON | NA | PANAONFHKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | PANAON |  | Territory 8 | 8.3703 | 123.8391 | Brgy. Lutao, Panaon, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1260 | PANPIL | IPI_002_GPONA_01 | PANPILFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.7954 | 122.6057 | Pangi, Ipil, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN250 | PANTAO | NA | PANTAOFLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | PANTAO RAGAT |  | Territory 8 | 8.0597 | 124.1843 | PantaoRagat_Poblacion East, Pantao Ragat, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN252 | PANTAR | NA | PANTARFLWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | PANTAR |  | Territory 8 | 8.0642 | 124.2651 | Pantar_Poblacion, Pantar, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN534 | PATAWA | NA | PATAWAFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LABASON |  | Territory 8 | 8.0956 | 122.6132 | Patawag, Labason, Zamboanga Del Norte | IPIL | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 76 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN347 | PATIMA | LIO_001_GPONA_01 | PATIMAFHKLWXY TCFGAFATIMALILOYZDNFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LILOY |  | Territory 8 | 8.116 | 122.6635 | Fatima, Liloy, Zamboanga Del Norte | IPIL | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 77 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN575 | PAYAO | NA | PAYAOFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | PAYAO |  | Territory 8 | 7.586 | 122.8036 | Poblacion (Payao), Payao, Zamboanga Sibugay | MIMELD | GT | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1324 | PGD-701 | PGD_701_HYB_01 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8333 | 123.4367 | HUAWEI CABINET ALONG SABATI ST. BRGY. SAN JOSE PAGADIAN CITY | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1325 | PGD-702 | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8227 | 123.4407 | HUAWEI CABINETINSIDE SANTIAGO ELEMENTARY SCHOOL, BRGY. SANTIAGO, PAGADIAN CITY | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1321 | PGD-703 | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8332 | 123.4453 | HUAWEI CABINET URBAN POOR BRGY. LUMBIA PAGADIAN CITY | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1320 | PGD-704 | PGD_704_GPONA_01 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8462 | 123.4601 | HUAWEI CABINETNEAR BASKET BALL COURT OF SUNRISE VILLAGE BRGY. TIGUMA PAGADIAN CITY | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1322 | PGD-705 | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8268 | 123.4301 | HUAWEI CABINETALONG BANGASAN ST. INSIDE BALANGASAN ELEMENTARY SCHOOL BRGY. BALANGASAN PAGADIAN CITY | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1323 | PGD-706 | PGD_706_HYB_01 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8237 | 123.4286 | HUAWEI CABINETOPPOSITE OF BALANGASAN DAY CARE BGRY. BALANGASAN PAGADIAN CITY | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1365 | PGD-707 | PGD_707_HYB_01 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8232 | 123.4072 | HUAWEI CABINET NEAR BUENAVISTA MERCHANDISE, NAPOLAN ROAD, BARANGAY NAZARETH II, PAGADIAN CITY, ZAMB | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1622 | PILMICO REPEATER | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.289 | 124.26 | Dalipuga, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN317 | PINAN | NA | PINANFKLVWXDY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | PIÑAN |  | Territory 8 | 8.4857 | 123.4513 | Purok Orchids Pinan(NewPinan)_Poblacion North, Pinan (New Pinan), Zamboanga Del Norte | CLAMBA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1270 | PIPOL | NA | PIPOLFHKWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8226 | 123.4376 | Peoples Plaza,F.S. Fajares Ave. Gatas (Pob.), Pagadian City, Zamboanga Del Sur | TUBOD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1737 | PLARDLMISOCC | NA | PLARDLMISOCCFHKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | PLARIDEL |  | Territory 8 | 8.6053 | 123.6901 | Plaridel_Southern Poblacion, Plaridel, Misamis Occidental | CLAMBA | PHILTOWER | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1105 | PLRDL2 | PLD_001_GPONA_01 | PLRDL2FHKLWY TCFGALOOCPROPLARIDMOCCFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | PLARIDEL |  | Territory 8 | 8.6082 | 123.724 | Looc Proper, Plaridel, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2019 | PMIRAYBALIAMISOCC | NA | PMIRAYBALIAMISOCCFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | BALIANGAO |  | Territory 8 | 8.6676 | 123.6021 | Punta Miray, Baliangao, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1748 | POBMANTICAO | NA | POBMANTICAOFHLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MANTICAO |  | Territory 8 | 8.399 | 124.2905 | Poblacion Manticao, Misamis Oriental | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1253 | POBPIL | IPI_001_GPONA_01, IPI_001_GPONA_02 | POBPILFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.7822 | 122.582 | Veteran's Village (Ruiz), Ipil, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN723 | POLANC | NA | POLANCFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | POLANCO |  | Territory 8 | 8.5336 | 123.3567 | Polanco_Poblacion North, Polanco, Zamboanga Del Norte | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1695 | POLODAP | NA | POLODAPFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6317 | 123.4106 | Polo, Dapitan City, Zamboanga Del Norte | DAPITA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN319 | POTUNG | NA | POTUNGFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.5456 | 123.4912 | Potungan, Dapitan City, Zamboanga Del Norte | CLAMBA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN578 | PTOGO | NA | PTOGOHWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PITOGO |  | Territory 8 | 7.4497 | 123.3141 | Poblacion (Pitogo), Pitogo, Zamboanga Del Sur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1289 | RGODOD | NA | RGODODFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | GODOD |  | Territory 8 | 8.0036 | 122.8169 | Brgy. Dipopor, Godod, Zamboanga del Norte | DAPITAN | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 78 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN608 | RJDALM | NA | RJDALMFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | JOSE DALMAN |  | Territory 8 | 8.3936 | 122.9823 | Madalag, Jose Dalman (Ponot), Zamboanga Del Norte | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 79 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN531 | RJOSIA | NA | RJOSIAFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIAYAN |  | Territory 8 | 8.2481 | 123.0703 | Polayo, Siayan, Zamboanga Del Norte | DAPITAN | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 80 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN15 | RMANTI | NA | RMANTIFHKLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MANTICAO |  | Territory 8 | 8.3825 | 124.4075 | Donque Hill Upper Malubog, Manticao, Misamis Oriental | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN593 | ROSEL | NA | ROSELFL | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | ROSELLER LIM |  | Territory 8 | 7.7293 | 122.3798 | San Fernandino, Roseller Lim, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN321 | ROXASM | NA | ROXASMH | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | PRESIDENT ROXAS |  | Territory 8 | 8.5207 | 123.2302 | Langatian, Pres. Manuel A. Roxas, Zamboanga Del Norte | DAPITAN | GT | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 81 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN643 | RTLIM | ROL_001_GPONA_01 | RTLIMFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | ROSELLER LIM |  | Territory 8 | 7.6577 | 122.4658 | Surabay, Roseller Lim, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1215 | RTLIM FOC | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | ROSELLER LIM |  | Territory 8 | 7.658 | 122.4683 | Surabay, Roseller Lim, Zamboanga Sibugay | IPIL | GT | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN883 | RTOMAR | NA | RTOMARFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MARGOSATUBIG |  | Territory 8 | 7.5475 | 123.1877 | Limamawan, Margosatubig, Zamboanga Del Sur | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN594 | SAGUN | NA | SAGUNFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | VINCENZO A. SAGUN |  | Territory 8 | 7.5168 | 123.1679 | Kapatagan, Vincenzo A. Sagun, Zamboanga Del Sur | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN322 | SALUG | SAL_001_GPONA_01 | SALUGFHKLVWXY TCFGAPOBSALUGZDNFHKLVWYNF | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SALUG |  | Territory 8 | 8.1093 | 122.7549 | Salug_Poblacion (Salug), Salug, Zamboanga Del Norte | DAPITAN | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 82 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN266 | SALVAD | NA | SALVADFHLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | SALVADOR |  | Territory 8 | 7.9023 | 123.8417 | Purok 4 Salvador_Poblacion, Salvador, Lanao Del Norte | TUBOD | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN253 | SAPAD | NA | SAPADFHLVWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | SAPAD |  | Territory 8 | 7.8485 | 123.8392 | Buriasan (Pob.), Sapad, Lanao Del Norte | TUBOD | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN323 | SAPANG | NA | SAPANGFHLWYFHLWY TCFGAPOBSDLAGAMOCCFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | SAPANG DALAGA |  | Territory 8 | 8.544 | 123.5592 | Sapang Dalaga_Poblacion, Sapang Dalaga, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1083 | SCAYAB | DPL_005_GPONA_01 | SCAYABFKLVWXYF TCFGAPRKCSICAYDPOLOGZDNFKLVWYSFK | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.6188 | 123.3525 | Purok Central Sicayab, Dipolog City, Zamboanga Del Norte | DAPITAN | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1965 | SEMIRASIRAWAIZDNJ | NA | SEMIRASIRAWAIZDNFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIRAWAI |  | Territory 8 | 7.5622 | 122.2359 | Guban, Sirawai, Zamboanga del Norte, Philippines | IPIL | GT | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN644 | SIAY | NA | SIAYFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | SIAY |  | Territory 8 | 7.711 | 122.8693 | Siay_Poblacion, Siay, Zamboanga Sibugay | IPIL FOC | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN535 | SIAYAN | NA | SIAYANFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIAYAN |  | Territory 8 | 8.2517 | 123.1108 | Siayan Training Center Compd, Siayan Proper (Pob.), Siayan, Zamboanga Del Norte | DAPITA | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 83 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN324 | SIBUTA | NA | SIBUTAFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIBUTAD |  | Territory 8 | 8.6054 | 123.4803 | Sibutad_Poblacion (Sibutad), Sibutad, Zamboanga Del Norte | CLAMBA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN612 | SIKAWA | NA | SIKAWAFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | SAPANG DALAGA |  | Territory 8 | 8.495 | 123.5689 | Locus, Sapang Dalaga, Misamis Occidental | CLAMBA | GT | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN739 | SILUM | NA | SILUMFHLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MANTICAO |  | Territory 8 | 8.377 | 124.2636 | Punta Silum, Manticao, Misamis Oriental | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN325 | SINACB | SCB_001_GPONA_01 | SINACBFHKLWY SINACBYFKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | SINACABAN |  | Territory 8 | 8.284 | 123.841 | Purok Santal Sinacaban_Poblacion, Sinacaban, Misamis Occidental | CLAMBA | PHILTOWER | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN789 | SINDAN | SNG_001_GPONA_01 | SINDANFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SINDANGAN |  | Territory 8 | 8.2327 | 122.9984 | A. Mabini St., Sindangan_Poblacion, Sindangan, Zamboanga Del Norte | DAPITA | GT | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 84 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN537 | SIOCON | NA | SIOCONFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIOCON |  | Territory 8 | 7.7057 | 122.1402 | Poblacion (Siocon), Siocon, Zamboanga Del Norte | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1333 | SIRA BALSIO RELAY | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | ROSELLER LIM |  | Territory 8 | 7.767 | 122.156 | Mt. Lacauan Surabay, Roseller Lim, Zamboanga Sibugay | IPIL | GT | [6 empty] | #N/A
MIN580 | SMIGUE | NA | SMIGUEFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | SAN MIGUEL |  | Territory 8 | 7.65 | 123.2676 | SanMiguel_Poblacion, San Miguel, Zamboanga Del Sur | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1255 | SMORO | NA | SMOROFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | SAN MIGUEL |  | Territory 8 | 7.7075 | 123.292 | Mati, San Miguel, Zamboanga Del Sur | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1334 | SOMINO | NA | SOMINOFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | SOMINOT |  | Territory 8 | 8.0394 | 123.3793 | Sominot_Poblacion, Sominot (Don Mariano Marcos), Zamboanga Del Sur | TUBOD | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN581 | SPABLO | NA | SPABLOFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | SAN PABLO |  | Territory 8 | 7.6513 | 123.4569 | SanPablo_Poblacion (San Pablo), San Pablo, Zamboanga Del Sur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN613 | SRAWAI | NA | SRAWAIFHLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIRAWAI |  | Territory 8 | 7.5869 | 122.1482 | Sirawai Proper (Pob.), Sirawai, Zamboanga Del Norte | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1650 | STELENAILGN | NA | STELENAILGNFHLWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1929 | 124.2273 | Iligan CitySanta Elena Abuno, Iligan City, Lanao Del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1591 | STMARIPGDIAN | NA | STMARIPGDIANFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8319 | 123.442 | BrgyStaMaria_PagadianCity_ZamboangadelSur | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2563 | STOMASMUTIAZDN | NA | STOMASMUTIAZDNFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | MUTIA |  | Territory 8 | 8.417 | 123.4786 | Mutia, Zamboanga del Norte, Philippines | CLAMBA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW15 | SUAREZTEMPO | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.187 | 124.216 | Back of Brgy. hall of Brgy. Suarez Iligan City | ILIGAN | GT | [6 empty] | #N/A
MIN1303 | SULITA | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | NAGA |  | Territory 8 | 7.8376 | 122.7141 | Santa Clara, Naga, Zamboanga Sibugay | MIMELD | FTAP | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN254 | SULNAG | NA | SULNAGFHLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | SULTAN NAGA DIMAPORO |  | Territory 8 | 7.7951 | 123.7204 | SultanNagaDimaporo_Poblacion, Sultan Naga Dimaporo (Karomatan), Lanao Del Norte | TUBOD | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1257 | TABAK | NA | TABAKFHKLWXY TCFGAUPULACANLABANGZDSFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LABANGAN |  | Territory 8 | 7.9138 | 123.4877 | Upper Pulacan, Labangan, Zamboanga Del Sur | TUBOD | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN585 | TABINA | NA | TABINAFLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | TABINA |  | Territory 8 | 7.4604 | 123.4128 | Tabina_Poblacion, Tabina, Zamboanga Del Sur | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN255 | TAGOLN | NA | TAGOLNFKLWY TCFGAKIAZARTGOLOALDNFKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | TAGOLOAN |  | Territory 8 | 8.1376 | 124.2715 | Kiazar (Pob.), Tagoloan, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1236 | TAGTIC | NA | TAGTICFHLWY TCFGATAGTICKPATAGLDNFHLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KAPATAGAN |  | Territory 8 | 7.9349 | 123.6395 | Taguitic, Kapatagan, Lanao Del Norte | TUBOD | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN586 | TALUSA | NA | TALUSAFLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TALUSAN |  | Territory 8 | 7.4264 | 122.8096 | Poblacion (Talusan), Talusan, Zamboanga Sibugay | MIMELD | PHILTOWER | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN256 | TAMBO | ILG_002_GPONA_01, ILG_002_GPONA_02 | TAMBOFKLVWXY TAMBOVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2441 | 124.2544 | Santo Rosario, Iligan City, Lanao Del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN326 | TAMBUL | TBG_001_GPONA_01 | TAMBULFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | TAMBULIG |  | Territory 8 | 8.0688 | 123.5416 | BLISS site Calolot, Tambulig, Zamboanga Del Sur | OZAMIS | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN268 | TAMPAR | NA | TAMPARFWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | TAMPARAN |  | Territory 8 | 7.8654 | 124.3301 | Linuk, Tamparan, Lanao Del Sur | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN538 | TAMPIL | NA | TAMPILFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | TAMPILISAN |  | Territory 8 | 7.9737 | 122.6649 | Poblacion (Tampilisan), Tampilisan, Zamboanga Del Norte | IPIL | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 85 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1201 | TAMPL2 | NA | TAMPL2FHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | TAMPILISAN |  | Territory 8 | 7.9535 | 122.6489 | Znac, Tampilisan, Zamboanga Del Norte | IPIL | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 86 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2267 | TANGKILANSINDANZDN | NA | TANGKILANSINDANZDNFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SINDANGAN |  | Territory 8 | 8.295 | 123.0026 | Datu Tangkilan, Sindangan, Zamboanga del Norte, Philippines | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 87 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1328 | TGB-701 | TGB_701_GPONA_01 | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TANGUB CITY |  | Territory 8 | 8.0669 | 123.7467 | HUAWEI CABINET ALONG FIRST STREET NEAR JUNJING COPRA BUYER, BARANGAY THIRD, TANGUB CITY | OZAMIS | GT | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN257 | TIBANG | NA | TIBANGFKLVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.239 | 124.2442 | Tibanga Highway Tibanga, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN645 | TIGBAN | NA | TIGBANFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TUNGAWAN |  | Territory 8 | 7.5586 | 122.4095 | Langon, Tungawan, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN588 | TIGBAW | NA | TIGBAWFKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | TIGBAO |  | Territory 8 | 7.8337 | 123.2243 | Purok 2 Tigbao, Tigbao, Zamboanga Del Sur | MIMELD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN889 | TIGPAL | NA | TCFGATIGPALAYTUNGAWZSIBFHKLWY TIGPALFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TUNGAWAN |  | Territory 8 | 7.4874 | 122.3384 | Tigpalay, Tungawan, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN590 | TIGUMA | NA | TCFGABULATOKPGDIANZDSFHKLY TIGUMAFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8453 | 123.4458 | Bulatok, Pagadian City, Zamboanga Del Sur | TUBOD | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1150 | TINAPO | NA | TCFGATIPANOYILIGANLDNFHKLWYOFH TINAPOFHKLWXYS | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1956 | 124.2535 | Tipanoy, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN327 | TIPAN | NA | TIPANFLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY |  | Territory 8 | 8.5041 | 123.7697 | Purok 7 Tipan, Oroquieta City, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN591 | TITAY | TIY_001_GPONA_01 | TITAYFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TITAY |  | Territory 8 | 7.8701 | 122.5628 | Titay_Poblacion (Titay), Titay, Zamboanga Sibugay | IPIL | PHILTOWER | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1206 | TNAPO2 | NA | TCFGABARAASILIGANLDNFKLVWY TNAPO2FKLVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2096 | 124.242 | Baraas Tubod, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1095 | TOPLAH | DPL_001_GPONA_01 | TOPLAHFHKKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.59 | 123.3418 | Quezon Ave cor Echavez St Barra (Pob.), Dipolog City, Zamboanga Del Norte | DAPITA | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN258 | TRNSCO | NA | TRNSCOZ | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1827 | 124.1999 | Transco Compound Maria Cristina, Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN742 | TUBIGA | NA | TUBIGAFLVWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | INITAO |  | Territory 8 | 8.5377 | 124.3211 | Tubigan, Initao, Misamis Oriental | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN707 | TUBOD | ILG_003_GPONA_01, ILG_003_GPONA_02 | TUBODFHLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | TUBOD |  | Territory 8 | 8.0525 | 123.7903 | Mabini St., Tubod_Poblacion, Tubod, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN328 | TUDELA | TUD_001_GPONA_01 | TUDELAFHKLX | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TUDELA |  | Territory 8 | 8.2494 | 123.8334 | Purok 6 Gumbil, Tudela, Misamis Occidental | CLAMBA | PHILTOWER | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN802 | TUKURA | TUK_001_GPONA_01 | TUKURAFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | TUKURAN |  | Territory 8 | 7.856 | 123.5792 | Curvada, Tukuran, Zamboanga Del Sur | TUBOD | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN592 | TUNGAW | TWN_001_GPONA_01 | TUNGAWFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TUNGAWAN |  | Territory 8 | 7.6017 | 122.4208 | Libertad (Pob.), Tungawan, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN646 | TVISIO | NA | TVISIOFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIOCON |  | Territory 8 | 7.7324 | 122.2769 | TVI Siocon Mining Poblacion (Siocon), Siocon, Zamboanga Del Norte | IPIL | GT | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1599 | ZDNPH | NA | ZDNPHFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.6022 | 123.3506 | Zamboanga del Norte Provl.,Hosp. Sergio Osmena St Biasong (Pob.), Dipolog City, Zamboanga Del Norte | DAPITAN | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2036 | ROBILIGAN | NA | ROBILIGAN1IDFWYFWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2188 | 124.2394 | Macapagal Ave., Poblacion, ILIGAN CITY, LANAO DEL NORTE, REGION X (NORTHERN MINDANAO), MIN | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2376 | RUPAGANBCOLODLDN | NA | RUPAGANBCOLODLDNFKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | BACOLOD |  | Territory 8 | 8.1916 | 124.0527 | Rupagan, BACOLOD, LANAO DEL NORTE | ILIGAN | GT | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2319 | SANISIDTUNGAWZSIB | NA | SANISIDTUNGAWZSIBFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TUNGAWAN |  | Territory 8 | 7.6772 | 122.3517 | San Isidro, TUNGAWAN, ZAMBOANGA SIBUGAY | IPIL | UNITY | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2388 | SISAYTUNGAWZSIB | NA | SISAYTUNGAWZSIBFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TUNGAWAN |  | Territory 8 | 7.6257 | 122.3732 | Sisay, TUNGAWAN, ZAMBOANGA SIBUGAY | IPIL | PHILTOWER | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2265 | MAKILASIPILZSIB | NA | MAKILASIPILZSIBFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.723 | 122.5291 | Makilas_IpilZS | IPIL | PHILTOWER | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2709 | DAWODPITANZDN | NA | DAWODAPITANZDNFHLWYNX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6476 | 123.4178 | Brgy_Dawo (pob)_Dapitan City_Zambodelnorte | DAPITA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2377 | BAYBAYKOLAMBLDN | KOL_001_GPONA_01 | BAYBAYKOLAMBLDNFLVWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KOLAMBUGAN |  | Territory 8 | 8.1105 | 123.8878 | BrgyLibertad_Kolambugan_LanaodelNorte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2030 | GNPOWERLEGZ | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1835 | 124.0829 | Kauswagan, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1926 | ILIGAN TELIC | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2474 | 124.2469 | Purok 2, Santiago, ILIGAN CITY, LANAO DEL NORTE, REGION X (NORTHERN MINDANAO), MIN | ILIGAN | GT | [6 empty] | #N/A
MIN2020 | ABUNOILIGANLDNCOW | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1847 | 124.2161 | St. Vincent Ferrer church, Zone Madasigon 1, Brgy. Suarez Iligan City¦ | ILIGAN | GT | [6 empty] | #N/A
MIN2492 | DAPITA_D | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6478 | 123.419 | Gloria de Dapitan (Fantasyland),, Dawo (Pob.), DAPITAN CITY, ZAMBOANGA DEL NORTE, REGION IX (ZAMBOANGA PENINSULA), MIN | DAPITA | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW25 | PULACANLABANGZDSCOW | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LABANGAN |  | Territory 8 | 7.9112 | 123.4977 | 1ST INFANTRY DIVISION, PULACAN, LABANGAN MILITARY CAMP ZAMBOANGA DEL SUR | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW29 | ALBIAMARAWILDSCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY |  | Territory 8 | 7.9983 | 124.2925 | AL-BIRUNI INTERNATIONAL ACADEMY (ALBIA), INC, MSU CAMPUS, MARAWI CITY ¦ | ILIGAN | GT | [6 empty] | #N/A
MIN2715 | ILANGSJOSEPGDIANZDS | NA | ILANGSJOSEPGDIANZDSFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8355 | 123.4305 | Purok Santan-B, Brgy San Jose | TUBOD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2545 | P10POBMANTICMOR | NA | P10POBMANTICMORFHKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MANTICAO |  | Territory 8 | 8.4036 | 124.2859 | Manticao, Misamis Oriental, Philippines | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2361 | SIARISINDANZDN | NA | SIARISINDANZDNFKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SINDANGAN |  | Territory 8 | 8.3217 | 122.9877 | Siari, Sindangan, Zamboanga del Norte, Philippines | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 88 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2315 | PALOMOCTITAYZSIB | NA | PALOMOCTITAYZSIBFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TITAY |  | Territory 8 | 7.9145 | 122.5982 | BrgyPalomoc_Titay_ZS | IPIL | UNITY | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3119 | TABIDOZAMISMOCC | NA | TABIDOZAMISMOCCFHKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.111 | 123.797 | CapSite_BrgyTabid_OzamisCity | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW28 | POBILIGANLDNCOW | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2288 | 124.2387 | Dy Pico, Iligan City, Misamis Oriental, Philippines | ILIGAN | GT | [6 empty] | #N/A
MIN2714 | YSAGLUMBIAPGDIANZDS | NA | YSAGLUMBIAPGDIANZDSFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8275 | 123.4429 | Upper Lumbia,Pagadian City | TUBOD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2964 | GTSTOREOROQUIMOCCPC | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY |  | Territory 8 | 8.4827 | 123.8058 | E. Enerio St, Oroquieta City, Misamis Occidental, Philippines | CLAMBA | GT | [6 empty] | #N/A | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3574 | PGD-901 | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8251 | 123.4396 | Alano Ave. Corner Cabrera Sts.Pagadian City | TUBOD | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2584 | POBSAGUIALDS | NA | POBSAGUIALDSFHLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | SAGUIARAN |  | Territory 8 | 8.0362 | 124.2706 | Brgy. Poblacion, Saguiaran, Lanao del Sur | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2723 | SAMPANAPOLPGDIANZDS | PGD_013_GPONA_01 | SAMPANAPOLPGDIANZDSFLVX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8167 | 123.4137 | Napolan_PagadianCity_ZamboangaDelSur | DAO | GT | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2362 | TIGUHALPUYANZDS | NA | TIGUHALPUYANZDSFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.7041 | 123.2077 | Tiguha, Zamboanga del Sur, Philippines | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3171 | AGUADAOZAMISMOCC | NA | AGUADAOZAMISMOCCFW | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1487 | 123.8423 | Brgy. Aguada, Ozamis City | OZAMIS | FTAP | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3170 | TALAIRONOROQUIMOCC | NA | TALAIRONOROQUIMOCCFKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY |  | Territory 8 | 8.4658 | 123.8032 | Calamba, Misamis Occidental, Philippines | CLAMBA | PHILTOWER | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2720 | BLINTAWAKPGDIANZDS | PGD_009_GPONA_01 | BLINTAWAKPGDIANZDSFLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8312 | 123.4029 | BALINTAWAK | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3144 | BLANCIAMOLAVEZDS | NA | BLANCIAMOLAVEZDSFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MOLAVE |  | Territory 8 | 8.0792 | 123.4915 | MOLAVE_Reloc, Purok Maloloy-on, Blancia,Molave, Zamboanga del Sur | OZAMIS | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2721 | BVISTAPGDIANZDS | NA | BVISTAPGDIANZDSFLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8237 | 123.4065 | Baloyboan_PagadianCity_ZamboangaDelSur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2719 | KAGWASANPGDIANZDS | NA | KAGWASANPGDIANZDSFLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8726 | 123.4226 | Bogo_PagadianCity_ZamboangaDelSur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3143 | LANGATIANPROXASZDN | NA | LANGATIANPROXASZDNFHL | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | PRESIDENT ROXAS |  | Territory 8 | 8.5196 | 123.2345 | RoxasM Reloc, Brgy.Poblacion, roxas, zamboanga del norte | DAPITAN | PHILTOWER | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 89 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3121 | MACRISBALOILDN | NA | MACRISBALOILDNFKLVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1579 | 124.2035 | BrgyMaria-Cristina_ILIGAN CITY_LANAO DEL NORTE | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3118 | P4AGUADAOZAMISMOCC | NA | P4AGUADAOZAMISMOCCFKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1511 | 123.8452 | CapSite_BrgyLam-an_OzamisCity | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3181 | PULOTOZAMISMOCC | NA | PULOTOZAMISMOCCFKLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1289 | 123.8115 | BrgyPulot_OzamisCity | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3185 | SOUTHGALASDPOLOGZDN | NA | SOUTHGALASDPOLOGZDNFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5194 | 123.2316 | Purok Kalamboan, Sta Filomena, Dipolog City, Zamboanga Del Norte | DAPITAN | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2870 | TUBODILIGANLDN | NA | TUBODILIGANLDNFLX | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2121 | 124.2354 | Brgy. Tubod, Iligan City, Lanao del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2722 | TUGASBALANGPGDIANZDS | NA | KAPALBALANGPGDIANZDSFLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8234 | 123.4243 | Brgy. Balangasan, Pagadian City, Zamboanga del Sur | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2340 | GUINOMANDIPLAZSIB | NA | GUINOMANDIPLAZSIBFKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | DIPLAHAN |  | Territory 8 | 7.8279 | 122.9527 | Brgy. Guinoman, Diplahan, Zamboanga Sibugay | MIMELD | PHILTOWER | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2711 | PANGIPILZSIB | IPI_004_GPONA_01 | PANGIPILZSIBFL | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.7993 | 122.6148 | Brgy. Pangi, Ipil, Zamboanga Sibugay | IPIL | PHILTOWER | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2551 | P5POBNAAWANMOR | NA | P5POBNAAWANMORFKLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | NAAWAN |  | Territory 8 | 8.4328 | 124.2889 | Aguada (Pob.), Ozamis City, Misamis Occidental | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2724 | NAGMAHALDAOPGDIANZDS | NA | NAGMAHALDAOPGDIANZDSFLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8454 | 123.427 | Prk Nagmahal, Dao | DAO | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3124 | TURNO3DPOLOGZDN | NA | TURNO3DPOLOGZDNFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5753 | 123.3605 | Dapitan City, Zamboanga del Norte, Philippines | DAPITAN | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3180 | P4BAGAKAYOZAMISMOCC | NA | P4BAGAKAYOZAMISMOCCFKLVWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1424 | 123.8151 | Purok 4, Bagakay, Ozamiz City, Misamis Occidental, Philippines | OZAMIS | UNITY | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3186 | FILOMENADPOLOGZDN | NA | FILOMENADPOLOGZDNFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5658 | 123.3375 | Filomena, Dipolog City | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3248 | HINAPLANONILIGANLDN | NA | HINAPLANONILIGANLDNFLX | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2509 | 124.2629 | Purok2, Hinaplanon, Iligan City, Lanao del Norte, Philippines | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3251 | TAMBACANILIGANLDN | NA | TAMBACANILIGANLDNFKLWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2244 | 124.2344 | Brgy Tambacan, Iligan City, Lanao del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3249 | ORCHSANTIAGILIGANLDN | NA | ORCHSANTIAGILIGANLDNFKLVWXY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2524 | 124.248 | Santiago, Iligan City, Lanao Del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3333 | SANITOIPILZSIB | NA | SANITOIPILZSIBFLWX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.7896 | 122.5931 | Barangay Sanito, Ipil, Zamboanga Sibugay | IPIL | PHILTOWER | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3708 | BANGKEROHANIPILZSIB | NA | BANGKEROHANIPILZSIBFX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.7722 | 122.5857 | Bangkerohan, Ipil, Zamboanga Sibugay, Philippines | IPIL | PHILTOWER | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2712 | TAWAGSURPGDIANZDS | NA | TAWAGSURPGDIANZDSFX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8421 | 123.4787 | Bulanit_PagadianCity_ZamboangaDelSur | TUBOD | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3488 | SNTALUCIAPGDIANZDS | NA | SNTALUCIAPGDIANZDSFX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8196 | 123.433 | CapSite_BrgySantaLucia(Pob)_PagadianCity | DAO | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3709 | POB2IPILZSIB | NA | POB2IPILZSIBFX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.7817 | 122.5884 | 2020_CapSIte_BrgypobIpil_ZSIB | IPIL | PHILTOWER | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3710 | TAWAYIPILZSIB | NA | TAWAYIPILZSIBFX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.8039 | 122.5849 | 2020_CapSIte_BrgyTaway_Ipil_ZSIB | IPIL | PHILTOWER | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3699 | TAMPILMARAWILDS | NA | TAMPILMARAWILDSFLVWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY |  | Territory 8 | 8.0153 | 124.2885 | 2020CapSite_BrgyTampilong_MarawiCity_LDS | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2547 | POBLUGAITMOR | NA | POBLUGAITMORFLWXY | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LUGAIT |  | Territory 8 | 8.3435 | 124.2588 | Brgy. Poblacion, Lugait, Misamis Oriental | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3169 | MALAUBNGOZAMISMOCC | NA | MALAUBNGOZAMISMOCCFLW | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.134 | 123.8293 | Brgy. Malaubang, Ozamiz, Misamis Occidental | OZAMIS | PHILTOWER | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3184 | TALISAYDPITANZDN | NA | TALISAYDPITANZDNFWX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6662 | 123.4193 | Purok Matagobtob, Talisay, Dapitan City, Zamboanga Del Norte | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3362 | DICAYASDPOLOGZDN | NA | DICAYASDPOLOGZDNFKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5879 | 123.3584 | Brgy. Dicayas, Dipolog City, Zamboanga Del Norte | DAPITA | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3305 | TURNO1DPOLOGZDN | NA | TURNO1DPOLOGZDNFKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.5853 | 123.3507 | Brgy. Turno, Dipolog City, Zamboanga Del Norte | DAPITAN | PHILTOWER | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3149 | Z2SUAREZILIGANLDN | NA | Z2SUAREZILIGANLDNFWX | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1879 | 124.2178 | Zone Aries II, Brgy. Suarez, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3551 | TCFGAAGUA2OZAMISMOCC | NA | TCFGAAGUA2OZAMISMOCCFHLWY | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1545 | 123.8478 | Brgy. Aguada, Ozamis City, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3639 | MAKIANGMOLAVEZDS | NA | MAKIANGMOLAVEZDSFWX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MOLAVE |  | Territory 8 | 8.0888 | 123.4882 | PUROK MAKIANGAYON BLANCIA MOLAVE, ZAMBOANGA DEL SUR | OZAMIS | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3737 | BONGBONGOZAMISMOCC | NA | BONGBONGOZAMISMOCCFW | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1355 | 123.8155 | Brgy. Bongbong, Ozamis City, Misamis Occidental | OZAMIS | GT | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3329 | TCFGAP8HINAILIGANLDN | NA | TCFGAP8HINAILIGANLDNFLW | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2516 | 124.2708 | Upper Hinaplanon, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3247 | PALAOILIGANLDN | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.231 | 124.2494 | Brgy Palao,Iligan City, Lanao Del Norte | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3189 | MAGDAUPIPILZSIB | NA | MAGDAUPIPILZSIBFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL |  | Territory 8 | 7.7481 | 122.5819 | P/Acacia, Brgy Magdaup, Ipil, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3148 | MALAMBUSIOCONZDN | NA | MALAMBUSIOCONZDNFWX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | SIOCON |  | Territory 8 | 7.6072 | 122.1219 | Brgy.malambuhangin, siocon,zamboanga del norte | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3583 | TCAICALANGAURORAZDS | NA | TCAICALANGAURORAZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | AURORA |  | Territory 8 | 7.9425 | 123.5827 | Brgy. Alang-Alang, Aurora, Zamboanga Del Sur | TUBOD | UNITY | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3645 | TCFGAESTAKADPOLOGZDN | NA | TCFGAESTAKADPOLOGZDNFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY |  | Territory 8 | 8.578 | 123.3459 | Brgy. Estaka, Dipolog City, Zamboanga del Norte | DAPITA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3307 | TCFGABCOLDOZAMISMOCC | NA | TCFGABCOLDOZAMISMOCCF_DFLW | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1724 | 123.8455 | Brgy. Bacolod, Ozamis City, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW60 | TUKAPUALDNCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | PUALAS |  | Territory 8 | 7.7894 | 124.0729 | Diamla, Pualas, Lanao del Sur | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4015 | TCAICKAWITPGDIANZDS | NA | TCAICKAWITPGDIANZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.828 | 123.4499 | Brgy. Kawit, Pagadian City Zamboanga del Sur | TUBOD | UNITY | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3584 | TCAICVILLARPGDIANZDS | NA | TCAICVILLARPGDIANZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8283 | 123.4247 | Lot No. 4 Purok Villarin, Barangay Banale, Pagadian City | DAO | UNITY | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3602 | TCAICZ3MURIPGDIANZDS | NA | TCAICZ3MURIPGDIANZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8219 | 123.4667 | Purok Zone 3, Brgy. Muricay, Pagadian City, Zamboanga del Sur | TUBOD | UNITY | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3803 | TCFGADMLUNAMARAWILDS | MRW_001_GPONA_01 | TCFGADMLUNAMARAWILDSFLW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY |  | Territory 8 | 7.9989 | 124.2573 | 2nd Street, MSU Campus, Marawi City, Lanao del Sur | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3879 | TCFGABANADEROZAMISMOCC | NA | TCFGABANADEROZAMISMOCCFLW | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY |  | Territory 8 | 8.1494 | 123.8218 | National Highway, Brgy. Banadero, Ozamis City, Misamis Occidental | OZAMIS | FTAP | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3998 | TCLDCSANMIGILIGANLDN | NA | TCLDCSANMIGILIGANLDNFW | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | Iligan City |  | Territory 8 | 8.2402 | 124.2496 | Brgy. San Miguel ,Iligan City, Lanao Del Norte | ILIGAN | LDIC | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3532 | TCFGAORODPITANZDN | NA | TCFGAORODPITANZDNLY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6771 | 123.4531 | Mapang - Mapang, Oro, Dapitan City, Zamboanga del Norte | DAPITA | FTAP | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4037 | TCAICBALINPGDIANZDS | NA | TCAICBALINPGDIANZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY (CAPITAL) |  | Territory 8 | 7.8373 | 123.3986 | Brgy. Balintawak, Pagadian City, Zamboanga City | DAO | UNITY | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3309 | TCLDCPALAO02ILIGANLDN | NA | TCLDCPALAO02ILIGANLDNFW | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2283 | 124.2458 | Brgy Palao, Iligan City, Lanao Del Norte | ILIGAN | LDIC | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2157 | 101st Infantry Brigade | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | Pinan Municipal |  | Territory 8 | 8.4848 | 123.4527 | 101st Brigade Camp at Brgy Del Pilar, Pinan, Zambo del Norte | CLAMBA | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2762 | Camp Pintoy - 103rd BGE | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.1846 | 124.216 | Camp Pintoy Suarez Iligan City | ILIGAN | GT | [6 empty] | #N/A
MIN2763 | Gloria de Dapitan Complex ( Fantasyland Dapitan) | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6448 | 123.418 | Gloria de Dapitan Complex, Brgy. Dawo, Dapitan City | DAPITAN | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3527 | Dominique Square Subd, Iligan City | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2198 | 124.2526 | Dominique Square Subd, Iligan City | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2703 | DELAUSMDALUMLDS | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MADALUM |  | Territory 8 | 7.8545 | 124.1141 | Delausan, Madalum, Lanao del Sur | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2318 | SANTONIORLIMZSIB | NA | SANTONIORLIMZSIBFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | ROSELLER LIM |  | Territory 8 | 7.6961 | 122.4234 | Don Perfecto, Roseller T Lim, Zamboanga Sibugay | IPIL | FTAP | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4175 | TCISMALORTANGUIBMOCC | NA | TCISMALORTANGUIBMOCCFW | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TANGUB CITY |  | Territory 8 | 8.0633 | 123.7537 | Brgy. Maloro, Tangub City, Misamis Occidental | OZAMIS | ISON | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3603 | TCLBSNEWLABANGZDS | NA | TCLBSNEWLABANGZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LABANGAN |  | Territory 8 | 7.8591 | 123.5014 | Brgy. New Labangan, Labangan, Zamboanga del Sur | TUBOD | LDIC | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3883 | MDASIGONMOLAVEZDS | NA | MDASIGONMOLAVEZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MOLAVE |  | Territory 8 | 8.097 | 123.4872 | Mabini St Brgy. Madasigon, Molave, Zamboanga del Sur | OZAMIS | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4173 | TCISGULAYDPOLOGZDN | NA | TCISGULAYDPOLOGZDNLY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (CAPITAL) |  | Territory 8 | 8.5584 | 123.3673 | Brgy. Gulayon, Dipolog City, Zamboanga del Norte | DAPITA | ISON | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4166 | TCAGMARANDKPATAGLDN | NA | TCAGMARANDKPATAGLDNFW | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KAPATAGAN |  | Territory 8 | 7.9249 | 123.7688 | Brgy. Maranding, Kapatagan, Lanao del Norte | TUBOD | ALT GLOBAL | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4169 | TCAGPOBLKPATAGLDN | NA | TCAGPOBLKPATAGLDNFW | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KAPATAGAN |  | Territory 8 | 7.9002 | 123.773 | Brgy. Poblacion, Kapatagan, Lanao del Norte | TUBOD | ALT GLOBAL | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4188 | TCAGHINAPILIGANLDN | NA | TCAGHINAPILIGANLDNFW | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2484 | 124.2577 | Brgy. Hinaplanon, Iligan City | ILIGAN | ALT GLOBAL | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3886 | TORPOBILIGANLDN | NA | TORPOBILIGANLDNFW | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2282 | 124.2401 | Torralba St., Brgy Poblacion, Iligan City, Lanao Del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2316 | SAMPOLIDIPLAZSIB | NA | SAMPOLIDIPLAZSIBFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | DIPLAHAN |  | Territory 8 | 7.7831 | 122.9617 | Sampoli B, DIPLAHAN, ZAMBOANGA SIBUGAY | MIMELD | PHILTOWER | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3250 | MARIACHRISILIGANLDN | NA | MARIACHRISILIGANLDNFKLWY | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | Iligan City |  | Territory 8 | 8.2012 | 124.2054 | Maria Christina, Iligan City, Lanao Del Norte | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3252 | MAHAYAHAYILIGANLDN | NA | MAHAYAHAYILIGANLDNFLW | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | Iligan City |  | Territory 8 | 8.2219 | 124.2382 | Mahayhay, Iligan City, Lanao Del Noete | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4204 | TCAGP5TIBANGILIGANLDN | NA | TCAGP5TIBANGILIGANLDNFW | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2378 | 124.2398 | Purok 5 Canaway, Brgy.Tibanga,Iligan City,Lanao Del Norte | ILIGAN | ALT GLOBAL | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4176 | TCISOLINGDPOLOGZDN | NA | TCISOLINGDPOLOGZDNLY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (CAPITAL) |  | Territory 8 | 8.527 | 123.317 | Brgy. Olingan, Dipolog City, Zamboanga del Norte | DAPITA | ISON | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4180 | TCISSTAFILDPOLOGZDN | NA | TCISSTAFILDPOLOGZDNLY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (CAPITAL) |  | Territory 8 | 8.5663 | 123.3452 | Brgy. Santa Filomina, Dipolog City, Zamboanga del Norte | DAPITA | ISON | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4181 | TCISSCAYABDPITANZDN | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (CAPITAL) |  | Territory 8 | 8.6307 | 123.3509 | Brgy. Sicayab Bocana, Dapitan City, Zamboanga del Norte | DAPITAN | ISON | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4182 | TCISSTCRUZDPITANZDN | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN CITY |  | Territory 8 | 8.6578 | 123.4198 | Brgy. Santa Cruz, Dapitan City, Zamboanga del Norte | DAPITA | ISON | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3805 | TCAGEBABAKMARAWILDS | NA | TCAGEBABAKMARAWILDSFLW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY (CAPITAL) |  | Territory 8 | 8.0073 | 124.2725 | Brgy. East Babak/D3, Marawi City, Lanao Del Sur | ILIGAN | ALT GLOBAL | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2356 | TAGUISIANMBUHAYZSIB | NA | TAGUISIANMBUHAYZSIB | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | MABUHAY |  | Territory 8 | 7.3648 | 122.971 | Taguisian, MABUHAY, ZAMBOANGA SIBUGAY | MIMELD | GT | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3997 | TCLDCBALINTPGDIANZDS | NA | TCLDCBALINTPGDIANZDSFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY |  | Territory 8 | 7.8273 | 123.4147 | Purok Salingsing 2, Brgy. Balintawak, Pagadian City, Zamboanga del Sur | DAO | LDIC | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4152 | TCISLABUYTANGUIBMOCC | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TANGUB CITY |  | Territory 8 | 8.0627 | 123.721 | Brgy.Labuyo, TANGUB CITY, MISAMIS OCCIDENTAL | OZAMIS | ISON | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3531 | TCFGABAYABAOBUTIGLDS | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | BUTIG |  | Territory 8 | 7.7439 | 124.307 | Bayabao Poblacion, Butig, Lanao Del Sur | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4240 | TCAICKULAMBUGRLIMZSIB | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | ROSELLER LIM |  | Territory 8 | 7.652 | 122.474 | Brgy. Kulambugan, RT Lim, Zamboanga Sibugay | IPIL | UNITY | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4239 | TCAICMAGSAYRLIMZSIB | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | ROSELLER LIM |  | Territory 8 | 7.6416 | 122.4614 | BRGY. MAGSAYSAY R.T LIM, ZAMBOANGA SIBUGAY | IPIL | UNITY | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3985 | TCEDCSTACRUZKBASALZSIB | NA | TCEDCSTACRUZKBASALZSIB | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | KABASALAN |  | Territory 8 | 7.7976 | 122.7648 | BRGY. STA CRUZ, KABASALAN, ZAMBOANGA SIBUGAY | MIMELD | EDOTCO | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4206 | TCISCANUBOROQUIMOCC | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY (CAPITAL) |  | Territory 8 | 8.4925 | 123.7994 | BARANGAY CANUBAY, OROQUIETA CITY, Misamis Occidental | CLAMBA | ISON | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4123 | TCDTDATUPANSBUUGZSIB | NA | TCDTDATUPANSBUUGZSIB | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | BUUG |  | Territory 8 | 7.7251 | 123.0627 | Datu Panas St. Poblacion, Buug, Zamboanga Sibugay | MIMELD | SBA | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4205 | TCDTIMIARPOBBUUGZSIB | NA | TCDTIMIARPOBBUUGZSIB | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | BUUG |  | Territory 8 | 7.7268 | 123.0511 | Miari, Brgy. Poblacion, Buug, Zamboanga Sibugay | MIMELD | SBA | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4334 | TCAGCESPOBTUBODLDN | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | TUBOD (Capital) |  | Territory 8 | 8.0445 | 123.7932 | Brgy. Poblacion, Tubod (Capital), Lanao Del Norte | TUBOD | ALT GLOBAL | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4363 | TCAGTAMBACILIGANLDN | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | CITY OF ILIGAN |  | Territory 8 | 8.2257 | 124.2368 | Brgy. Tambacan, Iligan City, Lanao Del Norte | ILIGAN | ALT GLOBAL | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4191 | TCAICSTFILDPOLOGZDN | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (Capital) |  | Territory 8 | 8.5717 | 123.3398 | Brgy. Santa Filomena, Dipolog City, Zamboanga del Norte | DAPITAN | UNITY | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3361 | TCEDCP2DALIPILIGANLDN | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.3097 | 124.2584 | Dalipuga, Iligan, Lanao del Norte | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3322 | TCAICPUGAANILIGANLDN | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.227 | 124.2743 | Brgy Pug-an, Iligan CIty, Lanao Del Norte | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4371 | TCAICMARAWPOBMARAWILDS | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY (Capital) |  | Territory 8 | 8.0068 | 124.2792 | Brgy. Raya Saduc, Marawi City, Lanao del Sur | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2561 | TCEDCTAMBOPIAGAPLDS | NA | TCEDCTAMBOPIAGAPLDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | Piagapo |  | Territory 8 | 7.9823 | 124.1842 | Brgy. Katumbacan, PIAGAPO, LANAO DEL SUR | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2854 | TCEDCDMALUNAMARAWILDS | NA | TCEDCDMALUNAMARAWILDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY (CAPITAL) |  | Territory 8 | 7.995 | 124.2521 | Brgy.Dimalna,Marawi City,lanao Del sur | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4336 | TCEDCCATPOBOROQUIMOCC | NA | TCEDCCATPOBOROQUIMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | CITY OF OROQUIETA (Capital) |  | Territory 8 | 8.4848 | 123.8031 | Catane St., Poblacion , Loboc, Oroquieta City, Misamis Occidental | CLAMBA | EDOTCO | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4629 | MINAOGDPOLOGZDNAS | NA | MINAOGDPOLOGZDNAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (CAPITAL) |  | Territory 8 | 8.5995 | 123.3448 | BrgyMinaog, Dipolog city Zamboanga Del Norte | DAPITAN | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4731 | TCEDCMONCHINGSIAYZSIB | NA | TCEDCMONCHINGSIAYZSIB | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | SIAY |  | Territory 8 | 7.7365 | 122.8348 | Brgy.Monching , SIAY , ZAMBOANGA SIBUGAY | IMELDA | EDOTCO | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4691 | TCAICSEBACTUDELAMOCC | NA | TCAICSEBACTUDELAMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TUDELA |  | Territory 8 | 8.2498 | 123.8453 | Brgy. Basirang, Tudela, Misamis Occidental | CLAMBA | UNITY | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4712 | TCEDCSANPEDROINITAOMOR | NA | TCEDCSANPEDROINITAOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | INITAO |  | Territory 8 | 8.4877 | 124.2984 | Brgy. San Pedro, Initao, Misamis Oriental | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4701 | TCISPOBSOUTHPOLANCZDN | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | POLANCO |  | Territory 8 | 8.5269 | 123.3598 | Pob. South, Polanco, Zamboanga Del Norte | DAPITAN | ISON | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4270 | SUNSETBLVDDPOLOGZDNAS | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (CAPITAL) |  | Territory 8 | 8.5871 | 123.3371 | Dipolog sunset boulevard, BrgyCentral, Dipolog City, Zamboanga Del Norte | DAPITAN | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4358 | TCEDCTOMASCABILILIGANLDN | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2072 | 124.2224 | Brgy. Tomas Cabili, Iligan City, Lanao Del Norte | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4732 | TCEDCMOHONALORANMOCC | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | ALORAN |  | Territory 8 | 8.3864 | 123.8325 | Brgy. Mohon, Aloran, Misamis Occidental | CLAMBA | EDOTCO | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4733 | TCAICRAWANLALALDN | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | LALA |  | Territory 8 | 8.0004 | 123.7793 | Brgy Raw-An, Lala, Lanao Del Norte | TUBOD | UNITY | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4700 | TCEDCP6LAPASACLARINMOCC | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | CLARIN |  | Territory 8 | 8.1918 | 123.8602 | PUROK 6, LAPASAN CLARIN, MISAMIS OCCIDENTAL | CLAMBA | EDOTCO | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4719 | TCCRESNVICENTEKTIPUNZDN | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | KATIPUNAN |  | Territory 8 | 8.4955 | 123.3035 | Brgy. San Vicente ,KATIPUNAN ,ZAMBOANGA DEL NORTE | DAPITAN | CREI | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 90 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4715 | TCEDCLUMBAYAOBLINDOLDS | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | BALINDONG |  | Territory 8 | 7.9102 | 124.1979 | Brgy. Poblacion (Balindong), Balindong (Watu), Lanao del Sur | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2565 | TCAICPOBBUBONGLDS | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | BUBONG |  | Territory 8 | 7.9846 | 124.3651 | Brgy. Poblacion, BUBONG, LANAO DEL SUR | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4717 | TCEDCSINONOCSNACABMOCC | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | SINACABAN |  | Territory 8 | 8.3109 | 123.8439 | Sitio Bahay, Brgy. Sinonoc, Sinacaban Misamis Occidental | CLAMBA | EDOTCO | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4621 | MARAWIPOBTEMP | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY |  | Territory 8 | 8.0037 | 124.2793 | Sagonsongan. Marawi City, Lanao del sur | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4612 | AMAYPACHOSPTEMP | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY |  | Territory 8 | 8.004 | 124.2839 | Amai Pakpak Medical Center, Marawi, City Lanao del Sur | ILIGAN | GT | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2699 | ANDRADELCARILIGANLDN | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2368 | 124.2592 | Andrada Heights Subdivision, DelCarmen,IliganCity | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4112 | TCAGPOBWESTBALOILDN | NA | NA | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | BALOI |  | Territory 8 | 8.1129 | 124.2213 | Brgy. West Poblacion, Baloi, Lanao Del Norte | ILIGAN | ALT GLOBAL | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4743 | TCAICLILSADUCMARAWILDS | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY |  | Territory 8 | 8.0098 | 124.291 | Marcos Blvd. Capitol Hills, Brgy. Lilod Saduc, City Of Marawi (Capital), Lanao Del Sur | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4748 | TCEDCBARCELDPITANZDN | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DAPITAN |  | Territory 8 | 8.5256 | 123.4577 | Purok Daisy, Brgy. Barcelona, Dapitan City, Zamboanga del Norte | CLAMBA | EDOTCO | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4029 | TCPHTPOBINITAOMOR | NA | NA | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | INITAO |  | Territory 8 | 8.5039 | 124.3081 | Poblacion, Initao, Misamis Oriental | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4609 | BONIFACIODPOLOGZDNAS | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG |  | Territory 8 | 8.588 | 123.3416 | Bonifacio st., Brgy Barra, Dipolog City, Zamboanga del Norte | DAPITAN | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3608 | LILOY POI | NA | LILOY POI | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LILOY |  | Territory 8 | 8.112 | 122.6708 | Brgy. Fatima, Liloy Zamboanga del Norte | IPIL | GT | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 91 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4692 | TCAICEASTPOBRIZALZDN | NA | TCAICEASTPOBRIZALZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | RIZAL |  | Territory 8 | 8.5226 | 123.5534 | Brgy.East Poblacion , RIZAL , ZAMBOANGA DEL NORTE | CLAMBA | UNITY | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN879 | ALUDO | NA | ALUDUY1LUGUSSULUFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | LUGUS | Alu-Duyong | Territory 8 | 5.6814 | 120.8597 | Alu-Duyong, Lugus, Sulu | ZAMBO | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1616 | APLAYMANICA | NA | APLAYMANICAFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.0182 | 122.2024 | Aplaya, Manicahan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN540 | ASINAN | ZMB_035 | ASINANFHKLWXY TCFGAASINANRDZAMBOAZDSFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9474 | 122.1228 | Asinan Road Boalan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1760 | BALIWASANZDS | NA | BALIWASANZDSFKLMVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Baliwasan | Territory 8 | 6.916 | 122.0563 | Baliwasan, Zamboanga City, Zamboanga Del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1766 | BANGKALPTKUL | NA | BANGKALPTKULFHKLXZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO |  | Territory 8 | 6.0507 | 121.0177 | San Raymundo, Jolo, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN786 | BATOBA | NA | BATOBAFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | TANDUBAS |  | Territory 8 | 5.0745 | 119.8857 | Balimbing Proper, Panglima Sugala (Balimbing), TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1219 | BEGANG | NA | BEGANGFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.6858 | 122.0157 | Begang, City of Isabela, City of Isabela (Not a province) | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2502 | BGETABIAWAN | NA | BGETABIAWANLY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.7209 | 121.9857 | 104th Brigade, Tabiawan, Basilan | GTZAMBOFOCID | GT | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN566 | BLANCO | ZMB_030 | BLANCOFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9189 | 122.1552 | 9th St. H.J. Omar Arena Blanco, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN541 | BMORET | ZMB_003 / BALWSN-LSA06 | BMORETFHKLMWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9181 | 122.0618 | Delfin Compound Baliwasan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1420 | BNGAO2 | NA | BNGAO2FHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.03 | 119.7734 | Ridjiki Blvd. Bongao_Poblacion, Bongao, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN791 | BOALAN | NA | BOALANFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9557 | 122.1269 | Zone 5 Boalan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1405 | BOLONG | ZMB_021 | BOLONGFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.0997 | 122.2383 | Purok 6 Bolong, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN787 | BONGAO | NA | BONGAOFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.0341 | 119.7566 | Capitol Hills Bongao_Poblacion, Bongao, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1462 | BUDWAK | NA | KALIMBUDWA1PATKULSULUFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PATIKUL |  | Territory 8 | 6.0439 | 121.0112 | Kalimahayan Village, Latih, Patikul, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1397 | BUNGUI | NA | BUNGUIFHKLWXYV | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.1055 | 122.1944 | Bunguiao, Zamboanga City, Zamboanga Del Sur | VITALI | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2022 | CAMPBAROSULU | NA | CAMPBAROSULUFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | SIASI |  | Territory 8 | 5.5457 | 120.8164 | Campong Baro, Siasi, Sulu | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2522 | CAMPBAUTISTA | NA | CAMPBAUTISTAFWLYHK | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO |  | Territory 8 | 6.0563 | 121.0115 | Campo Busbus Jolo, Sulu | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1837 | CAMPBUDDATU | NA | TAGBAKINDANASULUFHKLWX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | INDANAN |  | Territory 8 | 6.0245 | 120.9965 | Camp Bud Datu, Alat, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1723 | CAMPUNOLAMIT | NA | CAMPUNOLAMITFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LAMITAN CITY |  | Territory 8 | 6.6105 | 122.1748 | Brgy.CampoUno_Lamitan_Basilan Campo Uno, City of Lamitan, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1202 | CANELR | NA | CANELRFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Cotta | Territory 8 | 6.9203 | 122.0723 | Canelar, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN801 | CATALI | ZMB_002 | CATALIFKLMVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Santa Catalina | Territory 8 | 6.9081 | 122.1031 | Dr. Evangelista Street Santa Catalina, Zamboanga City, Zamboanga Del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1768 | CATALINALEG | ZMB_004 | CATALINAZDSFKLVWXDY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Santa Catalina | Territory 8 | 6.908 | 122.0815 | Santa Catalina, Zamboanga City, Zamboanga Del Sur | ZAMBO | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1079 | CAWA2 | NA | CAWA2FHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | South Centro (Pob.) | Territory 8 | 6.9092 | 122.0636 | San Jose Cawacawa, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1755 | CHINPIERSULU | NA | CHINPIERSULUXZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO (Capital) | Alat | Territory 8 | 6.0486 | 120.9972 | Moore Avenue, Brgy Alat., Jolo, Sulu | ZAMBO | GT | [6 empty] | #N/A
MIN1635 | CIUDADMEDCTR | NA | CIUDADMEDCTRFWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Barangay Zone I (Pob.) | Territory 8 | 6.915 | 122.0768 | Ciudad Medical Center Brgy. Zone 1 Nunez Extension, Zamboanga City Arena Blanco, Zamboanga City, Zamboanga Del Sur | ZAMBO | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3524 | KM11MERCEDZAMBOAZDS | NA | KM11MERCEDZAMBOAZDSFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Quezon | Territory 8 | 6.9732 | 122.1434 | Zone II, Brgy. Culianan, Zamboanga City | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN544 | CURUAN | ZMB_039 | CURUANFHLXFHL TCFGACURUANZAMBOAZDSFHL | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Piel | Territory 8 | 7.2102 | 122.2316 | Curuan, Zamboanga City, Zamboanga Del Sur | VITALI | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN521 | DARUL | NA | DARULFLWXYV | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | LANGUYAN | Dulong Bayan | Territory 8 | 5.2661 | 120.0786 | Darussalam, Languyan, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN579 | DITA | ZMB_036 | DITAFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.1597 | 122.2345 | Poblacion, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2413 | DIVISORIAZDS | ZMB_006 | DIVISORIAZDSFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9472 | 122.1027 | MCLL HIGHWAY, BRGY. DIVISORIA, ZAMBOANGA CITY, ZAMBOANGA DEL SUR | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN548 | DVISOR | DVR_001 | DVISORFHKLXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9472 | 122.1122 | Zone II Bolan Divisoria, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN808 | EBENEZER | ZMB_022 | EBENEZERFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9232 | 122.022 | Calarian, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1047 | FALCAT | NA | FALCATFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Tetuan | Territory 8 | 6.9176 | 122.0942 | Falcatan Tetuan, Zamboanga City, Zamboanga Del Sur | ZAMBO | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN454 | GAEA | NA | GAEAFHKLWXYZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | TONGKIL | Kahikukuk | Territory 8 | 6.1328 | 121.8321 | Kahikukuk, Tongkil, Sulu | ZAMBO | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1844 | GOVALVZAMBOAZDS | NA | GOVALVZAMBOAZDSFKLMVWXY GOVALVZAMBOAZFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9135 | 122.0784 | Gov. Alverez Avenue Z. C. | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN549 | GOVRAM | NA | GOVRAMFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9303 | 122.0525 | Gov. Ramos St. San Roque, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1252 | GRANDE | NA | GRANDEFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9136 | 122.0528 | Baliwasan Grande, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1216 | GTZAMBOFOCID | ZMB_007 / TETUAN-LSA01 | GTZAMBOFOCIDFWXYDZDD | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Tetuan | Territory 8 | 6.9193 | 122.0809 | Don Toribio, Solidaridad sts Tetuan, Zamboanga City, Zamboanga Del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN794 | GUIWAN | ZMB_008 / GUIWAN-LSA06 | GUIWANFHKLMWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9273 | 122.092 | Daisy Road Guiwan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN13 | GUSU | GUSZAM-LSA06 | GUSUFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9193 | 122.0509 | San Jose Gusu, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN455 | INDANA | NA | INDANAFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | INDANAN |  | Territory 8 | 5.9729 | 120.9735 | Poblacion (Indanan), Indanan, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN830 | INDUST | ZMB_034 | INDUSTFKLVWXYPN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9701 | 121.9462 | Ayala Industrial Ayala, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1220 | ISABE2 | NA | POB1ISBELABASKLVYFW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.7052 | 121.9713 | Isabela Proper (Pob.), City of Isabela, City of Isabela (Not a province) | GTZAMBOFOCID | GT | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN828 | ISABEL | BSILAN-LSA06 | ISABELFHLVXZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.7017 | 121.9797 | Sunrise Village (Pob.), City of Isabela, City of Isabela (Not a province) | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN522 | JAKART | NA | JAKARTFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | LANGUYAN |  | Territory 8 | 5.3269 | 120.2164 | Jakarta (Lookan Latuan), Languyan, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN776 | JOLO | NA | JOLOFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO (Capital) | Walled City (Pob.) | Territory 8 | 6.0508 | 121.0018 | Scott Road Walled City (Pob.), Jolo, Sulu | ZAMBO | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN457 | JOLO2 | NA | JOLO2FHLXZFHL | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PATIKUL |  | Territory 8 | 6.0568 | 121.0191 | Sitio Palar Gandasuli, Patikul, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1245 | JOLO4 | NA | JOLO4XZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO |  | Territory 8 | 6.0587 | 121.0065 | Busbus, Jolo, Sulu | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN464 | KAJAT | NA | KAJAT KAJAT1INDANASULUFHKLWY KAJATX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | INDANAN | Kajatian | Territory 8 | 6.0448 | 120.9983 | Kajatian, Indanan, Sulu | ZAMBO | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1801 | KCC1ZAMBO | NA | KCC1ZAMBOFKWYFKWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Canelar | Territory 8 | 6.9201 | 122.0733 | KCC Mall of Zamboanga, Gov. Camins Road, Zamboanga City_Barangay Zone II (Pob.), Zamboanga City, Zamboanga Del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN559 | LABUAN | NA | LABUANFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.098 | 121.9031 | Labuan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1221 | LAMIT2 | NA | LAMIT2FHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LAMITAN CITY |  | Territory 8 | 6.6591 | 122.1387 | Quezon Blvd., Malinis (Pob.), City of Lamitan, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN631 | LAMITA | NA | LAMITAFHLXZZ LAMUTNTHZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LAMITAN CITY |  | Territory 8 | 6.6629 | 122.1397 | Malinis (Pob.), City of Lamitan, Basilan | GTZAMBOFOCID | GT | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1102 | LANGUYAN RELAY (DARUSALAMLANGUYTAWI) | NA | DARUSALAMLANGUYTAWIFL | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | LANGUYAN |  | Territory 8 | 5.2641 | 120.0999 | Adnin, Languyan, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN876 | LANTAKA | NA | LANTAKAFHLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Barangay Zone III (Pob.) | Territory 8 | 6.9028 | 122.0784 | Valderosa St., Zamboanga City_Barangay Zone III (Pob.), Zamboanga City, Zamboanga Del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN60 | LANTAW | NA | LANTAWFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LANTAWAN |  | Territory 8 | 6.6549 | 121.9008 | Atongatong, Lantawan, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1477 | LAUM | NA | LAUMFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | MAIMBUNG |  | Territory 8 | 5.9342 | 121.0244 | Brgy. Laum, Maimbung, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1618 | LNOTEBASILAN | NA | LNOTEBASILANKVXKLYFW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.6878 | 121.9821 | Lower Lanote, Isabela City, Caddayan, Akbar, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN563 | LUNZUR | ZMB_024 | LUNZURFKLVWXY TCFGAHARMONYZAMBOAZDSFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Lunzuran | Territory 8 | 6.958 | 122.0912 | Harmony St., Lunzuran, Zamboanga City, Zamboanga Del Sur | ZAMBO | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN458 | LUUK | NA | LUUKFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | LUUK | Tubig-Puti (Pob.) | Territory 8 | 5.9673 | 121.3119 | TubigPuti (Pob.), Luuk, Sulu | ZAMBO | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1246 | LUUK2 | NA | LUUK2FHLXZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | LUUK |  | Territory 8 | 6.0027 | 121.3073 | TanduBato, Luuk, Sulu | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN1147 | LUYAHN | ZMB_010 | LUYAHNFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Tumaga | Territory 8 | 6.9509 | 122.0791 | Luyahan, Zamboanga City, Zamboanga Del Sur | ZAMBO | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN61 | MALUSO | NA | TCFGATOWNSITEMLUSOFWLYVK | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | MALUSO |  | Territory 8 | 6.5436 | 121.8695 | Townsite (Pob.), Maluso, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN565 | MAMPA | ZMB_019 | MAMPAFKLVWXYMP | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9146 | 122.124 | Arquiza Drive Purok I Mampang, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1516 | MAMPAZAMBOA | NA | MAMPAZAMBOAFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9112 | 122.1402 | Purok 4, Kilometer 7, Mampang, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN554 | MANGUS | NA | MANGUSHFLXZJ | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.3491 | 122.2836 | Mangusu, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN567 | MANICA | ZMB_037 | MANICAFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.0187 | 122.1864 | National Road, Manicahan, Zamboanga City, Zamboanga Del Sur | VITALI | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN523 | MAPUN | NA | MAPUNJX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | MAPUN |  | Territory 8 | 6.9761 | 118.5082 | Mahalo, Mapun (Cagayan De TawiTawi), TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1614 | MARCOSPUTIK | NA | MARCOSPUTIKFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9353 | 122.0978 | Marcos Drive, Putik, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1307 | MASIN | NA | MASINFKLWYV | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9528 | 121.9791 | Maasin, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1615 | MENZIBASILAN | NA | MENZIBASILANFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.6868 | 121.9699 | Brgy. Menzi, Isabela City, Caddayan, Akbar, Basilan | GTZAMBOFOCID | GT | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN844 | MERCED | ZMB_023 | MERCEDFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9661 | 122.1675 | Calle Socorro, Balinsungay Mercedes, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN641 | MINDPR | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9089 | 122.0747 | MindProCitimall La Purisima street Zamboanga City_Barangay Zone II (Pob.), Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN553 | MKAWIT | ZMB_025 | MKAWITFHKLWXY TCFGADONMARTINZAMBOAZDSFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9463 | 121.987 | Dona Martina Drive Cawit, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN568 | MRCED2 | ZMB_018 | MRCED2FKLVWXY TCFGAREALMRCEDZAMBOAZDSFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9575 | 122.1448 | Real St. Mercedes, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN850 | MTCABA | NA | MTCABAFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9471 | 122.053 | Mt. Cabatangan Cabatangan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN606 | MTTAGU | NA | MTTAGUFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.2908 | 122.2725 | Mt. TaguiteTaguiti, Zamboanga City, Zamboanga Del Sur | VITALI | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1772 | NEW SIASI RELAY | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | SIASI |  | Territory 8 | 5.5275 | 120.8564 | Brgy Singko, Siasi Sulu | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN793 | ORCHID | NA | ORCHIDFDWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Canelar | Territory 8 | 6.9184 | 122.0639 | Garden Orchid Hotel Gov. Camins Road, Canelar, Zamboanga City, Zamboanga Del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1758 | PAGASATAWI | NA | PAGASATAWIFHKLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.0189 | 119.7724 | Pagasa, Bongao, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1412 | PARIAN | NA | PARIANFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PANDAMI |  | Territory 8 | 5.5336 | 120.7564 | Brgy. Parian Dakula, Pandami, Sulu, Maguindanao | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN459 | PARSUL | NA | PARSULFHLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO |  | Territory 8 | 5.9148 | 120.9089 | Lupa Abu, Parang, Sulu, Philippines | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN525 | PASIAG | NA | PASIAGFHLWXYZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.0186 | 119.7474 | Pasiagan, Bongao, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN573 | PASONA | NA | PASONAFHKLWXY PASONAWXYNFHKL | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9626 | 122.0674 | Pasonanca, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | [6 empty] | #N/A
MIN1771 | PASONANCAZDS | ZMB_011 | PASONANCAZDSFHKLWXYVP | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9438 | 122.0695 | Pasonanca, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1425 | PATALO | NA | ABREEZADAVAODDSIDF PATALOFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.0459 | 121.9111 | Patalon, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN462 | PATIKU | NA | PATIKUZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PATIKUL |  | Territory 8 | 6.0881 | 121.1003 | Kan Ague, Patikul, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN557 | PERSIN | NA | PERSINFKLMVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Barangay Zone I (Pob.) | Territory 8 | 6.9064 | 122.0776 | Doña Vicenta Bldg. Pilar St. Zamboanga City_Barangay Zone I (Pob.), Zamboanga City, Zamboanga Del Sur | ZAMBO | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN894 | PHIL HEALTH REPEATER | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Santa Catalina | Territory 8 | 6.907 | 122.079 | Philhealth Office, Tomas Claudio ST. Santa Catalina, Zamboanga City, Zamboanga Del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN804 | PUTIK | NA | PUTIKFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9439 | 122.0942 | National Highway Putik, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1756 | PUTIKZDS | ZMB_012 | PUTIKZDSFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9345 | 122.0869 | Putik, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN453 | RBAGSA | NA | RBAGSAFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | TALIPAO |  | Territory 8 | 6.0131 | 121.1543 | Bagsak, Talipao, Sulu | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1133 | RECODO | NA | RECODOFKLXV | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.957 | 121.9546 | Recodo, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1775 | RECODOZDS | NA | RECODOZDSFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9537 | 121.9627 | Recodo, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1767 | RIOHONDOZDS | NA | RIOHONDOZDSXZ | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.8992 | 122.0863 | Rio Hondo, Zamboanga City Zamboanga del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN456 | RJOLO | NA | RJOLOFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PATIKUL |  | Territory 8 | 6.0153 | 121.0783 | Danag, Patikul, Sulu | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN574 | RLBUAN | NA | RLBUANFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.054 | 121.9102 | Sitio Balikakas Patalon, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN62 | RMALUS | NA | RMALUSFKLVWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LANTAWAN |  | Territory 8 | 6.5876 | 121.9266 | Switch Yakal, Lantawan, Basilan | GTZAMBOFOCID | GT | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN460 | RPARAN | NA | RPARANFLXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PARANG |  | Territory 8 | 5.9495 | 120.9306 | Wanni Piyanjihan, Parang, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN461 | RPATIC | NA | RPATICFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PATIKUL |  | Territory 8 | 6.0696 | 121.0407 | Sandah, Patikul, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN63 | RSCLAR | NA | RSCLARFHKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.7045 | 122.0002 | Tabiawan, City of Isabela, City of Isabela (Not a province) | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN64 | RTUBUR | NA | RTUBURFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | TUBURAN |  | Territory 8 | 6.6206 | 122.2617 | Languyan, Hadji Mohammad Ajul, Basilan | GTZAMBOFOCID | GT | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1507 | SANGA2AIRPT | NA | SANGA2AIRPTFHKLWX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.044 | 119.745 | Sangasanga Airport Sangasanga, Bongao, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN714 | SANGAL | ZMB_033 | SANGALFKLVWXY SANGALKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.0738 | 122.2107 | Fishing Port St. Sangali, Zamboanga City, Zamboanga Del Sur | VITALI | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1779 | SANGALIZDS | NA | SANGALIZDSFWLYKV | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.0679 | 122.2013 | Sangali, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1795 | SANJOSEGUZDS | ZMB_013 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9158 | 122.0463 | Suterville , Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN526 | SAPA | NA | SAPAFHLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | SAPASAPA |  | Territory 8 | 5.0917 | 120.2728 | Sapasapa (Pob.), SapaSapa, TawiTawi | GTZAMBOFOCID | GT | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN524 | SAPIE | NA | SAPIEFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | SITANGKAI |  | Territory 8 | 4.6612 | 119.3923 | Imam Sapie, Sitangkai, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN463 | SIASI | NA | SIASIFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | SIASI |  | Territory 8 | 5.5454 | 120.8184 | Campo Islam, Siasi, Sulu | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN886 | SIASI RELAY | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | SIASI |  | Territory 8 | 5.5588 | 120.8264 | Siundo, Siasi, Sulu | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN536 | SIBUCO | NA | SIBUCOFJX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIBUCO |  | Territory 8 | 7.2932 | 122.0664 | Sibuco_Poblacion, Sibuco, Zamboanga Del Norte | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1413 | SIMBAHANSUL | NA | SIMBAHANSULFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PANGUTARAN |  | Territory 8 | 6.3055 | 120.5818 | Brgy. Simbahan, Pangaturan, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN921 | SIMUNU | NA | SIMUNUFWX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | SIMUNUL |  | Territory 8 | 4.898 | 119.8482 | Bakong, Simunul, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1087 | SITANGKAY RELAY | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | SITANGKAI |  | Territory 8 | 4.8287 | 119.4924 | Datu Amilhamja Jaafar, Sitangkai, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN527 | SITANK | NA | SITANKFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | SITANGKAI |  | Territory 8 | 4.8411 | 119.4592 | Datu Amilhamja Jaafar, Sitangkai, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN12 | SMARIA | ZMB_026 | SMARIAFKLMVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9282 | 122.0679 | Padua Drive Santa Maria, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1596 | SNMIGBASILAN | NA | AGUADA1ISBELABASFHKLWY SNMIGBASILANHKVXZ | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.6975 | 121.9677 | Aguada, City of Isabela, City of Isabela (Not a province) | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN582 | SNROQ | NA | SNROQFKLMVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9339 | 122.0461 | Macrohon Drive San Roque, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1096 | SNUNOC | ZMB_020 | SNUNOCFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9356 | 122.0073 | Sinunoc, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN712 | SPLAZA | NA | SPLAZAFHKLVWXY SPLAZAZDSIDFK | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Barangay Zone III (Pob.) | Territory 8 | 6.9061 | 122.0738 | Shoppers Plaza Climaco Ave Zamboanga City_Barangay Zone III (Pob.), Zamboanga City, Zamboanga Del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1762 | SROQUEZDS | NA | SROQUEZDSFHKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9279 | 122.048 | San Roque, ZAMBOANGA CITY | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN65 | STCLAR | NA | STCLARFHKLVWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LAMITAN CITY |  | Territory 8 | 6.6792 | 122.0638 | Santa Clara, City of Lamitan, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1431 | STHSQR | NA | STHSQRFWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Barangay Zone I (Pob.) | Territory 8 | 6.906 | 122.0768 | Gov. Lim Avenue cor. P. Lorenzo St., Zamboanga City, Zamboanga del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN528 | SUBIAN | NA | SUBIANFLWX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | SOUTH UBIAN |  | Territory 8 | 5.1986 | 120.5119 | Looran Tampakan Dampong, South Ubian, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN584 | SUMISI | NA | SUMISIXHKLYFW TUMAHU1SUMSIPBASHKLYFWAF | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | SUMISIP |  | Territory 8 | 6.4778 | 122.0358 | Tumahubong, Sumisip, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1146 | TALON | ZMB_045 | TALONFHKLWXYF TCFGATALONZAMBOAZDSFHKLWYNFK | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9113 | 122.0992 | Talontalon, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1711 | TALON2ZDS | NA | TALON2ZDSFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9102 | 122.1158 | #475 Teresa Drive Talontalon, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN529 | TANDUB | NA | TANDUBFLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | TANDUBAS |  | Territory 8 | 5.1367 | 120.3459 | Kakoong, Tandubas, TawiTawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1461 | TANJON | NA | KALIMTULAY1INDANASULUFHKLWY TANJONX | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | INDANAN |  | Territory 8 | 6.0486 | 120.9928 | Zone 3 Brgy. Tulay, Indanan Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN68 | TBURAN | NA | TBURANFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | TUBURAN |  | Territory 8 | 6.6422 | 122.2734 | Tuburan Proper (Pob.), Hadji Mohammad Ajul, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1383 | TETU2 | ZMB_014 | TETU2FHKLMWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9276 | 122.0837 | Brgy. Tetuan, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN587 | TETUAN | ZMB_001 | TETUANFHKLMWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9185 | 122.0857 | Dr. J. Estrada St,. Reyes Comp., Tetuan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1107 | TICTAP | ZMB_038 | TCFGATICTAPULZAMBOAZDSFHKLWYPFH TICTAPFHKLWXYS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.4165 | 122.3248 | Tictapul, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN589 | TIGBA2 | NA | TCFGATIGBAOZAMBOAZDSFHKLWY TIGBA2FHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.4398 | 122.3257 | Sitio Tigbao Licomo, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN465 | TLIPAO | NA | TLIPAOFWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | TALIPAO |  | Territory 8 | 5.9777 | 121.1143 | Buntod, Talipao, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1258 | TLISA | NA | TCFGATLISAYZAMBOAZDSFKLVWY TLISAFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9377 | 121.9978 | Talisayan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN67 | TPOTPO | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | TIPOTIPO |  | Territory 8 | 6.4938 | 122.1111 | Materling, Ungkaya Pukan, Basilan | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN539 | TUGBUN | ZMB_015 | TUGBUNFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9212 | 122.1059 | Saavedra Drive Tugbungan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1757 | TULUNGATUZDS | NA | TULUNGATUZDSFKLVWYNP | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9709 | 121.9553 | Talisayan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN803 | TUMAGA | ZMB_016 | TUMAGADFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9369 | 122.0772 | Dimas Bayot Drive, Tumaga, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1754 | TURKISH TOLERANCE HIGH SCHOOL REPEATER | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9387 | 121.9956 | Turkish Tolerance High school, Pitogo, Sinunoc, Zamboanga City | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN1259 | UCALER | NA | UCALERFHKLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9268 | 122.0339 | Calarian, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2788 | VETEXTSMARIAZAMBOZDS | NA | VETERMARIAZAMBOAZDSFHKLMWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.928 | 122.0779 | LB Compound, Sta Maria, Veterans Ext., Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN596 | VITALI | ZMB_031 | VITALIFHKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.37 | 122.2885 | Kalye Posporo Purok 3 Vitali, Zamboanga City, Zamboanga Del Sur | VITALI | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1617 | WESMINCOM | NA | WESMINCOMDFHKLDWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9197 | 122.0431 | Calarian, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1264 | WMMC | ZMB_017 | WMMC1ZAMBOAZDSIDFKWY WMMCODFKLVWX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Tetuan | Territory 8 | 6.9231 | 122.079 | Western Mindanao Medical Center Tetuan, Zamboanga City, Zamboanga Del Sur | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN805 | ZAMBOA | ZAMBOA-LSA01 / ZAMBOA-LSA06 | WINNHOTZAMBOAZDSEMFH ZAMBOAFKDLMVWX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9102 | 122.0722 | Mayor Jaldon St., Canelar, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN713 | ZAMECOZONE | NA | ZAMECOZONEFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Talisayan | Territory 8 | 7.0037 | 121.9237 | Zamboanga Economic Zone Zamboanga City_Barangay Zone IV (Pob.), Zamboanga City, Zamboanga Del Sur | ZAMBO | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1358 | ZMB-703 | ZMB_703 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9186 | 122.0562 | ALONG SAN JOSE GUSU CORNR MONSERAT ST. AT THE BACK OF WAITING SHED, ZAMBOANGA CITY | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1370 | ZMB-704 | ZMB_704 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9211 | 122.0728 | Beside KMZ De Zamboanga | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1319 | ZMB-705 | ZMB_705 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9146 | 122.0821 | HUAWEI CABINETALONG DON ALFARO ST. INFRONT OF ALTA MALL BRGY. TETUAN ZAMBOANGA CITY | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN1317 | ZMB-706 | ZMB_706 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.924 | 122.09 | ALONG NATIVIDAD ST. FRONT OF IMMACULATE CONCEPTION ELEMENTARY SCHOOL (ICES) | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1318 | ZMB-707 | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9179 | 122.0984 | ALONG DON ALFARO ST. FRONT OF JOSANS MOTOR BRGY TUGBUNGAN ZAMBOANGA CITY | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN1367 | ZMB-709 | NA | ZMB-709 | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9288 | 122.0884 | ALONG BOUGAINVILLA ST., NEAR ACE GAS STORE, ZAMBOANGA CITY | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN1316 | ZMB-710 | ZMB_710 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9478 | 122.0727 | HUAWEI CABINETALONG PASONANCA ROAD AT POLE IC1001 ZAMBOANGA CITY | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN1315 | ZMB-711 | ZMB_711 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.938 | 122.0929 | Along Putik Road, Near Putik Elementary School, Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2666 | ZWOODZAMBOAZDS | NA | ZWOODZAMBOAZDSFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9397 | 122.1337 | ZAMBOWOOD ROAD ZAMBOANGA CITY | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2875 | TALABAANZAMBOAZDS | NA | TALABAANZAMBOAZDSFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9539 | 122.173 | Zone 4, Brgy. Talabaan, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2415 | BRENTHOSPZAMBOAZDS | NA | BRENTHOSPZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9075 | 122.0681 | R.T. Lim Boulevard, Baliwasan, ZAMBOANGA CITY, ZAMBOANGA DEL SUR, REGION IX (ZAMBOANGA PENINSULA), MIN | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2040 | CULIANANZDSZ | ZMB_043 | CULIANANZDSFKLWXYV | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9624 | 122.1343 | Zone II,, Culianan, ZAMBOANGA CITY, ZAMBOANGA DEL SUR, REGION IX (ZAMBOANGA PENINSULA), MIN | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2575 | ARCOLAMITNBASCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LAMITAN CITY |  | Territory 8 | 6.7017 | 121.9796 | MALIGAYA, LAMITAN CITY, BASILAN | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN3073 | BONPATKULSULUCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PATIKUL |  | Territory 8 | 6.0642 | 121.1593 | BRGY. BONBON, PATIKUL, SULU | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3139 | PPATCHZAMBOAZDSCOW | NA | PPATCHZAMBOAZDSFWLY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Barangay Zone II (Pob.) | Territory 8 | 6.9083 | 122.0758 | PHONEPATCH BUILDING, LA PURISIMA ST., ZAMBOANGA CITY¦ | ZAMBO | LDIC | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW37 | BAYUGTLIPAOSULUCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | TALIPAO |  | Territory 8 | 6.933 | 122.0867 | 2SFBN BAYUG TALIPAO, SULU | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW38 | BULISUMSIPBASCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | SUMISIP |  | Territory 8 | 6.4216 | 122.0349 | BULI-BULI, SUMISIP BASILAN | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN2877 | LUMBANGANZAMBOAZDS | NA | LUMBANGANZAMBOAZDSFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9698 | 122.1086 | Lumbangan, Zamboanga, Zamboanga del Sur, Philippines | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3089 | Z4SOCORZAMBOAZDS | NA | Z4SOCORZAMBOAZDSFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9526 | 122.1599 | Talabaan, Zamboanga, Zamboanga del Sur, Philippines | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MINCOW40 | ABONGMLUSOBASCOW | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | MALUSO |  | Territory 8 | 6.4854 | 121.9154 | Maluso, Basilan | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN2582 | NIANGKAANOMARSULU | NA | NIANGKAANOMARSULUFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | OMAR |  | Territory 8 | 6.9492 | 122.0904 | Omar, Sulu | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3097 | SNUNOCZAMBOAZDS | NA | SNUNOCZAMBOAZDSFHKLWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9359 | 122 | Brgy Sinunoc, Z.C. | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3459 | KAJADJIDINDANASULU | NA | KAJADJIDINDANASULUF | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | INDANAN |  | Territory 8 | 5.9938 | 121.0068 | Palan, Indanan, 7407 Sulu, Philippines | GTZAMBOFOCID | GT | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3155 | TPOMATRLNGUPUKANBAS | NA | TPOMATRLNGUPUKANBASFHKLWXY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | TIPOTIPO |  | Territory 8 | 6.4904 | 122.1153 | Tipo-Tipo, Basilan, Philippines | GTZAMBOFOCID | GT | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2874 | SINUBONGZAMBOAZDS | NA | SINUBONGZAMBOAZDSFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.0282 | 121.9258 | Sinubung, Zamboanga, Zamboanga del Sur, Philippines | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3111 | Z8AYALAZAMBOAZDS | NA | Z8AYALAZAMBOAZDSFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9676 | 121.9406 | Zone 8, Calle Pilar, Ayala, Zamboanga City, Zamboanga del Sur, Zamboanga, Zamboanga del Sur, Philippines | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3125 | PMABOLOZAMBOAZDS | NA | PMABOLOZAMBOAZDSFNFKLVWX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9396 | 122.0084 | Mabolo Drive, Sinunoc | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2882 | CAWITZAMBOAZDS | NA | CAWITZAMBOAZDSFKLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9628 | 121.9721 | Cawit, Zamboanga City | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2873 | P5CABATZAMBOAZDS | NA | P5CABATZAMBOAZDSFLVWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9412 | 122.0623 | Cabatangan, Zamboanga, Zamboanga del Sur, Philippines | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3513 | VLDROSAZ3ZAMBOAZDSAS | NA | VLDROSAZ31ZAMBOAZDSASFFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9036 | 122.0771 | Valderosa St., Zamboanga City_Barangay Zone III (Pob.), Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3512 | CMNONUEVOZAMBOAZDSAS | NA | CMNONUEVO1ZAMBOAZDSASFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9161 | 122.0759 | Nunez Ext., Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3483 | BALIWASANZAMBOAZDSAS | NA | BALIWASAN1ZAMBOAZDSASHHFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9138 | 122.0629 | WMSU, Baliwasan Rd, Baliwasan, Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3707 | CANELARZAMBOAZDSAS | NA | CANELARZAMBOAZDSASFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9167 | 122.0713 | Brgy Canelar, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3113 | CANDIDODRVZAMBOAZDS | NA | CANDIDODRVZAMBOAZDSFLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9126 | 122.0889 | Zamboanga, Philippines | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3100 | SNRISETLONZAMBOAZDS | NA | SNRISETLONZAMBOAZDSFX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9055 | 122.1167 | Sunrise, Talon, Zamboanga City | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3164 | LODIUTAYZAMBOAZDS | NA | LODIUTAYZAMBOAZDSFL | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9126 | 122.1204 | Logoy Duitay, Talon Talon, Zamboanga City | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3101 | CHIMNGTUGBZAMBOAZDS | NA | CHIMNGTUGBZAMBOAZDSFLX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.917 | 122.1108 | Chimangs, Tugbungan, Zamboanga City | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3163 | P4LUNZURZAMBOAZDS | NA | P4LUNZURZAMBOAZDSFKLV | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9642 | 122.0965 | Purok 4, Lunzuran, Zamboanga City | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1947 | ASTURIASJOLOSULU | NA | ASTURIASJOLOSULUFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO |  | Territory 8 | 6.046 | 121.0049 | Brgy Asturias, Jolo, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3174 | Z2TUMAGAZAMBOAZDS | NA | Z2TUMAGAZAMBOAZDSFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9368 | 122.0814 | W3QH+PQM, Tumaga- Lunzuran Rd, Zamboanga, Zamboanga Sibugay, Philippines | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2597 | MAGANDALAMITNBAS | NA | MAGANDALAMITNBASFKLVWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LAMITAN CITY |  | Territory 8 | 6.6582 | 122.1461 | Maganda, Lamitan City, Basilan, Philippines | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3098 | PEREZTMAGZAMBOAZDS | ZMB_042 | PEREZTMAGZAMBOAZDSFKLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9429 | 122.0842 | Tumaga, Zamboanga, Zamboanga del Sur, Philippines | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3099 | GUIWANZAMBOAZDS | NA | GUIWANZAMBOAZDSFLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9317 | 122.0869 | Guiwan, Zamboanga City | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2572 | Z3TULAYJOLOSULU | NA | Z3TULAY1JOLOSULUFLW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO |  | Territory 8 | 6.0527 | 120.9936 | Brgy Tulay, Jolo, Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2333 | PASIAGANBONGAOTAWI | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.0093 | 119.7587 | Pasiagan, Bongao, Tawi Tawi | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3357 | BUENAVSTAZAMBOAZDS | NA | BUENAVSTAZAMBOAZDSFLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.2415 | 122.2621 | BrgyBuenavista_ZAMBOANGA CITY_ZAMBOANGA DEL SUR | VITALI | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3343 | SCOMVILLZAMBOAZDS | NA | SCOMVILLZAMBOAZDSFLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9287 | 122.0428 | CapSite_BrgyCalarian02_ZamboangaCity | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3706 | LUNZURANZAMBOAZDS | NA | LUNZURANZAMBOAZDSFWX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9503 | 122.0895 | BrgyTumaga_01_ZamboangaCity_ZamboangaDelSur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3175 | P1CABALZAMBOAZDS | NA | P1CABALZAMBOAZDSFLVWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9904 | 122.1683 | Purok 1, Brgy. Cabaluay, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3712 | KM6MAMPAZAMBOAZDS | NA | KM6MAMPAZAMBOAZDSFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9147 | 122.1314 | Km. 6, Brgy. Mampang, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3177 | LOGOYTALONZAMBOAZDS | NA | LOGOYTALONZAMBOAZDSFLWXYN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9086 | 122.1231 | Logoy Jutay, Brgy. Talon-talon, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3196 | KASANYANGANZAMBOAZDS | NA | KASANYANGANZAMBOAZDSFLWYN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9097 | 122.0958 | Brgy. Kasanyangan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3360 | TCFGADRATILZAMBOAZDS | NA | TCFGADRATILZAMBOAZDSFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9217 | 122.0883 | HB Fronting Daga Manuel Dr. Crispin Atilano St., Brgy. Tetuan, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3961 | TCFGAZ4CULZAMBOAZDS | NA | TCFGAZ4CULZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9845 | 122.1403 | Brgy Culianan, Zamboanga City | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3187 | TCAICCLMACOZAMBOAZDS | NA | TCAICCLMACOZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9357 | 122.0699 | Climaco Compound, Brgy. Sta. Maria, Zamboanga, Zamboanga del Sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3279 | TCAICBASCOMZAMBOAZDS | NA | TCAICBASCOMZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9244 | 122.0897 | BASILIO COMP., NATIVIDAD ST., (NEAR JUMBO BRIDGE) TETUAN ZAMBOANGA CITY | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3652 | TCAICTUMAGAZAMBOAZDS | NA | TCAICTUMAGAZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9446 | 122.0794 | Brgy. Tumaga, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3653 | TCAICLBUAN2ZAMBOAZDS | NA | TCAICLBUAN2ZAMBOAZDSFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.0891 | 121.9029 | Brgy. Labuan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3655 | TCAICISMCEDZAMBOAZDS | NA | TCAICISMCEDZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9659 | 122.146 | San Isidro,Brgy. Mercedes, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3814 | TCAICZ1LAPAZAMBOAZDS | NA | TCAICZ1LAPAZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9773 | 121.9532 | Zone 1, La Paz, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3875 | TCAICTUGBUNZAMBOAZDS | NA | TCAICTUGBUNZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.92 | 122.0996 | Tugbungan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3850 | TCFGASNRQUEZAMBOAZDS | NA | TCFGASNRQUEZAMBOAZDSFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9362 | 122.054 | Brgy. San Roque, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3993 | TCFGASNUNOCZAMBOAZDS | NA | TCFGASNUNOCZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9298 | 122.0093 | Brgy. Sinunoc, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4086 | TCAICLAWINZAMBOAZDS | NA | TCAICLAWINZAMBOAZDSLY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.0815 | 121.9026 | Lawingan, Barangay Labuan Zamboanga City, Zamboanga Del sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3276 | TCAICAMPANGZAMBOAZDS | NA | TCAICAMPANGZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9185 | 122.1495 | Arena Blanco, Brgy. Mampang, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3799 | TCAICBUANZINDANASULU | NA | TCAICBUANZINDANASULUFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | INDANAN |  | Territory 8 | 6.0395 | 120.9827 | Buanza, Indanan, Sulu | GTZAMBOFOCID | UNITY | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3809 | TCAICBRIGONZAMBOAZDS | NA | TCAICBRIGONZAMBOAZDSFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9267 | 122.1044 | Barigon, Tugbungan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2038 | INTLAIRPTZAMBOAZDSLS | NA | INTLAIRPTZAMBOAZDSLSFK | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9199 | 122.0616 | Camins, Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2594 | UNIVDEZAMBOAZDSLS | NA | UNIVDEZAMBOAZDSLSFKWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9046 | 122.0758 | JS Alano St., Zamboanga City | GTZAMBOFOCID | GT | [6 empty] | #N/A
MINCOW65 | PASEOZ3ZAMBOAZDSCOW | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9014 | 122.0813 | Petit Barracks, Paseo del Mar, Zamboanga City | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN3633 | MERSUITESZAM2PNP | NA | MERSUITESZAM2PNPFFFWXRFK | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9195 | 122.0671 | Camins, Zamboanga City | GTZAMBOFOCID | GT | [6 empty] | #N/A
MIN3168 | FLAMALAGZAMBOAZDS | NA | FLAMALAGZAMBOAZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9325 | 122.0205 | Brgy. Malagutay, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | PHILTOWER | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3341 | TLUNGATU02ZAMBOAZDS | NA | P2APOKONTAGUMDDNFLW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9723 | 121.9659 | Tulungatung, Zamboanga City | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4036 | TCFGABOALANZAMBOAZDS | NA | TCFGABOALANZAMBOAZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9598 | 122.1153 | Brgy. Boalan, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3979 | TCAICSIBULZAMBOAZDS | NA | TCAICSIBULZAMBOAZDSFLWX | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.3338 | 122.2396 | Brgy. Sibulao, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4071 | TCLDCSNUNOCZAMBOAZDS | NA | TCLDCSNUNOCZAMBOAZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9337 | 122.0032 | Kapatid Drive Street, Brgy. Sinunuc, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | LDIC | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3983 | TCLDCCALZ8ZAMBOAZDS | NA | TCLDCCALZ8ZAMBOAZDSFLWY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9746 | 121.9429 | CALLE PILAR ZONE 8, BRGY AYALA, ZAMBOANGA CITY, ZAMBOANGA DEL SUR | GTZAMBOFOCID | LDIC | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2167 | Navy Head Quarter ( WESMINCOM ) | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | Zamboanga City |  | Territory 8 | 122.0374 | 6.9175 | Naval Base, Western Mindanao Command, Upper Calarian, Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2165 | Zamboanga Doctors Hospital | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | Zamboanga City |  | Territory 8 | 122.0799 | 6.9153 | Veterans Ave,Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2154 | Edwin Andrews Airbase | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | Zamboanga City |  | Territory 8 | 122.0647 | 6.9266 | Edwin Andrews Airbase, Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3626 | WESMINCOM Mansion, Zamboanga City | NA | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9183 | 122.0406 | WESMINCOM Mansion, Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3477 | TANDUBATOLUUKSULU | NA | TANDUBATOLUUKSULUFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | Luuk |  | Territory 8 | 5.9937 | 121.3073 | Brgy. Tandu-Bato,Luuk,Sulu | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3338 | SSJCAWAZAMBOAZDS | NA | SSJCAWAZAMBOAZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9131 | 122.0644 | SLSI Building, Brgy. San Jose Cawa-cawa, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4241 | PASONAZAMBOAZDS | NA | PASONAZAMBOAZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9631 | 122.0666 | Brgy. Pasonanca, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3829 | LAMIONBONGAOTAWI | NA | LAMIONBONGAOTAWI | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | Bongao (Capital) |  | Territory 8 | 5.0258 | 119.7752 | Brgy. Lamion, Bongao Tawi-tawi | GTZAMBOFOCID | GT | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3344 | TCLDCSALAANZAMBOAZDS | NA | TCLDCSALAANZAMBOAZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9885 | 122.1199 | Zone 1 Barangay Salaan, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | LDIC | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3345 | TCLDCZWOODZAMBOAZDS | NA | TCLDCZWOODZAMBOAZDSFW | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.953 | 122.1319 | Lumbayao, Brgy. Zambowood, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | LDIC | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2808 | SMINDPROZAMBOAZSID | SMMIND-LSA04 | SMINDPROZAMBOAZDSIDFKWXY | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Barangay Zone II (Pob.) | Territory 8 | 6.9077 | 122.0759 | La Purisma St., Zamboanga City | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3323 | TCLDCCABOLAMITNBAS | NA | TCLDCCABOLAMITNBASLY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LAMITAN CITY (CAPITAL) |  | Territory 8 | 6.6512 | 122.1333 | Brgy. Limook, Lamitan City, Basilan | GTZAMBOFOCID | LDIC | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3735 | TCAICBUSBUSJOLOSULU | NA | TCAICBUSBUSJOLOSULUFLWY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO (CAPITAL) |  | Territory 8 | 6.059 | 121.0068 | Brgy. Bus-bus, Jolo, Sulu | GTZAMBOFOCID | UNITY | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3696 | TCAICMOOREAVJOLOSULU | NA | TCAICMOOREAVJOLOSULUFWLY | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | JOLO (CAPITAL) |  | Territory 8 | 6.0483 | 120.9972 | Moore Ave, Brgy. Alat, Jolo, Sulu | GTZAMBOFOCID | UNITY | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4217 | TCAICMAUBOHPATKULSULU | NA | NA | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PATIKUL |  | Territory 8 | 6.0658 | 121.0127 | Brgy.Mauboh,Patikul,SULU | GTZAMBOFOCID | UNITY | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4273 | WMSUCAMPUS2ZAMBOAZDSAS | NA | WMSUCAMPUS2ZAMBOAZDSAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9124 | 122.06 | Western Mindanao State University, Brgy. Baliwasan, zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3145 | POBSAPATAWI | NA | POBSAPATAWI | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | Sapa-Sapa |  | Territory 8 | 5.0916 | 120.2727 | Brgy Poblacion, Sapa-Sapa, Tawi-tawi | GTZAMBOFOCID | GT | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4272 | ALAVARZAMBOAZDSAS | NA | ALAVARZAMBOAZDSAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9157 | 122.087 | Alavar Restaurant, Brgy. Tetuan, Zamboanga City, Zamboanga del Sur | TETUAN FOC | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4534 | PURICULTUREZAMBOAZDSAS | NA | PURICULTUREZAMBOAZDSAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9073 | 122.0758 | Barangay Zone II (Pob.), Zamboanga City, Zamboanga del Sur | TETUAN FOC | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4605 | SUCABONZAMBOAZDSAS | NA | SUCABONZAMBOAZDSAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9073 | 122.075 | Sucabon, Barangay Zone II (Pob.), Zamboanga City, Zamboanga del Sur | TETUAN FOC | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4535 | ADZUCAMPUSZAMBOAZDS | NA | ADZUCAMPUSZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9096 | 122.076 | Ateneo de Zamboanga University, Zone IV, Zamboanga City, Zamboanga Del Sur | TETUAN FOC | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4537 | STABARBARAZAMBOAZDS | NA | STABARBARAZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9033 | 122.082 | Brgy Santa barbara, zamboanga City, Zamboanga Del Sur | TETUAN FOC | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1363 | ZMB-702 | ZMB_702 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | San Jose Cawa-cawa | Territory 8 | 6.9109 | 122.0672 | ALONG BOA ST. CORNER SAN JOSE ST. ZAMBOANGA CITY | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1369 | ZMB-701 | ZMB_701 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Barangay Zone II (Pob.) | Territory 8 | 6.9062 | 122.0772 | HUAWEI CABINETALONG GOV. LIM AVENUE NEAR WESTERN MINDANAO COOPERATIVE COLLEGE ZAMBOANGA CITY | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1368 | ZMB-708 | ZMB_708 | NA | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | San Roque | Territory 8 | 6.9311 | 122.0774 | Along Gov. Ramos Beside NIA, Zamboanga City | ZAMBO | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4831 | TCCREP2LUCENAPROSPAGS |  | NA | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD (Capital) | Lucena | Territory 8 | 8.5673 | 125.8713 | Purok 2, Brgy. Lucena, Prosperidad Agusan del Norte | BUTUAN (TECHNICAL OFFICE) | CREI | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4636 | TCAICZ1BULAGENSANSCOT |  | TCAICZ1BULAGENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Bula | Territory 7 | 125.1896 | 6.1048 | Jose Divinagracia Blvd., Brgy Bula, General Santos City, South Cotabato | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3183 | DUNGOANMLANGNCOT |  |  | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | M'LANG | Dungo-an | Territory 7 | 124.8707 | 6.9497 | CapSite_BrgyDungo-an_Mlang_NorthCotabato | MLANG | PHILTOWER | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4380 | TCEDCDADOSDINAIGMGDN |  | TCEDCDADOSDINAIGMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT (DINAIG) | Makir | Territory 7 | 124.3217 | 7.0274 | Brgy. Makir, Datu Odin Sinsuat (Dinaig), Maguindanao | COTABATO | EDOTCO | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4353 | TCAICAWANGDINAIGMGDN |  | TCAICAWANGDINAIGMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ODIN SINSUAT (DINAIG) | Awang | Territory 7 | 124.2104 | 7.1564 | Brgy. Awang, Datu Odin Sinsuat, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3561 | TCAICBUAYANGENSANSCOT |  | TCAICBUAYANGENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Buayan | Territory 7 | 125.2299 | 6.111 | PUROK MASAGANA BUAYAN GENERAL SANTOS CITY | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4030 | LAGAO13GENSANSCOTAS |  |  | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Lagao (1st & 3rd) | Territory 7 | 125.1865 | 6.118 | Jose Catolico Sr Ave, Lagao, General Santos City, South Cotabato | GENSAN | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | MARC ANTHONY M. LUBANG | 8463 | 9176888302 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2089 | GTZAMBOFOCOD_D |  | GTZAMBOFOCOD_D | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Tetuan | Territory 8 | 122.0799 | 6.9153 | Zamboanga Doctor's Hospital, Veterans Ave, Zamboanga City | GTZAMBOFOCID | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4562 | TCEDCBUHANGMGALANAGN | TCEDCBUHANGMGALANAGN | TCEDCBUHANGMGALANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | MAGALLANES | Buhang | Territory 8 | 9.0273 | 125.521 | National Hi-way, Brgy. Poblacion, Magallanes, Butuan, Agusan del Norte | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4716 | TCEDCSTAIRENEPROSPAGS | TCEDCSTAIRENEPROSPAGS | TCEDCSTAIRENEPROSPAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | PROSPERIDAD (Capital) | Santa Irene | Territory 8 | 8.6674 | 125.8767 | Brgy. Santa Irene, Prosperodad (Capital), Agusan Del Sur | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1922 | STPAULUNIVTEMP |  | STPAULUNIVTEMP | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY (Capital) | Luna | Territory 8 | 9.7893 | 125.494 | Saint Paul Univercity, Surigao City, Surigao Del Norte | BUTUAN (TECHNICAL OFFICE) |  | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4811 | TCEDCGAMUTTAGOLOSDS | N/A | TCEDCGAMUTTAGOLOSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | TAGO | Gamut | Territory 8 | 9.0034 | 126.1642 | Brgy. Gamut, Tago, Surigao del Sur | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4243 | TCAGP7LIMAHABUTUANAGN | N/A | TCAGP7LIMAHABUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Limaha Pob. (Bgy. 14) | Territory 8 | 8.955 | 125.5345 | Purok 7, Brgy, Limaha, Butuan City, Agusan Del Norte | BUTUAN (TECHNICAL OFFICE) | ALT GLOBAL | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4174 | TCISLANGELESBUTUANAGN | N/A | TCISLANGELESBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Los Angeles | Territory 8 | 9.0146 | 125.6068 | Brgy Los Angeles, Butuan City, Agusan Del Norte | BUTUAN (TECHNICAL OFFICE) | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4484 | TCISMANAPABUENVAGN | N/A | TCISMANAPABUENVAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUENAVISTA | Manapa | Territory 8 | 8.9774 | 125.4437 | Brgy.Manapa, Buenavista, AgusanDelNorte | BUTUAN (TECHNICAL OFFICE) | ISON | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4111 | TCFGAPOB3TRENTOAGS | N/A | TCFGAPOB3TRENTOAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | TRENTO | Poblacion | Territory 8 | 8.0524 | 126.0586 | Putrok2-B,Poblacion,Trento,Agusan del Sur | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4523 | TCAICSNAGUSTINTANDAGSDS | NA | TCAICSNAGUSTINTANDAGSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | CITY OF TANDAG (Capital) | San Agustin Norte | Territory 8 | 9.0767 | 126.1826 | Brgy.SanAgustin, Tandag City, SurigaoDelSur | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4502 | TCAICSNJUANSNJOSEDNGT | NA | TCAICSNJUANSNJOSEDNGT | REGION XIII (Caraga) | DINAGAT ISLANDS | SAN JOSE (Capital) | San Jose (Pob.) | Territory 8 | 10.0115 | 125.5726 | Brgy. San Jose (Pob.), San Jose, Dinagat Islands | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3564 | TCLDCAMBAGOBUTUANAGN | NA | TCLDCAMBAGOBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Ambago | Territory 8 | 8.9601 | 125.4988 | Emenville Subdivision, Brgy Ambago, Butuan City, Agusan del Norte | BUTUAN (TECHNICAL OFFICE) | LDIC | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3285 | TCATCSUMILBUTUANAGN | NA | TCATCSUMILBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Sumilihon | Territory 8 | 8.9787 | 125.603 | Brgy Sumilihon, Butuan City, Agusan del Norte | BUTUAN (TECHNICAL OFFICE) | ATC | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2702 | TCAICREDEEMBUTUANAGN | NA | TCAICREDEEMBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Holy Redeemer Pob. (Bgy. 23) | Territory 8 | 8.9573 | 125.5293 | Emelia Compound, Brgy. Holy Redeemer 03, Butuan City, Agusan del Sur | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3093 | TCFGAANTIPOLODCARMESDN | NA | TCFGAANTIPOLODCARMESDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | DEL CARMEN | Antipolo | Territory 8 | 9.8114 | 126.0092 | Brgy. Antipolo, Del Carmen, Surigao Del Norte | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4665 | TCAICCANLANIPASURGAOSDN | NA | TCAICCANLANIPASURGAOSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY (Capital) | Canlanipa | Territory 8 | 9.7744 | 125.4932 | Brgy. Canlanipa, Surigao City, Surigao del Norte | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4682 | TCLDCDOONGBUTUANAGN | NA | TCLDCDOONGBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Doongan | Territory 8 | 8.9528 | 125.5229 | Brgy Doongan_Butuan City_Agusan del Norte | BUTUAN (TECHNICAL OFFICE) | LDIC | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4926 | TCCREBALEGUIANJABONAGN | NA | TCCREBALEGUIANJABONAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | JABONGA | Baleguian | Territory 8 | 9.3554 | 125.5553 | P1-B Baleguian Jabonga, Agusan del Norte | BUTUAN (TECHNICAL OFFICE) | CREI | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4694 | TCCREP8PATROCISJOSEFAGS | NA | TCCREP8PATROCISJOSEFAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | SANTA JOSEFA | Patrocinio | Territory 8 | 7.9799 | 126.0475 | Purok 4, Brgy. Patrocino, Sta. Josefa, Agusan del Sur | BUTUAN (TECHNICAL OFFICE) | CREI | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4697 | TCEDCKAUSWAGCABADAGN | NA | TCEDCKAUSWAGCABADAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | CITY OF CABADBARAN | Kauswagan | Territory 8 | 9.1275 | 125.5314 | Brgy. Kauswagan, Cabadbaran, Agusan Del Norte | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4809 | TCCRETALIGABUTUANAGN | NA | TCCRETALIGABUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Taligaman | Territory 8 | 8.9383 | 125.6304 | Brgy. Taligaman, Butuan City, Agusan Del Norte | BUTUAN (TECHNICAL OFFICE) | CREI | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4794 | TCAICBAGAKAYCLAVERSDN | NA | TCAICBAGAKAYCLAVERSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER | Bagakay (Pob. West) | Territory 8 | 9.5727 | 125.7307 | Barangay Bagakay, Claver, Surigao Del Norte | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4812 | TCEDCSAGUNTOLAPAZAGS | NA | TCEDCSAGUNTOLAPAZAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | LA PAZ | Sagunto | Territory 8 | 8.2434 | 125.7825 | Camam-onan, Sagunto, La Paz, Butuan City | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4795 | TCAICOSMENADAPASDN | NA | TCAICOSMENADAPASDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | DAPA | Osmeña | Territory 8 | 9.7802 | 126.0751 | Barangay Osmena, Dapa, Surigao Del Norte | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4796 | TCEDCP1BROOKSBUNAWAGS | NA | TCEDCP1BROOKSBUNAWAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | BUNAWAN | Bunawan Brook | Territory 8 | 8.158 | 126.0119 | Purok 1, Durian, Brgy. Brooks, Bunawan, Agusan del Sur | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3301 | TCFGAGOLDRIBBUTUANAGN | NA | TCFGAGOLDRIBBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Maon Pob. (Bgy. 1) | Territory 8 | 8.9364 | 125.5422 | Brgy Maon Pob (Brgy 1)_Butuan City_Agusan del Norte | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | ESTANISLAO S. PATULA JR. | 10008610 | 9175885909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4810 | TCEDCSNPABLOTUBODSDN | NA | TCEDCSNPABLOTUBODSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | TUBOD | San Pablo | Territory 8 | 9.5511 | 125.5675 | BRGY. POBLACION (TUBOD),TUBOD,SURIGAO DEL NORTE | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4797 | TCEDCPOB3BUENVAGN | NA | TCEDCPOB3BUENVAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUENAVISTA | Poblacion 3 | Territory 8 | 8.9739 | 125.4094 | J. Rizal Avenue cor Burgos St. Beunavista, Agusan del Norte | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3611 | CLAVER POI | NA | CLAVER POI | REGION XIII (Caraga) | SURIGAO DEL NORTE | CLAVER | Panatao | Territory 8 | 9.537 | 125.8521 | Claver, Surigao Der Norte | BUTUAN (TECHNICAL OFFICE) |  | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3844 | TCFGAANTONGBUTUANAGN | NA | TCFGAANTONGBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Antongalon | Territory 8 | 8.9479 | 125.6216 | Brgy. Antongalon, Butuan City Agusan del Norte | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4108 | TCAICBAYUG3ROSARAGS | NA | TCAICBAYUG3ROSARAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | ROSARIO | Bayugan 3 | Territory 8 | 8.3001 | 126.0037 | Brgy. Bayugan 3, ROSARIO, Agusan del Sur | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4947 | TCEDCPOB12CABADAGN | NA | TCEDCPOB12CABADAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | CITY OF CABADBARAN | Poblacion 12 | Territory 8 | 9.1147 | 125.538 | Brgy. Poblacion, Cabadbaran, Agusan Del Norte | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4220 | TCAICPOB2TRENTOAGS | NA | TCAICPOB2TRENTOAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | TRENTO | Poblacion | Territory 8 | 8.0364 | 12606536 | Brgy. Poblacion02_Trento Agusan Del Sur | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4505 | TCAICSTACRUZSNJOSEDNGT | NA | TCAICSTACRUZSNJOSEDNGT | REGION XIII (Caraga) | DINAGAT ISLANDS | SAN JOSE (Capital) | Santa Cruz | Territory 8 | 8.0364 | 126.0654 | Brgy. Poblacion02_Trento Agusan Del Sur | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4799 | TCEDCP2CUMAWASBISLIGSDS | NA | TCEDCP2CUMAWASBISLIGSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | CITY OF BISLIG | Comawas | Territory 8 | 8.1836 | 126.3377 | Purok 2, Brgy. Kumawas, Bislig City, Surigao del Sur | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4525 | TCSBAMANGAGBISLIGSDS | NA | TCSBAMANGAGBISLIGSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | CITY OF BISLIG | Mangagoy | Territory 8 | 8.1884 | 126.355 | Brgy. Mangagoy, Bislig City, Surigao del Sur | BUTUAN (TECHNICAL OFFICE) | SBA | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4798 | TCEDCTAGCATCARMENAGN |  | TCEDCTAGCATCARMENAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | CARMEN | Tagcatong | Territory 8 | 8.9979 | 125.2677 | Brgy. Tagcatong, Carmen, Agusan Del Norte | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4828 | TCCREP5LIBUACROSARAGS | NA | TCCREP5LIBUACROSARAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | ROSARIO | Libuac | Territory 8 | 8.3933 | 126.0127 | Purok 5, Brgy. Libuac, Rosario, Agusan del Sur | BUTUAN (TECHNICAL OFFICE) | CREI | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4829 | TCCRETAGBUYACSNTGOAGN | NA | TCCRETAGBUYACSNTGOAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | SANTIAGO | Tagbuyacan | Territory 8 | 9.299 | 125.5476 | PUROK 3, BRGY. POBLACION 1, SANTIAGO | BUTUAN (TECHNICAL OFFICE) | CREI | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3610 | SIARGAO POI | NA | SIARGAO POI | REGION XIII (Caraga) | SURIGAO DEL NORTE | DAPA | Union | Territory 8 | 9.7534 | 126.0931 | Dapa, Surigao Del Norte | BUTUAN (TECHNICAL OFFICE) |  | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4664 | TCAICBRGY12POBDAPASDN | NA | TCAICBRGY12POBDAPASDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | DAPA | Barangay 12 (Pob.) | Territory 8 | 9.7642 | 126.0382 | Brgy. 12, Dapa, Surigao del Norte | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4522 | TCAICUWAKBRGY1DAPASDN | NA | TCAICUWAKBRGY1DAPASDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | DAPA | Barangay 1 (Pob.) | Territory 8 | 9.7555 | 126.0557 | Brgy. 1, Dapa, Surigao Del Norte | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2851 | BARIRA_TOGAIG_D |  | BARIRA_TOGAIG_D | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | BARIRA | Barira (Pob.) | Territory 7 | 124.3231 | 7.5583 | Barira (Pob.), BARIRA, MAGUINDANAO, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | COTABATO | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3161 | KORON4_D |  |  | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | CITY OF KORONADAL (Capital) | Zone II (Pob.) | Territory 7 | 124.8454 | 6.5001 | Ace Centerpoint Mall, Koronadal City, South Cotabato | GENSAN | GT | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3831 | MAROGONGLDSCOW_D |  | MAROGONGLDSCOW_D | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MALABANG | Matalin | Territory 7 | 124.0753 | 7.6295 | Brgy. Matalin, Malabang, Lanao del Sur, Matalin, MALABANG, LANAO DEL SUR, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | COTABATO | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3587 | PADIDUGLANSAR2_KAPATAN_D |  | PADIDUGLANSAR2_KAPATAN_D | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN | Kapatan | Territory 7 | 125.2389 | 5.8971 | Glan Padidu, GLAN, SARANGANI, REGION XII (SOCCSKSARGEN), MIN | GENSAN | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4135 | POLONU_D |  | POLONU_D | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TUPI | Kablon | Territory 7 | 124.9696 | 6.3133 | Project D_5TH SPECIAL FORCES BATTALION_Kablon_South Cotabato | GENSAN | GT | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3868 | TCFGABAYANGAMTANOGMGDN_D |  | TCFGABAYANGAMTANOGMGDN_D | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | MATANOG | Bugasan Sur (Pob.) | Territory 7 | 124.259 | 7.4653 | Bugasan Sur (Pob.), MATANOG, MAGUINDANAO, AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM), MIN | COTABATO | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4258 | TCFGALIMBONULINGMGDN_D |  | TCFGALIMBONULINGMGDN_D | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Poblacion VII | Territory 7 | 124.2453 | 7.1969 | BARMM Office, Poblacion VII, COTABATO CITY, COTABATO CITY (Not a Province), REGION XII (SOCCSKSARGEN), MIN | COTABATO | GT | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4171 | TCISDATALTAMMALUNGSAR |  | TCISDATALTAMMALUNGSAR | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON | Datal Tampal | Territory 7 | 125.2237 | 6.3327 | Brgy. Datal Tampal, Malungon, Sarangani | GENSAN | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4252 | BAYANCALOBUTUANAGN_D | NA | BAYANCALOBUTUANAGN_D | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Doongan | Territory 8 | 8.9558 | 125.5284 | Tioaquen Residence, Balbarino Subd. Doongan, Butuan City | BUTUAN (TECHNICAL OFFICE) | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2774 | MENZISBELABAS_D | NA | MENZISBELABAS_D | REGION IX (ZAMBOANGA PENINSULA) | BASILAN | ISABELA CITY | Menzi | Territory 8 | 121.9618 | 6.666 | Veterans Ave, Zamboanga City | GTZAMBOFOCID |  | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4718 | TCEDCBULIBULISUMSIPBAS | NA | TCEDCBULIBULISUMSIPBAS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | SUMISIP | Buli-buli | Territory 8 | 122.0353 | 6.4196 | Brgy. Buli-Buli, Sumisip, Basilan | ZAMBO | EDOTCO | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4808 | TCEDCZ3PASOBZAMBOAZDS | NA | TCEDCZ3PASOBZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Culianan | Territory 8 | 122.129 | 6.9721 | Zone 3, Brgy.Pasobolong, Zamboanga City | GTZAMBOFOCID | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4302 | TCEDCPAMUCUTNZAMBOAZDS | NA | TCEDCPAMUCUTNZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Pamucutan | Territory 8 | 121.9562 | 6.9991 | Brgy. Pamucutan, Zamboanga City, Zamboanga Del Sur | GTZAMBOFOCID | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3334 | TCAICCARMENCDOMOR |  | TCAICCARMENCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Carmen | Territory 8 | 124.6064 | 8.4623 | Brgy. Canito-an, Cagayan De Oro City, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4720 | TCAICCARMENCDOMOR | NA | TCAICCARMENCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Carmen | Territory 8 | 124.6064 | 8.4623 | Brgy. Canito-an, Cagayan De Oro City, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4738 | TCAICNHAINDAHAGCDOMOR | NA | TCAICNHAINDAHAGCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Indahag | Territory 8 | 124.6718 | 8.4444 | Brgy. Indahag, Cagayan de Oro City, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4711 | TCEDCSUMPONGINDAHAGCDOMOR | NA | TCEDCSUMPONGINDAHAGCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Indahag | Territory 8 | 124.6592 | 8.4309 | Brgy. Indahag, Cagayan De Oro, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3200 | TCEDCDONJULIOPUNTODCDOMOR | NA | TCEDCDONJULIOPUNTODCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Puntod | Territory 8 | 124.6582 | 8.4984 | Escobido Street, Brgy. Puntod, Cagayan de Oro City | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4466 | TCFGABRGY18GINGOOMOR | NA | TCFGABRGY18GINGOOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY | Barangay 18-A (Pob.) | Territory 8 | 125.1048 | 8.8303 | Brgy. 18(Pob.), Gingoog, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4749 | TCAICLAPINIGKPATAGLDN |  | TCAICLAPINIGKPATAGLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | KAPATAGAN | Lapinig | Territory 8 | 7.9214 | 123.6875 | National Highway, Brgy. Lapinig, Kapatagan, Lanao Del Norte | TUBOD | UNITY | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4753 | TCEDCBALATACTANGUIBMOCC |  | TCEDCBALATACTANGUIBMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TANGUB CITY | Sumirap | Territory 8 | 8.0386 | 123.6631 | Brgy. Sumirap, Tangub City, Misamis Occidental | TUBOD | EDOTCO | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4750 | TCEDCPAGLAUMDUMALIZDS |  | TCEDCPAGLAUMDUMALIZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | DUMALINAO | Paglaum (Pob.) | Territory 8 | 7.8159 | 123.3613 | Malinawan A. Dumalinao, Zamboanga Del Sur | PAGADIAN | EDOTCO | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4801 | TCEDCKITABOGTITAYZSIB |  | TCEDCKITABOGTITAYZSIB | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | TITAY | Kitabog | Territory 8 | 7.8383 | 122.5812 | Brgy. Kitabog, Titay, Zamboanga Sibugay | IPIL FOC | EDOTCO | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4752 | TCEDCTUBODLWOODZDS |  | TCEDCTUBODLWOODZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LAKEWOOD | Tubod | Territory 8 | 7.8055 | 123.2068 | Asian Highway Purok Mangga / Brgy. Tubod, Lakewood, Zamboanga Del Sur | MIMELD | EDOTCO | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4751 | TCEDCDONJOSEMNUKANZDN |  | TCEDCDONJOSEMNUKANZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | MANUKAN | Don Jose Aguirre | Territory 8 | 8.5235 | 123.1455 | Brgy. Don Jose, Aguirre, Manukan, Zamboanga del Norte | DAPITAN | EDOTCO | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 92 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4806 | TCEDCGALASDPOLOGZDN |  | TCEDCGALASDPOLOGZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (Capital) | Galas | Territory 8 | 8.5519 | 123.3409 | Sitio Lubing Ogis, Brgy. Galas, Dipolog City, Zamboanga del Norte | DAPITAN | EDOTCO | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4814 | TCEDCSUAREZILIGANLDN |  | TCEDCSUAREZILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | Suarez | Territory 8 | 8.1935 | 124.2159 | Brgy. Suarez, Iligan City, Lanao del Norte | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4826 | TCAICISHAISUAREILIGANLDN |  | TCAICISHAISUAREILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | Suarez | Territory 8 | 8.1809 | 124.2174 | Lot 1-B Brgy. Suarez Iligan Lanao Del Norte | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4672 | TCAICSANNICOLSRAWAIZDN |  | TCAICSANNICOLSRAWAIZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIRAWAI | San Nicolas (Pob.) | Territory 8 | 7.5884 | 122.1389 | Brgy. San Nicolas (Pob.), Sirawai, Zamboanga del Norte | IPIL FOC | UNITY | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2667 | TCFGASANTIAGOILIGANLDN |  | TCFGASANTIAGOILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | Santiago | Territory 8 | 8.2433 | 124.2459 | Brgy. Santiago, Iligan City, Lanao del Norte | ILIGAN |  | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4957 | TCEDCTURNODPOLOGZDN |  | TCEDCTURNODPOLOGZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (Capital) | Turno | Territory 8 | 8.5788 | 123.3546 | Brgy Turno Dipolog City Zamboanga Del Norte | DAPITAN | EDOTCO | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3315 | TCFGAP2LUINABILIGANLDN |  | TCFGAP2LUINABILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | Luinab | Territory 8 | 8.2444 | 124.2688 | Brgy.Luinab,ILIGAN CITY,LANAO DEL NORTE | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4387 | TCAICPOBDADOMULONLDS |  | TCAICPOBDADOMULONLDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MULONDO | Poblacion (Dado) | Territory 8 | 7.9204 | 124.3601 | Brgy. Poblacion (Dado), MULONDO, LANAO DEL SUR | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4807 | TCEDCMAPDALIPILIGANLDN |  | TCEDCMAPDALIPILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | Dalipuga | Territory 8 | 8.3235 | 124.2537 | Lot 3883-B-16 Mapalad, Brgy. Dalipuga, Iligan City | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1692 | TCEDCP2LABOOZAMISMOCC |  | TCEDCP2LABOOZAMISMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY | Labo | Territory 8 | 8.181 | 123.8303 | Lasola Lot, Purok 2, Labo, Ozamis City, Misamis Occidental | OZAMIS | EDOTCO | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4955 | TCAICSEMINPALAOILIGANLDN |  | TCAICSEMINPALAOILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | Palao | Territory 8 | 8.2277 | 124.2509 | Quezon Ave. Cor. Seminary Drive Bldg., Brgy. Palao, Iligan City, Lanao Del Norte | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4657 | TCAICSUHARABISIOCONZDN |  | TCAICSUHARABISIOCONZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIOCON | Bucana | Territory 8 | 7.6986 | 122.1264 | Brgy. Bucana, Siocon, Zamboanga del Norte | IPIL FOC | UNITY | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5099 | TCEDCP2MOBODOROQUIMOCC |  | TCEDCP2MOBODOROQUIMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY (Capital) | Mobod | Territory 8 | 8.4935 | 123.7824 | Brgy.Mobod_Oroquieta_Misamis Occidental | CLAMBA | EDOTCO | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5090 | TCAICPOB2OROQUIMOCC |  | TCAICPOB2OROQUIMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY (Capital) | Poblacion II | Territory 8 | 8.4849 | 123.8075 | Brgy. Poblacion II OROQUIETA CITY (CAPITAL) MISAMIS OCCIDENTAL | CLAMBA | UNITY | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5096 | TCEDCDELMONTEBUUGZSIB |  | TCEDCDELMONTEBUUGZSIB | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | BUUG | Del Monte | Territory 8 | 7.7217 | 123.0003 | Brgy. Del Monte Buug, Buug, Zamboanga Sibugay | MIMELD | EDOTCO | AREA 6 | ZAMBOANGA | IMELDA | EVERARD A. PENAFLOR | CEDRIC MARK A. RAGO | 10015178 | 9176882612 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4823 | TCEDCCAWAYANMARANTLDS |  | TCEDCCAWAYANMARANTLDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARANTAO | Cawayan | Territory 8 | 7.9498 | 124.2294 | Brgy Cawayan Kalaw, Marantao, Lanao Del Sur | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4936 | TCAICLOWPOLTANGUIBMOCC |  | TCAICLOWPOLTANGUIBMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | TANGUB CITY | Barangay VI - Lower Polao (Pob.) | Territory 8 | 8.0762 | 123.7394 | Piltel Cmpd., Brgy. Barangay Vi - Lower Polao (Pob.), Tangub City, Misamis Occidental | TUBOD | UNITY | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4930 | TCEDCPOB3CLARINMOCC |  | TCEDCPOB3CLARINMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | CLARIN | Poblacion III | Territory 8 | 8.2026 | 123.8578 | Barangay Poblacion 111, Clarin, Misamis Occidental | OZAMIS | EDOTCO | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4931 | TCCREBINUANGANSINDANZDN |  | TCCREBINUANGANSINDANZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SINDANGAN | Binuangan | Territory 8 | 8.2641 | 122.971 | Binuangon Sindangan, Zamboanga del Norte | DAPITAN | CREI | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 93 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4922 | TCATCTERESTUBODILIGANLDN |  | TCATCTERESTUBODILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | Tubod | Territory 8 | 8.2155 | 124.2478 | Purok Sta Teresita, Tubod Iligan City | ILIGAN | ATC | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4956 | TCEDCTINAGOZAMISMOCC |  | TCEDCTINAGOZAMISMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY | Tinago | Territory 8 | 8.1451 | 123.8362 | Purok Green Valley, Brgy. Tinago, Ozamis City, Misamis Occidental | OZAMIS | EDOTCO | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4658 | TCAICNEWLITUBANSIOCONZDN |  | TCAICNEWLITUBANSIOCONZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | SIOCON | New Lituban | Territory 8 | 7.7104 | 122.1703 | Brgy. New Lituban, Siocon, Zamboanga del Norte | IPIL FOC | UNITY | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4923 | TCAICSNJOSEPGDIANZDS |  | TCAICSNJOSEPGDIANZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY (Capital) | San Jose (Pob.) | Territory 8 | 7.8289 | 123.4332 | Padap Rd., Brgy. San Jose (Poblacion), Pagadian, Zamboanga Del Sur | PAGADIAN | UNITY | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | GLENN STEWART R. ARAO-ARAO | 10008511 | 9176885068 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5088 | TCCRETWAGANORTELABANGZDS |  | TCCRETWAGANORTELABANGZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LABANGAN | Tawagan Norte | Territory 8 | 7.8742 | 123.4797 | Brgy. Tawagan Norte Labangan, Zamboange del Sur | PAGADIAN | CREI | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4929 | TCAICSUDLONMOLAVEZDS |  | TCAICSUDLONMOLAVEZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MOLAVE | Sudlon | Territory 8 | 8.0922 | 123.4916 | Purok Millunium, Brgy. Sudlon, Molave Zamboanga Del Sur | PAGADIAN | UNITY | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4925 | TCCREBOBONGANLBASONZDN |  | TCCREBOBONGANLBASONZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | LABASON | Bobongan | Territory 8 | 8.0762 | 122.5728 | Brgy. Bonbongan, Labason, Zambaonga del Norte | IPIL FOC | CREI | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 94 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4674 | TCFGAP1POBBMSALIPZDS |  | TCFGAP1POBBMSALIPZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MIDSALIP | Poblacion B | Territory 8 | 8.0325 | 123.3127 | Brgy. Poblacion B, Midsalip, Zamboanga Del Sur | PAGADIAN | FTAP | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4675 | TCFGAPIKALAWAGSNAGALDN |  | TCFGAPIKALAWAGSNAGALDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | SULTAN NAGA DIMAPORO (KAROMATAN) | Dabliston | Territory 8 | 7.8074 | 123.7009 | Brgy. Dabliston, Sultan Naga Dimaporo (Karomatan), Lanao Del Norte | TUBOD | FTAP | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4335 | TCISLANGCANGOROQUIMOCC |  | TCISLANGCANGOROQUIMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OROQUIETA CITY (Capital) | Langcangan Upper | Territory 8 | 8.4782 | 123.7943 | Brgy. Langcangan Upper, Oroquieta City, Misamis Occidental | CLAMBA | ISON | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4384 | TCAICPOONAPOONABLDS |  | TCAICPOONAPOONABLDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | POONA BAYABAO (GATA) | Madanding | Territory 8 | 7.8361 | 124.3478 | Brgy. Madanding, Poona Bayabao (Gata), Lanao del Sur | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4932 | TCEDCLOWERPULACLABANGZDS |  | TCEDCLOWERPULACLABANGZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | LABANGAN | Lower Pulacan | Territory 8 | 7.8963 | 123.4909 | Lower Pulacan, Labangan, Zamboanga del Sur | PAGADIAN | EDOTCO | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4610 | RIZALDPOLOGZDNAS |  | RIZALDPOLOGZDNAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (Capital) | Central (Pob.) | Territory 8 | 8.5869 | 123.3416 | Rizal Ave, brgy Central, Dipolog City, Zamboanga del Norte | DAPITAN | GT | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4670 | TCFGANABILIDPROXASZDN |  | TCFGANABILIDPROXASZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | PRES. MANUEL A. ROXAS | Nabilid | Territory 8 | 8.5134 | 123.2529 | Brgy. Nabilid, Pres. Manuel A. Roxas, Zamboanga del Norte | DAPITAN | FTAP | AREA 5 | PAGADIAN | SINDANGAN | FRANCISCO S. YONGCO | MARLON O. MACAPOBRE | 10021087 | 95 9176885119 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4804 | TCAICTAMBOPOBPUALASLDS |  | TCAICTAMBOPOBPUALASLDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | PUALAS | Tambo (Pob.) | Territory 8 | 7.8226 | 124.0792 | Brgy. Tambo (Pob.), Pualas, Lanao del Sur | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4378 | TCSBAPARIDIMARAWILDS |  | TCSBAPARIDIMARAWILDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY (Capital) | Olawa Ambolong | Territory 8 | 7.9978 | 124.3142 | Brgy. Olawa Ambolong, Marawi City, Lanao del Sur | ILIGAN | SBA | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2581 | TCFGABALAGUNUNMAGUILDS |  | TCFGABALAGUNUNMAGUILDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MAGUING | Balagunun | Territory 8 | 7.8834 | 124.3598 | Brgy. Balagunun, MAGUING, LANAO DEL SUR | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4349 | TCAICMAPANTAOTUGAYALDS |  | TCAICMAPANTAOTUGAYALDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | TUGAYA | Dandanun | Territory 8 | 7.8797 | 124.168 | BrgyDandanun, Tugaya, Lanao del Sur | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3804 | TCFGAMARPOBMARAWILDS |  | TCFGAMARPOBMARAWILDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY (Capital) | Marawi Poblacion | Territory 8 | 8.0127 | 124.2768 | Brgy. Poblacion, Marawi City, Lanao del Sur | ILIGAN | SBA | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4372 | TCSBAMORILOKMARAWILDS |  | TCSBAMORILOKMARAWILDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY (Capital) | Bangon | Territory 8 | 7.9989 | 124.2802 | Brgy.Bangon, Marawi City, Lanao Del Sur | ILIGAN | SBA | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4793 | TCEDCMARIBOLBAYABLDS |  | TCEDCMARIBOLBAYABLDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | LUMBA-BAYABAO (MAGUING) | Maribo (Pob.) | Territory 8 | 7.8659 | 124.3697 | LUMBA-BAYABAO (MAGUING), LANAO DEL SUR | ILIGAN | EDOTCO | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4820 | TCEDCP1LABINOZAMISMOCC |  | TCEDCP1LABINOZAMISMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY | Labinay | Territory 8 | 8.1006 | 2891123.757 | Purok 1 Labinay Tangub City, Misamis Occidental | TUBOD | EDOTCO | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2560 | TCSBABUADIAMLOYMASIYLDS |  | TCSBABUADIAMLOYMASIYLDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MASIU | Buadi Amloy | Territory 8 | 7.8159 | 124.3263 | Brgy. Buadi Amloy, MASIU, LANAO DEL SUR | ILIGAN | SBA | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4177 | TCISPOBMALUNGSAR |  | TCISPOBMALUNGSAR | REGION XII (SOCCSKSARGEN) | SARANGANI | MALUNGON | Poblacion | Territory 7 | 125.2642 | 6.3775 | Brgy. Poblacion, Malungon, Sarangani | GENSAN | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4649 | TCAICROSARYHTS5COTABMGDN |  |  | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Rosary Heights V | Territory 7 | 124.2546 | 7.2088 | Brgy. Rosary Heights III, Cotabato City, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4244 | TCAICPOBLA6COTABMGDN |  | TCAICPOBLA6COTABMGDN | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Poblacion VI | Territory 7 | 124.2467 | 7.2253 | Alejandro Dorotheo St. Brgy. Poblacion 6, Cotabato City, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4783 | TCAICCANRY2POLOMOSCOT |  | TCAICCANRY2POLOMOSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK | Cannery Site | Territory 7 | 125.0843 | 6.2359 | Lot 37 E5 Ligtas Subd. Cannery Site, Polomolok, South Cotabato | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4782 | TCAICBLAYONPOBTUPISCOT |  | TCAICBLAYONPOBTUPISCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TUPI | Poblacion | Territory 7 | 124.9485 | 6.3357 | Balayon St.Brgy. Poblacion Tupi South Cotabao , Tupi, South Cotabato | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4445 | TCAICKALIANMANGUDMGDN |  | TCAICKALIANMANGUDMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | MANGUDADATU | Kalian | Territory 7 | 124.8436 | 6.6936 | Brgy. Kalian, Mangunadatu, Maguindanao | MLANG | UNITY | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4412 | TCEDCKAPINGKOBARONGMGDN |  | TCEDCKAPINGKOBARONGMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN SA BARONGIS (LAMBAYONG) | Barurao | Territory 7 | 124.542 | 6.7687 | Brgy. Kapingkong, Lambayong (Mariano Marcos), Sultan Kudarat | TACURONG | EDOTCO | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4462 | TCFGAAPO4POBKIDAPNCOT |  | TCFGAAPO4POBKIDAPNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CITY OF KIDAPAWAN (Capital) | Singao | Territory 7 | 125.0714 | 6.9977 | Apo Sandawa Homes Phase 4, Brgy. Singao, Kidapawan City, North Cotabato | KIDAPAWAN | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2841 | TCAICFMILLANCOTABMGDN |  | TCAICFMILLANCOTABMGDN | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Rosary Heights I | Territory 7 | 124.244 | 7.2106 | Brgy. Rosary Heights, Cotabato City, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4687 | TCAICTUAYANIHOFFERMGDN |  | TCAICTUAYANIHOFFERMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU HOFFER AMPATUAN | Tuayan I | Territory 7 | 124.4262 | 6.8509 | Brgy. Tuayan I, Datu Hoffer Ampatuan, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4699 | TCEDCSPENMATLIMALABALDS |  | TCEDCSPENMATLIMALABALDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MALABANG | Matalin | Territory 8 | 124.0776 | 7.6328 | Brgy. Matalin, Malabang, Lanao del Sur | COTABATO | EDOTCO | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4756 | TCAICLILIONG2CARMENNCOT |  | TCAICLILIONG2CARMENNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CARMEN | Liliongan | Territory 7 | 124.7825 | 7.3653 | Barangay Liliongan, Carmen, North Cotabato | MLANG | UNITY | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4443 | TCFGAPOBKBACANNCOT |  | TCFGAPOBKBACANNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN | Poblacion | Territory 7 | 124.826 | 7.1052 | Brgy. Poblacin, Kabacan, North Cotabato | MLANG | FTAP | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4542 | TCFGABRGYPOB5MIDSAYNCOT |  | TCFGABRGYPOB5MIDSAYNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP | Barangay Poblacion 8 | Territory 7 | 124.5366 | 7.1977 | Barangay Poblacion 8. Midsayap, North Cotabato | MIDSAYAP | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4685 | TCFGADUALINGALEOSNNCOT |  | TCFGADUALINGALEOSNNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALEOSAN | Dualing | Territory 7 | 124.5683 | 7.1619 | Brgy. Dualing, Aleosan, North Cotabato | MIDSAYAP | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4789 | TCAICSANISI4GENSANSCOT |  | TCAICSANISI4GENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | San Isidro (Lagao 2nd) | Territory 7 | 125.1818 | 6.1491 | Brgy. San Isidro (Lagao 2Nd), General Santos City (Dadiangas), South Cotabato | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4784 | TCEDCSUDAPIN2KIDAPNCOT |  | TCEDCSUDAPIN2KIDAPNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CITY OF KIDAPAWAN (Capital) | Sudapin | Territory 7 | 125.1121 | 7.0278 | Brgy. Sudapin, Kidapawan City, North Cotabato | KIDAPAWAN | EDOTCO | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4787 | TCFGASANISIDROKIDAPNCOT |  | TCFGASANISIDROKIDAPNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CITY OF KIDAPAWAN (Capital) | San Isidro | Territory 7 | 125.0344 | 7.0795 | Brgy. San Isidro, Kidapawan, North Cotabato | KIDAPAWAN | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4780 | TCFGABUALTLUNANNCOT |  | TCFGABUALTLUNANNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | TULUNAN | Bual | Territory 7 | 124.8929 | 6.7876 | Brgy. Bual, Tulunan, North Cotabato | MLANG | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4772 | TCFGABKAYPAITTANTANSCOT |  | TCFGABKAYPAITTANTANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | TANTANGAN | Bukay Pait | Territory 7 | 124.7666 | 6.5643 | Brgy. Bukay Pait, Tantangan, South Cotabato | KORONADAL | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4761 | TCEDCBAGOLBASALEOSNNCOT |  | TCEDCBAGOLBASALEOSNNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALEOSAN | Bagolibas | Territory 7 | 124.591 | 7.1261 | Brgy. Bagolibas, Aleosan, North Cotabato | MIDSAYAP | EDOTCO | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4768 | TCEDCLAMBABANGASCOT |  | TCEDCLAMBABANGASCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | BANGA | Lamba | Territory 7 | 124.8183 | 6.3537 | Brgy. Lamba, Banga, South Cotabato | KORONADAL | EDOTCO | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4651 | TCAICP13FATIGENSANSCOT |  | TCAICP13FATIGENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Fatima | Territory 7 | 125.1056 | 6.0779 | Brgy. Fatima, General Santos City, South Cotabato | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4769 | TCAGBAGANGDULUNMGDN |  | TCAGBAGANGDULUNMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | GUINDULUNGAN | Bagan | Territory 7 | 124.4018 | 6.9524 | Brgy. Bagan, Guindulungan, Maguindanao | COTABATO | ALT GLOBAL | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4771 | TCAGKATIDTUANKBACANNCOT |  | TCAGKATIDTUANKBACANNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN | Katidtuan | Territory 7 | 124.8739 | 7.0944 | Brgy. Katidtuan, Kabacan, North Cotabato | MLANG | ALT GLOBAL | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4396 | TCAICPAULABIONKABUNMGDN |  | TCAICPAULABIONKABUNMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | NORTHERN KABUNTALAN | Gayonga | Territory 7 | 124.4779 | 7.2019 | Bo. Of Gayonga, Municipality of Kabuntalan, Maguindanao | MIDSAYAP | UNITY | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4729 | TCLDCMCARTHURPOBKIDAPNCOT |  | TCLDCMCARTHURPOBKIDAPNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CITY OF KIDAPAWAN (Capital) | Poblacion | Territory 7 | 125.0885 | 7.0089 | MCARTHUR ST, KIDAPAWAN CITY, COTABATO | KIDAPAWAN | LDIC | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4683 | TCAICMIDTIMANGGALMGDN |  | TCAICMIDTIMANGGALMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU ANGGAL MIDTIMBANG | Midtimbang (Pob.) | Territory 7 | 124.341 | 6.9925 | Brgy. Midtimbang (Pob.), Datu Anggal Midtimbang, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3605 | TCAICLBANGAL2GENSANSCOT |  | TCAICLBANGAL2GENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Labangal | Territory 7 | 125.1444 | 6.1189 | Near Mindanao Polytechnic College Digos-Makar Road Crossing, Labangal, General Santos City, South Cotabato | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4762 | TCAICNALAPAANPIKITNCOT |  | TCAICNALAPAANPIKITNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT | Nalapaan | Territory 7 | 124.6242 | 7.0991 | Brgy. Nalapaan, Pikit, North Cotabato | MIDSAYAP | UNITY | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4758 | TCEDCCWBOYPOBPAGLASMGDN |  | TCEDCCWBOYPOBPAGLASMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | DATU PAGLAS | Poblacion | Territory 7 | 124.8733 | 6.7523 | "Cowboy Compound, National Highway, Datu Paglas, Maguindanao" | TACURONG | EDOTCO | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4760 | TCEDCOSIASKBACANNCOT |  | TCEDCOSIASKBACANNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN | Osias | Territory 7 | 124.839 | 7.1036 | Brgy Osias, Kabacan, North Cotabato | MLANG | EDOTCO | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4764 | TCEDCKALASUYN2KIDAPNCOT |  | TCEDCKALASUYN2KIDAPNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | CITY OF KIDAPAWAN (Capital) | Kalasuyan | Territory 7 | 125.085 | 7.036 | "JR. Brgy. Kalasuyan Kidapawan City , City of Kidapawan (Capital), Cotabato (North Cotabato)" | KIDAPAWAN | EDOTCO | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4813 | TCAICPOBMAROGOLDS |  | TCAICPOBMAROGOLDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MAROGONG | Marogong Proper (Pob.) | Territory 8 | 124.149 | 7.6788 | Brgy.MarogongProper, Marogong, LanaoDelSur | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4447 | TCISZ2POBKNADALSCOT |  | TCISZ2POBKNADALSCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KORONADAL CITY | Poblacion | Territory 7 | 124.8556 | 6.4934 | Brgy. Zone II (Pob.), Koronadal City (Capital), South Cotabato | GENSAN | ISON | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4385 | TCAICPIGCALGNNULINGMGDN |  | TCAICPIGCALGNNULINGMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN KUDARAT (NULING) | Pigcalagan | Territory 7 | 124.3532 | 7.2643 | Brgy. Pigcalagan, Sultan Kudarat, Maguindanao | MIDSAYAP | UNITY | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4650 | TCFGAZONE4POBKNADALSCOT |  | TCFGAZONE4POBKNADALSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | CITY OF KORONADAL (Capital) | Zone IV (Pob.) | Territory 7 | 124.8309 | 6.5009 | Brgy. Zone Iv (Pob.), Koronadal City (Capital), Koronadal City (Capital) | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4429 | TCEDCPIDTIGUILAMBAYSKUD |  | TCEDCPIDTIGUILAMBAYSKUD | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) | Midtapok | Territory 7 | 124.6739 | 6.7999 | Brgy. Midtapok, Lambayong (Mariano Marcos), Sultan Kudarat | TACURONG | EDOTCO | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4785 | TCEDCLIBERTAD2SURALLSCOT |  | TCEDCLIBERTAD2SURALLSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SURALLAH | Libertad (Pob.) | Territory 7 | 124.7498 | 6.367 | 847Camia cor. Dahlia Street., Libertad , Surallah, South Cotabato | KORONADAL | EDOTCO | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5006 | TCAICKALANGN2COTABMGDN |  | TCAICKALANGN2COTABMGDN | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Kalanganan II | Territory 7 | 124.202 | 7.1982 | Brgy. Kalanganan II, City Of Cotabato, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4765 | TCEDCMILBUKPLIMBASKUD |  | TCEDCMILBUKPLIMBASKUD | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | PALIMBANG | Milbuk | Territory 7 | 124.2727 | 6.1606 | Brgy. Milbuk, Palimbang, Sultan Kudarat | GENSAN | EDOTCO | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4998 | TCAICMALANGTPANDAGMGDN |  | TCAICMALANGTPANDAGMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PANDAG | Malangit | Territory 7 | 124.7834 | 6.7406 | Brgy. Malangit, Pandag, Maguindanao | TACURONG | UNITY | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4641 | TCFGAMBUHAYZ4KNADALSCOT |  | TCFGAMBUHAYZ4KNADALSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | CITY OF KORONADAL (Capital) | Zone III (Pob.) | Territory 7 | 124.8435 | 6.4998 | Brgy. Zone III (Pob.), Koronadal City, South Cotabato | GENSAN | FTAP | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4788 | TCAGBARANGRNALMADANCOT |  | TCAGBARANGRNALMADANCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALAMADA | Barangiran | Territory 7 | 124.5488 | 7.4261 | Brgy. Barangiran, Alamada, North Cotabato | MIDSAYAP | ALT GLOBAL | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5079 | TCAICSANVCENTESNIÑOSCOT |  | TCAICSANVCENTESNIÑOSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | SANTO NIÑO | Poblacion | Territory 7 | 124.6517 | 6.4904 | Poblacion, Sto. Nino, South Cotabato | KORONADAL | UNITY | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4461 | TCISKAMANGAMAASIMSAR |  | TCISKAMANGAMAASIMSAR | REGION XII (SOCCSKSARGEN) | SARANGANI | MAASIM | Kamanga | Territory 7 | 125.0578 | 5.8586 | Brgy. Kamanga, Maasim, Sarangani | GENSAN | ISON | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4400 | TCAICPOB5MIDSAYNCOT |  | TCAICPOB5MIDSAYNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP | Barangay Poblacion 5 | Territory 7 | 124.5318 | 7.1942 | Brgy.Poblacion 5,Midsayap,COTABATO (NORTH COTABATO) | MIDSAYAP | UNITY | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4693 | TCCREP10BATANGVALENBUK |  | TCCREP10BATANGVALENBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF VALENCIA | Batangan | Territory 8 | 125.1207 | 7.9039 | Purok 10, Brgy. Batangan, Valencia City | CDO NDC | CREI | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4702 | TCEDCKIBANGAYLANTAPBUK |  | TCEDCKIBANGAYLANTAPBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | LANTAPAN | Kibangay | Territory 8 | 124.8955 | 8.0485 | Brgy. Kibangay, Lantapan, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4745 | TCEDCP7VINTARVALENBUK |  | TCEDCP7VINTARVALENBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF VALENCIA | Vintar | Territory 8 | 125.1916 | 7.9434 | Purok 7 Vintar Valencia City , City of Valencia, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4818 | TCEDCBAGUIOSFERNBUK |  | TCEDCBAGUIOSFERNBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | SAN FERNANDO | Little Baguio | Territory 8 | 125.3023 | 7.9229 | Brgy. Little Baguio, San Fernando, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4454 | TCAICNEBOVALENBUK | TCAICNEBOVALENBUK | TCAICNEBOVALENBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF VALENCIA | Lilingayon | Territory 8 | 124.9783 | 7.9745 | Brgy Lilingayon, Valencia City, Bukidnon | CDO NDC | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4900 | TCCREBAGONTASVALENBUK |  | TCCREBAGONTASVALENBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF VALENCIA | Bagontaas | Territory 8 | 125.0979 | 7.9334 | Barrio Bagontaas, Valencia City, Bukidnon | CDO NDC | CREI | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4924 | TCEDCZAMBOANGMALAYBBUK |  | TCEDCZAMBOANGMALAYBBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF MALAYBALAY (Capital) | Zamboanguita | Territory 8 | 125.3006 | 8.21 | Brgy. Zamboanguita, Malaybalay, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4951 | TCEDCMTVIEWLUROGVALENBUK | TCEDCMTVIEWLUROGVALENBUK |  | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF VALENCIA | Lurogan | Territory 8 | 7.9818 | 125.0016 | Mt. View College, Mt. Nebo, Valencia City, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5256 | TCAICHALAPITAN2SFERNBUK |  | TCAICHALAPITAN2SFERNBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | SAN FERNANDO | Halapitan (Pob.) | Territory 8 | 125.3268 | 7.9191 | Brgy Poblacion Halapitan San Fernando, BUKIDNON | CDO NDC | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4405 | TCAGMALANANGOPOLMOR |  | TCAGMALANANGOPOLMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | OPOL | Malanang | Territory 8 | 124.5709 | 8.491 | Brgy. Malanang, Opol, Misamis Oriental | CDO NDC | ALT GLOBAL | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4721 | TCAICNAIKINGONCDOMOR |  | TCAICNAIKINGONCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Baikingon | Territory 8 | 124.5723 | 8.4658 | Brgy. Baikingon, Cagayan De Oro, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5309 | TCISMASIAGBAGUMBSKUD |  | TCISMASIAGBAGUMBSKUD | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | BAGUMBAYAN | Masiag | Territory 7 | 124.4565 | 6.4656 | Brgy. Masiag, Bagumbayan, Sultan Kudarat | TACURONG | ISON | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4360 | TCAICROSARYHTSXCOTABMGDN |  | TCAICROSARYHTSXCOTABMGDN | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Rosary Heights X | Territory 7 | 124.2336 | 7.1977 | Brgy Rosary Heights X, Cotabato City, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4655 | TCAICSANJOSEGENSANSCOT |  | TCAICSANJOSEGENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | San Jose | Territory 7 | 125.1025 | 6.0886 | Brgy.SanJose, General Santos City, South Cotabato | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4759 | TCEDCPINAMTONMTALAMNCOT |  | TCEDCPINAMTONMTALAMNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MATALAM | Pinamaton | Territory 7 | 124.9899 | 7.2628 | Brgy. Pinamaton, Matalam, North Cotabato | MLANG | EDOTCO | AREA 12 | COTABATO 2 | MLANG | GILSON A. NAVARRA | JUN MARLO M. CASTRODES | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5071 | TCEDCOLYMPOGGENSANSCOT |  | TCEDCOLYMPOGGENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Olympog | Territory 7 | 125.1934 | 6.2197 | Purok 2, Brgy Olympog, General Santos City, South Cotabato | GENSAN | EDOTCO | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5282 | TCEDCCALABANITGLANSAR |  | TCEDCCALABANITGLANSAR | REGION XII (SOCCSKSARGEN) | SARANGANI | GLAN | Calabanit | Territory 7 | 125.2085 | 5.8186 | Brgy. Calabanit, Glan, Sarangani Province | GENSAN | EDOTCO | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5298 | TCEDCCROSSPALKNPOLOMOSCOT |  | TCEDCCROSSPALKNPOLOMOSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | POLOMOLOK | Crossing Palkan | Territory 7 | 125.0125 | 6.266 | Purok 3 Brgy Crossing Palkan, Polomolok, South Cotabato | GENSAN | EDOTCO | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010552 | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5126 | TCEDCMONTAYLIBUNGNCOT |  | TCEDCMONTAYLIBUNGNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | LIBUNGAN | Montay | Territory 7 | 124.5528 | 7.2879 | Barangay Montay, Libungan, North Cotabato | MIDSAYAP | EDOTCO | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4690 | TCAICLAKELAHITLSEBUSCOT |  | TCAICLAKELAHITLSEBUSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | LAKE SEBU | Lake Lahit | Territory 7 | 124.7192 | 6.2457 | Brgy. Lake Lahit, LakeSebu, SouthCotabato | KORONADAL | UNITY | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4767 | TCEDCSIBSIB2TLUNANNCOT |  | TCEDCSIBSIB2TLUNANNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | TULUNAN | Sibsib | Territory 7 | 124.893 | 6.8232 | Brgy. Sibsib, Tulunan, North Cotabato | MLANG | EDOTCO | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5169 | TCEDCPOBTBOLISCOT |  | TCEDCPOBTBOLISCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | T'BOLI | Poblacion | Territory 7 | 124.8221 | 6.2128 | Brgy. Poblacion, T'boli, South Cotabato | KORONADAL | EDOTCO | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4625 | TCEDCROSARYHTS1COTABMGDN |  | TCEDCROSARYHTS1COTABMGDN | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Rosary Heights I | Territory 7 | 124.2401 | 7.2201 | Brgy. Bagua II, Cotabato City, Maguindanao | COTABATO | EDOTCO | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4875 | TCFGABAOALMADANCOT |  | TCFGABAOALMADANCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | ALAMADA | Bao | Territory 7 | 124.6459 | 7.3889 | Brgy. Bao, Alamada, North Cotabato | MIDSAYAP | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5302 | TCAICESPERNZAKNADALSCOT |  | TCAICESPERNZAKNADALSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | CITY OF KORONADAL (Capital) | Esperanza | Territory 7 | 124.8898 | 6.4914 | Brgy.Esperanza, Koronadal City, South Cotabato | GENSAN | UNITY | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | PETER L. MANDIN | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5142 | TCFGABATULWNPIKITNCOT |  | TCFGABATULWNPIKITNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | PIKIT | Batulawan | Territory 7 | 124.672 | 7.0735 | Brgy Batulawan, Pikit, North Cotabato | MLANG | FTAP | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4526 | TCAICTABONBISLIGSDS | NA | TCAICTABONBISLIGSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | CITY OF BISLIG | Tabon | Territory 8 | 8.18 | 126.3622 | Brgy. Tabon, Bislig City, Surigao del Sur | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4517 | TCFGAP3BOLHOONMIGUELSDS | NA | TCFGAP3BOLHOONMIGUELSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | SAN MIGUEL | Bolhoon | Territory 8 | 8.8659 | 125.9762 | Brgy. Bolhoon SAN MIGUEL SURIGAO DEL SUR | BUTUAN (TECHNICAL OFFICE) | FRONTIER | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5093 | TCFGAP3HORNASANAGUSTNSDS | NA | TCFGAP3HORNASANAGUSTNSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | SAN AGUSTIN | Hornasan | Territory 8 | 8.7604 | 126.2363 | Brgy. Hornasan SAN AGUSTIN SURIGAO DEL SUR | BUTUAN (TECHNICAL OFFICE) | FRONTIER | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4938 | TCEDCALTATIGUMPGDIANZDS |  |  | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | PAGADIAN CITY (Capital) | Tiguma | Territory 8 | 7.8475 | 123.4626 | Tiguma, PAGADIAN CITY (Capital), ZAMBOANGA DEL SUR | PAGADIAN | EDOTCO | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4382 | TCAICMORIATAOTARAKALDS |  |  | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | TARAKA | Moriatao Loksa Datu | Territory 8 | 7.8939 | 124.3363 | Brgy. Moriato Loksa Datu, Taraka, Lanao Del Sur | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4959 | TCEDCMINAOGDPOLOGZDN |  | TCEDCMINAOGDPOLOGZDN | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL NORTE | DIPOLOG CITY (Capital) | Minaog | Territory 8 | 8.5972 | 123.3503 | P-Boli St., Brgy. Minaog, Dipolog City, Zamboanga del Norte | DAPITAN | EDOTCO | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5101 | TCPHTPOBLACIONMHAYAGZDS |  | TCPHTPOBLACIONMHAYAGZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | MAHAYAG | Poblacion (Upper Mahayag) | Territory 8 | 8.1253 | 123.4345 | Mahayag, Zamboanga del Sur | PAGADIAN | PHILTOWER | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4390 | TCAICTARIKBUADILDS |  | TCAICTARIKBUADILDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | BUADIPOSO-BUNTONG | Tarik | Territory 8 | 7.9546 | 124.3773 | Brgy. Tarik BUADIPOSO-BUNTONG LANAO DEL SUR | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4374 | TCSBARAYASADUCMARAWILDS |  | TCSBARAYASADUCMARAWILDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARAWI CITY (Capital) | Raya Saduc | Territory 8 | 8.0017 | 124.2889 | Brgy. Raya Saduc, Marawi City, Lanao Del Sur | ILIGAN | SBA | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4671 | TCPHTKIWALANILIGANLDN |  | TCPHTKIWALANILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | Kiwalan | Territory 8 | 8.2861 | 124.2678 | BrgyKiwalan, Iligan City Lanao del Norte | ILIGAN | PHILTOWER | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5106 | TCEDCIMPERAGUAOZAMISMOCC |  | TCEDCIMPERAGUAOZAMISMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIS CITY | Aguada (Pob.) | Territory 8 | 8.1452 | 123.8447 | Brgy. Aguada (Pob.) OZAMIZ CITY MISAMIS OCCIDENTAL | OZAMIS | EDOTCO | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4710 | TCEDCKALUBIDCARLSBUK |  | TCEDCKALUBIDCARLSBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS | Kalubihon | Territory 8 | 124.9084 | 7.673 | Brgy. Kalubihon, Don Carlos, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4747 | TCEDCBACUSAPNGANTBUK | TCEDCBACUSAPNGANTBUK |  | REGION X (NORTHERN MINDANAO) | BUKIDNON | PANGANTUCAN | Bacusanon | Territory 8 | 124.7121 | 7.8843 | Bacusanon, Pangantucan, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4817 | TCEDCP2LAMPANKALILABUK | TCEDCP2LAMPANKALILABUK |  | REGION X (NORTHERN MINDANAO) | BUKIDNON | KALILANGAN | Lampanusan | Territory 8 | 124.7625 | 7.6541 | Purok 2 Lampanusan, Kalilangan, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5089 | TCEDCSAYREDONCARDCARLSBUK | TCEDCSAYREDONCARDCARLSBUK |  | REGION X (NORTHERN MINDANAO) | BUKIDNON | DON CARLOS | Don Carlos Sur (Pob.) | Territory 8 | 124.9973 | 7.6797 | Sayre Highway, Brgy. Poblacion, Don Carlos, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4946 | TCEDCEASTPOBKIBAWEBUK | TCEDCEASTPOBKIBAWEBUK | TCEDCEASTPOBKIBAWEBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | KIBAWE | East Kibawe (Pob.) | Territory 8 | 7.5702 | 124.9902 | Roxas cor. J. Luna St., Brgy. Poblacion, Kibawe, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4928 | TCEDCBULAYPOBDANGCABUK | TCEDCBULAYPOBDANGCABUK | TCEDCBULAYPOBDANGCABUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | DANGCAGAN | Poblacion | Territory 8 | 7.614 | 125.0031 | Purok 1B, Sitio Bulayak, Dancagan, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4739 | TCAIC1BPOBQUEZONBUK | TCAIC1BPOBQUEZONBUK |  | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON | Poblacion (Kiokong) | Territory 8 | 125.0988 | 7.7306 | Brgy. 2, Poblacion, Quezon, Bukidnon | CDO NDC | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5104 | TCFGAP4ALANIBLANTAPBUK | TCFGAP4ALANIBLANTAPBUK |  | REGION X (NORTHERN MINDANAO) | BUKIDNON | LANTAPAN | Alanib | Territory 8 | 8.025 | 124.9831 | Brgy. Alanib LANTAPAN BUKIDNON | CDO NDC | FTAP | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5110 | TCFGAMANDAINGCABANGBUK | TCFGAMANDAINGCABANGBUK |  | REGION X (NORTHERN MINDANAO) | BUKIDNON | CABANGLASAN | Mandaing | Territory 8 | 8.0383 | 125.2867 | Brgy.Mandaing_Cabanglasan_Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5108 | TCFGABACLAYONLANTAPBUK | TCFGABACLAYONLANTAPBUK |  | REGION X (NORTHERN MINDANAO) | BUKIDNON | LANTAPAN | Baclayon | Territory 8 | 8.0126 | 125.0022 | Brgy.Baclayon_Lantapan_Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5290 | TCAICLOMUYNKIAMBASAR |  | TCAICLOMUYNKIAMBASAR | REGION XII (SOCCSKSARGEN) | SARANGANI | KIAMBA | Lomuyon | Territory 7 | 124.7841 | 5.9171 | Brgy. Lomuyon Kiamba Sarangani | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5125 | TCFGALOWRPAATNKBACANNCOT |  | TCFGALOWRPAATNKBACANNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | KABACAN | Paatan Lower | Territory 7 | 124.8294 | 7.0778 | Purok Lewlewa, Barangay Lower Paatan, Kabacan, North Cotabato | MLANG | FTAP | AREA 13 | COTABATO 2 | MLANG | ARNOLD L. SAGUSAY | JUN MARLO M. CASTRODES | 10009384 | 9175880915 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5278 | TCAICTAMBOMASTURMGDN |  | TCAICTAMBOMASTURMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | SULTAN MASTURA | Tambo | Territory 7 | 124.2633 | 7.3173 | Brgy. Tambo, Sultan Mastura, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5057 | TCPHTSAGASA01ESPERSKUD |  | TCPHTSAGASA01ESPERSKUD | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | ESPERANZA | Sagasa | Territory 7 | 124.5335 | 6.7396 | Brgy.Sagasa01_Esperanza_SultanKudarat | TACURONG | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4990 | TCPHTBALUNTAYALABELSAR |  | TCPHTBALUNTAYALABELSAR | REGION XII (SOCCSKSARGEN) | SARANGANI | ALABEL (Capital) | Baluntay | Territory 7 | 125.2481 | 6.1274 | Brgy. Baluntay, Alabel (Capital), Sarangani | GENSAN | PHILTOWER | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4221 | TCFGAPOB4TRENTOAGS | NA | TCFGAPOB4TRENTOAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | TRENTO | Poblacion | Territory 8 | 8.0413 | 126.0543 | Brgy. Poblacion 4, Trento, Agusan Del Sur | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3306 | TCPHTSANJUAN02SURGAOSDN | NA | TCPHTSANJUAN02SURGAOSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY (Capital) | San Juan | Territory 8 | 9.7864 | 125.4817 | Purok 9, Navalca, Brgy San Juan, Surigao City, Surigao del Norte | BUTUAN (TECHNICAL OFFICE) | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5092 | TCEDCP6MABUHAYSMONICSDN | NA | TCEDCP6MABUHAYSMONICSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | SANTA MONICA (SAPAO) | Mabuhay (Pob.) | Territory 8 | 10.0174 | 126.0486 | Purok 6, Brgy. Mabuhay, Santa Monica, Surigao del Norte | BUTUAN (TECHNICAL OFFICE) | EDOTCO | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5144 | TCPHTTAGONGONTAGBINASDS | NA | TCPHTTAGONGONTAGBINASDS | REGION XIII (Caraga) | SURIGAO DEL SUR | TAGBINA | Tagongon | Territory 8 | 8.4174 | 125.2036 | BRGY. SAN JUAN, HINATUAN, SURIGAO DEL SUR | BUTUAN (TECHNICAL OFFICE) | PHILTOWER | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5100 | TCFGASANISIDROGIGAQTSDN | NA | TCFGASANISIDROGIGAQTSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | GIGAQUIT | San Isidro | Territory 8 | 9.5599 | 125.6784 | Brgy. San Isidro GIGAQUIT SURIGAO DEL NORTE | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5252 | TCFGACALOCANMGALANAGN | NA | TCFGACALOCANMGALANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | MAGALLANES | Caloc-an | Territory 8 | 9.0588 | 125.533 | Brgy. Caloc-an MAGALLANES AGUSAN DEL NORTE | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5105 | TCAICNICOLWASHSURGAOSDN | NA | TCAICNICOLWASHSURGAOSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY (Capital) | Washington (Pob.) | Territory 8 | 9.7896 | 125.4946 | Brgy. Washington (Pob.) SURIGAO CITY (Capital) SURIGAO DEL NORTE | BUTUAN (TECHNICAL OFFICE) | UNITY | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5176 | TCATCTAGUIBOBUTUANAGN | NA | TCATCTAGUIBOBUTUANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Taguibo | Territory 8 | 8.9789 | 125.6241 | Brgy Taguibo, Butuan City, Agusan Del Norte | BUTUAN (TECHNICAL OFFICE) | ATC | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4730 | TCPHTWASHINPOBSURGAOSDN | NA | TCPHTWASHINPOBSURGAOSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | SURIGAO CITY (Capital) | Washington (Pob.) | Territory 8 | 9.7878 | 125.4923 | Brgy. Washinton Poblacion, Surigao City, Surigao Del Norte | BUTUAN (TECHNICAL OFFICE) | PHILTOWER | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5254 | TCFGAMANATTRENTOAGS | NA | TCFGAMANATTRENTOAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | TRENTO | Manat | Territory 8 | 8.0915 | 126.0869 | Brgy. Manat, Trento, Agusan Del Sur | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5375 | JROSALESAVEBUTUANAGNAS | NA | JROSALESAVEBUTUANAGNAS | REGION XIII (Caraga) | AGUSAN DEL NORTE | BUTUAN CITY (Capital) | Doongan | Territory 8 | 8.954 | 125.5305 | J. Rosales Street, Brgy. Doongan, Butuan City, Agusan Del Norte | BUTUAN (TECHNICAL OFFICE) |  | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5319 | TCFGAP4HUBANGSFRANCAGS | NA | TCFGAP4HUBANGSFRANCAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | SAN FRANCISCO | Hubang | Territory 8 | 8.5187 | 125.9643 | Brgy. Hubang Poblacion 4, San Francisco, Agusan Del Sur | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5356 | TCFGAMATINAOMAINITSDN | NA | TCFGAMATINAOMAINITSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | MAINIT | Matin-ao | Territory 8 | 9.5486 | 125.4806 | Brgy. Matinao, Mainit, Surigao Del Norte | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5317 | TCFGAP1TAMBISBAROBOSDS | NA | TCFGAP1TAMBISBAROBOSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | BAROBO | Tambis | Territory 8 | 8.537 | 1260521 | Brgy. Tambis, Poblacion 1, Barobo, Surigao Del Sur | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5331 | TCFGAMAGPAYANGMAINITSDN | NA | TCFGAMAGPAYANGMAINITSDN | REGION XIII (Caraga) | SURIGAO DEL NORTE | MAINIT | Magpayang | Territory 8 | 9.5332 | 125.5622 | Brgy. Magpayang, Mainit, Surigao Del Norte | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5318 | TCFGASUMOTAGOLOSDS | NA | TCFGASUMOTAGOLOSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | TAGO | Sumo-sumo | Territory 8 | 8.9774 | 126.2392 | Brgy. Sumo-Sumo, Tago, Surigao Del Sur | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5320 | TCFGAP4AURORASJOSEFAGS | NA | TCFGAP4AURORASJOSEFAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | SANTA JOSEFA | Aurora | Territory 8 | 8.011 | 126.0177 | Brgy. Aurora, Poblacion 4, Santa Josefa, Agusan Del Sur | BUTUAN (TECHNICAL OFFICE) | FTAP | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3941 | B1MALAYBBUK |  | B1MALAYBBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF MALAYBALAY (Capital) | Sumpong | Territory 8 | 8.1632 | 125.1199 | Brgy. Sumpong, Malaybalay City, Bukidnon | CDO NDC | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4668 | FORTICHMALAYBBUKAS |  | FORTICHMALAYBBUKAS | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH | Tankulan (Pob.) | Territory 8 | 125.1268 | 8.1558 | Sayre Highway, Malaybalay City, Bukidnon | CDO NDC | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4669 | BRGY8MALAYBBUKAS |  | BRGY8MALAYBBUKAS | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF MALAYBALAY (Capital) | Barangay 8 (Pob.) | Territory 8 | 8.1538 | 125.129 | Sayre Highway, Malaybalay City, Bukidnon | CDO NDC |  | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4735 | TCAICMOHONTAGOLOMOR |  | TCAICMOHONTAGOLOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TAGOLOAN | Mohon | Territory 8 | 8.5401 | 124.7813 | Brgy. Mohon, Tagoloan, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4722 | TCAICSANLUISGINGOOMOR |  | TCAICSANLUISGINGOOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY | San Luis | Territory 8 | 8.882 | 125.0373 | Brgy. San Luis, Gingoog City, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4746 | TCAICSOLANAJASAANMOR |  | TCAICSOLANAJASAANMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | JASAAN | Solana | Territory 8 | 8.6254 | 124.7671 | Brgy. Solana, Jasaan, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4805 | TCEDCCAMPCROSLIBONABUK | TCEDCCAMPCROSLIBONABUK |  | REGION X (NORTHERN MINDANAO) | BUKIDNON | LIBONA | Crossing | Territory 8 | 8.3252 | 124.7998 | Camp Philips, Crossing Libona, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4790 | TCAICDANSOLIHONCDOMOR | TCAICDANSOLIHONCDOMOR |  | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Dansolihon | Territory 8 | 8.3069 | 124.5782 | Brgy. Dansolihon, City Of Cagayan De Oro (Capital), Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4792 | TCEDCTRINBUGOCDOMOR | TCEDCTRINBUGOCDOMOR |  | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Bugo | Territory 8 | 8.5082 | 124.7693 | Inside Southfields School, Villa Trinitas Puerto, Cagayan de Oro City, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10004188 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5098 | TCEDCUPPERCANITOCDOMOR | TCEDCUPPERCANITOCDOMOR |  | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Canito-an | Territory 8 | 8.4447 | 124.6206 | Brgy. Canito-an CAGAYAN DE ORO CITY (CAPITAL) MISAMIS ORIENTAL | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3254 | TCAICCANITOANCDOMOR | TCAICCANITOANCDOMOR |  | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Canito-an | Territory 8 | 8.4553 | 124.6019 | Calaanan, Brgy. Canitoan, Cagayan de Oro City, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4954 | TCAICMCASANDIGHILCDOMOR | TCAICMCASANDIGHILCDOMOR |  | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Macasandig | Territory 8 | 8.4593 | 124.6502 | Macasandig Hill, Cagayan de Oro, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5087 | TCISLOWERDAYAWVNUEVAMOR | TCISLOWERDAYAWVNUEVAMOR |  | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | VILLANUEVA | San Martin | Territory 8 | 8.5712 | 124.7805 | Brgy. San Martin, Villanueva, Misamis Oriental | CDO NDC | ISON | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4437 | TCISNARRATABLONCDOMOR | TCISNARRATABLONCDOMOR |  | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Tablon | Territory 8 | 8.4805 | 124.736 | Brgy. Tablon, Cagayan de Oro City, Misamis Oriental | CDO NDC | ISON | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4404 | TCAICTAGPANGICDOMOR | TCAICTAGPANGICDOMOR |  | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Tagpangi | Territory 8 | 8.3671 | 124.5622 | Brgy.Tagpangi02_CagayanDeOroCity(Capital)_MisamisOriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4953 | TCEDCBOLNSIRCAMANCDOMOR |  | TCEDCBOLNSIRCAMANCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Camaman-an | Territory 8 | 8.4694 | 124.6591 | Bolonsori Road, Brgy. Camaman-an, Cagayan de Oro | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4421 | TCPHTVILCARMENCDOMOR |  | TCPHTVILCARMENCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Carmen | Territory 8 | 8.4847 | 124.6304 | Brgy. Carmen, Cagayan de Oro City, Misamis Oriental | CDO NDC | PHILTOWER | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4939 | TCEDCHIWAYIPONANCDOMOR |  | TCEDCHIWAYIPONANCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Iponan | Territory 8 | 8.5041 | 124.5931 | Brgy. Iponan, Cagayan de Oro City, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4819 | TCEDCPAGATPATCDOMOR |  | TCEDCPAGATPATCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Pagatpat | Territory 8 | 8.4475 | 124.5811 | Brgy. Pagatpat, Cagayan de Oro City, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4935 | TCAICZ2BONBONCDOMOR |  | TCAICZ2BONBONCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Bonbon | Territory 8 | 8.5082 | 124.652 | Zone 2, Bonbon, Cagayan De Oro, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4825 | TCEDCIPONANBULAOCDOMOR |  | TCEDCIPONANBULAOCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Iponan | Territory 8 | 8.4816 | 124.5909 | Iponan Bulao, Cagayan De Oro City | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4940 | TCEDCZ2BULUACDOMOR |  | TCEDCZ2BULUACDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Bulua | Territory 8 | 8.5082 | 124.623 | CDO Upper Bulua, Zone 2 Bulua Cagayan de Oro City, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4417 | TCEDCZ7PATAGCDOMOR |  | TCEDCZ7PATAGCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Patag | Territory 8 | 8.4917 | 124.6193 | Brgy.Patag, Cagayan de Oro, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4147 | TCAICPOBLAGUINMOR |  | TCAICPOBLAGUINMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LAGUINDINGAN | Poblacion | Territory 8 | 8.573 | 124.4387 | Poblacion, Laguindingan, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3232 | TCISBACONGLAPASACDOMOR |  | TCISBACONGLAPASACDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Lapasan | Territory 8 | 8.4835 | 124.6649 | 261 Baconga S., (at the back of Brgy. Hall Lapasan) Cagayan De Oro , Misamis Oriental | CDO NDC | ISON | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4803 | TCAICP3AGUSACDOMOR |  | TCAICP3AGUSACDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Gusa | Territory 8 | 8.468 | 124.687 | Purok 3A, Brgy. Gusa, City Of Cagayan De Oro (Capital), Misamis Oriental" | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4791 | TCAICZ7PUERTOMFORTBUK |  | TCAICZ7PUERTOMFORTBUK | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Puerto | Territory 8 | 8.4491 | 124.7961 | Zone 7, Brgy. Upper Puerto, Cagayan De Oro City, Misamis Oriental | CDO NDC | UNITY | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2251 | TCEDCINDAHAGCDOMOR |  | TCEDCINDAHAGCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Indahag | Territory 8 | 8.4467 | 124.6626 | Tipolohon St., Barangay Camaman-an,Cagayan De Oro City, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4411 | TCAGUPPALANLUMBIACDOMOR |  | TCAGUPPALANLUMBIACDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Lumbia | Territory 8 | 8.4125 | 124.605 | Westgate Highlands, Brgy. Lumbia, Cagayan de Oro, Misamis Oriental | CDO NDC | ALLIANCE | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4413 | TCAGCROSINGLUMBIACDOMOR |  | TCAGCROSINGLUMBIACDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Lumbia | Territory 8 | 8.4015 | 124.612 | Brgy. Lumbia, Cagayan de Oro, Misamis Oriental | CDO NDC | ALLIANCE | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4835 | TCEDCPNRBARRAOPOLMOR |  | TCEDCPNRBARRAOPOLMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | OPOL | Barra | Territory 8 | 8.5106 | 124.6054 | PNR Subdivision, Barra, OPOL, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4837 | TCEDCP6PUERTOCDOMOR |  | TCEDCP6PUERTOCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Puerto | Territory 8 | 8.5003 | 124.7548 | Pailagao Property, Sayre Highway, Purok 6 Brgy. Puerto CDO | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5065 | TCAICTAMBLER01GENSANSCOT |  | TCAICTAMBLER01GENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Tambler | Territory 7 | 125.1348 | 6.0248 | Brgy.Tambler, General Santos City, South Cotabato | GENSAN | UNITY | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | PEEJAY L. ORILLANEDA | 10010627 | 9176882695 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4478 | TCFGAMAUSWGNALABELSAR |  | TCFGAMAUSWGNALABELSAR | REGION XII (SOCCSKSARGEN) | SARANGANI | ALABEL (Capital) | Poblacion (Alabel) | Territory 7 | 124.9888 | 6.5878 | Brgy. Mauswagon, Alabel, Sarangani | GENSAN | FTAP | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | ROIEN CARL C. ROJO | 10010655 | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4816 | TCEDCCONVENINDAHGCDOMOR |  | TCEDCCONVENINDAHGCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Indahag | Territory 8 | 8.4199 | 124.6444 | BRGY. INDAHAG CAGARAN DE ORO CITY | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3862 | TCFGABRGY07MALAYBBUK |  | TCFGABRGY07MALAYBBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF MALAYBALAY (Capital) | Barangay 7 (Pob.) | Territory 8 | 8.151 | 125.1316 | Purok 2, Brgy. 7, Malaybalay City, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4824 | TCEDCAUREAPOBVALENBUK |  | TCEDCAUREAPOBVALENBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF VALENCIA | Poblacion | Territory 8 | 7.9067 | 125.0831 | Purok 4A, Poblacion, Valencia City, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1746 | KATIPUNANVNUEVAMOR |  | KATIPUNANVNUEVAMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | VILLANUEVA | Katipunan | Territory 8 | 8.5719 | 124.7578 | STEAG, BrgyKatipunan, Villanueva, MisamisOriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4435 | TCLDCGATAWAOLDS |  | TCLDCGATAWAOLDS | REGION X (NORTHERN MINDANAO) | BUKIDNON | KALILANGAN | Poblacion | Territory 8 | 7.6324 | 124.7266 | Brgy.Gata_Wao_LanaoDelSur | CDO NDC | LDIC | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4438 | TCISAGUSANCDOMOR |  | TCISAGUSANCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Gusa | Territory 8 | 8.4824 | 124.7577 | Brgy. Agusan, Cagayan de Oro, Misamis Oriental | CDO NDC | ISON | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4552 | TCEDCGUSAHIWAYCDOM |  | TCEDCGUSAHIWAYCDOM | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Gusa | Territory 8 | 8.4761 | 124.687 | Brgy. Gusa, CAGAYAN DE ORO CITY (CAPITAL), MISAMIS ORIENTAL | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3815 | TCAICWATERFBALINGMOR |  | TCAICWATERFBALINGMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | BALINGOAN | Lapinig (Pob.) | Territory 8 | 8.7371 | 124.7781 | Brgy Waterfall, Balingasag, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4933 | TCEDCBRGY27POBCDOMOR |  | TCEDCBRGY27POBCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Barangay 27 (Pob.) | Territory 8 | 8.4825 | 124.6491 | Rivera St. corner Corrales Avenue CDO City, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4934 | TCEDCACACIACARMENCDOMOR |  | TCEDCACACIACARMENCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Carmen | Territory 8 | 8.4706 | 124.6379 | Brgy Carmen, Cagayan de Oro City, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5146 | TCAICCASINGTAGOLOMOR |  | TCAICCASINGTAGOLOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | TAGOLOAN | Casinglot | Territory 8 | 8.5146 | 125.1063 | Brgy Casinglot Tagoloan Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5147 | TCEDCBRGY26POBGINGOOMOR |  | TCEDCBRGY26POBGINGOOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY | Barangay 26 (Pob.) | Territory 8 | 8.8088 | 125.1063 | Brgy 26 Gingoog Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5054 | TCPHTBARASTACUROSKUD |  | TCPHTBARASTACUROSKUD | REGION XII (SOCCSKSARGEN) | SULTAN KUDARAT | CITY OF TACURONG | Baras | Territory 7 | 124.6583 | 6.6161 | Brgy. Baras, Tacurong City, Sultan Kudarat | TACURONG | PHILTOWER | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | NOELJAN G. BAJAO | 10012969 | 9176884320 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4419 | TCISCARMEN05CDOMOR |  | TCISCARMEN05CDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Carmen | Territory 8 | 8.4746 | 124.6289 | Brgy. Carmen CAGAYAN DE ORO CITY (CAPITAL) MISAMIS ORIENTAL | CDO NDC | ISON | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4660 | TCAICHOTELCONCHITCDOMOR |  | TCAICHOTELCONCHITCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Barangay 33 (Pob.) | Territory 8 | 8.4783 | 124.652 | Barangay 33 (Pob.), Cagayan De Oro, Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5257 | TCAICLOWPALANLUMBIACDOMOR |  | TCAICLOWPALANLUMBIACDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Lumbia | Territory 8 | 8.4012 | 124.595 | Brgy Lumbia, CDO City | CDO NDC | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5103 | TCFGAMIBANTANGQUEZONBUK |  | TCFGAMIBANTANGQUEZONBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON | Mibantang | Territory 8 | 7.6646 | 125.1092 | Brgy. Mibantang QUEZON BUKIDNON | CDO NDC | FTAP | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5094 | TCFGANTULONGANKIBAWEBUK |  | TCFGANTULONGANKIBAWEBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | KIBAWE | Natulongan | Territory 8 | 7.5328 | 125.0233 | Brgy. Natulongan KIBAWE BUKIDNON | CDO NDC | FTAP | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5102 | TCFGAP3LIBORANBAUNGBUK |  | TCFGAP3LIBORANBAUNGBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | BAUNGON | Liboran | Territory 8 | 8.3526 | 124.6519 | Brgy. Liboran BAUNGON BUKIDNON | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5109 | TCFGAKILIOGLIBONABUK |  | TCFGAKILIOGLIBONABUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | LIBONA | Kiliog | Territory 8 | 8.3377 | 124.7025 | Brgy. Kiliog LIBONA BUKIDNON | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4457 | TCISLUNOTANGINGOOMOR |  | TCISLUNOTANGINGOOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY | Lunotan | Territory 8 | 8.7185 | 125.0277 | Brgy.Lunotan03_GingoogCity_MisamisOriental | CDO NDC | ISON | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5251 | TCFGAAPOMACOTEMALAYBBUK |  | TCFGAAPOMACOTEMALAYBBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF MALAYBALAY (Capital) | Apo Macote | Territory 8 | 7.9762 | 125.2084 | Brgy.ApoMacote_MalaybalayCity(Capital)_Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4468 | TCFGABUGCAONLANTAPBUK |  | TCFGABUGCAONLANTAPBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | LANTAPAN | Bugcaon | Territory 8 | 8.0426 | 125.113 | Zone 1, Bugcaon, Lantapan, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5314 | TCFGATAMBAGANMEDINAMOR |  | TCFGATAMBAGANMEDINAMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MEDINA | Tambagan | Territory 8 | 8.9075 | 125.0127 | Brgy. Tambagan , Medina, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5113 | TCFGAP4CABANGAMALAYBBUK |  | TCFGAP4CABANGAMALAYBBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF MALAYBALAY (Capital) | Cabangahan | Territory 8 | 8.0212 | 125.1402 | Purok 4, Cabangahan, City of Malaybalay, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5255 | TCFGAP1SIMAYAMALAYBBUK |  | TCFGAP1SIMAYAMALAYBBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF MALAYBALAY (Capital) | Simaya | Territory 8 | 8.0138 | 125.1574 | Brgy. Simaya MALAYBALAY CITY (CAPITAL) BUKIDNON | CDO NDC | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5354 | TCFGASANKANANMFORTBUK |  | TCFGASANKANANMFORTBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH | Sankanan | Territory 8 | 8.3154 | 124.8598 | Brgy. Sankanan, Manolo Fortich, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5316 | TCFGAMENZIDMILAGMFORTBUK |  | TCFGAMENZIDMILAGMFORTBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH | Damilag | Territory 8 | 8.3851 | 124.8079 | Purok 18, MARB Homes, Menzi, Brgy. Damilag, Manolo Fortich, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5387 | TCAICDELAPAQUEZONBUK |  | TCAICDELAPAQUEZONBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | QUEZON | Delapa | Territory 8 | 7.6692 | 125.129 | Purok 1, Brgy. Delapa, Quezon, Bukidnon | CDO NDC | UNITY | AREA 3 | BUKIDNON | QUEZON | RODERICK LASTIMOSA | RAYMAR B. MANALO | 10012896 | 9176884289 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5384 | TCEDCBRGY5POBTLAKAGBUK |  | TCEDCBRGY5POBTLAKAGBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | TALAKAG | Barangay 5 (Pob.) | Territory 8 | 8.2291 | 124.6 | Brgy. 5, Poblacion, Talakag, Bukidnon | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | MARK DAVID C. RABOY | 10010553 | 9176882613 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5389 | TCEDCPOBLADMULOGBUK |  | TCEDCPOBLADMULOGBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | DAMULOG | Poblacion (New Damulog) | Territory 8 | 7.4823 | 124.942 | Brgy Poblacion Damulog, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | MARAMAG | RODERICK LASTIMOSA | ROSSI AGA CLAUDE PUERTO | 10020662 | 9176884969 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5385 | TCEDCSNMIGUEL2MFORTBUK |  | TCEDCSNMIGUEL2MFORTBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH | San Miguel | Territory 8 | 8.3858 | 124.8378 | Brgy. San Miguel, Manolo Fortich, Bukidnon | CDO NDC | EDOTCO | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3849 | TCEDCCANITOAN3CDOMOR |  | TCEDCCANITOAN3CDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (Capital) | Canito-an | Territory 8 | 8.4791 | 124.6046 | Brgy. Canitoan, Cagayan De Oro City, Misamis Oriental | CDO NDC | EDOTCO | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3981 | TCFGATANKULANPOBMFORTBUKR |  | TCFGATANKULANPOBMFORTBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH | Tankulan (Pob.) | Territory 8 | 8.3641 | 124.8679 | ST. JOSEPH VILLAGE, BRGY. TANKULAN, MANOLO FORTICH | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5315 | TCFGAZ5MANTBUGAOMFORTBUK |  | TCFGAZ5MANTBUGAOMFORTBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH | Mantibugao | Territory 8 | 8.4402 | 124.8181 | Brgy. Mantibugao MANOLO FORTICH BUKIDNON | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5111 | TCFGAP1MIGLAMINMALAYBBUK |  | TCFGAP1MIGLAMINMALAYBBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF MALAYBALAY (Capital) | Miglamin | Territory 8 | 8.0388 | 125.2442 | Brgy. Miglamin MALAYBALAY CITY (CAPITAL) BUKIDNON | CDO NDC | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5407 | TCFGAALAE2MFORTBUK |  | TCFGAALAE2MFORTBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH | Alae | Territory 8 | 8.434 | 124.8052 | Brgy. Alae, Manolo Fortich, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5325 | TCFGAP1KISOLNSUMLAOBUK |  | TCFGAP1KISOLNSUMLAOBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | SUMILAO | Kisolon | Territory 8 | 8.3366 | 124.975 | Purok 1, Kisolon, Sumilao, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5253 | TCFGAP4KIBENTONIMPASBUK |  | TCFGAP4KIBENTONIMPASBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUG-ONG | Kibenton | Territory 8 | 8.1998 | 124.9723 | Brgy. Kibenton IMPASUG-ONG BUKIDNON | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5411 | TCFGABAYBAYALUBIJMOR |  | TCFGABAYBAYALUBIJMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | ALUBIJID | Baybay | Territory 8 | 8.5873 | 124.4766 | Purok 4 Baybay, Brgy. Alubijid, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5342 | TCFGACMKPOBIMPASBUK |  | TCFGACMKPOBIMPASBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | IMPASUG-ONG | Poblacion | Territory 8 | 8.2843 | 124.9903 | Sitio CMK, Barangay Poblacion, Impasug-ong, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5392 | TCAICODIONGANGINGOOMOR |  | TCAICODIONGANGINGOOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | GINGOOG CITY | Odiongan | Territory 8 | 8.8499 | 125.1667 | Barangay Odiongan, Gingoog Misamis Oriental | CDO NDC | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5388 | TCAICSANCARLOSVALENBUK |  | TCAICSANCARLOSVALENBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | CITY OF VALENCIA | San Carlos | Territory 8 | 7.9627 | 125.0766 | Brgy. San Carlos, Valencia City, Bukidnon | CDO NDC | UNITY | AREA 3 | BUKIDNON | VALENCIA | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5344 | TCFGAP2DAHILAMFORTBUK |  | TCFGAP2DAHILAMFORTBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH | Dahilayan | Territory 8 | 8.2239 | 124.8498 | Purok 2, Barangay Dahilayan, Manolo Fortich, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5343 | TCFGASTONINOMFORTBUK |  | TCFGASTONINOMFORTBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | MANOLO FORTICH | Santo Niño | Territory 8 | 8.4326 | 124.8646 | Zone 2, Brgy. Sto. Nino, Manolo Fortich, Bukidnon | CDO NDC | FTAP | AREA 3 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5346 | TCFGADULONGLBERTDMOR |  | TCFGADULONGLBERTDMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | LIBERTAD | Dulong | Territory 8 | 8.5669 | 124.3609 | Purok 1, Dulong, Brgy. Libertad, Misamis Oriental | CDO NDC | FTAP | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3846 | TEDCJPLAURELPANABODDN | NA | TEDCJPLAURELPANABODDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | CITY OF PANABO | Cagangohan | Territory 7 | 7.2822 | 125.6747 | Cagangohan, Panabo City, Davao del Norte | DVO-TAGUM | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4774 | TCCREITALOMRIVDAVAODDS |  | NA | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Talomo River | Territory 7 | 7.1844 | 125.479 | Barangay Talomo River, Davao City | DVO-TAGUM | CREI | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4755 | TCEDCDACUDCALINDAVAODDS | NA | TCEDCDACUDCALINDAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Dacudao | Territory 7 | 7.2103 | 125.479 | Brgy. Dacudao, Calinan District, Davao City, Davao del Sur | DVO-TAGUM | EDOTCO | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2470 | TCAICJMCSASADAVAODDS | na |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Buhangin (Pob.) | Territory 7 | 7.136 | 125.645 | Back of Chowking, Philippine Japan Friendship Highway Sasa Buhangin District, Buhangin Airport, Davao City, 8000 Davao del Sur | DVO-MATINA | UNITY | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4645 | TCAICP7COMMUNALDAVAODDS | na |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Buhangin (Pob.) | Territory 7 | 7.1413 | 125.6404 | PUROK UPPER STA. CRUZ, BRGY ACACIA, Buhangin, Davao City | DVO-MATINA | UNITY | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4580 | TCEDCLADISLAWDAVAODDS | na |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Buhangin (Pob.) | Territory 7 | 7.0982 | 125.6143 | Rodriguez Prop. Buhangin Rd. cor. Landislawa Rd. Davao City , City of Davao, Davao Del Sur | DVO-MATINA | EDOTCO | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4684 | TCEDCBATVILCATPEQDVODDS | NONE |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Catalunan Pequeño | Territory 7 | 7.0676 | 125.5246 | Batalla Village, Catalunan Pequeno, Davao City | DVO-MATINA | EDOTCO | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4639 | TCAICTABALIZADADAVAODDS | NA |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Toril (Pob.) | Territory 7 | 6.997 | 125.4938 | Brgy. Lizada, Toril District, Davao City, Davao del Sur | DVO-MATINA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4566 | TCAGTALOMOPOBDAVAODDS | none |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Talomo (Pob.) | Territory 7 | 7.0499 | 125.5492 | Brgy. Talomo, Davao City | DVO-MATINA | ALLIANCE | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4565 | TCISTALOM3POBDAVAODDS | none |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Talomo (Pob.) | Territory 7 | 7.0552 | 125.5459 | BARANGAY TALOMO, DAVAO CITY | DVO-MATINA | ISON | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4841 | TCEDCBANGKTALOMODAVAODDS | none |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Talomo (Pob.) | Territory 7 | 7.0565 | 125.5622 | Bangkal, San Miguel, Brgy. Talomo (Pob.), Davao City, Davao del Sur | DVO-MATINA | EDOTCO | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2456 | TCAICCROSSTORDAVAODDS | none |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Toril (Pob.) | Territory 7 | 7.021 | 125.497 | Crossing Bayabas, Toril, Davao City, Davao Del Sur | DVO-MATINA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4242 | TCAICLUBOGANDAVAODDS | none |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Lubogan | Territory 7 | 7.0378 | 125.493 | Brgy. Lubogan, Toril, Davao City, Davaodel Sur | DVO-MATINA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4688 | TCEDSANAGUSMARIADVOC | NA | TCEDSANAGUSMARIADVOC | REGION XI (DAVAO REGION) | DAVAO OCCIDENTAL | SANTA MARIA | San Agustin | Territory 7 | 6.5708 | 125.4803 | Brgy. San Agustin, Sta. Maria, Davao Occidentalm | DIGOS | EDOTCO | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4728 | TCFGANEWVISAMTANAODDS | NA | TCFGANEWVISAMTANAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | MATANAO | New Visayas | Territory 7 | 6.7328 | 125.2217 | Brgy. New Visayas, Matanao, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5221 | TCAICPIAPEPADADADDS | NA | TCAICPIAPEPADADADDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | PADADA | Piape | Territory 7 | 6.6487 | 125.3812 | Brgy. Piape, Padada, Davao del Sur | DIGOS | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5015 | TCEDCBRGY15BDAVAODDS |  |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Barangay 15-B (Pob.) | Territory 7 | 7.0806 | 125.6197 | Soliman St, Brgy 15, Davao City, Davao Del Sur | DVO-MATINA | EDOTCO | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4587 | TCISORCHIDSTSASADAVAODDS |  |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Panacan | Territory 7 | 7.1389 | 125.6559 | Dona Caridad Village, 230, Km. 12 Orchids Street, Davao City, 8000 Davao del Sur | DVO-PANABO | ISON | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | JAN RYVEN A. LUMABAO | 10010845 | 9176882003 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4726 | TCAICBUNAWANPOBDVODDS |  | TCAICBUNAWANPOBDVODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Bunawan (Pob.) | Territory 7 | 7.247 | 125.648 | BRGY. BUNAWAN POBLACION, DAVAO CITY, DAVAO DEL SUR | DVO-PANABO | UNITY | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4726 | TCAICBUNAWANPOBDVODDS | NA | TCAICBUNAWANPOBDVODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Bunawan (Pob.) | Territory 7 | 7.2469 | 125.6479 | BRGY. BUMAWAN POBLACION, DAVAO CITY, DAVAO DEL SUR | DVO-PANABO | UNITY | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5049 | TCEDCMAMBAGASAMALDDN | NA | TCEDCMAMBAGASAMALDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL | Mambago-A | Territory 7 | 7.0976 | 125.7061 | BRGY. MAMBAGO-A, SAMAL DISTRICT, IGACOS, DAVAO DEL NORTE | DVO-PANABO | EDOTCO | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4898 | TCFGACOGONSAMALDDN | NA | TCFGACOGONSAMALDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL | Cogon | Territory 7 | 7.1533 | 125.7149 | Brgy. Cogon-Babak, IGACOS, Davap Del Norte | DVO-PANABO | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5052 | TCPHTMAMBAGOBSAMALDDN | NA | TCPHTMAMBAGOBSAMALDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL | Mambago-B | Territory 7 | 7.1114 | 125.6935 | Brgy. Mambago-B, IGACOS, Davao del Norte | DVO-PANABO | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5051 | TCPHTSANISIBABKSAMALDDN | na | TCPHTSANISIBABKSAMALDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL | San Isidro (Babak) | Territory 7 | 7.1894 | 125.7132 | P-08 San Isidro-Babak, IGACOS, Davao del Norte | DVO-PANABO | PHILTOWER | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2442 | TCAICCORTESS36DDAVAODDS | na | TCAICCORTESS36DDAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY | Barangay 36-D (Pob.) | Territory 7 | 7.0644 | 125.6129 | Cortes Printing Press Building, Rizal St., Brgy. 36-D, Davao City, Davao del Sur. | DVO-ABREEZA | UNITY | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | CESAR C. AMIGABLE | 10008515 | 9176885513 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4874 | TCFGASARMIENTOPARANGMGDN |  | TCFGASARMIENTOPARANGMGDN | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | MAGUINDANAO | PARANG | Landasan (Sarmiento) | Territory 7 | 124.2479 | 7.3418 | De Jesus Zone, Brgy. Sarmiento, Parang Maguindanao | COTABATO | FTAP | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | MICHEL P. MEDALLA | 10004246 | 9176884689 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5135 | TCFGALOWRKIWANMIDSAYNCOT |  | TCFGALOWRKIWANMIDSAYNCOT | REGION XII (SOCCSKSARGEN) | COTABATO (NORTH COTABATO) | MIDSAYAP | Kiwanan | Territory 7 | 124.5543 | 7.2044 | Purok Daisy, Lower Kiwanan, Midsayap, Cotabato | MIDSAYAP | FTAP | AREA 13 | COTABATO 2 | MIDSAYAP | ARNOLD L. SAGUSAY | ANTHONY JOHN E. SAGRADO | 10015074 | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4678 | TCAICROSARYHT7COTABMGDN |  | TCAICROSARYHT7COTABMGDN | REGION XII (SOCCSKSARGEN) | COTABATO CITY | COTABATO CITY | Rosary Heights VII | Territory 7 | 124.2396 | 7.2009 | CitiMall, Brgy Rosary Heights VII, Cotabato City, Maguindanao | COTABATO | UNITY | AREA 13 | COTABATO 2 | COTABATO | ARNOLD L. SAGUSAY | ERWIN JOHN R. DIZON | 10012481 | 9176880855 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3596 | TCFGAMARMANKLAMTAGUMDDN | NA | TCFGAMARMANKLAMTAGUMDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY (CAPITAL) |  | Territory 7 | 7.4529 | 125.7821 | R' MENDEES PENSION HOUSE CAPITOL RD., PUROK MARGARITA BRGY MANKILAM TAGUM CITY | TAGUM | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3558 | TCAICAMAZBACA19BDAVAODDS | NA |  | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.096 | 125.6012 | Amazon St., Bacaca Road, Poblacion District, Barangay 19-B, Davao City | JUNA | UNITY | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4638 | TCFGADATOCZ1DIGOSDDS | NA | TCFGADATOCZ1DIGOSDDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY (CAPITAL) |  | Territory 7 | 6.7588 | 125.3609 | Brgy. Zone 1 (Pob.). Digos City, Davao del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4642 | LAPURZALEXTZ3DIGOSDDSAS | NA | LAPURZALEXTZ3DIGOSDDSAS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY (CAPITAL) |  | Territory 7 | 6.7453 | 125.3552 | Brgy. Zone 1, Digos City, Davao Del Sur | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4643 | MOLAVZONE3DIGOSDDSAS | NA | MOLAVZONE3DIGOSDDSAS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY (CAPITAL) |  | Territory 7 | 6.7497 | 125.3501 | Brgy. Zone 1, Digos City, Davao Del Sur | DIGOS | GT | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4689 | TCEDCANISLIGANMACODDO | NA | TCEDCANISLIGANMACODDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | MABINI (DOÑA ALICIA) |  | Territory 7 | 7.3401 | 125.8584 | Brgy. Cadunan ,Mabini (Doña Alicia) ,Davao De Oro | TAGUM | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4777 | TCAGP3SOUTHERNPANABODDN | NA | TCAGP3SOUTHERNPANABODDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3334 | 125.65 | Purok 3, Southern Davao, City of Panabo, Davao Del Norte | JUNA | ATC | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4781 | TCAICFUERZATAGUMDDM | NA | TCAICFUERZATAGUMDDM | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY (CAPITAL) |  | Territory 7 | 7.4973 | 125.819 | Nueva Fuerza, Tagum City, Davao Del Norte | TAGUM | UNITY | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4766 | TCEDCLIBERTADSTOMASDDN | NA | TCEDCLIBERTADSTOMASDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | SANTO TOMAS |  | Territory 7 | 7.4796 | 125.6418 | Brgy La Libertad, Santo Tomas, Davao del Norte | TAGUM | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3802 | TCEDCDAHICANMATIDVOR | NA | TCEDCDAHICANMATIDVOR | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | MATI CITY (CAPITAL) |  | Territory 7 | 6.94 | 126.2629 | Brgy.Dahican, Mati, Davao Oriental | MATI | EDOTCO | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4754 | TCEDCALEJANDRADAVAODDS | NA | TCEDCALEJANDRADAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.2653 | 125.6636 | BRGY.ALEJANDRA NAVARRO (LASANG), DAVAO CITY, DAVAO DEL SUR | JUNA | EDOTCO | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4775 | TCEDCMAPAWAMARAGUDDO | NA | TCEDCMAPAWAMARAGUDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | MARAGUSAN (SAN MARIANO) |  | Territory 7 | 7.2862 | 126.148 | BARANGAY MAPAWA, MARUGUSAN, COMPOSTELLA VALLEY | TAGUM | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4779 | TCFGAP8SANMIGTAGUMDDN | NA | TCFGAP8SANMIGTAGUMDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY (CAPITAL) |  | Territory 7 | 7.4422 | 125.765 | PUROK 8, BRGY. SAN MIGUEL, TAGUM, DAVAO DEL NORTE | TAGUM | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4773 | TCCRE1CMAGAYCOMPOSDDO | NA | TCCRE1CMAGAYCOMPOSDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | COMPOSTELA |  | Territory 7 | 7.7195 | 126.1059 | Brgy. Mangayon, Compostela, Davao De Oro | TAGUM | CREI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3659 | TCAICSFRANSTONINODAVAODDS | NA | TCAICSFRANSTONINODAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0787 | 125.5079 | Purok 16, Don Ramon Cuizon Village, Phase 2, Brgy Sto Niño, Tugbok District, Davao City, Davao Del Sur | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4763 | TCEDCMAINITNABUNDDO | NA | TCEDCMAINITNABUNDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | NABUNTURAN (CAPITAL) |  | Territory 7 | 7.5086 | 126.0223 | Purok 5 Reserba Brgy. Mainit Nabunturan Compostela Valley , Nabunturan (Capital), Davao de Oro | TAGUM | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4231 | TCPHTASTORGASTCRUZDDS | NA | TCPHTASTORGASTCRUZDDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.9043 | 125.4587 | Brgy. Astorga, Santa Cruz, Davao del Sur | DIGOS | PTCI | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4776 | TCAICPILTELZ3STCRUZDDS | NA | TCAICPILTELZ3STCRUZDDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.8339 | 125.418 | Piltel Sta. Cruz, Padre Burgos St., Zone Iii (Pob.), Sta. Cruz, Davao Del Sur | DIGOS | UNITY | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4757 | TCAICDARONGSTCRUZDDS | NA | TCAICDARONGSTCRUZDDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | SANTA CRUZ |  | Territory 7 | 6.9271 | 125.4669 | Brgy. Darong, Santa Cruz, Davao Del Sur | DIGOS | UNITY | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4559 | TCFGAPADILLOZ2DIGOSDDS | NA | TCFGAPADILLOZ2DIGOSDDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DIGOS CITY (CAPITAL) |  | Territory 7 | 6.7521 | 125.3568 | Brgy. Zone2, Digos City, Davao Del Sur | DIGOS | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4648 | TCAICSVIL2CATGRANDDAVAODDS | NA | TCAICSVIL2CATGRANDDAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0796 | 125.5443 | South Villa Heights II, Catalunan Grande, Davao City, Davao del Sur | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4786 | TCEDCMANKILATAGUMDDN | NA | TCEDCMANKILATAGUMDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY (CAPITAL) |  | Territory 7 | 7.4535 | 125.771 | Brgy. Mankilam, Tagum City, Davao del Norte | TAGUM FOC | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4770 | TCEDCCAPUNGKPALONDDN | NA | TCEDCCAPUNGKPALONDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG |  | Territory 7 | 7.6288 | 125.7013 | Brgy. Capungagan, Kapalong, Davao Del Norte | TAGUM FOC | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4853 | TCAICMANAMBULNDAVAODDS | NA | TCAICMANAMBULNDAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0969 | 125.4573 | Manambulan, Davao City, Davao Del Sur | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4583 | TCISMAGSAY30CDAVAODDS | NA | TCISMAGSAY30CDAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0725 | 125.6201 | Barangay 30-C (Pob.), Davao City, Davao Del Sur | JUNA | ISON | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4727 | TCEDCPAGASAKPALONDDN | NA | TCEDCPAGASAKPALONDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | KAPALONG |  | Territory 7 | 7.5772 | 125.6915 | Brgy. Pag-Asa ,Kapalong ,Davao Del Norte | TAGUM FOC | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4965 | TCEDCURBAANDILIMAWABDDO | NA | TCEDCURBAANDILIMAWABDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | MAWAB |  | Territory 7 | 7.4669 | 125.9638 | Urbano Compound, Brgy. Andili (Poblacion), Mawab, Davao de Oro | TAGUM FOC | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3968 | TCEDCMANINGCOZAMISMOCC | NA | TCEDCMANINGCOZAMISMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | OZAMIZ CITY |  | Territory 8 | 8.1656 | 123.8583 | Lot 2-F, Bgy Maningcol, Ozamiz City, Misamis Occidental | OZAMIS | EDOTCO | AREA 4 | ILIGAN | OZAMIS | ARNEL B. BITOON | NELVI JOHN M. ABAMONGA | 10008512 | 9176885394 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4324 | TCAICSEMUTAKBARBAS | NA | TCAICSEMUTAKBARBAS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | AKBAR |  | Territory 8 | 6.658 | 122.195 | Brgy. Semut, Akbar, Basilan | TETUAN FOC | UNITY | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3957 | TCFGAKLAYBATOLAMITNBASCOW | NA | TCFGAKLAYBATOLAMITNBASCOW | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LAMITAN CITY |  | Territory 8 | 6.6636 | 122.1535 | Brgy. Kulay Bato, Lamitan City, Basilan | TETUAN FOC | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4299 | TCLDCTOWNSITEMLUSOBAS | NA | TCLDCTOWNSITEMLUSOBAS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | MALUSO |  | Territory 8 | 6.5427 | 121.875 | BrgyPort Holland Zone IV (Lower)_MALUSO_BASILAN | TETUAN FOC | LDIC | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4802 | TCEDCLICOMOZAMBOAZDS | NA | TCEDCLICOMOZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 7.4585 | 122.3299 | Brgy. Licomo, Zamboanga City, Zamboanga del Sur | TETUAN FOC | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4822 | TCEDCZ2SNROQUEZAMBOAZDS | NA | TCEDCZ2SNROQUEZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9373 | 122.044 | Zone 2, Barangay San Roque, Zamboanga City, Zamboanga del Sur | GTZAMBOFOCID | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4827 | TCAICTALISAYANZAMBOAZDS | NA | TCAICTALISAYANZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9758 | 121.9364 | Brgy. Talisayan, Zamboanga City, Zamoanga del Sur | TETUAN FOC | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2573 | TCLDCBUSBUSJOLOSULU | NA | TCLDCBUSBUSJOLOSULU | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | JOLO (CAPITAL) |  | Territory 8 | 6.0561 | 121.0026 | Brgy. Walled City(Pob), Jolo (Capital), Sulu | TETUAN FOC | LDIC | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4945 | TCEDCAUROTUMAGZAMBOAZDS | NA | TCEDCAUROTUMAGZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9286 | 122.0851 | Lim Prop Aurora St. Tumaga Zamboanga City , City of Zamboanga, Zamboanga Del Sur | TETUAN FOC | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4942 | TCEDCPASONANZAMBOAZDS | NA | TCEDCPASONANZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9469 | 122.0742 | Brgy. Pasonanca, Zamboanga City, Zamboanga del Sur | TETUAN FOC | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3190 | TCFGASNTABARBISBELABAS | NA | TCFGASNTABARBISBELABAS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.7144 | 121.9676 | Brgy. Santa Barbara, Isabela City, Basilan | TETUAN FOC | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4291 | TCLDCANULINGPATKULSULU | NA | TCLDCANULINGPATKULSULU | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | PATIKUL |  | Territory 8 | 6.0395 | 121.0043 | Brgy. Anuling, Patikul, Sulu | TETUAN FOC | LDIC | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4288 | TCLDCKAJATINDANASULU | NA | TCLDCKAJATINDANASULU | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | INDANAN |  | Territory 8 | 6.0437 | 120.9883 | Brgy. Kajatian, Indanan, Sulu | TETUAN FOC | LDIC | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5086 | TCAICSTAMARIAZAMBOAZDS | NA | TCAICSTAMARIAZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9306 | 122.0662 | Gov. Ramos Ave., Brgy. Sta.Maria, Zamboanga City, Zamboanga Del Sur | TETUAN FOC | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4074 | TCFGAP6BINUANGISBELABAS | NA | TCFGAP6BINUANGISBELABAS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.7051 | 121.9838 | Brgy. Sunrise Village (Pob.), Isabela City, Basilan | TETUAN FOC | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4279 | TCLDCPAHUTBONGAOTAWI | NA | TCLDCPAHUTBONGAOTAWI | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.0274 | 119.7409 | Brgy. Pahut, Bongao (Capital), Tawi-Tawi | TETUAN FOC | LDIC | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4937 | TCEDCVTERTETUANZAMBOAZDS | NA | TCEDCVTERTETUANZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.924 | 122.0805 | Veterans Avenue Extension, Tetuan, Zamboanga City | TETUAN FOC | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1961 | TCFGASEASIDEISBELABAS | NA | TCFGASEASIDEISBELABAS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.706 | 121.976 | Brgy. Eastside, Isabela City, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5091 | TCCRECANELARZAMBOAZDS | NA | TCCRECANELARZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9174 | 122.0694 | BRGY. CANELAR,ZAMBOANGA CITY,ZAMBOANGA DEL SUR | GTZAMBOFOCID | FTAP | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4836 | TCEDCMAKDUMSIBUTUTAWI | NA | TCEDCMAKDUMSIBUTUTAWI | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | SIBUTU |  | Territory 8 | 4.7241 | 119.4976 | Brgy. Tandubanak, Sibutu Island, Tawi-Tawi | GTZAMBOFOCID | EDOTCO | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4943 | TCEDCUPPERCALARZAMBOAZDS | NA | TCEDCUPPERCALARZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9265 | 122.0246 | Upper Calarian, Zamboanga City | GTZAMBOFOCID | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5095 | TCAICMALAGUTAYZAMBOAZDS | NA | TCAICMALAGUTAYZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9487 | 122.0272 | Brgy. Malagutay ZAMBOANGA CITY ZAMBOANGA DEL SUR | GTZAMBOFOCID | UNITY | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5145 | TCFGAKLAYBATOLAMITNBAS | NA | TCFGAKLAYBATOLAMITNBAS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | LAMITAN CITY |  | Territory 8 | 6.6636 | 122.1535 | Brgy. Kulay Bato, Lamitan City, Basilan | GTZAMBOFOCID | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4278 | TCLDCPAHUT02BONGAOTAWI | NA | TCLDCPAHUTBONGAOTAWI | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.0202 | 119.7385 | Brgy. Pahut, Bongao (Capital), Tawi-Tawi | GTZAMBOFOCID | LDIC | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2072 | DONPABLOZAMBOAZDSAS | NA | DONPABLOZAMBOAZDSAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | Zamboanga City |  | Territory 8 | 6.9036 | 122.0754 | DBP, DON PABLO LORENZO ST., ZONE IV, ZAMBOANGA CITY, Zamboanga Del Sur | TETUAN FOC | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4285 | TCLDCLUUKSIASISULU | NA | TCLDCLUUKSIASISULU | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | SULU | SIASI |  | Territory 8 | 5.5527 | 120.9147 | Brgy. Luuk Laminusa, Siasi, Sulu | TETUAN FOC | LDIC | AREA 7 | BASULTA | SULU | DARIUS LORETO S. BENDIJO | JEFFREY C. SIEGUE | 10010058 | 9176882181 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4098 | TCEDCTETUANZAMBOAZDS | NA | TCEDCTETUANZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9168 | 122.0894 | Brgy. Tetuan, Zamboanga City, Zamboanga del Sur | TETUAN FOC | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4941 | TCEDCMAHALOMAPUNTAWI | NA | TCEDCMAHALOMAPUNTAWI | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | MAPUN |  | Territory 8 | 6.9855 | 118.4985 | Brgy. Mahalo, Mapun, Cagayan de Tawi-tawi | TETUAN FOC | EDOTCO | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5248 | TCEDCRIZALPOBLUPONDVOR | NA | TCEDCRIZALPOBLUPONDVOR | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | LUPON |  | Territory 7 | 6.8968 | 126.0142 | Rizal St., Poblacion, Lupon, Davao Oriental | TAGUM FOC | EDOTCO | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4271 | BUSTERMINALZAMBOAZDSAS | NA | BUSTERMINALZAMBOAZDSAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9501 | 122.1085 | Divisoria, Zamboanga City | TETUAN FOC | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5107 | TCEDCDONRAMONAISBELABAS | NA | TCEDCDONRAMONAISBELABAS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | ISABELA CITY |  | Territory 8 | 6.6999 | 121.9703 | Brgy. Dona Ramona, City of Isabela, Basilan | TETUAN FOC | EDOTCO | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5363 | TCEDCSNJOSEGUSZAMBOAZDS | NA | TCEDCSNJOSEGUSZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9171 | 122.0458 | J Jireh School, Suterville, San Jose Guso | TETUAN FOC | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2670 | ZSCMSTZAMBOAZDSAS | NA | ZSCMSTZAMBOAZDSAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.8991 | 122.084 | Rio Hondo, Zamboanga City | TETUAN FOC | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4250 | TCPHTSTAFILOMILIGANLDN | NA | TCPHTSTAFILOMILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.2687 | 124.2624 | Santa Filomena, iligan City, Lanao del Norte | ILIGAN | PTCI | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5313 | TCPHTDIGKILAANILIGANLDN | NA | TCPHTDIGKILAANILIGANLDN | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY |  | Territory 8 | 8.249 | 124.3188 | Purok 1- Narra, Brgy. Digkilaan, Iligan City, Lanao del Norte | ILIGAN | PTCI | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4354 | TCAICBANGONDLAUSLUMBACLDS | NA | TCAICBANGONDLAUSLUMBACLDS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | LUMBACA-UNAYAN |  | Territory 8 | 7.7477 | 124.209 | Barangay Bangon, Lumbaca Unayan, Lanao del Sur | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4538 | TCPHTSANITO2IPILZSIB | NA | TCPHTSANITO2IPILZSIB | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA SIBUGAY | IPIL (CAPITAL) |  | Territory 8 | 7.7937 | 122.6062 | BRGY. PANGI,IPIL,ZAMBOANGA SIBUGAY | IPIL | PTCI | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4815 | TCAICMANSBAJOLJAENAMOCC | NA | TCAICMANSBAJOLJAENAMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | LOPEZ JAENA |  | Territory 8 | 8.5358 | 123.7802 | National Highway, Brgy. Mansabay Bajo, Lopez Jaena, Misamis Occidental | CLAMBA | UNITY | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5259 | TCFGAPUNTODPLARIDMOCC | NA | TCFGAPUNTODPLARIDMOCC | REGION X (NORTHERN MINDANAO) | MISAMIS OCCIDENTAL | Plaridel |  | Territory 8 | 8.6099 | 123.6855 | Brgy.Puntod, Plaridel, Misamis Occidental | CLAMBA | FTAP | AREA 4 | ILIGAN | CALAMBA | ARNEL B. BITOON | ROVI D. COBAR | 6102 | 9176888002 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5345 | TCFGACABALANTMANTICMOR | NA | TCFGACABALANTMANTICMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MANTICAO |  | Territory 8 | 8.3686 | 124.3289 | Purok Bougainvilla, Brgy.Cabalantian, Manticao, Misamis Oriental | ILIGAN | FTAP | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5348 | TCAICTUODMANTICMOR | NA | TCAICTUODMANTICMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | MANTICAO |  | Territory 8 | 8.345 | 124.3535 | Purok 4 A, Barangay Tuod, Manticao Misamis Oriental | ILIGAN | UNITY | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4627 | TCAGLOT61UPRDMINTALDAVAODDS | NA | TCAGLOT61UPRDMINTALDAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0868 | 125.4877 | Brgy Mintal, Davao City | JUNA | ATC | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4962 | TCFGAP2AELIZALDEMACODDO | NA | TCFGAP2AELIZALDEMACODDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | MACO |  | Territory 7 | 7.3877 | 125.9809 | PUROK 2-A, BRGY. ELIZALDE, MACO, DAVAO DE ORO | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4897 | TCFGAMAGATOSACIONDDN | NA | TCFGAMAGATOSACIONDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | ASUNCION |  | Territory 7 | 7.5561 | 125.7268 | Brgy.Magatos01_Asuncion(Saug)_DavaoDelNorte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4481 | TCAGTAMBOBONGDAVAODDS | NA | TCAGTAMBOBONGDAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1886 | 125.342 | Brgy.Tambobong_DavaoCity_DavaoDelSur | JUNA | ATC | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN2399 | TCAICJADEMARFORI8ADAVAODDS | NA | TCAICJADEMARFORI8ADAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0787 | 125.6011 | Brgy. 8-A, Davao City, Davao Del Sur | JUNA | UNITY | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GLENN C. BLASON | 10004389 | 9176884692 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4280 | TCLDCNALILBONGAOTAWI | NA | TCLDCNALILBONGAOTAWI | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.0277 | 119.7657 | Bgry Nalil, Bongao, Tawi Tawi | TETUAN FOC | LDIC | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4282 | TCLDCPOBBONGAOTAWI | NA | TCLDCPOBBONGAOTAWI | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | TAWI-TAWI | BONGAO |  | Territory 8 | 5.0337 | 119.774 | Brgy Poblacion, Bongao, Tawi Tawi | TETUAN FOC | LDIC | AREA 7 | BASULTA | TAWITAWI | DARIUS LORETO S. BENDIJO | CHRISTIAN MARK D. PAYAT | 10014473 | 9176886000 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5258 | TCFGATABLASUSEWTBURANBAS | NA | TCFGATABLASUSEWTBURANBAS | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | BASILAN | TUBURAN |  | Territory 8 | 6.6087 | 122.1922 | Brgy.TablasUsew_Tuburan_Basilan | TETUAN FOC | FTAP | AREA 7 | BASULTA | BASILAN | DARIUS LORETO S. BENDIJO | MARVELOUS MARVIN E. MALCO | 10010155 | 9176882262 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4964 | TCPHTNEWALBAYMARAGUDDO | NA | TCPHTNEWALBAYMARAGUDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | MARAGUSAN (SAN MARIANO) |  | Territory 7 | 7.341 | 126.1596 | Brgy.NewAlbay_Maragusan(SanMariano)_DavaoDeOro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4972 | TCPHTP9BANTCANNBATANDDO | NA | TCPHTP9BANTCANNBATANDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | NEW BATAAN |  | Territory 7 | 7.5977 | 126.1295 | Brgy.Kahayag_NewBataan_DavaoDeOro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5030 | TCPHTBONIFAKINGPANTUKDDO | NA | TCPHTBONIFAKINGPANTUKDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | PANTUKAN |  | Territory 7 | 7.1346 | 125.8908 | Brgy.Kingking(Pob.)01_Pantukan_DavaoDeOro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5031 | TCPHTP3TIBAGONPANTUKDDO | NA | TCPHTP3TIBAGONPANTUKDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | PANTUKAN |  | Territory 7 | 7.2336 | 125.8656 | Purok 3, Brgy. Tibagon, Pantukan, Davao de Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5380 | TCEDCSNJOSECAWAZAMBOAZDS | NA | TCEDCSNJOSECAWAZAMBOAZDS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9114 | 122.0658 | Barrio of San Jose, Cawa-Cawa, Zamboanga City | TETUAN FOC | EDOTCO | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5472 | M2SC2WIMSUZAMBOAZDSAS | NA | M2SC2WIMSUZAMBOAZDSAS | REGION IX (ZAMBOANGA PENINSULA) | ZAMBOANGA DEL SUR | ZAMBOANGA CITY |  | Territory 8 | 6.9123 | 122.06 | WMSU, Baliwasan, Zamboanga City | TETUAN FOC | GT | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | VICTOR E. CANSECO | 10008611 | 9175886049 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4725 | DVO_105_GPONA_01 | NA | DVO_105_GPONA_01 | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0538 | 125.5859 | Col. Emilio Escandor Street, Cor, Quimpo Blvd., Matina, Davao City | JUNA | GT | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3493 | TCFGAAPOKONTAGUMDDN | NA | TCFGAAPOKONTAGUMDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY (CAPITAL) |  | Territory 7 | 7.4181 | 125.8351 | Purok 6, Brgy. Apokon, Tagum City, Davao del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | RONALD T. SARAGENA | 10008516 | 9176885533 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4489 | TCAGP2AILAMULIGDAVAODDS | NA | TCAGP2AILAMULIGDAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0842 | 125.4724 | P-2A Mulig, Davao City | JUNA | ATC | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3224 | TCFGAMGUGPOSOUTHTAGUMDDN | NA | TCFGAMGUGPOSOUTHTAGUMDDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | TAGUM CITY (CAPITAL) |  | Territory 7 | 7.4418 | 125.795 | Purok 1-B, Narisma Rd., Brgy. San Miguel, Tagum City, Davao Del Norte | TAGUM FOC | FTAP | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4492 | TCAGBAGOOSHIRODAVAODDS | NA | TCAGBAGOOSHIRODAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0774 | 125.4929 | Brgy. Bago Oshiro, Davao City, Davao Del Sur | JUNA | ATC | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5154 | TCAICMINTALDAVAODDS | NA | TCAICMINTALDAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0913 | 125.4999 | Rubia St., Brgy. Mintal, Davao City, Davao del Sur | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | PAUL RECY C. DUMANLAG | 10010023 | 9176880383 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4896 | TCPHTSANROQUENBATANDDO | NA | TCPHTSANROQUENBATANDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | NEW BATAAN |  | Territory 7 | 7.5887 | 126.137 | Purok 4, Brgy. San Roque, New Bataan,, Davao de Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5045 | TCPHTMADUAOPANABODDN | NA | TCPHTMADUAOPANABODDN | REGION XI (DAVAO REGION) | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.2783 | 125.6415 | Purok 2, Brgy. Maduao, Panabo City, Davao del Norte | JUNA | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4971 | TCPHTCAMANLANGANBATANDDO | NA | TCPHTCAMANLANGANBATANDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | NEW BATAAN |  | Territory 7 | 7.5038 | 126.104 | Purok 4, Brgy. Camanlangan, New Bataan, Davao De Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4967 | TCPHTP4BPOBMONTEVDDO | NA | TCPHTP4BPOBMONTEVDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONTEVISTA |  | Territory 7 | 7.7199 | 125.9922 | Purok 4B, Brgy. Poblacion, Montevista, Davao de Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5009 | TCPHTSANRAFACATEELDVOR | NA | TCPHTSANRAFACATEELDVOR | REGION XI (DAVAO REGION) | DAVAO ORIENTAL | CATEEL |  | Territory 7 | 7.7661 | 126.4543 | Brgy. San Rafael, Cateel, Davao Oriental | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4966 | TCPHTNEWVISMONTEVDDO | NA | TCPHTNEWVISMONTEVDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONTEVISTA |  | Territory 7 | 7.6851 | 126.0218 | Sitio Mindahilaya, Brgy.NewVisayas, Davao de Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN3559 | TCPHTGEMVILMAADAVAODDS | NA | TCPHTGEMVILMAADAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0798 | 125.589 | Purok 18, 95 Amethyst, GEM Village, Brgy Ma-a, Davao City, Davao Del Sur | JUNA | PTCI | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | GERICK G. LAYAN | 10010703 | 9176882755 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5155 | TCAICCALINAN01DAVAODDS | NA | TCAICCALINAN01DAVAODDS | REGION XI (DAVAO REGION) | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1884 | 125.4609 | 2019CapSite_BrgyCalinan(Pob.)02_DAVAO CITY_DAVAO DEL SUR | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4968 | TCPHTLINOANMONTEVDDO | NA | TCPHTLINOANMONTEVDDO | REGION XI (DAVAO REGION) | DAVAO DE ORO | MONTEVISTA |  | Territory 7 | 7.6833 | 125.9877 | Prk 3, Brgy. Linoan, Montevista, Davao de Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5395 | TCEDCMHAYAHAYSNJOSEDNGT |  |  | REGION XIII (Caraga) | DINAGAT ISLAND | SAN JOSE |  | Territory 8 | 10.0076 | 125.5789 | Brgy Mahayahay, San Jose, Dinagat Island | BUTUAN |  | AREA 1 | BUTUAN | SURIGAO | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5362 | TCAICMARCELINABAYUGAGS | NA | TCAICMARCELINABAYUGAGS | REGION XIII (Caraga) | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.661 | 125.7842 | Purok 1, Marcelina,Bayugan City, Agusan Del Sur | BUTUAN | UNITY | AREA 1 | BUTUAN | SAN FRANCISCO | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4604 | TCAICMANGAGBISLIGSDS | NA | TCAICMANGAGBISLIGSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | BISLIG CITY |  | Territory 8 | 8.1856 | 126.3528 | Brgy. Mangagoy, Bislig City, Surigao del Sur | BUTUAN | UNITY | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4518 | TCFGASAGBAYANMIGUELSDS | NA | TCFGASAGBAYANMIGUELSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | SAN MIGUEL |  | Territory 8 | 8.9679 | 125.9773 | Purok 2, Brgy. Sagbayan, San Miguel, Surigao Del Sur | BUTUAN | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5329 | TCFGABRETANIAAGUSTNSDS | NA | TCFGABRETANIAAGUSTNSDS | REGION XIII (Caraga) | SURIGAO DEL SUR | SAN AGUSTIN |  | Territory 8 | 8.6951 | 126.2074 | Purok 5, Brgy. Bretania, San Agustin, Surigao del Sur | BUTUAN | FTAP | AREA 1 | BUTUAN | BISLIG | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5357 | TCFGAPOBLACIONMGALANAGN | NA | TCFGAPOBLACIONMGALANAGN | REGION XIII (Caraga) | AGUSAN DEL NORTE | MAGALLANES |  | Territory 8 | 9.0202 | 125.5182 | Brgy.Poblacion_Magallanes_AgusanDelNorte | BUTUAN | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN2960 | GSMLAY | NA | GSMLAY | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1558 | 125.1268 | Globe Store Malaybalay, Barangay 3 (Pob.), Malaybalay City | MALAYBALAY | GT | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4661 | TCAICVYMHOTELCDOMOR | NA | TCAICVYMHOTELCDOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4359 | 124.619 | Pueblo de Oro, Barangay Canitoan), Cagayan De Oro, Misamis Oriental | CDO | UNITY | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5324 | TCFGAPOBLASALAYMOR | NA | TCFGAPOBLASALAYMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.8624 | 124.7933 | Brgy. Poblacion, Salay, Misamis Oriental | CDO | FTAP | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5494 | BRGY22POBCDOMOREM | NA | BRGY22POBCDOMOREM | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4884 | 124.6539 | Brgy. Barangay 22 (Pob.) CAGAYAN DE ORO CITY (CAPITAL) MISAMIS ORIENTAL | CDO | GT | AREA 2 | CDO | CAGAYAN DE ORO CITY | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5469 | TCAICCANAYANMALAYBBUK | NA | TCAICCANAYANMALAYBBUK | REGION X (NORTHERN MINDANAO) | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.1901 | 125.1507 | Purok 01, Brgy. Canayan, Malaybalay City, Bukidnon | MALAYBALAY | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5391 | TCAICDAANLUNGSODGINGOOMOR | NA | TCAICDAANLUNGSODGINGOOMOR | REGION X (NORTHERN MINDANAO) | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.8364 | 125.1333 | National Highway, Purok 1, Barangay Daan Lungsod, Gingoog Misamis Oriental | GINGOOG | UNITY | AREA 2 | CDO | GINGOOG CITY | MARK WENDEL L. JURIAL | KENT JUDE I. LOLO | 10014472 | 9176883353 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5133 | TCFGADALAPITNMTALAMNCOT | NA | TCFGADALAPITNMTALAMNCOT | REGION XII (SOCCSKSARGEN) | NORTH COTABATO | MATALAM |  | Territory 7 | 7.0416 | 124.8976 | Purok Langka, Brgy. Dalapitan, Matalam, North Cotabato | MLANG | FTAP | AREA 12 | COTABATO 2 | MLANG | GILSON A. NAVARRA | JUN MARLO M. CASTRODES | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5495 | TCAGLOVELAGAOGENSANSCOT | NA | TCAGLOVELAGAOGENSANSCOT | REGION XII (SOCCSKSARGEN) | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1234 | 125.1831 | Emerald St. Loveland Subd., Brgy. Lagao, General Santos | GENSAN | ATC | AREA 11 | GENSAN | GENSAN | RENE M. FENIS | JOHN ALVER C. FORONES | 10010465 | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4333 | TCAICTUBURANPGDIANZDS | [12 empty] | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5312 | TCPHTKAWIT2PGDIANZDS | [12 empty] | AREA 5 | PAGADIAN | PAGADIAN CITY | FRANCISCO S. YONGCO | PHE ERICKSON G. ALERE | 8459 | 9176888029 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4366 | TCPHTZ5ABUNOILIGANLDN |  |  | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | [7 empty] | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5322 | TCLDCILIANMARANTLDS |  |  | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | MARANTAO | [7 empty] | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5351 | TCFGASULANGONDPITANZDN | [12 empty] | AREA 5 | PAGADIAN | DAPITAN | FRANCISCO S. YONGCO | ANDRO M. DURAGOS | 10001606 | 9177976850 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5350 | TCFGAPOB2TITAYZSIB | [12 empty] | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5376 | UBALDOLAYAILIGANLDNAS |  |  | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | ILIGAN CITY | [7 empty] | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | HARRY A. AREOLA | 10009375 | 9175880728 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3986 | TCPHTPRESROXASRLIMZSIB | [12 empty] | AREA 6 | ZAMBOANGA | IPIL | EVERARD A. PENAFLOR | VLADIMIR T. BUENAVISTA | 10010595 | 9176882668 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5355 | TCFGAMARANDINGLALALDN |  |  | REGION X (NORTHERN MINDANAO) | LANAO DEL NORTE | LALA | [7 empty] | AREA 4 | ILIGAN | TUBOD | ARNEL B. BITOON | DWIGHT S. QUENIAHAN | 6107 | 9176888106 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5488 | TCPHTBOLONG2ZAMBOAZDS | [12 empty] | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5489 | TCPHTLUMIYAPDIVZAMBOAZDSLY | [12 empty] | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5509 | TCPHTCULIANANZAMBOAZDS | [12 empty] | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | JOEY D. DAGOHOY | 10005455 | 9175884886 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5521 | NVALRHONDOZAMBOAZDSAS | [12 empty] | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5689 | GTFOCTETUANZAMBOAZDSAS | [12 empty] | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5640 | NUNEZONE4ZAMBOAZDSAS | [12 empty] | AREA 6 | ZAMBOANGA | ZAMBOANGA | EVERARD A. PENAFLOR | KARL PATRICK J. CARDOZA | 10009439 | 9175885223 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5401 | TCFGALUMBACTOROSAGUIALDS |  |  | AUTONOMOUS REGION IN MUSLIM MINDANAO (ARMM) | LANAO DEL SUR | SAGUIARAN | [7 empty] | AREA 4 | ILIGAN | ILIGAN | ARNEL B. BITOON | JOVANIE B. QUILAB | 10004136 | 9176884136 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1008 | CDO-612 | NA | NA |  | MISAMIS ORIENTAL | OPOL |  | Territory 8 | 8.5066 | 124.6047 | AT THE BACK OF PNP SUBSTATION, PYREX ST. PNROA SUBD., BRGY. BARRA, OPOL, MISAMIS ORIENTAL | CDO NDC | GT | AREA 2 | CDO | CDO NDC | MARK WENDEL L. JURIAL | GRANT JASON Q. TIONGCO | 7580 | 9176888747 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1001 | CDO-615 | NA | NA |  | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.5068 | 124.7576 | INFRONT OF D BARBER SHOP, CABILOGAN ST., BRGY. BUGO, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CDO NDC | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1156 | CDO-703 | NA | NA |  | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4907 | 124.6554 | INFRONT OF GT TOWER, GA ABUCAYAN ST., OSMENA EXT., CITY PROPER, CAGAYAN DE ORO | CDO NDC | GT | AREA 2 | CDO | CDO NDC | MARK WENDEL L. JURIAL | RICHARD C. DAROCA | 10010633 | 9176882682 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN1158 | CDO-706 | NA | NA |  | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4883 | 124.7376 | ALONG PRES. ROXAS ST., ZONE 2, BRGY. AGUSAN, CAGAYAN DE ORO CITY | CDO NDC | GT | AREA 2 | CDO | CDO NDC | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5459 | TCFGAPOBALEGRISDN | NA |  |  | SURIGAO DEL NORTE | ALEGRIA |  | Territory 8 |  |  |  | BUTUAN | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA |  |  | #N/A | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5338 | TCFGATIGAOCORTESSDS | NA | TCFGATIGAOCORTESSDS |  | SURIGAO DEL SUR | CORTES |  | Territory 8 | 9.208 | 126.1743 | Purok-6, Brgy. Tigao, Cortes, Surigao Del Sur | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5321 | TCFGABASILISAREMRAGN | NA | TCFGABASILISAREMRAGN |  | AGUSAN DEL NORTE | BASILISA (RIZAL) |  | Territory 8 | 9.0658 | 125.5795 | Brgy. Basilisa REMEDIOS T. ROMUALDEZ AGUSAN DEL NORTE | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5339 | TCFGAVINAPORCARMENAGN | NA | TCFGAVINAPORCARMENAGN |  | AGUSAN DEL NORTE | CARMEN |  | Territory 8 | 9.0823 | 125.2156 | P-3, Brgy. Vinapor, Carmen, Agusan Del Norte | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5394 | TCAICP13POBBAYUGAGS | NA | TCAICP13POBBAYUGAGS |  | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7118 | 125.7499 | Purok 13, Poblacion, Bayugan City, Agusan Del Sur | Butuan | UNITY | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5366 | STMICHAELNASIPAGNAS | NA | STMICHAELNASIPAGNAS |  | AGUSAN DEL NORTE | NASIPIT |  | Territory 8 | 8.9881 | 125.3407 | Rizal Park, Atupan St, Brgy 4 Nasipit, Agusan Del Sur | Butuan | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | LOUIE DEEN G. RATILLA | 10010594 | 9176881690 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4110 | TCFGAPOBLABAHPROSPAGS | NA | TCFGAPOBLABAHPROSPAGS |  | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.6057 | 125.9104 | Purok 1,Brgy. Poblacion,Properedad,Agusan Del Sur | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5417 | TCFGAPARANGCANTILSDS | NA | TCFGAPARANGCANTILSDS |  | SURIGAO DEL SUR | CANTILAN |  | Territory 8 | 9.2822 | 125.9434 | Brgy. Parang, Cantilan, Surigao Del Sur | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5340 | TCAICSANJOSEPROSPAGS | NA | TCAICSANJOSEPROSPAGS |  | AGUSAN DEL SUR | PROSPERIDAD |  | Territory 8 | 8.6781 | 125.8407 | Purok 2, San Jose, Prosperidad, Agusan Del Sur | Butuan | UNITY | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5341 | TCAICDAKUTANESPERAGS | NA | TCAICDAKUTANESPERAGS |  | AGUSAN DEL SUR | ESPERANZA |  | Territory 8 | 8.6665 | 125.6867 | Purok 1, Dakutan, Esperanza, Agusan Del Sur | Butuan | UNITY | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5470 | TCFGACOMAGASCABADAGN | NA | TCFGACOMAGASCABADAGN |  | AGUSAN DEL NORTE | CABADBARAN CITY |  | Territory 8 | 9.1342 | 125.5569 | Brgy.Comagascas, Cabadbaran City, Agusan Del Norte | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5473 | TCLDCJAGUPITSNTGOAGN | NA | TCLDCJAGUPITSNTGOAGN |  | AGUSAN DEL NORTE | SANTIAGO |  | Territory 8 | 9.2418 | 125.5594 | Purok 3, Brgy. Jagupit, Santiago, Agusan del Norte | Butuan | LDIC | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4114 | TCFGASNICOLASTALACAGS | NA | TCFGASNICOLASTALACAGS |  | AGUSAN DEL SUR | TALACOGON |  | Territory 8 | 8.4594 | 125.7815 | BrgySan Nicolas (Pob.)_TALACOGON_Agusan Del Sur | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5409 | TCFGABALUBAL2CDOMOR | NA | TCFGABALUBAL2CDOMOR |  | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY |  | Territory 8 | 8.4752 | 124.7687 | Brgy. Balubal , Cagayan De Oro, Misamis Oriental | CDO | FTAP | AREA 2 | BUKIDNON | CDO | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5326 | TCFGAZ2LINGIONMFORTBUK | NA | TCFGAZ2LINGIONMFORTBUK |  | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.4004 | 124.8878 | Zone 2, Lingi-on, Manolo Fortich, Bukidnon | MALAYBALAY | FTAP | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | EDMAR E. EDUBAS | 10010984 | 9176882909 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4877 | TCFGACONCEPMKLALANCOT | NA | TCFGACONCEPMKLALANCOT |  | NORTH COTABATO | MAKILALA |  | Territory 7 | 6.9553 | 125.0602 | Brgy.Concepcion, Makilala, North Cotabato | KIDAPAWAN | FTAP | AREA 12 | COTABATO 1 | KIDAPAWAN | GILSON A. NAVARRA | GERUINE CHRIS C. NACARIO | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4881 | TCAICNDDUDADEASTGENSANSCOT | NA | TCAICNDDUDADEASTGENSANSCOT |  | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1174 | 125.1704 | Oval Plaza, Brgy. Dadiangas East (Pob.), General Santos City, South Cotabato | GENSAN | UNITY | AREA 11 | COTABATO 1 | GENSAN | GILSON A. NAVARRA | JOHN ALVER C. FORONES |  | 9176882476 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4948 | TCPHTSNANDRESBUNAWAGS | NA | TCPHTSNANDRESBUNAWAGS |  | AGUSAN DEL SUR | BUNAWAN |  | Territory 8 | 8.2105 | 125.9905 | Brgy. San Andres, Bunawan, Agusan Del Sur | Butuan | PTCI | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5359 | TCFGAHIMAMAUGTAGANASDN | NA | TCFGAHIMAMAUGTAGANASDN |  | SURIGAO DEL NORTE | TAGANAAN |  | Territory 8 | 9.7164 | 125.5709 | Purok 4, Brgy. Himamaug, Tagana-an, Surigao Del Norte | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUN CHRISTIAN M. SAMPORNA | 10012991 | 9176884387 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5330 | TCFGAGUADALUPESPERAGS | NA | TCFGAGUADALUPESPERAGS |  | AGUSAN DEL SUR | ESPERANZA |  | Territory 8 | 8.5821 | 125.7084 | Brgy.Guadalupe, Esperanza, Agusan Del Sur | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5468 | TCAICMAGSAYMALAYBBUK | NA | TCAICMAGSAYMALAYBBUK |  | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.0967 | 125.0991 | Purok 02, Brgy. Magsaysay, Valencia City, Bukidnon | MALAYBALAY | UNITY | AREA 3 | BUKIDNON | MALAYBALAY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5493 | P1LIBERTADBUTUANAGNAS | NA | P1LIBERTADBUTUANAGNAS |  | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9444 | 125.503 | NATIONAL HIGHWAY, PUROK 1, LIBERTAD, BUTUAN CITY AGUSAN DEL NORTE | Butuan | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | SERGIE LOU L. BUNANI | 10013587 | 9176880870 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5457 | TCFGABALETEPOBBAYUGAGS | NA | TCFGABALETEPOBBAYUGAGS |  | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7204 | 125.7575 | Purok 7 Ballete St. Poblacion Bayugan City, Agusan del Sur | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5131 | TCFGAMARBELMTALAMNCOT | NA | TCFGAMARBELMTALAMNCOT |  | NORTH COTABATO | MATALAM |  | Territory 7 | 7.1219 | 124.9249 | Purok Santan, Marbel, Matalam, North Cotabato | MLANG | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | JUN MARLO M. CASTRODES | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5526 | TCCRECANAWAYKITCHAAGN | NA | TCCRECANAWAYKITCHAAGN |  | AGUSAN DEL NORTE | KITCHARAO |  | Territory 8 | 9.4077 | 125.5598 | Purok 1, Brgy. Canaway, Kitcharao, Agusan del Norte | Butuan | CREI | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5576 | TCAICDALUMNGCBNULINGMGDN | NA | TCAICDALUMNGCBNULINGMGDN |  | MAGUINDANAO | SULTAN KUDARAT (NULING) |  | Territory 7 | 7.264 | 124.2857 | Brgy. Dalumangcob, Sultan Kudarat, Maguindanao Del Norte | COTABATO | UNITY | AREA 12 | COTABATO 1 | COTABATO | GILSON A. NAVARRA | MICHEL P. MEDALLA |  |  | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5308 | TCAICPAITANESPERSKUD | NA | TCAICPAITANESPERSKUD |  | SULTAN KUDARAT | ESPERANZA |  | Territory 7 | 6.7678 | 124.5327 | Brgy. Paitan, Esperanza, Sultan Kudarat | TACURONG | UNITY | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO |  |  | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5558 | TCFGAMABUATANDAGSDS | NA | TCFGAMABUATANDAGSDS |  | SURIGAO DEL SUR | TANDAG CITY |  | Territory 8 | 9.0618 | 126.2025 | Brgy. Mabua, Tandag City (Capital), Surigao Del Sur | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5461 | TCFGATIDMANHINATUSDS | NA | TCFGATIDMANHINATUSDS |  | SURIGAO DEL SUR | HINATUAN |  | Territory 8 | 8.2992 | 126.3731 | Purok 2, Brgy. Tidman, Hinatuan, Surigao Del Sur | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | BRYAN J. ANDOY | 10014471 | 9176883132 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5077 | TCPHTMAGSAYSAYPOLOMOSCOT | NA | TCPHTMAGSAYSAYPOLOMOSCOT |  | SOUTH COTABATO | POLOMOLOK |  | Territory 7 | 6.2028 | 125.0594 | Brgy. Magsaysay, Polomolok, South Cotabato | GENSAN | PTCI | AREA 12 | COTABATO 1 | GENSAN | GILSON A. NAVARRA | QUERICO CALEB U. FEDERIS |  | 9176882606 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5416 | TCFGAPIANINGBUTUANAGN | NA | TCFGAPIANINGBUTUANAGN |  | AGUSAN DEL NORTE | BUTUAN CITY |  | Territory 8 | 8.9908 | 125.6427 | Brgy. Pianing, Butuan City, Agusan del Norte | Butuan | FTAP | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | FRANK KIT P. OLOROCISIMO | 10008514 | 9176885441 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5374 | FILIBAYUGAGSAS | NA | FILIBAYUGAGSAS |  | AGUSAN DEL SUR | BAYUGAN CITY |  | Territory 8 | 8.7105 | 125.7689 | Purok 6, Barangay Fili, Bayugan City, Agusan Del Sur | Butuan | GT | AREA 1 | BUTUAN | AMPAYON | KIMBERLOUGH H. PLAZA | JUNICE DALE L. GRANA | 10011898 | 9176883684 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN4134 | TCSBANHAIDCBUHADAVAODDS | NA | TCSBANHAIDCBUHADAVAODDS |  | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.103 | 125.6198 | Dumanlas, Brgy. Buhangin, Davao City, Davao del Sur | JUNA | SBA | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5195 | TCAICBINUGAODAVAODDS | NA | TCAICBINUGAODAVAODDS |  | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 6.9757 | 125.4781 | Central 2, Brgy. Binugao, Davao City, Davao del Sur | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5022 | TCFGAAPLAYA02DIGOSDDS | NA | TCFGAAPLAYA02DIGOSDDS |  | DAVAO DEL SUR | DIGOS CITY (CAPITAL) |  | Territory 7 | 6.7472 | 125.3643 | Luna Bataan Street, Brgy. Aplaya, Digos City, Davao del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ARTHUR A. NUEVO JR | 10009230 | 9175883150 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4960 | TCPHTPRK4KATIPUNBATANDDO | NA | TCPHTPRK4KATIPUNBATANDDO |  | DAVAO DE ORO | NEW BATAAN |  | Territory 7 | 7.633 | 126.1033 | Purok 9, Brgy.Katipunan, New Bataan, Davao De Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4970 | TCPHTP5MIPANGINABUNDDO | NA | TCPHTP5MIPANGINABUNDDO |  | DAVAO DE ORO | NABUNTURAN (CAPITAL) |  | Territory 7 | 7.5357 | 125.9157 | Purok 4, Brgy. Mipangi, Nabunturan, Davao de Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5014 | TCPHTPOBBANAYDVOR | NA | TCPHTPOBBANAYDVOR |  | DAVAO ORIENTAL | BANAYBANAY |  | Territory 7 | 6.9759 | 126.023 | Brgy.Poblacion, Banaybanay, Davao Oriental | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4982 | TCPHTPANIKIANBANAYDVOR | NA | TCPHTPANIKIANBANAYDVOR |  | DAVAO ORIENTAL | BANAYBANAY |  | Territory 7 | 6.9975 | 126.0325 | Brgy. Panikan, Banaybanay, Davao Oriental | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5185 | TCAICCALINAN02DAVAODDS | NA | TCAICCALINAN02DAVAODDS |  | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1742 | 125.4623 | Calinan, Davao City, Davao del Sur | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4969 | TCPHTP15POBNABUNDDO | NA | TCPHTP15POBNABUNDDO |  | DAVAO DE ORO | NABUNTURAN (CAPITAL) |  | Territory 7 | 7.5948 | 125.9633 | Purok 15, Brgy. Poblacion, Nabunturan, Davao de Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5228 | TCFGAKIDALAPONGMALITADVOC | NA | TCFGAKIDALAPONGMALITADVOC |  | DAVAO OCCIDENTAL | MALITA (CAPITAL) |  | Territory 7 | 6.4237 | 125.5846 | Brgy. Kidalapong, Malita, Davao Occidental | JUNA | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4845 | TCFGABUNAWNDAVAODDS | NA | TCFGABUNAWNDAVAODDS |  | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1869 | 125.6212 | Purok 1, Mudiang, Bunawan, Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5027 | TCPHTBALSIAOKIBLAWDDS | NA | TCPHTBALSIAOKIBLAWDDS |  | DAVAO DEL SUR | KIBLAWAN |  | Territory 7 | 6.4929 | 125.2454 | Purok 7, Brgy. Balasiao, Kiblawan,, Davao del Sur | JUNA | PTCI | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4963 | TCPHTPRKDRIANPANGIMACODDO | NA | TCPHTPRKDRIANPANGIMACODDO |  | DAVAO DE ORO | MACO |  | Territory 7 | 7.4335 | 125.8389 | Purok Durian, Brgy. Pangi, Maco, Davao de Oro | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | PETER JAMES S. FELICIA | 10013866 | 9176885130 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5067 | SDPAZDDIANGASTHGENSANSCOTAS | NA | SDPAZDDIANGASTHGENSANSCOTAS |  | SOUTH COTABATO | GENERAL SANTOS CITY |  | Territory 7 | 6.1113 | 125.1756 | Outside Dadiangas South Central Elementary School along Señora Dela Paz St., Brgy. Dadiangas South | GENSAN | GT | AREA 12 | COTABATO 1 | GENSAN | GILSON A. NAVARRA | MARC ANTHONY M. LUBANG |  |  | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5529 | TCLDCSILAEMALAYBBUK | NA | TCLDCSILAEMALAYBBUK |  | BUKIDNON | MALAYBALAY CITY |  | Territory 8 | 8.176 | 125.3008 | Brgy. Silae MALAYBALAY CITY (CAPITAL) BUKIDNON | MALAYBALAY CITY | LDIC | AREA 3 | BUKIDNON | MALAYBALAY CITY | RODERICK LASTIMOSA | MARK LOUIE A. JAMIS | 10013809 | 9176885058 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN3801 | TCFGATIGATTODAVAODDS | NA | TCFGATIGATTODAVAODDS |  | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1232 | 125.5883 | Purok 4A, Brgy. Tigatto, Buhangin Dist., Davao City, Davao del Sur | JUNA | FTAP | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | BENJUN C. CRAVE | 10008613 | 9175886196 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5183 | TCAICCALINANPOBDAVAODDS | NA | TCAICCALINANPOBDAVAODDS |  | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1917 | 125.444 | Brgy. Calinan, Davao City, Davao del Sur | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5132 | TCFGAPATADONWSTMTALAMNCOT | NA | TCFGAPATADONWSTMTALAMNCOT |  | NORTH COTABATO | MATALAM |  | Territory 7 | 7.0805 | 124.9365 | Brgy. Patadon West, Matalam, North Cotabato | MLANG | FTAP | AREA 12 | COTABATO 1 | MLANG | GILSON A. NAVARRA | JUN MARLO M. CASTRODES | 10015846 | 9176886315 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4878 | TCEDCBALOGOCOTABMGDN | NA | TCEDCBALOGOCOTABMGDN |  | NORTH COTABATO | PIGKAWAYAN |  | Territory 7 | 7.2799 | 124.4564 | J.P. Rizal Street Brgy. Balogo Pigkawayan Cotabato , Pigkawayan, Cotabato (North Cotabato) | MIDSAYAP | EDOTCO | AREA 12 | COTABATO 1 | MIDSAYAP | GILSON A. NAVARRA | ANTHONY JOHN E. SAGRADO |  | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5041 | TCPHTNANYOPANABODDN | NA | TCPHTNANYOPANABODDN |  | DAVAO DEL NORTE | PANABO CITY |  | Territory 7 | 7.3352 | 125.6359 | Along Brgy. Road, Brgy.Nanyo_PanaboCity_DavaoDelNorte | JUNA | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5035 | TCPHTSAGAYEN01ACIONDDN | NA | TCPHTSAGAYEN01ACIONDDN |  | DAVAO DEL NORTE | ASUNCION |  | Territory 7 | 7.6452 | 125.7589 | Brgy.Sagayen01_Asuncion(Saug)_DavaoDelNorte | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5038 | TCPHTP3TUBODCARMENDDN | NA | TCPHTP3TUBODCARMENDDN |  | DAVAO DEL NORTE | CARMEN |  | Territory 7 | 7.3653 | 125.6319 | Purok 3, Brgy. Tubod, Carmen, Davao del Norte | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | IVAN J. MAGALLON | 10010847 | 9176882039 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5056 | TCPHTVILLAMORESPERSKUD | NA | TCPHTVILLAMORESPERSKUD |  | SULTAN KUDARAT | ESPERANZA |  | Territory 7 | 6.7034 | 124.5213 | Brgy. Villamor, Esperanza, Sultan Kudarat | TACURONG | PTCI | AREA 12 | COTABATO 1 | TACURONG | GILSON A. NAVARRA | GERALD TOM P. EBREO | 10015023 | 9176887370 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5021 | TCPHTP7APLAYA01DIGOSDDS | NA | TCPHTP7APLAYA01DIGOSDDS |  | DAVAO DEL SUR | DIGOS CITY (CAPITAL) |  | Territory 7 | 6.7418 | 125.3744 | Purok 7, Brgy. Aplaya, Digos City,, Davao Del Sur | JUNA | PTCI | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN4996 | TCPHTMACBICO1MASTURMGDN | NA | TCPHTMACBICO1MASTURMGDN |  | MAGUINDANAO | SULTAN MASTURA |  | Territory 7 | 7.2919 | 124.2963 | Brgy. Semba, Sultan Mastura, Maguindanao | COTABATO | PTCI | AREA 12 | COTABATO 1 | COTABATO | GILSON A. NAVARRA | MICHEL P. MEDALLA |  |  | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5078 | TCPHTAMBALGAN02SNINOSCOT | NA | TCPHTAMBALGAN02SNINOSCOT |  | SOUTH COTABATO | SANTO NIÑO |  | Territory 7 | 6.4106 | 124.6969 | Brgy. Ambalgan, Sto. Nino, South Cotabato | KORONADAL | PTCI | AREA 12 | COTABATO 1 | KORONADAL | GILSON A. NAVARRA | ALVIN C. APUD | 10011995 | 9176882369 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5034 | TCPHTP4DONANDREACIONDDN | NA | TCPHTP4DONANDREACIONDDN |  | DAVAO DEL NORTE | ASUNCION |  | Territory 7 | 7.6116 | 125.7591 | Prk.4, Brgy.DonaAndrea, Asuncion, Davao del Norte | TAGUM FOC | PTCI | AREA 9 | DAVAO 2 | TAGUM FOC | GERALD L. POTATO | GLEESON N. CAMEROS | 10014417 | 9176886224 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5053 | TCPHTPENAPLATA02SAMALDDN | NA | TCPHTPENAPLATA02SAMALDDN |  | DAVAO DEL NORTE | ISLAND GARDEN CITY OF SAMAL |  | Territory 7 | 7.085 | 125.7042 | Sitio Maag, Peñaplata, Island Garden City of Samal | JUNA | PTCI | AREA 8 | DAVAO 1 | JUNA | JENNER C. TOY | RODOLF ANTHONY V. BRAGA | 10010983 | 9176880852 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5167 | TCLDCGUMSAGLANSAR | NA | TCLDCGUMSAGLANSAR |  | SARANGANI | GLAN |  | Territory 7 | 5.7895 | 125.1919 | Brgy. Gumasa, Glan ,Sarangani | GENSAN | LDIC | AREA 12 | COTABATO 1 | GENSAN | GILSON A. NAVARRA | ROIEN CARL C. ROJO |  | 9176882704 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5229 | TCFGAPOBMALITADVOC | NA | TCFGAPOBMALITADVOC |  | DAVAO OCCIDENTAL | MALITA (CAPITAL) |  | Territory 7 | 6.4146 | 125.6012 | Brgy. Poblacion, Malita, Davao Occidental | JUNA | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5118 | TCLDCCAMNSIALMADANCOT | NA | TCLDCCAMNSIALMADANCOT |  | NORTH COTABATO | ALAMADA |  | Territory 7 | 7.3467 | 124.559 | Brgy. Camansi, Alamada, North Cotabato | MIDSAYAP | LDIC | AREA 12 | COTABATO 1 | MIDSAYAP | GILSON A. NAVARRA | ANTHONY JOHN E. SAGRADO |  | 9176886403 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5552 | TCFGATUGAYAVALENBUK | NA | TCFGATUGAYAVALENBUK |  | BUKIDNON | VALENCIA CITY |  | Territory 8 | 7.9138 | 125.0177 | Brgy. Tugaya, Purok 1, Valencia City | VALENCIA CITY | FTAP | AREA 3 | BUKIDNON | VALENCIA CITY | RODERICK LASTIMOSA | AIRREL RON R. ROMOROSA | 10015179 | 9176884647 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5294 | TCFGASEAITCROSRUBTUPISCOT | NA | TCFGASEAITCROSRUBTUPISCOT |  | SOUTH COTABATO | TUPI |  | Territory 7 | 6.3477 | 124.9356 | SEAIT_Brgy.CrossingRubber_Tupi_SouthCotabato | GENSAN | FTAP | AREA 12 | GENSAN | GENSAN | RENE M. FENIS | QUERICO CALEB U. FEDERIS | 10010305 | 9176880199 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5216 | TCFGAPRK4PANAGLIBKIBLAWDDS | NA | TCFGAPRK4PANAGLIBKIBLAWDDS |  | DAVAO DEL SUR | KIBLAWAN |  | Territory 7 | 6.5892 | 125.2398 | Purok 4, Barangay Panaglib, Kiblawan, Davao Del Sur | JUNA | FTAP | AREA 10 | DAVAO 3 | DIGOS | IAN C. ALBINA | ACE VINCENT M. LAPINID | 10014724 | 9176886703 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5243 | TCFGABATOISIDRODVOR | NA | TCFGABATOISIDRODVOR |  | DAVAO ORIENTAL | SAN ISIDRO |  | Territory 7 | 6.8353 | 126.1005 | Purok Makogihon 3, Katipunan Barangay Bato-bato San Isidro, Davao Oriental | MATI | FTAP | AREA 9 | DAVAO 2 | MATI | GERALD L. POTATO | MARVI B. MANDAWE | 10012882 | 9176884274 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5158 | TCAICTAGLUNODAVAODDS | NA | TCAICTAGLUNODAVAODDS |  | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.0669 | 125.4317 | Barangay Tagluno, Davao City, Davao Del Sur | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | BERNIE A. HISOLER | 10013320 | 9176884659 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5210 | TCAICNEWVALDAVAODDS | NA | TCAICNEWVALDAVAODDS |  | DAVAO DEL SUR | DAVAO CITY |  | Territory 7 | 7.1713 | 125.5371 | Purok 1, New Valencia Tugbok District, Davao City, Davao Del Sur | JUNA | UNITY | AREA 10 | DAVAO 3 | JUNA | IAN C. ALBINA | EDWIN D. PLAZA | 10008615 | 9175886414 | JHERYL JOHN S CALLO | ENCARNATO DOLDOL
MIN5412 | TCFGAZ3STANATAGOLOMOR | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5519 | TCPHTPANGASIHANGINGOOMOR | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5476 | TCEDCBONIFAQNOMAGSAYMOR | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5456 | TCPHTZ8CUGMANCDOMOR | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | BOB OMAR DEJECACION | 10004188 | 9175884188 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5360 | TCPHTARTADIMAGSAYMOR | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | DIONY S. OMANGPANG | 10001135 | 9177978822 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5599 | TCEDCP5POBCLAVERMOR | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5413 | TCFGAHINIGDAANELSALVMOR | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | ALVIN R. TUMASIS | 10008612 | 9175886052 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5525 | TCFGAHINAPLANCLAVERMOR | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5528 | NATUMOLANTAGOLOMORAS | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL
MIN5410 | TCFGASTACRUZCLAVERMOR | [12 empty] | AREA 2 | CDO | CDO | MARK WENDEL L. JURIAL | PETER JAMES B. BAHIAN | 10010602 | 9176882655 | ALBRETCH ARICAYOS | ENCARNATO DOLDOL